## olayn&Andlous
MELI HRDF
| Today's Date | 2016-02-24
| Project Manager | Enter in Settings
| Week Starts from | Sunday
| Start Date | 2016-01-01
0
[14 empty] | Dec 2015 |  |  |  |  | Jan 2016 | [30 empty] | Feb 2016 | [28 empty] | Mar 2016 | [30 empty] | Apr 2016
WBS | Primary Instructor | Secondary Instructor | Start | Duration | Act. Duration | Complete | End | Actual End | Act. Assigned | Complete | Act. Complete | Remaining | Act. Remaining | time axis 2015-12-27 to 2016-04-24
English | Abdulaziz |  | 2016-01-02 | 60 |  | 100% | 2016-03-01 | 2016-03-01 |  | 60 |  | 0 | 0
English for Logistics | Abdulaziz |  |  |  |  | #DIV/0! | -1 | -1 |  |  |  | 0 | 0
Introduction to Logistics | Amer Badarneh |  |  |  |  | #DIV/0! | -1 | -1 |  |  |  | 0 | 0
Transportation & Distribution | Amer Badarneh | Majed | 2016-01-03 | 58 |  | 20.69% | 2016-02-29 | 2016-02-29 |  | 12 |  | 46 | 0
Technology in Logistics | Osama |  | 2016-01-03 | 58 |  | 20.69% | 2016-02-29 | 2016-02-29 |  | 12 |  | 46 | 0
Warehousing | Majed Habruman |  |  |  |  | #DIV/0! | -1 | -1 |  |  |  | 0 | 0
Health & Safety | Majed Habruman |  | 2016-01-02 | 50 |  | 40% | 2016-02-20 | 2016-02-20 |  | 20 |  | 30 | 0
Sea Freight | Mohammed |  |  |  |  | #DIV/0! | -1 | -1 |  |  |  | 0 | 0
ADR | Amer Badarneh |  |  |  |  | #DIV/0! | -1 | -1 |  |  |  | 0 | 0
Effective Communication Skills | Amer Badarneh |  |  |  |  | #DIV/0! | -1 | -1 |  |  |  | 0 | 0
Team Work | Abdulaziz |  |  |  |  | #DIV/0! | -1 | -1 |  |  |  | 0 | 0
Customer Services | Majed Habruman |  |  |  |  | #DIV/0! | -1 | -1 |  |  |  | 0 | 0
Practical Training | Company |  |  |  |  | #DIV/0! | -1 | -1 |  |  |  | 0 | 0

## Sec
SETTINGS
Project
| Name of the Project | Project Gantt Chart
Secondary Instructor
| NAME | E-MAIL | PHONE
Amer
Majed
Mohammed
hosam

## Sheet1
name | Id | Company | time axis 2016-01-03 to 2016-04-06
Amer | 1 | olayn | Transportation & Distribution | 2016-01-03: x; 2016-01-04: 8; 2016-01-05: x; 2016-01-06: x; 2016-01-07: x; 2016-01-10: x; 2016-01-11: 8; 2016-01-12: x; 2016-01-13: x; 2016-01-14: x; 2016-01-17: x; 2016-01-18: 8; 2016-01-19: x; 2016-01-20: x; 2016-01-21: x; 2016-01-25: 8; 2016-02-01: 8; 2016-02-08: 8; 2016-02-14: x; 2016-02-15: 8; 2016-02-22: 8
| 2 | Andlous | Transportation & Distribution | 2016-01-03: x; 2016-01-04: 8; 2016-01-05: x; 2016-01-06: x; 2016-01-07: x; 2016-01-10: x; 2016-01-11: 8; 2016-01-12: x; 2016-01-13: x; 2016-01-14: x; 2016-01-17: x; 2016-01-18: 8; 2016-01-19: x; 2016-01-20: x; 2016-01-21: x; 2016-01-25: 8; 2016-02-01: 8; 2016-02-08: 8; 2016-02-14: x; 2016-02-15: 8; 2016-02-22: 8
| 3 | sundex | bar: 2016-01-17 to 2016-01-21; 2016-02-14 to 2016-02-15
| 4 | sundex | bar: 2016-01-24 to 2016-01-28; 2016-02-14 to 2016-02-15
| 5 | sundex | bar: 2016-01-31 to 2016-02-04; 2016-02-07 to 2016-02-08; 2016-02-14 to 2016-02-15
Majed | 1 | olayn | Customer Services | bar: 2016-01-03 to 2016-01-07; 2016-01-10 to 2016-01-14; 2016-01-17 to 2016-01-21; 2016-01-24 to 2016-01-28; 2016-01-31 to 2016-02-04
| 2 | Andlous | bar: 2016-02-07 to 2016-02-11; 2016-02-14 to 2016-02-18; 2016-02-21 to 2016-02-25; 2016-02-28 to 2016-03-01
| 4 | sundex
| 5 | sundex
| 4 | sundex
Aziz | 4 | olayn | bar: 2016-01-03 to 2016-01-07; 2016-01-10 to 2016-01-14; 2016-01-17 to 2016-01-21; 2016-01-24 to 2016-01-28
| 2 | Andlous | bar: 2016-01-31 to 2016-02-04; 2016-02-07 to 2016-02-11; 2016-02-14 to 2016-02-18
| 3 | sundex | bar: 2016-02-21 to 2016-02-25; 2016-02-28 to 2016-03-01
sundex
Mohmmad | 5 | olayn | bar: 2016-01-03 to 2016-01-07; 2016-01-10 to 2016-01-14; 2016-01-17 to 2016-01-21; 2016-01-24 to 2016-01-28; 2016-01-31 to 2016-02-04; 2016-02-07 to 2016-02-11; 2016-02-14 to 2016-02-18; 2016-02-21 to 2016-02-25; 2016-02-28 to 2016-03-01
Andlous
sundex
sundex
sundex
Osamah |  | sundex
sundex
sundex
sundex
sundex
sundex
sundex
sundex
sundex
sundex
sundex
sundex
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## aba husen
MELI HRDF
| Today's Date | 2016-02-24
| Project Manager | Enter in Settings
| Week Starts from | Sunday
| Start Date | 2016-01-01
0
[12 empty] | Dec 2015 |  |  |  |  | Jan 2016 | [30 empty] | Feb 2016 | [28 empty] | Mar 2016 | [30 empty] | Apr 2016
WBS | Primary Instructor | Secondary Instructor | Start | Duration | Complete | End | Actual End | Complete | Act. Complete | Remaining | Act. Remaining | time axis 2015-12-27 to 2016-04-24
English | Abdulaziz |  | 2016-01-02 | 60 | 88.33% | 2016-03-01 | #REF! | 53 |  | 7 | #REF!
English for Logistics | Abdulaziz |  | 2016-01-04 | 100 | 51% | 2016-04-12 | #REF! | 51 |  | 49 | #REF!
Introduction to Logistics | Amer Badarneh |  |  |  | #VALUE! | -1 | #REF! | الدورة اكتملت |  | #VALUE! | #REF!
Transportation & Distribution | Amer Badarneh | Majed | 2016-01-03 | 58 | 89.66% | 2016-02-29 | #REF! | 52 |  | 6 | #REF!
Technology in Logistics | Osama |  | 2016-01-03 | 58 | 89.66% | 2016-02-29 | #REF! | 52 |  | 6 | #REF!
Warehousing | Majed Habruman |  |  |  | #VALUE! | -1 | #REF! | الدورة اكتملت |  | #VALUE! | #REF!
Health & Safety | Majed Habruman |  | 2016-01-02 | 50 | #VALUE! | 2016-02-20 | #REF! | الدورة اكتملت |  | #VALUE! | #REF!
Sea Freight | Mohammed |  |  |  | #VALUE! | -1 | #REF! | الدورة اكتملت |  | #VALUE! | #REF!
ADR | Amer Badarneh |  |  |  | #VALUE! | -1 | #REF! | الدورة اكتملت |  | #VALUE! | #REF!
Effective Communication Skills | Amer Badarneh |  |  |  | #VALUE! | -1 | #REF! | الدورة اكتملت |  | #VALUE! | #REF!
Team Work | Abdulaziz |  |  |  | #VALUE! | -1 | #REF! | الدورة اكتملت |  | #VALUE! | #REF!
Customer Services | Majed Habruman |  |  |  | #VALUE! | -1 | #REF! | الدورة اكتملت |  | #VALUE! | #REF!
Practical Training | Company |  |  |  | #VALUE! | -1 | #REF! | الدورة اكتملت |  | #VALUE! | #REF!