## Intro Page
Introduction
Recruiting staff often takes a bit more time than you'd imagine. From the point when the replacement or new post has been agreed the approximate time needed to interview and offer the post is seven weeks. This allows three weeks for grading of the post and preparation of the documentation, a two week period for advertising and one week for shortlisting and inviting candidates to interview the following week. This is the minimum turnaround time and in most cases, particularly if key events are not planned in advance, the process takes longer. Use this template to plan key dates/resources and anticipate how long it will take to to get the right person to join your team. HR are piloting a web-only based approach to recruitment advertising, so a post can be advertised very quickly after it is signed off - potentially reducing the total time it takes to recruit by up to 2 weeks.
Enter todays date or project start date here: |  | 2010-01-17
Key Stage Summary | Assuming role does not need to be evaluated
Complete SAF process |  | 2010-01-31 12:00 | To use button above go to "Security Warning" near top of page, choose "options", "enable this content". On next page you can adjust some of the timelines to suit your scenario.
Finalise panel members and book diaries |  | 2010-02-01 12:00
Advertise |  | 2010-02-04
Deadline for applications |  | 2010-02-18
Shortlist |  | 2010-02-20
Interview |  | 2010-02-28
Verbal offer made |  | 2010-03-01
Verbal offer accepted |  | 2010-03-03
Contract sent out |  | 2010-03-04 12:00
Induction arrangements finalised |  | 2010-03-16 18:00
Anticipated start date |  | 2010-04-11 12:00
Please note dates are approximate and do not allow for public holidays or weekends.
Go To Detailed Planner

## Detailed Recruitment Planner
| All days are calendar days and not working weeks - so where we need to advertise for 2 weeks it shows as 14 days. You can adjust the time you should allow and timeline figures to suit the role you have in mind. For instance, for senior roles where notice periods are likely to be longer you can adjust this in cell D40. Where web only advertising is used you can choose this in cell D18. As we are piloting a web only advertising approach this defaults to 2 days. |  |  |  |  | 40195
You can edit timelines to suit your scenario by changing the "Timeline(days)" ot "Time you should allow (hours)
| Activity | Time you should allow (hours) | Timeline (days) | Key Dates (With HERA) | Key Dates (No HERA)
Preparation
| Identify the role requirements | 15 | 8 | 2010-01-25 | 2010-01-25
| Identify panel members | 80 | 0.25 | 2010-01-25 06:00 | 2010-01-25 06:00
| Identify and confirm support needs with administrative staff | 1 | 0.25 | 2010-01-25 12:00 | 2010-01-25 12:00
Existing role | Review and make any small changes to the role description (part 1 only) | 2 | 0.5 | 2010-01-26 | 2010-01-26
New role | Write the role description (parts 1 and 2) | 14 | 7 | 2010-02-02
New role | Evaluate the role (if writing new role) | 7 | 14 | 2010-02-16
| Agree selection method(s) and write questions for interview | 4 | 0.5 | 2010-02-16 12:00 | 2010-01-26
| Write the advert | 4 | 0.5 | 2010-02-17 | 2010-01-26 12:00
| Complete SAF process | 1 | 5 | 2010-02-22 | 2010-01-31 12:00
| Finalise panel members and book diaries | 3 | 1 | 2010-02-23 | 2010-02-01 12:00
| Rooms and catering booked for interviews | 1 | 0.5 | 2010-02-23 12:00 | 2010-02-02
| Advert finalised and posted (SELECT ADVERTISING TIMELINE IN CELL D18) | 3 | 2 | 2010-02-25 12:00 | 2010-02-04 |  | 14
| Advertise post | 1 | 14 | 2010-03-11 12:00 | 2010-02-18 |  | 2
| Deadline for applications | 0 | 0 | 2010-03-11 12:00 | 2010-02-18
| Shortlist | 14 | 2 | 2010-03-13 12:00 | 2010-02-20
| Update candidate status, invite people to interview and request references | 2 | 0.5 | 2010-03-14 | 2010-02-20 12:00
| Candidates confirm able to attend interview | 1 | 5 | 2010-03-19 | 2010-02-25 12:00
| Interview timetable produced | 2 | 0.5 | 2010-03-19 12:00 | 2010-02-26
| Pre-interview packs sent out to panel members | 1 | 1 | 2010-03-20 12:00 | 2010-02-27
| Pre-interview meeting | 1 | 0 | 2010-03-20 12:00 | 2010-02-27
Interview and Selection Stage
| Interview | 7 | 1 | 2010-03-21 12:00 | 2010-02-28
| Decision made | 2 | 0.5 | 2010-03-22 | 2010-02-28 12:00
Successful candidate | Verbal offer made | 1 | 0.5 | 2010-03-22 12:00 | 2010-03-01
| Verbal offer accepted | 1 | 2 | 2010-03-24 12:00 | 2010-03-03
| Appointment form and recruitment file summary sheet completed and papers sent to HR | 1 | 1 | 2010-03-25 12:00 | 2010-03-04
| HR System updated | 1 | 0.25 | 2010-03-25 18:00 | 2010-03-04 06:00
| Contract sent out | 1 | 0.25 | 2010-03-26 | 2010-03-04 12:00
| Contract returned and written offer accepted | 1 | 7 | 2010-04-02 | 2010-03-11 12:00
| Induction reminder sent out to line manager | 1 | 0.25 | 2010-04-02 06:00 | 2010-03-11 18:00
Other Candidate Communications
| Update candidate status and sent out reject letters once successful candidate (or second ranking candidate accepts) | 1 | 1 | 2010-04-03 06:00 | 2010-03-12 18:00
Successful candidate | Candidate notice period (SELECT LIKELY NOTICE PERIOD IN CELL D40) | 1 | 31 | 2010-05-03 | 2010-04-11 12:00 |  | 31
| Induction arrangements finalised | 7 | 5 | 2010-04-07 06:00 | 2010-03-16 18:00 |  | 62
| New member of staff joins | 0 | 0 | 2010-05-03 | 2010-04-11 12:00 |  | 93
| Total Effort (hours) | 182
| Elapsed Time for HERA Role (days) | 106
| Elapsed Time for Non-HERA Role (days) | 84.5
Formulas:
Key Dates (With HERA) = G2+[Timeline (days)]
Key Dates (With HERA) = [Key Dates (With HERA), row above]+[Timeline (days)]
Key Dates (No HERA) = G2+[Timeline (days)]
Key Dates (No HERA) = [Key Dates (No HERA), row above]+[Timeline (days)]
Note on D5: pd99: This will provide the critical path dates and end date for the recruitment project
Note on B8: pd99: Includes identifying and meeting any recruitment and selection training needs
Note on B9: pd99: To cover things like: booking panel members' diaries for shortlisting and interview booking rooms for interview preparing recruitment file preparing application packs preparing interview packs producing invitation to interview sending out reference requests sending out post interview letters etc etc
Note on B18: pd99: Includes any dialogue between business area and Riley's
Note on B20: pd99: Post must be advertised for at least two weeks if it is graded 3 or above
Note on B21: pd99: At least two members of the panel should be involved in this
Note on B25: pd99: Includes: interview time table role description interview record forms etc
Note on B28: pd99: Timings to include document ID checks