## Issue Tracker
|  |  |  | Date |  | 2017-11-07 |  |  | Open vs. Closed - Issue Tracking & Management
|  |  |  | Project Name: |  | Internal Audit Follow-up
|  |  |  | Department: |  | Khairan Resort
Office of the Internal Audit |  |  |  | Current Process Owner: |  | Mr. Nasser Al Qadoumi
|  |  |  | ID | Issue Name | Type | Criticality | Responsible | Status | Created | Closed | Notes and Comments
|  |  |  | 206 | Human Resources Management Program "Invision" | Operational | High | HR | Pending | 2017-08-01
| Outstanding Issues |  |  | 207 | Calculation of end of service benefits | Compliance | Medium | HR | Pending | 2017-08-01
|  |  |  | 208 | Training courses for staff | Operational | Medium | HR | Pending | 2017-08-01
| High | 17 |  | 209 | Succession Planning | Compliance | Medium |  | Pending | 2017-08-01
| Medium | 11 |  | 210 | Bank Reconciliations | Strategic | High | FINANCE | Pending | 2017-08-01
| Low | 5 |  | 211 | Attend staff "Al Bahar Restaurant" | Operational | High | FNB | Pending | 2017-08-01
|  |  |  | 212 | Warehouse control | Operational | Medium | FINANCE | Pending | 2017-08-01
Management Corrective Actions Taken to Date |  |  |  | 213 | Guest documents | Financial | High | RECEPTION | Pending | 2017-08-01
|  |  |  | 214 | Absence of strategy | Financial | Medium | EXECUTIVE OFFICE | Pending | 2017-08-01
|  |  |  | 215 | Maintenance work | Financial | High | MAINTENANCEDEPT. | Pending | 2017-08-01
|  |  | 0% | 216 | Evaluation of service contracts | Operational | Medium | HR/ FIN/ EXE | Pending | 2017-08-01
|  |  | 100% | 217 | the Preservation of the environment | Financial | Low | FINANCE | Pending | 2017-08-01
Not Completed |  | Completed |  | 218 | Failure to comply with the booking and reception rules on obtaining copies of civil cards and marriage documents | Financial | High | ? | Pending | 2017-08-01
|  |  |  | 219 | Food that comes out of the kitchen is not matched by invoices issued by the cashir | Financial | Medium | ? | Pending | 2017-08-01
|  |  |  | 220 | Lack of license from the relevant authorities regarding existing buildings and buildings under construction within the park | Financial | High | HR (TEC) | Pending | 2017-08-01
|  |  |  | 221 | Lack of marketing plan based on scientific grounds | Financial | High | STRUCTURE | Pending | 2017-08-01
Click Here to Update your Efforts on Corrective Actions |  |  |  | 222 | The absence of a quality auditor independent of operations within the organizational structure | Financial | Medium | AUDIT | Pending | 2017-08-01
|  |  |  | 223 | Lack of independence in opening complaints and suggestions box | Financial | Medium | ? | Pending | 2017-08-01
|  |  |  | 224 | Insufficient signs in the park | Operational | Low | ? | Pending | 2017-08-01
|  |  |  | 225 | The absence of periodic and independent monitoring of the Opera System | Operational | High | ? | Pending | 2017-08-01
|  |  |  | 226 | Non - definition of the cost of dishes on the automated system Micros - 2010 | Operational | Low | NOT TRUE | Pending | 2017-08-01
|  |  |  | 227 | Absence of a plan of action and strategic objectives for Al Khairan Park | Operational | High | TEC | Pending | 2017-08-01
|  |  |  | 228 | The absence of an approved tourist classification for Al - Khairan Park - 2010 | Operational | High | TEC | Pending | 2017-08-01
|  |  |  | 229 | Quality Standards | Operational | High | ? | Pending | 2017-08-01
|  |  |  | 230 | Website and automated booking - 2010 | Operational | High | IT / TEC | Pending | 2017-08-01
|  |  |  | 231 | Not updating the job description explaining the roles, duties and responsibilities of staff - 2010 | Operational | High | HR/ HR (TEC) | Pending | 2017-08-01
|  |  |  | 232 | Absence of interactive TV system in the rooms and chalets of the park (INTER- ACTIVE TV SYSTEM) - 2010 | Operational | Low | TEC | Pending | 2017-08-01
|  |  |  | 233 | No monthly reconciliation between the end of service provision and the staff leave in the Human Resources System (Invision) as compared to that recorded in the accounting system (SUN) | Operational | Medium | ? | Pending | 2017-08-01
|  |  |  | 234 | The Department of Personnel shall keep the employees' travel documents in the park | Operational | High | NOT TRUE | Pending | 2017-08-01
|  |  |  | 235 | High turnover of staff | Operational | High | HR / HR (TEC) | Pending | 2017-08-01
|  |  |  | 236 | Failure to document exit interview for resigning employees to document the results of the discussion of reasons for employee resignation | Operational | Medium | ? | Pending | 2017-08-01
|  |  |  | 237 | There is no evidence of conformity between the assets and copies of the recruitment documents | Operational | Low | ? | Pending | 2017-08-01
|  |  |  | 238 | Absence of safety and safety standards for personnel in maintenance operations | Operational | High | NOT TRUE | Pending | 2017-08-01

## Options (hidden)
Type | Criticality | Status |  | Min Create | Max Create | Min Close | Max Close | [7 empty] | Audit123
Financial | High | Completed |  | 2017-08-01 | 2017-08-01 | 0 | 0 | [7 empty] | TEC
Operational | Medium | Pending
Compliance | Low | In-Progress |  |  |  |  | Axis | Open | Closed | Total Open | Label Open | Total Close | Label Close | Total
Strategic |  |  |  | Start Date | 2017-08-01 |  | 2017-08-01 | 33 | 0 | 33 | 33 | 0 | 0 | 33
|  |  |  | End Date | 2017-12-31 |  | 2017-08-02 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-03 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-04 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-05 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-06 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-07 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-08 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-09 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-10 | 0 | 0 | 33 |  | 0 |  | 33
Count If Model | [6 empty] | 2017-08-11 | 0 | 0 | 33 |  | 0 |  | 33
High | 17 | 17 |  |  |  |  | 2017-08-12 | 0 | 0 | 33 |  | 0 |  | 33
Medium | 11 | 11 |  |  |  |  | 2017-08-13 | 0 | 0 | 33 |  | 0 |  | 33
Low | 5 | 5 | 33 |  |  |  | 2017-08-14 | 0 | 0 | 33 |  | 0 |  | 33
Value Added | [6 empty] | 2017-08-15 | 0 | 0 | 33 |  | 0 |  | 33
Percentage Completed |  | 100% |  |  |  |  | 2017-08-16 | 0 | 0 | 33 |  | 0 |  | 33
|  | 100 |  |  |  |  | 2017-08-17 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-18 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-19 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-20 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-21 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-22 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-23 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-24 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-25 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-26 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-27 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-28 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-29 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-30 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-08-31 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-01 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-02 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-03 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-04 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-05 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-06 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-07 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-08 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-09 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-10 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-11 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-12 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-13 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-14 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-15 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-16 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-17 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-18 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-19 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-20 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-21 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-22 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-23 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-24 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-25 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-26 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-27 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-28 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-29 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-09-30 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-01 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-02 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-03 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-04 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-05 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-06 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-07 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-08 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-09 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-10 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-11 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-12 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-13 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-14 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-15 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-16 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-17 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-18 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-19 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-20 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-21 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-22 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-23 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-24 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-25 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-26 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-27 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-28 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-29 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-30 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-10-31 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-01 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-02 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-03 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-04 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-05 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-06 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-07 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-08 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-09 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-10 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-11 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-12 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-13 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-14 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-15 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-16 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-17 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-18 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-19 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-20 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-21 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-22 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-23 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-24 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-25 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-26 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-27 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-28 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-29 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-11-30 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-01 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-02 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-03 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-04 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-05 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-06 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-07 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-08 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-09 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-10 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-11 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-12 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-13 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-14 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-15 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-16 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-17 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-18 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-19 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-20 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-21 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-22 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-23 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-24 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-25 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-26 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-27 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-28 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-29 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-30 | 0 | 0 | 33 |  | 0 |  | 33
[7 empty] | 2017-12-31 | 0 | 0 | 33 |  | 0 |  | 33
[8 empty] | 0 | 33 | 33 |  | 33 | 33 | 66
[8 empty] | 0 | 33 | 33 |  | 66 | 66 | 99
[8 empty] | 0 | 33 | 33 |  | 99 | 99 | 132
[8 empty] | 0 | 33 | 33 |  | 132 | 132 | 165
[8 empty] | 0 | 33 | 33 |  | 165 | 165 | 198
[8 empty] | 0 | 33 | 33 |  | 198 | 198 | 231
[8 empty] | 0 | 33 | 33 |  | 231 | 231 | 264
[8 empty] | 0 | 33 | 33 |  | 264 | 264 | 297
[8 empty] | 0 | 33 | 33 |  | 297 | 297 | 330
[8 empty] | 0 | 33 | 33 |  | 330 | 330 | 363
[8 empty] | 0 | 33 | 33 |  | 363 | 363 | 396
[8 empty] | 0 | 33 | 33 |  | 396 | 396 | 429
[8 empty] | 0 | 33 | 33 |  | 429 | 429 | 462
[8 empty] | 0 | 33 | 33 |  | 462 | 462 | 495
[8 empty] | 0 | 33 | 33 |  | 495 | 495 | 528
[8 empty] | 0 | 33 | 33 |  | 528 | 528 | 561
[8 empty] | 0 | 33 | 33 |  | 561 | 561 | 594
[8 empty] | 0 | 33 | 33 |  | 594 | 594 | 627
[8 empty] | 0 | 33 | 33 |  | 627 | 627 | 660
[8 empty] | 0 | 33 | 33 |  | 660 | 660 | 693
[8 empty] | 0 | 33 | 33 |  | 693 | 693 | 726
[8 empty] | 0 | 33 | 33 |  | 726 | 726 | 759
[8 empty] | 0 | 33 | 33 |  | 759 | 759 | 792
[8 empty] | 0 | 33 | 33 |  | 792 | 792 | 825
[8 empty] | 0 | 33 | 33 |  | 825 | 825 | 858
[8 empty] | 0 | 33 | 33 |  | 858 | 858 | 891
[8 empty] | 0 | 33 | 33 |  | 891 | 891 | 924
[8 empty] | 0 | 33 | 33 |  | 924 | 924 | 957
[8 empty] | 0 | 33 | 33 |  | 957 | 957 | 990
[8 empty] | 0 | 33 | 33 |  | 990 | 990 | 1023
[8 empty] | 0 | 33 | 33 |  | 1023 | 1023 | 1056
[8 empty] | 0 | 33 | 33 |  | 1056 | 1056 | 1089
[8 empty] | 0 | 33 | 33 |  | 1089 | 1089 | 1122
[8 empty] | 0 | 33 | 33 |  | 1122 | 1122 | 1155
[8 empty] | 0 | 33 | 33 |  | 1155 | 1155 | 1188
[8 empty] | 0 | 33 | 33 |  | 1188 | 1188 | 1221
[8 empty] | 0 | 33 | 33 |  | 1221 | 1221 | 1254
[8 empty] | 0 | 33 | 33 |  | 1254 | 1254 | 1287
[8 empty] | 0 | 33 | 33 |  | 1287 | 1287 | 1320
[8 empty] | 0 | 33 | 33 |  | 1320 | 1320 | 1353
[8 empty] | 0 | 33 | 33 |  | 1353 | 1353 | 1386
[8 empty] | 0 | 33 | 33 |  | 1386 | 1386 | 1419
[8 empty] | 0 | 33 | 33 |  | 1419 | 1419 | 1452
[8 empty] | 0 | 33 | 33 |  | 1452 | 1452 | 1485
[8 empty] | 0 | 33 | 33 |  | 1485 | 1485 | 1518
[8 empty] | 0 | 33 | 33 |  | 1518 | 1518 | 1551
[8 empty] | 0 | 33 | 33 |  | 1551 | 1551 | 1584
[8 empty] | 0 | 33 | 33 |  | 1584 | 1584 | 1617
[8 empty] | 0 | 33 | 33 |  | 1617 | 1617 | 1650
[8 empty] | 0 | 33 | 33 |  | 1650 | 1650 | 1683
[8 empty] | 0 | 33 | 33 |  | 1683 | 1683 | 1716
[8 empty] | 0 | 33 | 33 |  | 1716 | 1716 | 1749
[8 empty] | 0 | 33 | 33 |  | 1749 | 1749 | 1782
[8 empty] | 0 | 33 | 33 |  | 1782 | 1782 | 1815
[8 empty] | 0 | 33 | 33 |  | 1815 | 1815 | 1848
[8 empty] | 0 | 33 | 33 |  | 1848 | 1848 | 1881
[8 empty] | 0 | 33 | 33 |  | 1881 | 1881 | 1914
[8 empty] | 0 | 33 | 33 |  | 1914 | 1914 | 1947
[8 empty] | 0 | 33 | 33 |  | 1947 | 1947 | 1980
[8 empty] | 0 | 33 | 33 |  | 1980 | 1980 | 2013
[8 empty] | 0 | 33 | 33 |  | 2013 | 2013 | 2046
[8 empty] | 0 | 33 | 33 |  | 2046 | 2046 | 2079
[8 empty] | 0 | 33 | 33 |  | 2079 | 2079 | 2112
[8 empty] | 0 | 33 | 33 |  | 2112 | 2112 | 2145
[8 empty] | 0 | 33 | 33 |  | 2145 | 2145 | 2178
[8 empty] | 0 | 33 | 33 |  | 2178 | 2178 | 2211
[8 empty] | 0 | 33 | 33 |  | 2211 | 2211 | 2244
[8 empty] | 0 | 33 | 33 |  | 2244 | 2244 | 2277
[8 empty] | 0 | 33 | 33 |  | 2277 | 2277 | 2310
[8 empty] | 0 | 33 | 33 |  | 2310 | 2310 | 2343
[8 empty] | 0 | 33 | 33 |  | 2343 | 2343 | 2376
[8 empty] | 0 | 33 | 33 |  | 2376 | 2376 | 2409
[8 empty] | 0 | 33 | 33 |  | 2409 | 2409 | 2442
[8 empty] | 0 | 33 | 33 |  | 2442 | 2442 | 2475
[8 empty] | 0 | 33 | 33 |  | 2475 | 2475 | 2508
[8 empty] | 0 | 33 | 33 |  | 2508 | 2508 | 2541
[8 empty] | 0 | 33 | 33 |  | 2541 | 2541 | 2574
[8 empty] | 0 | 33 | 33 |  | 2574 | 2574 | 2607
[8 empty] | 0 | 33 | 33 |  | 2607 | 2607 | 2640
[8 empty] | 0 | 33 | 33 |  | 2640 | 2640 | 2673
[8 empty] | 0 | 33 | 33 |  | 2673 | 2673 | 2706
[8 empty] | 0 | 33 | 33 |  | 2706 | 2706 | 2739
[8 empty] | 0 | 33 | 33 |  | 2739 | 2739 | 2772
[8 empty] | 0 | 33 | 33 |  | 2772 | 2772 | 2805
[8 empty] | 0 | 33 | 33 |  | 2805 | 2805 | 2838
[8 empty] | 0 | 33 | 33 |  | 2838 | 2838 | 2871
[8 empty] | 0 | 33 | 33 |  | 2871 | 2871 | 2904
[8 empty] | 0 | 33 | 33 |  | 2904 | 2904 | 2937
[8 empty] | 0 | 33 | 33 |  | 2937 | 2937 | 2970
[8 empty] | 0 | 33 | 33 |  | 2970 | 2970 | 3003
[8 empty] | 0 | 33 | 33 |  | 3003 | 3003 | 3036
[8 empty] | 0 | 33 | 33 |  | 3036 | 3036 | 3069
[8 empty] | 0 | 33 | 33 |  | 3069 | 3069 | 3102
[8 empty] | 0 | 33 | 33 |  | 3102 | 3102 | 3135
[8 empty] | 0 | 33 | 33 |  | 3135 | 3135 | 3168
[8 empty] | 0 | 33 | 33 |  | 3168 | 3168 | 3201
[8 empty] | 0 | 33 | 33 |  | 3201 | 3201 | 3234
[8 empty] | 0 | 33 | 33 |  | 3234 | 3234 | 3267
[8 empty] | 0 | 33 | 33 |  | 3267 | 3267 | 3300
[8 empty] | 0 | 33 | 33 |  | 3300 | 3300 | 3333
[8 empty] | 0 | 33 | 33 |  | 3333 | 3333 | 3366
[8 empty] | 0 | 33 | 33 |  | 3366 | 3366 | 3399
[8 empty] | 0 | 33 | 33 |  | 3399 | 3399 | 3432
[8 empty] | 0 | 33 | 33 |  | 3432 | 3432 | 3465
[8 empty] | 0 | 33 | 33 |  | 3465 | 3465 | 3498
[8 empty] | 0 | 33 | 33 |  | 3498 | 3498 | 3531
[8 empty] | 0 | 33 | 33 |  | 3531 | 3531 | 3564
[8 empty] | 0 | 33 | 33 |  | 3564 | 3564 | 3597
[8 empty] | 0 | 33 | 33 |  | 3597 | 3597 | 3630
[8 empty] | 0 | 33 | 33 |  | 3630 | 3630 | 3663
[8 empty] | 0 | 33 | 33 |  | 3663 | 3663 | 3696
[8 empty] | 0 | 33 | 33 |  | 3696 | 3696 | 3729
[8 empty] | 0 | 33 | 33 |  | 3729 | 3729 | 3762
[8 empty] | 0 | 33 | 33 |  | 3762 | 3762 | 3795
[8 empty] | 0 | 33 | 33 |  | 3795 | 3795 | 3828
[8 empty] | 0 | 33 | 33 |  | 3828 | 3828 | 3861
[8 empty] | 0 | 33 | 33 |  | 3861 | 3861 | 3894
[8 empty] | 0 | 33 | 33 |  | 3894 | 3894 | 3927
[8 empty] | 0 | 33 | 33 |  | 3927 | 3927 | 3960
[8 empty] | 0 | 33 | 33 |  | 3960 | 3960 | 3993
[8 empty] | 0 | 33 | 33 |  | 3993 | 3993 | 4026
[8 empty] | 0 | 33 | 33 |  | 4026 | 4026 | 4059
[8 empty] | 0 | 33 | 33 |  | 4059 | 4059 | 4092
[8 empty] | 0 | 33 | 33 |  | 4092 | 4092 | 4125
[8 empty] | 0 | 33 | 33 |  | 4125 | 4125 | 4158
[8 empty] | 0 | 33 | 33 |  | 4158 | 4158 | 4191
[8 empty] | 0 | 33 | 33 |  | 4191 | 4191 | 4224
[8 empty] | 0 | 33 | 33 |  | 4224 | 4224 | 4257
[8 empty] | 0 | 33 | 33 |  | 4257 | 4257 | 4290
[8 empty] | 0 | 33 | 33 |  | 4290 | 4290 | 4323
[8 empty] | 0 | 33 | 33 |  | 4323 | 4323 | 4356
[8 empty] | 0 | 33 | 33 |  | 4356 | 4356 | 4389
[8 empty] | 0 | 33 | 33 |  | 4389 | 4389 | 4422
[8 empty] | 0 | 33 | 33 |  | 4422 | 4422 | 4455
[8 empty] | 0 | 33 | 33 |  | 4455 | 4455 | 4488
[8 empty] | 0 | 33 | 33 |  | 4488 | 4488 | 4521
[8 empty] | 0 | 33 | 33 |  | 4521 | 4521 | 4554
[8 empty] | 0 | 33 | 33 |  | 4554 | 4554 | 4587
[8 empty] | 0 | 33 | 33 |  | 4587 | 4587 | 4620
[8 empty] | 0 | 33 | 33 |  | 4620 | 4620 | 4653
[8 empty] | 0 | 33 | 33 |  | 4653 | 4653 | 4686
[8 empty] | 0 | 33 | 33 |  | 4686 | 4686 | 4719
[8 empty] | 0 | 33 | 33 |  | 4719 | 4719 | 4752
[8 empty] | 0 | 33 | 33 |  | 4752 | 4752 | 4785
[8 empty] | 0 | 33 | 33 |  | 4785 | 4785 | 4818
[8 empty] | 0 | 33 | 33 |  | 4818 | 4818 | 4851
[8 empty] | 0 | 33 | 33 |  | 4851 | 4851 | 4884
[8 empty] | 0 | 33 | 33 |  | 4884 | 4884 | 4917
[8 empty] | 0 | 33 | 33 |  | 4917 | 4917 | 4950
[8 empty] | 0 | 33 | 33 |  | 4950 | 4950 | 4983
[8 empty] | 0 | 33 | 33 |  | 4983 | 4983 | 5016
[8 empty] | 0 | 33 | 33 |  | 5016 | 5016 | 5049
[8 empty] | 0 | 33 | 33 |  | 5049 | 5049 | 5082
[8 empty] | 0 | 33 | 33 |  | 5082 | 5082 | 5115
[8 empty] | 0 | 33 | 33 |  | 5115 | 5115 | 5148
[8 empty] | 0 | 33 | 33 |  | 5148 | 5148 | 5181
[8 empty] | 0 | 33 | 33 |  | 5181 | 5181 | 5214
[8 empty] | 0 | 33 | 33 |  | 5214 | 5214 | 5247
[8 empty] | 0 | 33 | 33 |  | 5247 | 5247 | 5280
[8 empty] | 0 | 33 | 33 |  | 5280 | 5280 | 5313
[8 empty] | 0 | 33 | 33 |  | 5313 | 5313 | 5346
[8 empty] | 0 | 33 | 33 |  | 5346 | 5346 | 5379
[8 empty] | 0 | 33 | 33 |  | 5379 | 5379 | 5412
[8 empty] | 0 | 33 | 33 |  | 5412 | 5412 | 5445
[8 empty] | 0 | 33 | 33 |  | 5445 | 5445 | 5478
[8 empty] | 0 | 33 | 33 |  | 5478 | 5478 | 5511
[8 empty] | 0 | 33 | 33 |  | 5511 | 5511 | 5544
[8 empty] | 0 | 33 | 33 |  | 5544 | 5544 | 5577
[8 empty] | 0 | 33 | 33 |  | 5577 | 5577 | 5610
[8 empty] | 0 | 33 | 33 |  | 5610 | 5610 | 5643
[8 empty] | 0 | 33 | 33 |  | 5643 | 5643 | 5676
[8 empty] | 0 | 33 | 33 |  | 5676 | 5676 | 5709
[8 empty] | 0 | 33 | 33 |  | 5709 | 5709 | 5742
[8 empty] | 0 | 33 | 33 |  | 5742 | 5742 | 5775
[8 empty] | 0 | 33 | 33 |  | 5775 | 5775 | 5808
[8 empty] | 0 | 33 | 33 |  | 5808 | 5808 | 5841
[8 empty] | 0 | 33 | 33 |  | 5841 | 5841 | 5874
[8 empty] | 0 | 33 | 33 |  | 5874 | 5874 | 5907
[8 empty] | 0 | 33 | 33 |  | 5907 | 5907 | 5940
[8 empty] | 0 | 33 | 33 |  | 5940 | 5940 | 5973
[8 empty] | 0 | 33 | 33 |  | 5973 | 5973 | 6006
[8 empty] | 0 | 33 | 33 |  | 6006 | 6006 | 6039
[8 empty] | 0 | 33 | 33 |  | 6039 | 6039 | 6072
[8 empty] | 0 | 33 | 33 |  | 6072 | 6072 | 6105
Formulas:
Min Create = MIN(Table3[Created])
Max Create = MAX(Table3[Created])
Min Close = MIN(Table3[Closed])
Max Close = MAX(Table3[Closed])
Max Close = [Max Create]

## Summary Observations (hidden)
# | Issue | Risk Rating | Facility | Department | IA issued | Year identified | Status | Correction in Status
1 | Human Resources Management Program "Invision" | High | Khairan Resort | 2017 | Newly identified | Not resolved | Not resolved | Not resolved
2 | Calculation of end of service benefits | Moderate | Khairan Resort | 2017 | Newly identified | Not resolved | Not resolved | Not resolved
3 | Training courses for staff | Moderate | Khairan Resort | 2017 | Newly identified | Not resolved | Open | Not resolved
4 | Succession Planning | Moderate | Khairan Resort | 2017 | Newly identified | Not resolved | Open | Not resolved
5 | Bank Reconciliations | High | Khairan Resort | 2017 | Newly identified | Not resolved | Open | Not resolved
6 | Attend staff "Al Bahar Restaurant" | High | Khiran Resort | 2017 | Newly identified | Not resolved | Not resolved | Not resolved
7 | Warehouse control | Moderate | Khiran Resort | 2017 | Newly identified | Not resolved | Not resolved | Not resolved
8 | Guest documents | High | Khiran Resort | 2017 | Newly identified | Not resolved | Not resolved | Not resolved
9 | Absence of strategy | Moderate | Khiran Resort | 2017 | Newly identified | Not resolved | Not resolved | Not resolved
10 | Maintenance work | High | Khiran Resort | 2017 | Newly identified | Not resolved | Not resolved | Not resolved
11 | Evaluation of service contracts | Moderate | Khiran Resort | 2017 | Newly identified | Not resolved | Not resolved | Not resolved
12 | the Preservation of the environment | low | Khiran Resort | 2017 | Newly identified | Not resolved | Not resolved | Not resolved
13 | Failure to comply with the booking and reception rules on obtaining copies of civil cards and marriage documents | High | Khiran Resort | 2017 | Follow up | Not resolved | Not resolved | Not resolved
14 | Food that comes out of the kitchen is not matched by invoices issued by the cashir | Moderate | Khiran Resort | 2017 | Follow up | Partially closed | Not resolved | Not resolved
15 | Lack of license from the relevant authorities regarding existing buildings and buildings under construction within the park | High | Khiran Resort | 2017 | Follow up | Not resolved | Not resolved | Not resolved
16 | Lack of marketing plan based on scientific grounds | High | Khiran Resort | 2017 | Follow up | Not resolved | Not resolved | Not resolved
17 | The absence of a quality auditor independent of operations within the organizational structure | Moderate | Khiran Resort | 2017 | Follow up | Not resolved | Not resolved | Not resolved
18 | Lack of independence in opening complaints and suggestions box | Moderate | Khiran Resort | 2017 | Follow up | Partially closed | Not resolved | Not resolved
19 | Insufficient signs in the park | Value added | Khiran Resort | 2017 | Follow up | Not resolved
20 | The absence of periodic and independent monitoring of the Opera System | High | Khiran Resort | 2017 | Follow up | Not resolved
21 | Non - definition of the cost of dishes on the automated system Micros - 2010 | low | Khairan Resort | 2017 | Follow up | Not resolved
22 | Absence of a plan of action and strategic objectives for Al Khairan Park | High | Khairan Resort | 2017 | Follow up | Not resolved
23 | The absence of an approved tourist classification for Al - Khairan Park - 2010 | High | Khairan Resort | 2017 | Follow up | Not resolved
24 | Quality Standards | High | Khairan Resort | 2017 | Follow up | Not resolved
25 | Website and automated booking - 2010 | High | Khairan Resort | 2017 | Follow up | Not resolved
26 | Not updating the job description explaining the roles, duties and responsibilities of staff - 2010 | High | Khairan Resort | 2017 | Follow up | Partially closed
27 | Absence of interactive TV system in the rooms and chalets of the park (INTER- ACTIVE TV SYSTEM) - 2010 | Value added | Khairan Resort | 2017 | Follow up | Not resolved
28 | No monthly reconciliation between the end of service provision and the staff leave in the Human Resources System (Invision) as compared to that recorded in the accounting system (SUN) | Moderate | Khairan Resort | 2017 | Follow up | Not resolved
29 | The Department of Personnel shall keep the employees' travel documents in the park | High | Khairan Resort | 2017 | Follow up | Not resolved
30 | High turnover of staff | High | Khairan Resort | 2017 | Follow up | Not resolved
31 | Failure to document exit interview for resigning employees to document the results of the discussion of reasons for employee resignation | Moderate | Khairan Resort | 2017 | Follow up | Not resolved
32 | There is no evidence of conformity between the assets and copies of the recruitment documents | low | Khairan Resort | 2017 | Follow up | Not resolved
33 | Absence of safety and safety standards for personnel in maintenance operations | High | Khairan Resort | 2017 | Follow up | Not resolved

## Sheet1 (hidden)
for | Purchasing Department
Overall Risk Rating |  | Pointer
Start | 20 | Value | 100
Incidental | 30 | Pointer | 0.5
Minor | 50 | End | 99.5
Moderate | 100
|  | Net Value | 100
insert drop down list for all departments