## Sheet1
Activity ID | Activity Name | WBSL1 | WBSL2 | WBSL3 | WBSL4 | WBSL5 | WBSL6
A1090 | Excavation up to Basement Foundation Level | Building Project | Construction | Substructurte
A1110 | Temporary dewatering | Building Project | Construction | Substructurte
A1070 | Raft / footing excavation, and final formation | Building Project | Construction | Substructurte
A1080 | Foundation works (including Underground services, and waterproofing) | Building Project | Construction | Substructurte
A1100 | Basements concrete works (up to ground floor level) | Building Project | Construction | Substructurte
A1120 | Concrete columns, core walls, and stairs | Building Project | Construction | Superstructure
A1130 | Concrete beams and slabs | Building Project | Construction | Superstructure
A1140 | Masonry works | Building Project | Construction | Superstructure
A1160 | MEP works 1st Fix | Building Project | Construction | MEP Works
A1150 | Plaster works | Building Project | Construction | Rough Finishes
A1310 | Façade works (Precast concrete + Finishes) | Building Project | Construction | Façade Works
A1170 | Wet are waterproofing | Building Project | Construction | Rough Finishes
A1190 | Paint 1st coat | Building Project | Construction | Final Finishes
A1210 | MEP works 2 nd Fix | Building Project | Construction | MEP Works
A1200 | Tiles works | Building Project | Construction | Rough Finishes
A1220 | Suspended ceilings works | Building Project | Construction | Final Finishes
A1260 | Doors, windows, and hardware | Building Project | Construction | Final Finishes
A1280 | Conveying system | Building Project | Construction | Conveying system
A1180 | Roofing system | Building Project | Construction | Roofing
A1240 | Paint final coat | Building Project | Construction | Final Finishes
A1290 | External works and landscaping | Building Project | Construction | External works
A1230 | MEP works final Fix | Building Project | Construction | MEP Works
A1250 | Glazing works | Building Project | Construction | Final Finishes
A1270 | Metal works | Building Project | Construction | Final Finishes
A1320 | Testing and commissioning | Building Project | Testing and commissioning | Testing and commissioning
A1300 | Site furnishings | Building Project | Construction | Final Finishes