## Option No. (2)-Short
Project Delivery Schedule
| Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 20 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY |  | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2019
|  | DELIVERY DATE | [5 empty] | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 42 | 43 | 44
| P.O | 2019-09-08 | 1 | 6 | 1 | 9 | 30%
| Order ACK Letter | 2019-09-08 | 1 | 8 | 1 | 0 | 0%
| Down Payment | 2018-12-06 | 1 | 8 | 1 | 0 | 0%
| Customer Approval | 2018-12-16 | 1 | 8 | 1 | 0 | 0%
| Factory hand over | 2018-12-16 | 1 | 7 | 1 | 0 | 0%
| Purchasing Materials | 2018-12-06 | 1 | 5 | 1 | 0 | 0%
| Materials received | 2018-12-16 | 1 | 0 | 1 | 0 | 0%
| Time of Production | 2018-12-06 | 1 | 0 | 1 | 0 | 0%
| Ready to delivery | 2018-12-16 | 1 | 0 | 1 | 0 | 0%
POWER SYSTEM STUDY | Data Collection | 2018-12-30 | 4 | 2 | 0 | 0 | 0%
| Power System Study Stage 1 (Aggregate) | 2019-02-24 | 6 | 8 | 0 | 0 | 0%
| Load Flow Analysis |  | 3 | 2 | 0 | 0 | 0%
| Short Circuit Study |  | 5 | 1 | 0 | 0 | 0%
| Relay Coordination Study |  | 6 | 2 | 0 | 0 | 0%
| Transient Stability Analysis |  | 8 | 2 | 0 | 0 | 0%
| Power System Study Stage 2 (Aggregate) | 2019-03-10 | 6 | 10 | 0 | 0 | 0%
| Motor Starting Analysis |  | 10 | 2 | 0 | 0 | 0%
| Harmonic Analysis |  | 12 | 1 | 0 | 0 | 0%
| Cables Sizing |  | 10 | 4 | 0 | 0 | 0%
| Lightning Protection System design |  | 14 | 3 | 0 | 0 | 0%
| Review of Power System Study | 2019-03-17 | 14 | 3 | 0 | 0 | 0%
manufacturing base design | Ring Main Units | 2019-01-13 | 6 | 2 | 0 | 0 | 0%
| Manufacturing Clearance Design | 2019-01-14 | 8 | 4 | 0 | 0 | 0%
| Manufacturing Approval | 2019-01-15 | 12 | 1 | 0 | 0 | 0%
| Manufacturing & Delivery DDP to Site | 2019-01-16 | 13 | 13 | 0 | 0 | 0%
| Transformers | 2019-01-13 | 6 | 2 | 0 | 0 | 0%
| Manufacturing Clearance Design | 2019-01-18 | 8 | 4 | 0 | 0 | 0%
| Manufacturing Approval | 2019-01-19 | 12 | 1 | 0 | 0 | 0%
| Manufacturing & Delivery DDP to Site | 2019-01-20 | 13 | 13 | 0 | 0 | 0%
| Medium Voltage Switchgear | 2019-01-13 | 6 | 2 | 0 | 0 | 0% | bar: 6
| Manufacturing Clearance Design | 2019-01-22 | 8 | 4 | 0 | 0 | 0%
| Manufacturing Approval | 2019-01-23 | 12 | 1 | 0 | 0 | 0%
| Manufacturing & Delivery DDP to Site | 2019-01-24 | 13 | 19 | 0 | 0 | 0%
| Low Voltage Switchgear | 2019-01-13 | 6 | 2 | 0 | 0 | 0%
| Manufacturing Clearance Design - Base Design |  | 12 | 2 | 0 | 0 | 0%
| Manufacturing Clearance Design - Detailed |  | 15 | 2 | 0 | 0 | 0%
| Manufacturing Approval |  | 14 | 1 | 0 | 0 | 0%
| Manufacturing & Delivery DDP to Site: MDB |  | 17 | 14 | 0 | 0 | 0%
| Manufacturing & Delivery DDP to Site: Withdrawables |  | 17 | 18 | 0 | 0 | 0%
| Manufacturing & Delivery DDP to Site: VFD & SS Panels |  | 17 | 18 | 0 | 0 | 0%
| Manufacturing & Delivery DDP to Site: Power Factor Panels |  | 17 | 18 | 0 | 0 | 0%
| Manufacturing & Delivery DDP to Site: Local Control Stations |  | 17 | 12 | 0 | 0 | 0%
Factory Acceptance Test will add 1 Week on the deliveries
| Review & approval (1) | 2018-01-27 | 8 | 2 | 0 | 0 | 0%
manufacturing details design | Ring Main Units | 2019-02-17 | 10 | 2 | 0 | 0 | 0%
| Transformers | 2019-02-17 | 10 | 2 | 0 | 0 | 0%
| Medium Voltage Switchgear | 2019-02-17 | 10 | 2 | 0 | 0 | 0%
| Low Voltage Switchgear | 2019-02-17 | 10 | 2 | 0 | 0 | 0%
| Review & approval (2) | 2019-02-24 | 12 | 2 | 0 | 0 | 0%
manufacturing + FAT | Ring Main Units | 2019-04-21 | 10 | 12 | 0 | 0 | 0% | bar: 15 to 24
| Transformers | 2019-04-21 | 10 | 12 | 0 | 0 | 0% | bar: 15 to 26
| Medium Voltage Switchgear | 2019-06-16 | 10 | 20 | 0 | 0 | 0% | bar: 15 to 34
| Low Voltage Switchgear | 2019-07-14 | 17 | 20 | 0 | 0 | 0% | bar: 24 to 40; 43 to 44
| Service Scope 1: RMUs, Trafos, MV Swithcgear, LV Switchgear |  | 0 | 0 | 0 | 0 | 0%
Notes :-
The above mentioned dates are preliminary, where may will changed based on the exact date of contract signatures,approval dates , receipt the down payment, L/C Opening date...etc., however the below milestones are the basis of the changes:
1) Delivery milestones:-
| 1.1) Contract signatures from Both Parties (ABB & BIA). |  |  |  |  | DONE | 2018-12-20
1.2) Receipt the advance Payment as illustrated in the contract .
1.3) BIA Approval for Power System Study (1) & (2)
1.4) BIA Approval for manufacturing base design & details design.
1.5) BIA approval to proceed with Manufacturing , however the manufacturing period will be as following :-
I) Ring Main Units :- (10-12) Working weeks Starting from date of proceed signal with Manufacturing & L/C opening date .
II) Transformers:- (12) Working weeks Starting from date of proceed signal with Manufacturing & L/C opening date .
III) MV Switchgear:- (20)Working weeks Starting from date of proceed signal with Manufacturing & L/C opening date .
IV) Low Voltage Switchgear:- (18-20) Working weeks Starting from date of proceed signal with Manufacturing & L/C opening date .