## Option No. (2)-Short
Project Delivery Schedule
Select a period to highlight at right. A legend describing the charting follows. | [7 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY |  |  |  | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 2019
|  |  | Factory hand over date | [5 empty] | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week | Week
W.O NO# | PROJECT / CUSTOMER NAME | STATUS | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 42 | 43 | 44
AMP0001-1-2019 |  |  | 2019-03-01 | 1 | 8 | 1 |  | 100%
AMP0003-1-2019 |  |  | 2019-02-06 | 1 | 8 | 1 | 39 | 10%
AMP0008-2-2019 |  |  | 2019-03-03 | 1 | 11 | 1 | 35 | 0%
AMP0012-2-2019 |  |  | 2019-04-02 | 1 | 6 | 1 |  | 100% | bar: 1 to 20
AMP0016-3-2019 |  |  | 2019-06-20 | 1 | 8 | 1 |  | 100% | bar: 1 to 20
AMP0020-4-2019 |  |  | N/A | 1 | 8 | 1 | 0 | 10%
AMP0024-4-2019 |  |  | 2019-06-23 | 1 | 8 | 1 |  | 100%
AMP0025-5-2019 |  |  | N/A | 1 | 25 | 1 | 0 | 0%
AMP0033-6-2019 |  |  | N/A | 1 | 1 | 1 | 0 | 15%
AMP0034-7-2019 |  |  | 2019-07-07 | 1 | 0 | 1 | 17 | 0%
AMP0035-7-2019 |  |  | 2019-07-24 | 1 | 10 | 1 | 15 | 50%
AMP0037-8-2019 |  |  | N/A | 1 | 0 | 1 | 0 | 0%
AMP0038-8-2019 |  |  | 2019-08-21 | 1 | 4 | 1 |  | 100%
AMP0039-8-2019 |  |  | N/A | 1 | 0 | 1 | 0 | 0%
AMP0040-8-2019 |  |  | 2019-09-16 | 1 | 3 | 1 | 7 | 65%
AMP0041-8-2019 |  |  | 2019-08-31 | 1 | 10 | 1 | 9 | 15%
AMP0042-9-2019 |  |  | 2019-09-09 | 1 | 1 | 1 | 8 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2019-09-08 | 1 | 0 | 1 | 8 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2019-09-08 | 1 | 0 | 1 | 8 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2019-09-08 | 1 | 0 | 1 | 8 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2019-09-08 | 1 | 0 | 1 | 8 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2019-09-08 | 1 | 0 | 1 | 8 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2019-09-08 | 1 | 0 | 1 | 8 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
|  |  | 2018-12-06 | 1 | 0 | 1 | 47 | 0%
|  |  | 2018-12-16 | 1 | 0 | 1 | 46 | 0%
Formulas:
ACTUAL DURATION = IF([PERCENT COMPLETE]>=100%,"",IF(ISNUMBER([Factory hand over date]),INT(1+(TODAY()-[Factory hand over date])/7),0))

## Sheet1
| تاريخ التعميد | تاريخ بداية العمل | نسبة الانجازالحالية
AMP0001-1-2019
AMP0003-1-2019
AMP0008-2-2019
AMP0012-2-2019
AMP0016-3-2019
AMP0020-4-2019
AMP0024-4-2019
AMP0025-5-2019
AMP0033-6-2019
AMP0034-7-2019
AMP0035-7-2019
AMP0037-8-2019
AMP0038-8-2019
AMP0039-8-2019
AMP0040-8-2019
AMP0041-8-2019
AMP0042-9-2019