{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Data","Repport","Sheet2"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Data","index":0,"n_rows":12,"n_cols":13,"rows_kept":12,"cut":false,"hidden":false,"merged":[]}
[]
["المشروع","رقم المستخلص","النوع","تاريخ الاستحقاق","الحالة","رقم المعاملة","المبلغ","الضريبة","تارخ الحالة","المسئول","منصة اعتماد"]
["بن جلوي",20,"مستخلص","2020-02-01","تم الرفع",123456,125000,7000,"2020-02-15","جهة الاشراف بالموقع","-"]
["بن جلوي",20,"مستخلص","2020-02-01","رقم صادر",455555,120000,5000,"2020-03-01","الصيانة والتشغيل","مطالبة"]
["بن جلوي",20,"مستخلص","2020-03-14","امر دفع",6666,115000,3500,"2020-03-10","المالية","امر صرف"]
["البطحاء",25,"مستخلص","2020-03-10","تم الرفع",88888,88000,5000,"2020-03-12","جهة الاشراف بالموقع","-"]
["البطحاء",25,"مستخلص","2020-03-10","رقم صادر",6666,88000,6000,"2020-03-14","الصيانة والتشغيل","مطالبة"]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,"ملاحظة : يمكن تكرار اسم المشروع"]
[null,null,null,null,null,null,null,null,null,null,null,null,"ولكن لا يتكرر اسم المشروع مع رقم المستخلص"]

{"sheet":"Repport","index":1,"n_rows":5,"n_cols":11,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
[]
["المشروع","رقم المستخلص","النوع","تاريخ الاستحقاق","الحالة","رقم المعاملة","المبلغ","الضريبة","تحديث الحالة","المسئول","منصة اعتماد"]
["بن جلوي",20,"مستخلص","2020-02-01","رقم صادر",455555,120000,5000,"2020-03-01","الصيانة والتشغيل","مطالبة"]
["بن جلوي",20,"مستخلص","2020-03-14","امر دفع",6666,115000,3500,"2020-03-10","المالية","امر صرف"]
["البطحاء",25,"مستخلص","2020-03-10","رقم صادر",6666,88000,6000,"2020-03-14","الصيانة والتشغيل","مطالبة"]

{"sheet":"Sheet2","index":2,"n_rows":19,"n_cols":22,"rows_kept":19,"cut":false,"hidden":true,"merged":[]}
["بيان المستخلصات الشهرية ومتابعتها"]
[]
["المشروع","الجهة","استلام المشروع","نهاية المشروع","يوليو 2019","اغسطس2019","سبتمبر 2019","أكتوبر 2019","نوفمبر2019","ديسمبر2019","يناير 2020","فبراير 2020","مارس 2020","ابريل 2020","مايو 2020","يونيو 2020","يوليو 2020","أغسطس 2020","سبتمبر 2020","أكتوبر 2020","نوفمبر 2020","ديسمبر 2020"]
["المباني المجاورة","وزارة الحرس الوطني","2019-09-05",null,null,null,null,null,null,null,null,null,"2020-03-04","2020-04-04","2020-05-04","2020-06-04","2020-07-04","2020-08-04","2020-09-04","2020-10-04","2020-11-04","2020-12-04"]
["مكتب الرئيس","الهيئة العامة للرياضة","2019-09-06",null,null,null,null,null,null,null,null,null,null,"2020-04-05","2020-05-05","2020-06-05","2020-07-05","2020-08-05","2020-09-05","2020-10-05","2020-11-05","2020-12-05"]
["القوات البرية","الشربيني","2017-07-09",null,null,null,null,null,null,"2020-12-08","2020-01-08","2020-02-08","2020-03-08","2020-04-08","2020-05-08","2020-06-08","2020-07-08","2020-08-08","2020-09-08","2020-10-08","2020-11-08","2020-12-08"]
["مدينة التدريب","رئاسة الحرس الملكي","2020-02-10",null,null,null,null,null,null,null,null,"-","2020-03-09","2020-04-09","2020-05-09","2020-06-09","2020-07-09","2020-08-09","2020-09-09","2020-10-09","2020-11-09","2020-12-09"]
["الطيران","وزارة الحرس الوطني","2015-04-16",null,null,null,null,null,null,null,null,null,"2020-03-15","2020-04-15","2020-05-15","2020-06-15","2020-07-15","2020-08-15","2020-09-15","2020-10-15","2020-11-15","2020-12-15"]
["قوات الأمن الجديد","قوات الأمن الخاصة","2019-12-24",null,null,null,null,null,null,null,null,null,"2020-03-23","2020-04-23","2020-05-23","2020-06-23","2020-07-23","2020-08-23","2020-09-23","2020-10-23","2020-11-23","2020-12-23"]
["التدخل السريع","وزارة الحرس الوطني","2018-07-26",null,null,null,null,null,null,null,null,null,"2020-03-25","2020-04-25","2020-05-25","2020-06-25","2020-07-25","2020-08-25","2020-09-25","2020-10-25","2020-11-25","2020-12-25"]
["بن جلوي","الهيئة العامة للرياضة","2019-06-26",null,null,null,null,null,null,null,null,null,"2020-03-25","2020-04-25","2020-05-25","2020-06-25","2020-07-25","2020-08-25","2020-09-25","2020-10-25","2020-11-25","2020-12-25"]
["تركي","وزارة الحرس الوطني","2017-07-07",null,null,null,null,null,null,null,null,null,"2020-03-26","2020-04-26","2020-05-26","2020-06-26","2020-07-26","2020-08-26","2020-09-26","2020-10-26","2020-11-26","2020-12-26"]
["الحرس الملكي","رئاسة الحرس الملكي","2019-10-28",null,null,null,null,null,null,null,null,null,"2020-03-29","2020-04-29","2020-05-29","2020-06-29","2020-07-29","2020-08-29","2020-09-29","2020-10-29","2020-11-29","2020-12-29"]
["ضباء","الجمارك","2016-07-15",null,null,null,null,null,null,null,null,"2020-02-29","2020-03-31","2020-04-30","2020-05-31","2020-06-30","2020-07-31","2020-08-31","2020-09-30","2020-10-31","2020-11-30","2020-12-31"]
["البطحاء","الجمارك","2017-12-10",null,null,null,null,null,null,null,null,"2020-02-29","2020-03-31","2020-04-30","2020-05-31","2020-06-30","2020-07-31","2020-08-31","2020-09-30","2020-10-31","2020-11-30","2020-12-31"]
["قوى الأمن","وزارة الداخلية","2017-06-01",null,null,null,null,null,null,null,null,null,"2020-03-31","2020-04-30","2020-05-31","2020-06-30","2020-07-31","2020-08-31","2020-09-30","2020-10-31","2020-11-30","2020-12-31"]
["مطابع الهيئة","الهيئة العامة للرياضة","2020-01-01",null,null,null,null,null,null,null,"2020-01-31","2020-02-29","2020-03-31","2020-04-30","2020-05-31","2020-06-30","2020-07-31","2020-08-31","2020-09-30","2020-10-31","2020-11-30","2020-12-31"]
["المختبرات","امانة الرياض","2017-01-16",null,null,null,null,null,"2019-11-30","2019-12-06","-","-","-","-","-","-","-","-","-","-","-","-"]
["العديد","الجمارك",null,null,"2019-07-31","2019-08-31","2019-09-30","2019-10-31","2019-11-30","2019-12-31","2020-01-31","2020-02-29","2020-03-31","2020-04-30","2020-05-31","2020-06-30","2020-07-31","2020-08-31","2020-09-30","2020-10-31","2020-11-30","2020-12-31"]