## Cash Flow Sammry
Paymant Status | (All)
Periority | (All)
Row Labels | Sum of Amount
Chipsy October EP | 1484029.39
ABB | 165300
19-54-PO-HE-137-00 | 165300
Alammia | 28137
19-54-PO-SS-098-01 | 28137
BETA | 5100
19-54-PO-SS-103-00 | 5100
EGAT | 132734.32
19-54-PO-SS-079-01 | 132734.32
Electric Technology | 1092855.3
19-54-PO-HE-001-02 | 1092855.3
Hard Metal | 39645
19-54-PO-SS-080-01 | 39645
ONLINE | 19305.64
19-54-PO-IS-130-00 | 8692.68
19-54-PO-IS-138-00 | 10612.96
Sewedic Misr | 952.13
19-54-PO-RR-139-00 | 952.13
Grand Total | 1484029.39

## Old
[5 empty] | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4
Project Name | Project Code | Supplier | PO # | PO Code | Type 1 | Amount 1 | Paymant Date 1 | Paymant Status 1 | Mode Of Paymant 1 | Type 2 | Amount 2 | Paymant Date 2 | Paymant Status 2 | Mode Of Paymant 2 | Type 3 | Amount 3 | Paymant Date 3 | Paymant Status 3 | Mode Of Paymant 3 | Type 4 | Amount 4 | Paymant Date 4 | Paymant Status 4 | Mode Of Paymant 4 | Periority
Chipsy October EP | 19#54 | Electric Technology | 1 | 19-54-PO-HE-001-02 | Down Payment | 95045.79 | 2020-03-01 | Paid | Cash | Shopdrawing | 190091.58 | 2020-03-02 | Paid | Later 1 Month | Delivery | 527283.29 | 2020-04-15 | Paid | Later 45 Days | Delivery | 280434.64 | 2020-06-27 | Not Paid | Later 45 Days | A+
Chipsy October EP | 19#54 | EGAT | 79 | 19-54-PO-SS-079-01 | Down Payment | 33183.58 | 2020-03-29 | Paid | Cash | Delivery | 99550.74 | 2020-06-11 | Not Paid | Cash | [10 empty] | A
Chipsy October EP | 19#54 | Hard Metal | 80 | 19-54-PO-SS-080-01 | Delivery | 25000 | 2020-04-26 | Paid | Later 1 Month | Delivery | 14645 |  | Not Paid | Later 1 Month | [10 empty] | A
Chipsy October EP | 19#54 | Alammia | 98 | 19-54-PO-SS-098-01 | Delivery | 28104 | 2020-04-26 | Paid | Later 45 Days | Delivery | 33 |  | Not Paid | Later 1 Month | [10 empty] | A+
Chipsy October EP | 19#54 | BETA | 103 | 19-54-PO-SS-103-00 | Delivery | 3200 | 2020-04-26 | Paid | Later 1 Month | Delivery | 1900 |  | Not Paid | Later 1 Month | [10 empty] | A+
Chipsy October EP | 19#54 | ONLINE | 130 | 19-54-PO-IS-130-00 | Delivery | 4346.34 |  | Not Paid | Later 1 Month | Delivery | 4346.34 |  | Not Paid | Later 2 Months | [10 empty] | A
Chipsy October EP | 19#54 | ABB | 137 | 19-54-PO-HE-137-00 | Down Payment | 41325 | 2020-06-04 | Paid | Cash | Delivery | 107445 |  | Not Paid | Cash | Installation | 16530 |  | Not Paid | Cash | [5 empty] | A
Chipsy October EP | 19#54 | ONLINE | 138 | 19-54-PO-IS-138-00 | Delivery | 5306.48 |  | Not Paid | Later 1 Month | Delivery | 5306.48 |  | Not Paid | Later 2 Months | [10 empty] | A
Chipsy October EP | 19#54 | Sewedic Misr | 139 | 19-54-PO-RR-139-00 | Delivery | 952.13 |  | Not Paid | Later 2 Months | [15 empty] | A+
الجزء اللي باللون الاصفر عباره عن طلبات شراء وباقي الاجزاء عباره عن دفعات
لما بفلتر هنا عن الدفعات اللي لسا ما ادفاعتش بيجيب قيمتها و بيتجاهل باقي الدفعات
المطلوب دمج الدفعات تحت بعض ويكون الشكل مثل صفحه NEW

## New
محتاج كود او اي شي يعمله بالطريقه دي علشان اطلع منه Sammry مثل الموجود في اول صفحه وللعلم الشيت الاساسي فيه بيانات كتير جدا يعني صعب اعمله يدوي
Project Name | Project Code | Supplier | PO # | PO Code | Type | Amount | Paymant Date | Paymant Status | Mode Of Paymant | Periority
Chipsy October EP | 19#54 | Electric Technology | 1 | 19-54-PO-HE-001-02 | Down Payment | 95045.79 | 2020-03-01 | Paid | Cash | A+
Chipsy October EP | 19#54 | Electric Technology | 1 | 19-54-PO-HE-001-02 | Shopdrawing | 190091.58 | 2020-03-02 | Paid | Later 1 Month | A+
Chipsy October EP | 19#54 | Electric Technology | 1 | 19-54-PO-HE-001-02 | Delivery | 527283.29 | 2020-04-15 | Paid | Later 45 Days | A+
Chipsy October EP | 19#54 | Electric Technology | 1 | 19-54-PO-HE-001-02 | Delivery | 280434.64 | 2020-06-27 | Not Paid | Later 45 Days | A+
Chipsy October EP | 19#54 | EGAT | 79 | 19-54-PO-SS-079-01 | Down Payment | 33183.58 | 2020-03-29 | Paid | Cash | A
Chipsy October EP | 19#54 | EGAT | 79 | 19-54-PO-SS-079-01 | Delivery | 99550.74 | 2020-06-11 | Not Paid | Cash | A
Chipsy October EP | 19#54 | EGAT | 79 | 19-54-PO-SS-079-01
Chipsy October EP | 19#54 | EGAT | 79 | 19-54-PO-SS-079-01
Chipsy October EP | 19#54 | Hard Metal | 80 | 19-54-PO-SS-080-01 | Delivery | 25000 | 2020-04-26 | Paid | Later 1 Month | A
Chipsy October EP | 19#54 | Hard Metal | 80 | 19-54-PO-SS-080-01 | Delivery | 14645 |  | Not Paid | Later 1 Month | A
Chipsy October EP | 19#54 | Hard Metal | 80 | 19-54-PO-SS-080-01
Chipsy October EP | 19#54 | Hard Metal | 80 | 19-54-PO-SS-080-01
Chipsy October EP | 19#54 | Alammia | 98 | 19-54-PO-SS-098-01 | Delivery | 28104 | 2020-04-26 | Paid | Later 45 Days | A+
Chipsy October EP | 19#54 | Alammia | 98 | 19-54-PO-SS-098-01 | Delivery | 33 |  | Not Paid | Later 1 Month | A+
Chipsy October EP | 19#54 | Alammia | 98 | 19-54-PO-SS-098-01
Chipsy October EP | 19#54 | Alammia | 98 | 19-54-PO-SS-098-01
Chipsy October EP | 19#54 | BETA | 103 | 19-54-PO-SS-103-00 | Delivery | 3200 | 2020-04-26 | Paid | Later 1 Month | A
Chipsy October EP | 19#54 | BETA | 103 | 19-54-PO-SS-103-00 | Delivery | 1900 |  | Not Paid | Later 1 Month | A
Chipsy October EP | 19#54 | BETA | 103 | 19-54-PO-SS-103-00
Chipsy October EP | 19#54 | BETA | 103 | 19-54-PO-SS-103-00
Chipsy October EP | 19#54 | ONLINE | 130 | 19-54-PO-IS-130-00 | Delivery | 4346.34 |  | Not Paid | Later 1 Month | A
Chipsy October EP | 19#54 | ONLINE | 130 | 19-54-PO-IS-130-00 | Delivery | 4346.34 |  | Not Paid | Later 2 Months | A
Chipsy October EP | 19#54 | ONLINE | 130 | 19-54-PO-IS-130-00
Chipsy October EP | 19#54 | ONLINE | 130 | 19-54-PO-IS-130-00
Chipsy October EP | 19#54 | ABB | 137 | 19-54-PO-HE-137-00 | Down Payment | 41325 | 2020-06-04 | Paid | Cash | A
Chipsy October EP | 19#54 | ABB | 137 | 19-54-PO-HE-137-00 | Delivery | 107445 |  | Not Paid | Cash | A
Chipsy October EP | 19#54 | ABB | 137 | 19-54-PO-HE-137-00 | Installation | 16530 |  | Not Paid | Cash | A
Chipsy October EP | 19#54 | ABB | 137 | 19-54-PO-HE-137-00
Chipsy October EP | 19#54 | ONLINE | 138 | 19-54-PO-IS-138-00 | Delivery | 5306.48 |  | Not Paid | Later 1 Month | A
Chipsy October EP | 19#54 | ONLINE | 138 | 19-54-PO-IS-138-00 | Delivery | 5306.48 |  | Not Paid | Later 2 Months | A
Chipsy October EP | 19#54 | ONLINE | 138 | 19-54-PO-IS-138-00
Chipsy October EP | 19#54 | ONLINE | 138 | 19-54-PO-IS-138-00
Chipsy October EP | 19#54 | Sewedic Misr | 139 | 19-54-PO-RR-139-00 | Delivery | 952.13 |  | Not Paid | Later 2 Months | A
Chipsy October EP | 19#54 | Sewedic Misr | 139 | 19-54-PO-RR-139-00
Chipsy October EP | 19#54 | Sewedic Misr | 139 | 19-54-PO-RR-139-00
Chipsy October EP | 19#54 | Sewedic Misr | 139 | 19-54-PO-RR-139-00