## STEPS Workplan
STEPS Workplan
Please specify the month & year of the starting & ending date of each activity in the below columns
# | Project Code | Implementing Partner Name | Impact | Outcome No. | Outcome | Output No Sub-outcome No. | Output | Activity No. | Activity | Sub-activity | Deliverable (if any) | Activity starting date as planned in project document (Month/Year) | Activity ending date as planned in project document (Month/Year) | Activity duration (in months) | Progress reached (%) | Reason if delayed | Revised ending date of activity (Month/Year) | Final Remarks
1 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 1 | Community/beneficiaries mobilized and sensitized on project activities, beneficiaries' selection conducted in three (3) districts of Khanfir, Lawder and Zanjibar. | Activity 1.1 | Select and assign personnel with required technical skills and experiences to implement the activities. | The project staff meets with the line (FSL) ERRY II project manager / project overview / activities / tasks and responsibilities of each employee. |  | 2020-07-16 | 2020-07-31 | 1 | 100%
2 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 1 | Community/beneficiaries mobilized and sensitized on project activities, beneficiaries' selection conducted in three (3) districts of Khanfir, Lawder and Zanjibar. | Activity 1.2 | Inform stakeholders in targeted areas about the project activities, beneficiaries' selection criteria, project inputs entitlement and duration of the intervention | Meeting with the local authorities, (MOPIC), (MOA) and stakeholders at the governorate level and with the local authority and MOL and the stakeholders at the district levels to inform them about the project in general | Meeting minutes and attendance list for stakeholders and STEPS progress report | 2020-09-21 | 2020-10-15 | 2 | 100%
3 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 1 | Community/beneficiaries mobilized and sensitized on project activities, beneficiaries' selection conducted in three (3) districts of Khanfir, Lawder and Zanjibar. | Activity 1.3 | Mobilize and sensitize target beneficiaries on the project activities, inputs to be provided, criteria for selecting beneficiaries, gender awareness and sensitize beneficiaries/community on FFS and a complaint mechanism for them to raise concerns about the intervention. | Meeting with the targeted communties in three (3) districts of Khanfir, Lawder and Zanjibar, and mobilize and sensitize the target beneficiaries on the project activities, inputs to be provided, criteria for selecting beneficiaries, gender awareness /and sensitize beneficiaries community on FFS, and a complaint mechanism to be raised about the intervention. | Meeting minutes and attendance list for stakeholders and STEPS progress report | 2020-11-01 | 2020-11-30 | 1 | 100%
4 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 1 | Community/beneficiaries mobilized and sensitized on project activities, beneficiaries' selection conducted in three (3) districts of Khanfir, Lawder and Zanjibar. | Activity 1.4 | Formation of community committee in each locality (village) to support beneficiaries' selection and handle complaints from communities. | Condecing formation of community committees in 3 districts: Khanfer, Lawder and Zinjibar in each locality and (village). | Formation of community committee minutes and attendance lists | 2020-11-10 | 2020-12-16 | 2 | 100%
5 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 1 | Community/beneficiaries mobilized and sensitized on project activities, beneficiaries' selection conducted in three (3) districts of Khanfir, Lawder and Zanjibar. | Activity 1.5 | Conduct need assessments for different stakeholders |  |  | 2020-11-20 | 2020-11-30 | 1 | 100% |  |  | The needs assessment was completed according to the coordination between STEPS and the FAO.
6 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 2 | 10,300 beneficiary households selected and registered according to selection criteria for each intervention | Activity 2.1 | Identify and select beneficiaries in project sites according to selection criteria for respective value chain | Registering 10300 plus additional 200 HHs in 119 of the project sites in 3 districts Khanfer and Zinjibar & Lawder according to selection criteria for respective value chain (tomato, cereal and fattening). | Beneficiaries registration database KOBO and M&E beneficiaries verification report | 2020-10-16 | 2020-12-31 | 2 | 100%
7 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 2 | 10,300 beneficiary households selected and registered according to selection criteria for each intervention | Activity 2.2 | Register beneficiaries using KOBO Tool Kit. Details of a beneficiary to include at least four names — this is to avoid duplications of names between beneficiaries from the same area. | Training for 20 enumerators disaggregated 50% male and 50% female. They were selected in coordination with MAI in the targeted districts. Basically, they were trained on registration form, targeted and selection criteria and how to deal with targeted beneficiaries during registration process, | Beneficiaries registration database KOBO and M&E beneficiaries verification report | 2020-11-14 | 2021-02-02 | 2 | 100%
8 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 2 | 10,300 beneficiary households selected and registered according to selection criteria for each intervention | Activity 2.3 | Disaggregate beneficiaries by gender, age and location. | Registered female to be: 30% for tomato value chain, 90% for Dairy (Centers, WGs, and Individuals) + Fattening Value Chain and 30% for Cereal (sorghum & millet) Value Chain plus legumes & production kits | Training report and attendees information | 2020-11-14 | 2020-12-21 | 2 | 100%
9 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 2 | 10,300 beneficiary households selected and registered according to selection criteria for each intervention | Activity 2.4 | Upload registered beneficiaries to FAO on on-line platform for verification. | Entering registered beneficiaries information through FAO KOBO tool to be verified by FAO and address any short comings | Beneficiaries registration database KOBO and M&E beneficiaries verification report | 2020-11-16 | 2020-12-23 | 2 | 100%
10 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 3 | Baseline data collected for key value chains: cereal (sorghum & millet), legumes, vegetable (tomato), dairy and fattening; extension services and markets. | Activity 3.1 | Collect baseline data from selected beneficiaries using sampling and questionnaires provided by FAO Unit |  | Baseline survey raw data | 2021-01-01 | 2021-02-28 | 2 | 0%
11 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 3 | Baseline data collected for key value chains: cereal (sorghum & millet), legumes, vegetable (tomato), dairy and fattening; extension services and markets. | Activity 3.2 | Collect baseline data through FGD in selected communities as suggested by FAO M&E Unit |  | Baseline survey raw data | 2021-01-01 | 2021-02-28 | 2 | 0%
12 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 3 | Baseline data collected for key value chains: cereal (sorghum & millet), legumes, vegetable (tomato), dairy and fattening; extension services and markets. | Activity 3.3 | Collect baseline data from selected KIIs detennined by the FAO M&E Unit |  | Baseline survey raw data | 2021-01-01 | 2021-02-28 | 2 | 0%
13 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 3 | Baseline data collected for key value chains: cereal (sorghum & millet), legumes, vegetable (tomato), dairy and fattening; extension services and markets. | Activity 3.4 | Upload all collected data in Kobo; |  | Baseline survey raw data | 2021-01-01 | 2021-02-28 | 2 | 0%
14 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 3 | Baseline data collected for key value chains: cereal (sorghum & millet), legumes, vegetable (tomato), dairy and fattening; extension services and markets. | Activity 3.5 | Address shortcomings/missing data identified by FAO M&E Unit. |  | Baseline survey raw data | 2021-01-01 | 2021-02-28 | 2 | 0%
15 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 4 | Cereal, legume and vegetable seeds and fertilizer, ilTigation and biological kits provided to 5,300 beneficiaries in three (3) districts ofKhanfir, Lawder and Zanjibar. | Activity 4.1 | Distribute agriculture inputs (sorghum/millet and vegetable seeds, irrigation and biological kits and fertilizer) to beneficiaries as per verified and approved beneficiaries' lists. |  | Distribution lists signed by beneficaries and stamped by concerned authorties STEPS progress and terminal reports | 2021-02-01 | 2021-03-30 | 2 | 0%
16 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 4 | Cereal, legume and vegetable seeds and fertilizer, ilTigation and biological kits provided to 5,300 beneficiaries in three (3) districts ofKhanfir, Lawder and Zanjibar. | Activity 4.2 | Prepare and submit to FAO the interim narrative/post distribution report (Appendix 3) with the distribution lists signed by the beneficiaries acknowledging receipt of inputs. |  | Distribution lists signed by beneficaries and stamped by concerned authorties STEPS progress and terminal reports | 2021-02-01 | 2021-03-30 | 2 | 0%
17 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 5 | Dairy equipment and training on dairy value chain provided to 65 groups comprised of 250 BNFs; besides, 670 individual beneficiaries in Khanfir, Lawder and Zanjibar districts. | Activity 5.1 | Distribute dairy equipment to beneficiaries (groups and individuals) as per the lists verified and approved by FAO |  | STEPS progress and terminal reports Distribution lists signed by beneficaries and stamped by concerned authorties | 2021-02-01 | 2021-03-30 | 2 | 0%
18 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 5 | Dairy equipment and training on dairy value chain provided to 65 groups comprised of 250 BNFs; besides, 670 individual beneficiaries in Khanfir, Lawder and Zanjibar districts. | Activity 5.2 | Conduct training of dairy producers on traditional dairy products processing (cheese, sour milk, yoghurt, traditional cheese, etc.), milk hygiene and appropriate methods of milking, |  | STEPS progress and terminal reports Distribution lists signed by beneficaries and stamped by concerned authorties Training participants lists | 2021-02-01 | 2021-03-30 | 2 | 0%
19 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 6 | Animal feeds, animal sheds, fodder seeds and training on fattening provided to 5,000 beneficiaries in Khanfir, Lawder and Zanjibar districts. | Activity 6.1 | Distribute animal feeds (feed blocks, molasses and wheat bran), fodder seeds (Alfafa and Rhodes grass), fodder choppers, and animal shed to 5,000 beneficianes |  | STEPS progress and terminal reports Distribution lists signed by beneficaries and stamped by concerned authorties | 2021-03-30 | 2021-04-30 | 2 | 0%
20 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 6 | Animal feeds, animal sheds, fodder seeds and training on fattening provided to 5,000 beneficiaries in Khanfir, Lawder and Zanjibar districts. | Activity 6.2 | Train beneficiaries on small ruminants (goat and sheep) animal feeding/ fattening |  | STEPS progress and terminal reports Distribution lists signed by beneficaries and stamped by concerned authorties Training participants lists | 2021-03-30 | 2021-04-30 | 2 | 0%
21 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 7 | 35 farmer field schools (FFS) established with 875 farmers members trained on good agriculture practices and entrepreneurial skill in cereal, legume, tomato, dairy and fattening value chains | Activity 7.1 | Support formation of FFS at village levels | Forming FFS in the targeted districts: 10 FFS in Khanfer, 5 FFS in Zanjibar and 5 FFS in Lawder pluse lists of extension staff provided and approved by the Unit of Agricultural Extension in Abyan Gov | FFS/training records Training participants lists STEPS progress and terminal reports | 2021-03-30 | 2021-04-30 | 2 | 0%
22 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 7 | 35 farmer field schools (FFS) established with 875 farmers members trained on good agriculture practices and entrepreneurial skill in cereal, legume, tomato, dairy and fattening value chains | Activity 7.2 | Schedule visits by FFS facilitators/extension staff to identify key topics for training |  | FFS/training records Training participants lists STEPS progress and terminal reports | 2021-03-30 | 2021-04-30 | 2 | 0%
23 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 7 | 35 farmer field schools (FFS) established with 875 farmers members trained on good agriculture practices and entrepreneurial skill in cereal, legume, tomato, dairy and fattening value chains | Activity 7.3 | Distribute flyers on agronomic practices for cereals, legumes and vegetable crops |  |  | 2021-03-30 | 2021-04-30 | 2 | 0%
24 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 7 | 35 farmer field schools (FFS) established with 875 farmers members trained on good agriculture practices and entrepreneurial skill in cereal, legume, tomato, dairy and fattening value chains | Activity 7.4 | Provide training to FFS and keep register of participants present and location of FFS |  | FFS/training records Training participants lists STEPS progress and terminal reports | 2021-03-30 | 2021-04-30 | 2 | 0%
25 | UNJP/YEM/041/EC (ERRY II) | STEPS Foundation for Civil Development (STEPS) | Contribute to reduced vulnerability and strengthened resilience capacity of crisis-affected communities in Yemen through creation of sustainable livelihoods and access to basic services | Outcome 1 | Community livelihoods, productive assets and food security are improved to strengthen resilience and self-reliance | Output 7 | 35 farmer field schools (FFS) established with 875 farmers members trained on good agriculture practices and entrepreneurial skill in cereal, legume, tomato, dairy and fattening value chains | Activity 7.5 | Linking 200 (40% female-headed households) pilot rural small-scale entrepreneurs (SSEs) (e.g. milk collectors; women involved in home-processing of healthy traditional dairy products and backyard sheep/goat fattening businesses, producers of feed to ILO for skill training in entrepreneurship and marketing. | a) A detailed description of the Services including technical and operational requirements, budget, work plan and timeframe, performance indicators and means of verification, as well as inputs to be provided free-of-charge by the Service Provider and FAO, if any, are set out in detail in the Annex. b) The Service Provider recognizes that the receipt of funds by FAO for this Agreement takes place under specific terms of the European Commission which are duly reflected in this Agreement, as required. | FFS/training records Training participants lists STEPS progress and terminal reports | 2021-03-30 | 2021-04-30 | 2 | 0%

## Dashboard
1
STEPS Workplan Project 041/EC (ERRY II)
Description of KPI colors per activity status
|  |  | Activity Status | KPI Status
|  |  | Activity Completed (100%) | 1
|  |  | No progress (0%) yet didn't exceed its ending date | -1
To reflect progress made, Right click anywhere in this table and choose "Refresh"
Output | Activity | Activity ending date as planned | Reason if delayed | Progress reached (%) | Activity remaining period (in days) | Activity remaining period (in months) | KPI Status
10,300 beneficiary households selected and registered according to selection criteria for each intervention | Disaggregate beneficiaries by gender, age and location. | 2020-12-21 |  | 100% | -52 | -1.7 | 1
| Identify and select beneficiaries in project sites according to selection criteria for respective value chain | 2020-12-31 | (فارغ) | 100% | -42 | -1.4 | 1
| Register beneficiaries using KOBO Tool Kit. Details of a beneficiary to include at least four names — this is to avoid duplications of names between beneficiaries from the same area. | 2021-02-02 |  | 100% | -9 | -0.3 | 1
| Upload registered beneficiaries to FAO on on-line platform for verification. | 2020-12-23 |  | 100% | -50 | -1.7 | 1
35 farmer field schools (FFS) established with 875 farmers members trained on good agriculture practices and entrepreneurial skill in cereal, legume, tomato, dairy and fattening value chains | Distribute flyers on agronomic practices for cereals, legumes and vegetable crops | 2021-04-30 | (فارغ) | 0% | 78 | 2.6 | -1
| Linking 200 (40% female-headed households) pilot rural small-scale entrepreneurs (SSEs) (e.g. milk collectors; women involved in home-processing of healthy traditional dairy products and backyard sheep/goat fattening businesses, producers of feed to ILO for skill training in entrepreneurship and marketing. | 2021-04-30 | (فارغ) | 0% | 78 | 2.6 | -1
| Provide training to FFS and keep register of participants present and location of FFS | 2021-04-30 | (فارغ) | 0% | 78 | 2.6 | -1
| Schedule visits by FFS facilitators/extension staff to identify key topics for training | 2021-04-30 | (فارغ) | 0% | 78 | 2.6 | -1
| Support formation of FFS at village levels | 2021-04-30 | (فارغ) | 0% | 78 | 2.6 | -1
Animal feeds, animal sheds, fodder seeds and training on fattening provided to 5,000 beneficiaries in Khanfir, Lawder and Zanjibar districts. | Distribute animal feeds (feed blocks, molasses and wheat bran), fodder seeds (Alfafa and Rhodes grass), fodder choppers, and animal shed to 5,000 beneficianes | 2021-04-30 | (فارغ) | 0% | 78 | 2.6 | -1
| Train beneficiaries on small ruminants (goat and sheep) animal feeding/ fattening | 2021-04-30 | (فارغ) | 0% | 78 | 2.6 | -1
Baseline data collected for key value chains: cereal (sorghum & millet), legumes, vegetable (tomato), dairy and fattening; extension services and markets. | Address shortcomings/missing data identified by FAO M&E Unit. | 2021-02-28 |  | 0% | 17 | 0.6 | -1
| Collect baseline data from selected beneficiaries using sampling and questionnaires provided by FAO Unit | 2021-02-28 |  | 0% | 17 | 0.6 | -1
| Collect baseline data from selected KIIs detennined by the FAO M&E Unit | 2021-02-28 |  | 0% | 17 | 0.6 | -1
| Collect baseline data through FGD in selected communities as suggested by FAO M&E Unit | 2021-02-28 |  | 0% | 17 | 0.6 | -1
| Upload all collected data in Kobo; | 2021-02-28 |  | 0% | 17 | 0.6 | -1
Cereal, legume and vegetable seeds and fertilizer, ilTigation and biological kits provided to 5,300 beneficiaries in three (3) districts ofKhanfir, Lawder and Zanjibar. | Distribute agriculture inputs (sorghum/millet and vegetable seeds, irrigation and biological kits and fertilizer) to beneficiaries as per verified and approved beneficiaries' lists. | 2021-03-30 | (فارغ) | 0% | 47 | 1.6 | -1
| Prepare and submit to FAO the interim narrative/post distribution report (Appendix 3) with the distribution lists signed by the beneficiaries acknowledging receipt of inputs. | 2021-03-30 | (فارغ) | 0% | 47 | 1.6 | -1
Community/beneficiaries mobilized and sensitized on project activities, beneficiaries' selection conducted in three (3) districts of Khanfir, Lawder and Zanjibar. | Conduct need assessments for different stakeholders | 2020-11-30 | (فارغ) | 100% | -73 | -2.4 | 1
| Formation of community committee in each locality (village) to support beneficiaries' selection and handle complaints from communities. | 2020-12-16 |  | 100% | -57 | -1.9 | 1
| Inform stakeholders in targeted areas about the project activities, beneficiaries' selection criteria, project inputs entitlement and duration of the intervention | 2020-10-15 | (فارغ) | 100% | -119 | -4 | 1
| Mobilize and sensitize target beneficiaries on the project activities, inputs to be provided, criteria for selecting beneficiaries, gender awareness and sensitize beneficiaries/community on FFS and a complaint mechanism for them to raise concerns about the intervention. | 2020-11-30 | (فارغ) | 100% | -73 | -2.4 | 1
| Select and assign personnel with required technical skills and experiences to implement the activities. | 2020-07-31 |  | 100% | -195 | -6.5 | 1
Dairy equipment and training on dairy value chain provided to 65 groups comprised of 250 BNFs; besides, 670 individual beneficiaries in Khanfir, Lawder and Zanjibar districts. | Conduct training of dairy producers on traditional dairy products processing (cheese, sour milk, yoghurt, traditional cheese, etc.), milk hygiene and appropriate methods of milking, | 2021-03-30 | (فارغ) | 0% | 47 | 1.6 | -1
| Distribute dairy equipment to beneficiaries (groups and individuals) as per the lists verified and approved by FAO | 2021-03-30 | (فارغ) | 0% | 47 | 1.6 | -1
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Info (hidden)
Settings of drop down lists per tool
Bi-weekly workplan drop down lists | [11 empty] | Projects Workplans drop down lists |  | LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists ---- LoA drop down lists
IP_Name[Shortcut]
Project Code | M&E Focal Point | Project Start Date | Project End Date | Project Status | Project CTA/FP | Name | Deadline | Week | Progress Made (%) | Week | Column1 | M&E Tasks | Tasks status | IP Name | Shortcut | # of installment(s) per LoA | LOA type | Area of intervention | Category | Qty type | Date of distribution | Means of verification Type | Activity completed | Governorate | Unit of measurement A | Measurement unit per HH | Status
GAFSP (pipeline) | Abdulrahman | 2020-01-19 | 2021-03-18 | Ongoing | Kayouli/Ashraf | Abdulrahman | Regular basis/continuously | 05-09 April 2020 | N/A | 05-09 April 2020 | 1 | Need assessment | Actual | Al-Ekram Foundation | Al-Ekram | One installment | Original LoA (draft) | Agriculture | Input distribution | Actual Qty | January-2017 | Distribution list (Fingerprint) | Yes | Abyan | Bag | Bag | Pending |  | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
GCP/YEM/040/EC (Pro-Act) | Abdulrahman | 2019-10-15 | 2021-09-30 | Ongoing |  | Ghadeer | Daily basis | 12-16 April 2020 | 0% | 12-16 April 2020 | 2 | Data cleaning | Not applicable/required | Coalition of Humanitarian Relief | CHR | Two installments | Original LoA (stamped) | Fishery | Cash distribution | Additional Qty | February-2017 | Attendance sheet | No | Amant Al-Asimah | Block | Block | Completed | January | January-2017 | January-2018 | January-2019 | January-2020 | January-2021 | January-2022 | January-2023
GCP/YEM/042/GCR | Abdulrahman | 2018-06-05 | 2020-03-31 | Ongoing | Dr Farea | Hanaa | IPs haven't been selected yet | 05-16 April 2020 | 1% | 05-16 April 2020 | 3 | Verification | Planned | Field Medical Foundation | FMF | Three installments | LoA amendment (draft) | WASH | Training/awareness |  | March-2017 | Official stamped delivery note |  | Al-Bayda | Can | Can | LoA terminated | February | February-2017 | February-2018 | February-2019 | February-2020 | February-2021 | February-2022 | February-2023
OSRO/GLO/704/KUW | Abdulrahman | 2019-01-01 | 2020-10-31 | Ongoing | Ashraf | Hisham | On-hold | 19-23 April 2020 | 2% | 19-23 April 2020 | 4 | Baseline | A specific date will be scheduled | Ghadaq for Development | Ghadaq | Four installments | LoA amendment (stamped) | Cash for Work (CFW) | Capacity building |  | April-2017 |  |  | Al-Jawf | head | head | Amended/not received | March | March-2017 | March-2018 | March-2019 | March-2020 | March-2021 | March-2022 | March-2023
OSRO/YEM/002/CHA | Abdulrahman | 2018-11-12 | 2020-11-30 | Ongoing | Dr Walid | Nada | Weekly basis | 26-30 April 2020 | 3% | 26-30 April 2020 | 5 | Generation of distribution list | To be discussed with Alisher | Mayar Foundation for Development | Mayar | Five installments | 1st Amendment (stamped) |  | Assessment |  | May-2017 |  |  | Hodeidah | KG | KG |  | April | April-2017 | April-2018 | April-2019 | April-2020 | April-2021 | April-2022 | April-2023
OSRO/YEM/606/EC (EFRLP I) | Hisham | 2018-05-11 | 2019-04-30 | Ongoing | Fuad Al-Homaidi | Nuha | On-going | 19-30 April 2020 | 4% | 19-30 April 2020 | 6 | DDM | To be conducted by TPM | Rawabi Al-Nahdah Developmental Foundation | RADF | Six installments | 2nd Amendment (stamped) |  | Data collection |  | June-2017 |  |  | Ad Dhale'e | Ton | Unit |  | May | May-2017 | May-2018 | May-2019 | May-2020 | May-2021 | May-2022 | May-2023
OSRO/YEM/704/WBK | Hisham | 2019-02-01 | 2021-01-31 | Ongoing | Joel | Saqr | On-going to the next week | 03-07 May 2020 | 5% | 03-07 May 2020 | 7 | PDM |  | Yemen Womenn Union | YWU | Seven installments | 3rd Amendment (stamped) |  |  |  | July-2017 |  |  | Al-Mahweet | Unit |  |  | June | June-2017 | June-2018 | June-2019 | June-2020 | June-2021 | June-2022 | June-2023
OSRO/YEM/705/CHA | Hisham | 2019-03-31 | 2020-11-30 | Ongoing | Sami Nassar | Sindy | To be updated | 10-14 May 2020 | 6% | 10-14 May 2020 | 8 | Mid-term review |  | Veterinary and Agricultural Vocational Institute | VAVI | Eight installments |  |  |  |  | August-2017 |  |  | Al-Maharah |  |  |  | July | July-2017 | July-2018 | July-2019 | July-2020 | July-2021 | July-2022 | July-2023
OSRO/YEM/803/KSC | Nada | 2019-09-01 | 2021-02-28 | Ongoing | Dr Walid | Taha | 2020-04-05 | 03-14 May 2020 | 7% | 03-14 May 2020 | 9 | Training monitoring |  | Yemen Veterinary Medicine Association | YVMA | Nine installments |  |  |  |  | September-2017 |  |  | Taiz |  |  |  | August | August-2017 | August-2018 | August-2019 | August-2020 | August-2021 | August-2022 | August-2023
OSRO/YEM/805/KUW | Nada | 2019-07-15 | 2019-11-14 | Ongoing | Ashraf | Yusra | 2020-04-06 | 17-21 May 2020 | 8% | 17-21 May 2020 | 10 | Field monitoring visit |  | Ministry of Agriculture Irrigation | MAI | Ten installments |  |  |  |  | October-2017 |  |  | Hajjah |  |  |  | September | September-2017 | September-2018 | September-2019 | September-2020 | September-2021 | September-2022 | September-2023
OSRO/YEM/806/JPN | Saqr | 2017-08-01 | 2020-08-31 | Ongoing | Fuad Al-Homaidi |  | 2020-04-07 | 24-28 May 2020 | 9% | 24-28 May 2020 | 11 | Endline | [8 empty] | November-2017 |  |  | Hadramout |  |  |  | October | October-2017 | October-2018 | October-2019 | October-2020 | October-2021 | October-2022 | October-2023
OSRO/YEM/901/JPN | Saqr | 2017-12-04 | 2019-12-04 | Ongoing | Dr Walid |  | 2020-04-08 | 17-28 May 2020 | 10% | 17-28 May 2020 | 12 | Final evaluation | [8 empty] | December-2017 |  |  | Dammar |  |  |  | November | November-2017 | November-2018 | November-2019 | November-2020 | November-2021 | November-2022 | November-2023
OSRO/YEM/902/EC (EFRLP II) | Saqr | 2017-08-10 | 2020-08-09 | Ongoing | Christophe |  | 2020-04-09 | 31-May to 04 Jun 2020 | 11% | 31-May to 04 Jun 2020 | 13 | Collection of distribution list | [8 empty] | January-2018 |  |  | Raymah |  |  |  | December | December-2017 | December-2018 | December-2019 | December-2020 | December-2021 | December-2022 | December-2023
OSRO/YEM/904/BEL | Saqr | 2018-08-09 | 2020-08-31 | Ongoing | Dr Walid |  | 2020-04-10 | 07-11 Jun 2020 | 12% | 07-11 Jun 2020 | 14 | Design template | [8 empty] | February-2018 |  |  | Shabwah
OSRO/YEM/905/CHA | Saqr | 2018-12-01 | 2020-11-30 | Ongoing | Dr Walid |  | 2020-04-11 | 14-18 Jun 2020 | 13% | 14-18 Jun 2020 | 15 | Design database | [8 empty] | March-2018 |  |  | Saadah
UNJP/YEM/906/KUW | Saqr | 2019-07-01 | 2021-06-30 | Ongoing | Dr Farea |  | 12-16 April 2020 | 21-25 Jun 2020 | 14% | 21-25 Jun 2020 | 16 | M&E workplan | [8 empty] | April-2018 |  |  | Sana'a
OSRO/YEM/906/CHA | Sindy | 2019-09-25 | 2020-06-30 | Ongoing | Dr Sadek |  | 2020-04-12 | 28-Jun to 02 Jul 2020 | 15% | 28-Jun to 02 Jul 2020 | 17 | [7 empty] | Area of intervention |  | May-2018 |  |  | Aden
ProAct 2 (pipeline) | Sindy | 2020-01-01 | 2021-02-28 | Ongoing | Dr Sadek |  | 2020-04-13 | 05-09 July 2020 | 16% | 05-09 July 2020 | 18 | [9 empty] | June-2018 |  |  | Amran
Sanaa Basin 2 (pipeline) | Hisham | 2020-02-24 | 2021-02-23 | Ongoing | Ashraf/Lotf |  | 2020-04-14 | 12-16 July 2020 | 17% | 12-16 July 2020 | 19 | [9 empty] | July-2018 |  |  | Lahj
TCP/YEM/3701 | [6 empty] | 2020-04-15 | 19-23 July 2020 | 18% | 19-23 July 2020 | 20 | [9 empty] | August-2018 |  |  | Marib
TCP/YEM/3702 | [6 empty] | 2020-04-16 | 26-30 July 2020 | 19% | 26-30 July 2020 | 21 | [9 empty] | September-2018
UNJP/YEM/039/PBF | [6 empty] | 2020-04-17 | 02-06 Aug 2020 | 20% | 02-06 Aug 2020 | 22 | [9 empty] | October-2018
UNJP/YEM/041/EC (ERRY II) | [6 empty] | 2020-04-18 | 09-13 Aug 2020 | 21% | 09-13 Aug 2020 | 23 | [9 empty] | November-2018
OSRO/YEM/802/CHA | [6 empty] | 2020-04-19 | 16-20 Aug 2020 | 22% | 16-20 Aug 2020 | 24 | [9 empty] | December-2018
TCP/YEM/3801 (E) | [6 empty] | 2020-04-20 | 23-27 Aug 2020 | 23% | 23-27 Aug 2020 | 25 | [9 empty] | January-2019
OSRO/YEM/801/JPN | [6 empty] | 2020-04-21 | 30-Aug to 03 Sep 2020 | 24% | 30-Aug to 03 Sep 2020 | 26 | [9 empty] | February-2019
OSRO/YEM/804/CHA | [6 empty] | 2020-04-22 | 06-10 Sep 2020 | 25% | 06-10 Sep 2020 | 27 | [9 empty] | March-2019
OSRO/YEM/504/EC | [6 empty] | 2020-04-23 | 13-17 Sep 2020 | 26% | 13-17 Sep 2020 | 28 | [9 empty] | April-2019
UNJP/YEM/038/PBF | [6 empty] | 2020-04-24 | 20-24 Sep 2020 | 27% | 20-24 Sep 2020 | 29 | [9 empty] | May-2019
General task | [6 empty] | 2020-04-25 | 27-Sep to 01 Oct 2020 | 28% | 27-Sep to 01 Oct 2020 | 30 | [9 empty] | June-2019
Under all FAO projects | [6 empty] | 2020-04-26 | 04-08 Oct 2020 | 29% | 04-08 Oct 2020 | 31 | [9 empty] | July-2019
Other (specify) | [6 empty] | 2020-04-27 | 11-15 Oct 2020 | 30% | 11-15 Oct 2020 | 32 | [9 empty] | August-2019
[7 empty] | 2020-04-28 | 18-22 Oct 2020 | 31% | 18-22 Oct 2020 | 33 | [9 empty] | September-2019
[7 empty] | 2020-04-29 | 25-29 Oct 2020 | 32% | 25-29 Oct 2020 | 34 | [9 empty] | October-2019
[7 empty] | 2020-04-30 | 01-05 Nov 2020 | 33% | 01-05 Nov 2020 | 35 | [9 empty] | November-2019
[7 empty] | 2020-05-01 | 08-12 Nov 2020 | 34% | 08-12 Nov 2020 | 36 | [9 empty] | December-2019
[7 empty] | 2020-05-02 | 15-19 Nov 2020 | 35% | 15-19 Nov 2020 | 37 | [9 empty] | January-2020
[7 empty] | 2020-05-03 | 22-26 Nov 2020 | 36% | 22-26 Nov 2020 | 38 | [9 empty] | February-2020
[7 empty] | 2020-05-04 | 29-Nov to 03 Dec 2020 | 37% | 29-Nov to 03 Dec 2020 | 39 | [9 empty] | March-2020
[7 empty] | 2020-05-05 | 06-10 Dec 2020 | 38% | 06-10 Dec 2020 | 40 | [9 empty] | April-2020
[7 empty] | 2020-05-06 | 13-17 Dec 2020 | 39% | 13-17 Dec 2020 | 41 | [9 empty] | May-2020
[7 empty] | 2020-05-07 | 20-24 Dec 2020 | 40% | 20-24 Dec 2020 | 42 | [9 empty] | June-2020
[7 empty] | 2020-05-08 | 27-31 Dec 2020 | 41% | 27-31 Dec 2020 | 43 | [9 empty] | July-2020
OSRO/YEM/705/CHA | Abdulrahman | 2017-12-14 | 2019-03-19 | Ended |  |  | 2020-05-09 |  | 42% | [11 empty] | August-2020
OSRO/YEM/801/JPN | Abdulrahman | 2018-03-02 | 2019-06-15 | Ended |  |  | 2020-05-10 |  | 43% | [11 empty] | September-2020
OSRO/YEM/804/CHA | Abdulrahman | 2018-07-01 | 2018-12-31 | Ended |  |  | 2020-05-11 |  | 44% | [11 empty] | October-2020
OSRO/YEM/504/EC | Saqr | 2016-01-01 | 2019-02-28 | Ended |  |  | 2020-05-12 |  | 45% | [11 empty] | November-2020
UNJP/YEM/038/PBF | Saqr | 2018-01-01 | 2019-06-30 | Ended | Asha Sawyer |  | 2020-05-13 |  | 46% | [11 empty] | December-2020
OSRO/YEM/606/EC (EFRLP I) | Abdulrahman | 42767 | 43861 | Ended |  |  | 2020-05-14 |  | 47% | [11 empty] | January-2021
[7 empty] | 2020-05-15 |  | 48% | [11 empty] | February-2021
[7 empty] | 2020-05-16 |  | 49% | [11 empty] | March-2021
[7 empty] | 2020-05-17 |  | 50% | [11 empty] | April-2021
[7 empty] | 2020-05-18 |  | 51% | [11 empty] | May-2021
[7 empty] | 2020-05-19 |  | 52% | [11 empty] | June-2021
[7 empty] | 2020-05-20 |  | 53% | [11 empty] | July-2021
[7 empty] | 2020-05-21 |  | 54% | [11 empty] | August-2021
[7 empty] | 2020-05-22 |  | 55% | [11 empty] | September-2021
[7 empty] | 2020-05-23 |  | 56% | [11 empty] | October-2021
[7 empty] | 2020-05-24 |  | 57% | [11 empty] | November-2021
[7 empty] | 2020-05-25 |  | 58% | [11 empty] | December-2021
[7 empty] | 2020-05-26 |  | 59% | [11 empty] | January-2022
[7 empty] | 2020-05-27 |  | 60% | [11 empty] | February-2022
[7 empty] | 2020-05-28 |  | 61% | [11 empty] | March-2022
[7 empty] | 2020-05-29 |  | 62% | [11 empty] | April-2022
[7 empty] | 2020-05-30 |  | 63% | [11 empty] | May-2022
[7 empty] | 2020-05-31 |  | 64% | [11 empty] | June-2022
[7 empty] | 2020-06-01 |  | 65% | [11 empty] | July-2022
[7 empty] | 2020-06-02 |  | 66% | [11 empty] | August-2022
[7 empty] | 2020-06-03 |  | 67% | [11 empty] | September-2022
[7 empty] | 2020-06-04 |  | 68% | [11 empty] | October-2022
[7 empty] | 2020-06-05 |  | 69% | [11 empty] | November-2022
[7 empty] | 2020-06-06 |  | 70% | [11 empty] | December-2022
[7 empty] | 2020-06-07 |  | 71% | [11 empty] | January-2023
[7 empty] | 2020-06-08 |  | 72% | [11 empty] | February-2023
[7 empty] | 2020-06-09 |  | 73% | [11 empty] | March-2023
[7 empty] | 2020-06-10 |  | 74% | [11 empty] | April-2023
[7 empty] | 2020-06-11 |  | 75% | [11 empty] | May-2023
[7 empty] | 2020-06-12 |  | 76% | [11 empty] | June-2023
[7 empty] | 2020-06-13 |  | 77% | [11 empty] | July-2023
[7 empty] | 2020-06-14 |  | 78% | [11 empty] | August-2023
[7 empty] | 2020-06-15 |  | 79% | [11 empty] | September-2023
[7 empty] | 2020-06-16 |  | 80% | [11 empty] | October-2023
[7 empty] | 2020-06-17 |  | 81% | [11 empty] | November-2023
[7 empty] | 2020-06-18 |  | 82% | [11 empty] | December-2023
[7 empty] | 2020-06-19 |  | 83%
[7 empty] | 2020-06-20 |  | 84%
[7 empty] | 2020-06-21 |  | 85%
[7 empty] | 2020-06-22 |  | 86%
[7 empty] | 2020-06-23 |  | 87%
[7 empty] | 2020-06-24 |  | 88%
[7 empty] | 2020-06-25 |  | 89%
[7 empty] | 2020-06-26 |  | 90%
[7 empty] | 2020-06-27 |  | 91%
[7 empty] | 2020-06-28 |  | 92%
[7 empty] | 2020-06-29 |  | 93%
[7 empty] | 2020-06-30 |  | 94%
[7 empty] | 2020-07-01 |  | 95%
[7 empty] | 2020-07-02 |  | 96%
[7 empty] | 2020-07-03 |  | 97%
[7 empty] | 2020-07-04 |  | 98%
[7 empty] | 2020-07-05 |  | 99%
[7 empty] | 2020-07-06 |  | 100%
2020-07-07
2020-07-08
2020-07-09
2020-07-10
2020-07-11
2020-07-12
2020-07-13
2020-07-14
2020-07-15
2020-07-16
2020-07-17
2020-07-18
2020-07-19
2020-07-20
2020-07-21
2020-07-22
2020-07-23
2020-07-24
2020-07-25
2020-07-26
2020-07-27
2020-07-28
2020-07-29
2020-07-30
2020-07-31
2020-08-01
2020-08-02
2020-08-03
2020-08-04
2020-08-05
2020-08-06
2020-08-07
2020-08-08
2020-08-09
2020-08-10
2020-08-11
2020-08-12
2020-08-13
2020-08-14
2020-08-15
2020-08-16
2020-08-17
2020-08-18
2020-08-19
2020-08-20
2020-08-21
2020-08-22
2020-08-23
2020-08-24
2020-08-25
2020-08-26
2020-08-27
2020-08-28
2020-08-29
2020-08-30
2020-08-31
2020-09-01
2020-09-02
2020-09-03
2020-09-04
2020-09-05
2020-09-06
2020-09-07
2020-09-08
2020-09-09
2020-09-10
2020-09-11
2020-09-12
2020-09-13
2020-09-14
2020-09-15
2020-09-16
2020-09-17
2020-09-18
2020-09-19
2020-09-20
2020-09-21
2020-09-22
2020-09-23
2020-09-24
2020-09-25
2020-09-26
2020-09-27
2020-09-28
2020-09-29
2020-09-30
2020-10-01
2020-10-02
2020-10-03
2020-10-04
2020-10-05
2020-10-06
2020-10-07
2020-10-08
2020-10-09
2020-10-10
2020-10-11
2020-10-12
2020-10-13
2020-10-14
2020-10-15
2020-10-16
2020-10-17
2020-10-18
2020-10-19
2020-10-20
2020-10-21
2020-10-22
2020-10-23
2020-10-24
2020-10-25
2020-10-26
2020-10-27
2020-10-28
2020-10-29
2020-10-30
2020-10-31
2020-11-01
2020-11-02
2020-11-03
2020-11-04
2020-11-05
2020-11-06
2020-11-07
2020-11-08
2020-11-09
2020-11-10
2020-11-11
2020-11-12
2020-11-13
2020-11-14
2020-11-15
2020-11-16
2020-11-17
2020-11-18
2020-11-19
2020-11-20
2020-11-21
2020-11-22
2020-11-23
2020-11-24
2020-11-25
2020-11-26
2020-11-27
2020-11-28
2020-11-29
2020-11-30
2020-12-01
2020-12-02
2020-12-03
2020-12-04
2020-12-05
2020-12-06
2020-12-07
2020-12-08
2020-12-09
2020-12-10
2020-12-11
2020-12-12
2020-12-13
2020-12-14
2020-12-15
2020-12-16
2020-12-17
2020-12-18
2020-12-19
2020-12-20
2020-12-21
2020-12-22
2020-12-23
2020-12-24
2020-12-25
2020-12-26
2020-12-27
2020-12-28
2020-12-29
2020-12-30
2020-12-31
Note on C29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Other (such as designing template, follow-up, office work…etc.)