## CO Master Log
CHANGE ORDER MASTER LOG
S/N | SCR No | CO Type | Description | Agreed Price (SAR) | PR Status (Open/Closed/Cancelled) | PO No | Contract No | Contractor Name
[9 empty] | Name | Code | PO | Amount
1 | 1 | Agreed | Design Changes of approved Mayoralty Master Plan | 900000 | Closed | 6510772926 | 36148 | ACC
2 | 2 | Agreed | Variance from the Contract in the Design Office Facilities provided by the Contractor ( Negative) | -462672 | Closed | 6510776493 | 36148 | ACC
3 | 4 | Agreed | Additional Satellite office for SAPMT | 2857703 | Closed | 6510831388 | 36148 | ACC
4 | 3 | Agreed | Storm Drainage Change – Engineering | 21000 | Closed | 6510776488 | 36148 | ACC
5 | 5 | Agreed | Infrastructure Changes | 2900000 | Closed | 6510782024 | 36148 | ACC
6 | 6 | Agreed | Deletion of community Support Facilities – Engineering Scope | -3665207 | Closed | 6510788404 | 36148 | ACC
7 | 7 | Agreed | Implementation of Master Plan Changes | -701585 | Closed | 6510801441 | 36148 | ACC
8 | 8 | Agreed | Modifications of Housing Deep Seal Trap | -1550000 | Closed | 6510804320 | 36148 | ACC
9 | 9 | Agreed | Modification of Housing Alarm System | -9500 | Closed | 6510790293 | 36148 | ACC
10 | 10 | Agreed | Storm Drainage Change | 208000 | Closed | 6510790295 | 36148 | ACC
11 | 11 | Agreed | Potable & Firewater Additional Water Line | 31000 | Closed | 6510799583 | 36148 | ACC
12 | 12 | Agreed | Housing Satellite System and maid's bath | -73000 | Closed | 6510797824 | 36148 | ACC
13 | 13 | Agreed | Manhole foundation protective coating | -4130.5 | Closed | 6510799531 | 36148 | ACC
14 | 14 | Agreed | Modification of CMU Grout infill | -850000 | Closed | 6510830689 | 36148 | ACC
15 | 15 | Agreed | Architectural finishes changes | 0 | Closed | 6510819402 | 36148 | ACC
16 | 16 | Agreed | Deletion of HDPE 50 mm Fiber Optic Conduit | -225000 | Closed | 6510818611 | 36148 | ACC
17 | 17 | Agreed | Additional Lights fixtures at boundary wall | 359917 | Closed | 6510821957 | 36148 | ACC
18 | 18 | Agreed | RD-1 & PRMU Contractors’ Agreement | 0 | Closed | 6510853357 | 36148 | ACC
19 | 19 | Agreed | New Security Booth | 560895 | Closed | 6510851840 | 36148 | ACC
20 | 20 | Agreed | Door Hardware Changes | -1676921 | Closed | 6510871645 | 36148 | ACC
21 | 21 | Agreed | Aluminum Door Pull and Lever Handle | 330000 | Closed | 6510879642 | 36148 | ACC
22 | 22 | Agreed | Deletion of Rock Excavation | -4800000 | Closed | 6510976949 | 36148 | ACC
23 | 23 | Agreed | Temporary Mosque & Grocery Store | 1850000 | Closed | 6510874922 | 36148 | ACC
24 | 24 | Agreed | Profile Paint In Lieu of Texture Paint | 6083826 | Closed | 6510895504 | 36148 | ACC
25 | 25 | Agreed | IPS's Centrifugal Pumps Specifications and Deletion of Telecom Surface Markers | -158910 | Closed | 6510906995 | 36148 | ACC
65 | 1 |  | Deletion of SAPMT Office at Detailed Designed Facility | -1012103.7 | Closed | 6510786037 | 36216 | CAC
66 | 2 |  | Deletion of SEC Fiber Optics Systems | -653509.42 | Closed | 6510778409 | 36216 | CAC
67 | 3 |  | Deletion of BIM for Housing Units - Cancelled | 0 | Cancalled |  | 36216 | CAC
68 | 4 |  | COMPANY Satellite Site Offices for Area 2D/2E | 3559305.2 | Closed | 6510786961 | 36216 | CAC
69 | 5 |  | DELETION OF ONE OF THE TWO POTABLE WATER DISTRIBUTION LINES (Deleted) | 0 | Cancalled |  | 36216 | CAC
70 | 6 |  | Approved Master Plan (MP) Changes | -22000000 | Closed | 6510785832 | 36216 | CAC
71 | 5 |  | DELETION OF ONE OF THE TWO POTABLE WATER DISTRIBUTION LINES (Deleted) |  | Cancalled |  | 36216 | CAC
72 | 5 |  | Deletion of One of the Two Potable Water Distribution Lines | -952473.8 | Closed | 6510788078 | 36216 | CAC
73 | 9 |  | Modification of Grouting works for exterior CMU walls | -4100000 | Closed | 6510805147 | 36216 | CAC
74 | 10 |  | Modification of Housing Smoke Detector Quantities | -36000 | Closed | 6510805825 | 36216 | CAC
75 | 11 |  | Infrastructure Modifications & Additional Interface Points | -854000 | Closed | 6510817476 | 36216 | CAC
76 | 12 |  | Satellite Dish Connection | 100000 | Closed | 6510805826 | 36216 | CAC
77 | 13 |  | Housing Modifications IFB vs IFC | -1312922.5 | Closed | 6510829287 | 36216 | CAC
78 | 14 |  | Additional Boundary Gate Lighting | 240000 | Closed | 6510829252 | 36216 | CAC
79 | 15 |  | Overall Architectural Material Modification from the IFB | 0 | Closed | 6510809475 | 36216 | CAC
80 | 16 |  | Irrigation Pump Station Changes | 182668.14 | Closed | 6510896474 | 36216 | CAC
81 | 17 |  | Door Hardware Changes | -1575000 | Closed | 6510900049 | 36216 | CAC
82 | 18 |  | External Paint Changes (Cancelled) |  | Cancalled |  | 36216 | CAC
83 | 19 |  | Housing External Paint Changes | 5991138 | Closed | 6510901303 | 36216 | CAC
84 | 20 |  | Villa Main Double Door Accessories | 339009.94 | Closed | 6510911896 | 36216 | CAC
85 | 21 |  | Company Satellite office Steel Diesel Tank Deletion |  | Closed | 6510929322 | 36216 | CAC
86 | 21 |  | Company Satellite office Steel Diesel Tank Deletion | -191475 | Closed | 6510932521 | 36216 | CAC
137 | 1 |  | Modifictions to detail design due to master plan changes | 1091200 | Closed | 6510724631 | 3962 | NPCC
138 | 2 |  | Changes in scope of work for variations in portable water networks | 193600 | Closed | 6510726611 | 3962 | NPCC
139 | 3 |  | Variation in Electrical Distribution Netwroks | 4580106.2 | Closed | 6510746423 | 3962 | NPCC
140 | 4 |  | Additional Cut and Fill for the Roads | 6856675.5 | Closed | 6510745673 | 3962 | NPCC
141 | 5 |  | 452 | 3648081 | Closed | 6510751428 | 3962 | NPCC
142 | 6 |  | Changes to the North Utility Corridor | 335808 | Closed | 6510775677 | 3962 | NPCC
143 | 7 |  | Acidizing of Water Well at Pump Station No. 1 | 133000 | Closed | 6510756463 | 3962 | NPCC
144 | 8 |  | Relocation of Exst Electr Distribution Networks | 307353.43 | Closed | 6510775234 | 3962 | NPCC
145 | 9 |  | Plugging Total Loss Zone | 156750 | Closed | 6510768699 | 3962 | NPCC
146 | 10 |  | Abu Hadriyah Exit Road to Access Road 5 | 2560000 | Closed | 6510763131 | 3962 | NPCC
147 | 11 |  | Pot. Water Piping and Service Connections | -1670000 | Closed | 6510801381 | 3962 | NPCC
148 | 12 |  | Proc and Construction of NUC changes | 3280000 | Closed | 6510803795 | 3962 | NPCC
149 | 13 |  | Change Order 13, MV Cables | 3035812.5 | Closed | 6510810138 | 3962 | NPCC
150 | 14 |  | Replace Unsuitable Sub Grade | 1140000 | Closed | 6510817125 | 3962 | NPCC
151 | 15 |  | Changes to rip Rap Scope | 3627600 | Closed | 6510819879 | 3962 | NPCC
152 | 16 |  | Add/Delete MV Cables | 346500 | Closed | 6510819048 | 3962 | NPCC
153 | 17 |  | Road No. 6 NUC Detour Constructions | 65160 | Closed | 6510821395 | 3962 | NPCC
154 | 18 |  | Five Procurement and Construction Changes | 1690000 | Closed | 6510832292 | 3962 | NPCC
155 | 19 |  | Changes to MV Cables Routes for Grid Stations | 976887.5 | Closed | 6510832244 | 3962 | NPCC
156 | 20 |  | OAR Access Road, and MH adjustments | 2800000 | Closed | 6510837979 | 3962 | NPCC
157 | 21 |  | CO 21 - Add/Delete Works | -1560000 | Closed | 6510854703 | 3962 | NPCC
158 | 22 |  | Change Order 22 - Electrical items | 141000 | Closed | 6510857746 | 3962 | NPCC
159 | 23 |  | Change Order 23- Delete Rock Excavation Quantities | -4864080 | Closed | 6510863317 | 3962 | NPCC
160 | 24 |  | Deletion of operation and Maintenance Scope |  | Cancelled |  | 3962 | NPCC
161 | 25 |  | Deletion of Electrcail and Road systems Manitenance | -1842666 | Closed | 6510892806 | 3962 | NPCC
162 | 00000001 |  | Modifications of Project Site | 2700000 | Closed | 6510747482 | 3878 | NPCC | Modifications of Project Site | 3878 | 6510747482 | 2700000
163 | 00000005 | Agreed | Modification of Change Order No. 01 - TSF Modifications | 3275000 | Closed | 6510774295 | 3878 | NPCC | Modification of Change Order No. 01 - TSF Modifications | 3878 | 6510774295 | 3275000
164 | 00000006 | Agreed | Administration Office Building Modifications | 294000 | Closed | 6510820688 | 3878 | NPCC | Administration Office Building Modifications | 3878 | 6510820688 | 294000
165 | 00000007 | Agreed | Office Modifications | 29000 | Closed | 6510860253 | 3878 | NPCC | Office Modifications | 3878 | 6510860253 | 29000
166 | 00000009 | TBN | Additional Security Services (TBN Change Order) | 4586187 | Closed | 6510892573 | 3878 | NPCC | Additional Security Services (TBN Change Order) | 3878 | 6510892573 | 4586187
167 | 11 | Agreed | Revision to existing CO No 04 Rev 01 Additional Secuirty Services | 3900000 | Closed | 6510933485 | 3878 | NPCC | Revision to existing CO No 04 Rev 01 Additional Secuirty Services | 3878 | 6510933485 | 3900000
168 | 12 | Agreed | Fire Water System Modification Works | 320000 | Closed | 6510938339 | 3878 | NPCC | Fire Water System Modification Works | 3878 | 6510938339 | 320000
169 | 13 | Agreed | Thermal imaging Cameras | 29872 | Closed | 6510961812 | 3878 | NPCC | Thermal imaging Cameras | 3878 | 6510961812 | 29872
170 |  |  | Special Needs School Changes Engineering and Re-Design (deleted from system dude to SAP error - included in PR 3000711393) |  | Closed | 6510783185 | 36438 | BSC
171 | 8 |  | Special Needs School Changes Engineering and Re-Design (Include Structure Changes) | 1460000 | Closed | 6510817011 | 36438 | BSC
172 | 1 |  | Main Telecommunications Rooms (MTRs) and Floor Telecommunication Rooms (FTRs) changes to include minimum space requirements as specified in the TIA-569-C Standard. | 5900000 | Closed | 6510812779 | 36438 | BSC
173 |  |  | Fire Water Engineering Studies - CANCELLED |  | Cancelled |  | 36438 | BSC
174 | 6 |  | Modification to Building Envelope & Deletion of Below grade Insulation- FEED Verification | -975000 | Closed | 6510836738 | 36438 | BSC
175 | 4 |  | MECHANICAL MODIFICATION | -2150000 | Closed | 6510828314 | 36438 | BSC
176 | 2 |  | Additional backfill for E1 Campus | 226130.6 | Closed | 6510799053 | 36438 | BSC
177 | 3 |  | Company Site Satellite Office for E1,E2 & SNS | 3740000 | Closed | 6510803432 | 36438 | BSC
178 | 5 |  | Electrical and Telecom - FEED Verification | -285000 | Closed | 6510820810 | 36438 | BSC
179 | 7 |  | Special Needs School - Structure Changes - CANCELLED |  | Cancelled |  | 36438 | BSC
180 | 9 |  | Modification of two (2) tie-in points IN E1 Campus (Feasibility) | 65000 | Closed | 6510824034 | 36438 | BSC
181 | 10 |  | Construction Changes to SNS Buildings | 5200000 | Closed | 6510846044 | 36438 | BSC
182 | 11 |  | Modifications to Sewer Lines E1 - Cancelled | 0 | Cancelled |  | 36438 | BSC
183 | 12 |  | Change of Fire Water Pump Materials | -505000 | Closed | 6510842941 | 36438 | BSC
184 | 13 |  | Modifications to Schools Drop-Off Areas | 250000 | Closed | 6510843085 | 36438 | BSC
185 | 14 |  | External Stairs (E1 & E2) | 310000 | Closed | 6510855542 | 36438 | BSC
186 | 15 |  | Additional Privacy and Security requirements | 590000 | Closed | 6510868844 | 36438 | BSC
187 | 16 |  | Modification to Boundary Wall for Elementary Boys at E2 | 88000 | Closed | 6510863558 | 36438 | BSC
188 | 17 |  | Provision for Sink Connection in KG Class room toilet - CANCELLED |  | Cancelled |  | 36438 | BSC
189 | 18 |  | Additional Privacy Screen Sheets - Girls School only | 111738 | Closed | 6510908321 | 36438 | BSC
190 | 19 |  | GSM Tower cable conduits E1&E2 | 49500 | Closed | 6510911689 | 36438 | BSC
191 | 20 |  | Rock Excavation | -540000 | Closed | 6510949647 | 36438 | BSC
Note on E6: Eva, Raul C: New Value for CO#03 Rev. 02, SR 2,857,703. From SR 3,418,279-560,576.00
Note on E17: Nasser Albuti: Ras CO
Note on E91: Nasim, Talha: Revision 03 , version 4 21 July 19 - Add SAR 390,000

## PullDown
Code | Contract No. | PO No. | Value
code36438 | Deletion of SAPMT Office at Detailed Designed Facility | 6510786037 | -1012103.7 | code3878 | Modifications of Project Site | 3878 | 6510747482 | 2700000
|  |  |  | code3962 | Modification of Change Order No. 01 - TSF Modifications | 3878 | 6510774295 | 3275000
|  |  |  | code36148 | Administration Office Building Modifications | 3878 | 6510820688 | 294000
|  |  |  | code36216 | Office Modifications | 3878 | 6510860253 | 29000
|  |  |  | code36438 | Additional Security Services (TBN Change Order) | 3878 | 6510892573 | 4586187
[5 empty] | Revision to existing CO No 04 Rev 01 Additional Secuirty Services | 3878 | 6510933485 | 3900000
[5 empty] | Fire Water System Modification Works | 3878 | 6510938339 | 320000
[5 empty] | Thermal imaging Cameras | 3878 | 6510961812 | 29872
[5 empty] | Modifictions to detail design due to master plan changes | 3962 | 6510724631 | 1091200
[5 empty] | Changes in scope of work for variations in portable water networks | 3962 | 6510726611 | 193600
[5 empty] | Variation in Electrical Distribution Netwroks | 3962 | 6510746423 | 4580106.2
[5 empty] | Additional Cut and Fill for the Roads | 3962 | 6510745673 | 6856675.5
[5 empty] | 452 | 3962 | 6510751428 | 3648081
[5 empty] | Changes to the North Utility Corridor | 3962 | 6510775677 | 335808
[5 empty] | Acidizing of Water Well at Pump Station No. 1 | 3962 | 6510756463 | 133000
[5 empty] | Relocation of Exst Electr Distribution Networks | 3962 | 6510775234 | 307353.43
[5 empty] | Plugging Total Loss Zone | 3962 | 6510768699 | 156750
[5 empty] | Abu Hadriyah Exit Road to Access Road 5 | 3962 | 6510763131 | 2560000
[5 empty] | Pot. Water Piping and Service Connections | 3962 | 6510801381 | -1670000
[5 empty] | Proc and Construction of NUC changes | 3962 | 6510803795 | 3280000
[5 empty] | Change Order 13, MV Cables | 3962 | 6510810138 | 3035812.5
[5 empty] | Replace Unsuitable Sub Grade | 3962 | 6510817125 | 1140000
[5 empty] | Changes to rip Rap Scope | 3962 | 6510819879 | 3627600
[5 empty] | Add/Delete MV Cables | 3962 | 6510819048 | 346500
[5 empty] | Road No. 6 NUC Detour Constructions | 3962 | 6510821395 | 65160
[5 empty] | Five Procurement and Construction Changes | 3962 | 6510832292 | 1690000
[5 empty] | Changes to MV Cables Routes for Grid Stations | 3962 | 6510832244 | 976887.5
[5 empty] | OAR Access Road, and MH adjustments | 3962 | 6510837979 | 2800000
[5 empty] | CO 21 - Add/Delete Works | 3962 | 6510854703 | -1560000
[5 empty] | Change Order 22 - Electrical items | 3962 | 6510857746 | 141000
[5 empty] | Change Order 23- Delete Rock Excavation Quantities | 3962 | 6510863317 | -4864080
[5 empty] | Deletion of operation and Maintenance Scope | 3962
[5 empty] | Deletion of Electrcail and Road systems Manitenance | 3962 | 6510892806 | -1842666
[5 empty] | Design Changes of approved Mayoralty Master Plan | 36148 | 6510772926 | 900000
[5 empty] | Variance from the Contract in the Design Office Facilities provided by the Contractor ( Negative) | 36148 | 6510776493 | -462672
[5 empty] | Additional Satellite office for SAPMT | 36148 | 6510831388 | 2857703
[5 empty] | Storm Drainage Change – Engineering | 36148 | 6510776488 | 21000
[5 empty] | Infrastructure Changes | 36148 | 6510782024 | 2900000
[5 empty] | Deletion of community Support Facilities – Engineering Scope | 36148 | 6510788404 | -3665207
[5 empty] | Implementation of Master Plan Changes | 36148 | 6510801441 | -701585
[5 empty] | Modifications of Housing Deep Seal Trap | 36148 | 6510804320 | -1550000
[5 empty] | Modification of Housing Alarm System | 36148 | 6510790293 | -9500
[5 empty] | Storm Drainage Change | 36148 | 6510790295 | 208000
[5 empty] | Potable & Firewater Additional Water Line | 36148 | 6510799583 | 31000
[5 empty] | Housing Satellite System and maid's bath | 36148 | 6510797824 | -73000
[5 empty] | Manhole foundation protective coating | 36148 | 6510799531 | -4130.5
[5 empty] | Modification of CMU Grout infill | 36148 | 6510830689 | -850000
[5 empty] | Architectural finishes changes | 36148 | 6510819402 | 0
[5 empty] | Deletion of HDPE 50 mm Fiber Optic Conduit | 36148 | 6510818611 | -225000
[5 empty] | Additional Lights fixtures at boundary wall | 36148 | 6510821957 | 359917
[5 empty] | RD-1 & PRMU Contractors’ Agreement | 36148 | 6510853357 | 0
[5 empty] | New Security Booth | 36148 | 6510851840 | 560895
[5 empty] | Door Hardware Changes | 36148 | 6510871645 | -1676921
[5 empty] | Aluminum Door Pull and Lever Handle | 36148 | 6510879642 | 330000
[5 empty] | Deletion of Rock Excavation | 36148 | 6510976949 | -4800000
[5 empty] | Temporary Mosque & Grocery Store | 36148 | 6510874922 | 1850000
[5 empty] | Profile Paint In Lieu of Texture Paint | 36148 | 6510895504 | 6083826
[5 empty] | IPS's Centrifugal Pumps Specifications and Deletion of Telecom Surface Markers | 36148 | 6510906995 | -158910
[5 empty] | Deletion of SAPMT Office at Detailed Designed Facility | 36216 | 6510786037 | -1012103.7
[5 empty] | Deletion of SEC Fiber Optics Systems | 36216 | 6510778409 | -653509.42
[5 empty] | Deletion of BIM for Housing Units - Cancelled | 36216 |  | 0
[5 empty] | COMPANY Satellite Site Offices for Area 2D/2E | 36216 | 6510786961 | 3559305.2
[5 empty] | DELETION OF ONE OF THE TWO POTABLE WATER DISTRIBUTION LINES (Deleted) | 36216 |  | 0
[5 empty] | Approved Master Plan (MP) Changes | 36216 | 6510785832 | -22000000
[5 empty] | DELETION OF ONE OF THE TWO POTABLE WATER DISTRIBUTION LINES (Deleted) | 36216
[5 empty] | Deletion of One of the Two Potable Water Distribution Lines | 36216 | 6510788078 | -952473.8
[5 empty] | Modification of Grouting works for exterior CMU walls | 36216 | 6510805147 | -4100000
[5 empty] | Modification of Housing Smoke Detector Quantities | 36216 | 6510805825 | -36000
[5 empty] | Infrastructure Modifications & Additional Interface Points | 36216 | 6510817476 | -854000
[5 empty] | Satellite Dish Connection | 36216 | 6510805826 | 100000
[5 empty] | Housing Modifications IFB vs IFC | 36216 | 6510829287 | -1312922.5
[5 empty] | Additional Boundary Gate Lighting | 36216 | 6510829252 | 240000
[5 empty] | Overall Architectural Material Modification from the IFB | 36216 | 6510809475 | 0
[5 empty] | Irrigation Pump Station Changes | 36216 | 6510896474 | 182668.14
[5 empty] | Door Hardware Changes | 36216 | 6510900049 | -1575000
[5 empty] | External Paint Changes (Cancelled) | 36216
[5 empty] | Housing External Paint Changes | 36216 | 6510901303 | 5991138
[5 empty] | Villa Main Double Door Accessories | 36216 | 6510911896 | 339009.94
[5 empty] | Company Satellite office Steel Diesel Tank Deletion | 36216 | 6510929322
[5 empty] | Company Satellite office Steel Diesel Tank Deletion | 36216 | 6510932521 | -191475
[5 empty] | Special Needs School Changes Engineering and Re-Design (deleted from system dude to SAP error - included in PR 3000711393) | 36438 | 6510783185
[5 empty] | Special Needs School Changes Engineering and Re-Design (Include Structure Changes) | 36438 | 6510817011 | 1460000
[5 empty] | Main Telecommunications Rooms (MTRs) and Floor Telecommunication Rooms (FTRs) changes to include minimum space requirements as specified in the TIA-569-C Standard. | 36438 | 6510812779 | 5900000
[5 empty] | Fire Water Engineering Studies - CANCELLED | 36438
[5 empty] | Modification to Building Envelope & Deletion of Below grade Insulation- FEED Verification | 36438 | 6510836738 | -975000
[5 empty] | MECHANICAL MODIFICATION | 36438 | 6510828314 | -2150000
[5 empty] | Additional backfill for E1 Campus | 36438 | 6510799053 | 226130.6
[5 empty] | Company Site Satellite Office for E1,E2 & SNS | 36438 | 6510803432 | 3740000
[5 empty] | Electrical and Telecom - FEED Verification | 36438 | 6510820810 | -285000
[5 empty] | Special Needs School - Structure Changes - CANCELLED | 36438
[5 empty] | Modification of two (2) tie-in points IN E1 Campus (Feasibility) | 36438 | 6510824034 | 65000
[5 empty] | Construction Changes to SNS Buildings | 36438 | 6510846044 | 5200000
[5 empty] | Modifications to Sewer Lines E1 - Cancelled | 36438 |  | 0
[5 empty] | Change of Fire Water Pump Materials | 36438 | 6510842941 | -505000
[5 empty] | Modifications to Schools Drop-Off Areas | 36438 | 6510843085 | 250000
[5 empty] | External Stairs (E1 & E2) | 36438 | 6510855542 | 310000
[5 empty] | Additional Privacy and Security requirements | 36438 | 6510868844 | 590000
[5 empty] | Modification to Boundary Wall for Elementary Boys at E2 | 36438 | 6510863558 | 88000
[5 empty] | Provision for Sink Connection in KG Class room toilet - CANCELLED | 36438
[5 empty] | Additional Privacy Screen Sheets - Girls School only | 36438 | 6510908321 | 111738
[5 empty] | GSM Tower cable conduits E1&E2 | 36438 | 6510911689 | 49500
[5 empty] | Rock Excavation | 36438 | 6510949647 | -540000
Note on A5: Nizar: اختار الكود يعني رقم العقد
Note on B5: Nizar: ستظهر قائمة خاصة فقط بالكود الذي اخترته
Note on R40: Eva, Raul C: New Value for CO#03 Rev. 02, SR 2,857,703. From SR 3,418,279-560,576.00
Note on R51: Nasser Albuti: Ras CO
Note on R92: Nasim, Talha: Revision 03 , version 4 21 July 19 - Add SAR 390,000