## REPORT VOL3
Sales Doc. | Created On | Req.dlv.dt | PO | PO CREATION | Status | Instructions | Order Stage
2462369 | 2023-04-19 | 2023-07-24 | 4500532753 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
2468406 | 2023-05-02 | 2023-08-05 | 4500533693 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
2468408 | 2023-05-02 | 2023-08-05 | 4500533694 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
2469059 | 2023-05-04 | 2023-11-11 | 4500533695 | 2023-05-08 | On Time | Check with Warehouse Team | Critical stage
2470424 | 2023-05-08 | 2023-08-17 | 4500533696 | 2023-05-08 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
2472392 | 2023-05-14 | 2023-08-17 | 4500534548 | 2023-05-18 | On Time | Follow up with the supplier | Production Stage
2472395 | 2023-05-14 | 2023-08-15 | 4500534549 | 2023-05-18 | On Time | Follow up with the supplier | Production Stage
2474735 | 2023-05-21 | 2023-08-31 | 4500535642 | 2023-05-27 | On Time | nominate the forwarder | Nomination Stage
2475010 | 2023-05-22 | 2023-08-30 | 4500535643 | 2023-05-27 | On Time | nominate the forwarder | Nomination Stage
2475077 | 2023-05-22 | 2023-08-22 | 4500536041 | 2023-05-31 | On Time | Follow up with the supplier | Production Stage
2475585 | 2023-05-24 | 2023-08-30 | 4500535644 | 2023-05-27 | On Time | nominate the forwarder | Nomination Stage
2475596 | 2023-05-24 | 2023-08-30 | 4500535645 | 2023-05-27 | On Time | nominate the forwarder | Nomination Stage
2475881 | 2023-05-25 | 2023-09-03 | 4500536054 | 2023-05-31 | On Time | nominate the forwarder | Nomination Stage
2476580 | 2023-05-27 | 2023-08-31 | 4500535646 | 2023-05-27 | On Time | nominate the forwarder | Nomination Stage
2477444 | 2023-05-29 | 2023-09-23 | 4500536056 | 2023-05-31 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
2477985 | 2023-05-31 | 2023-09-09 | 4500536375 | 2023-06-06 | On Time | nominate the forwarder | Nomination Stage
2480045 | 2023-06-06 | 2023-09-11 | 4500536625 | 2023-06-10 | On Time | nominate the forwarder | Nomination Stage
2480046 | 2023-06-06 | 2023-09-12 | 4500536635 | 2023-06-11 | On Time | nominate the forwarder | Nomination Stage
2480706 | 2023-06-08 | 2023-09-14 | 4500536636 | 2023-06-11 | On Time | nominate the forwarder | Nomination Stage
2481448 | 2023-06-10 | 2023-09-16 | 4500536637 | 2023-06-11 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
2485063 | 2023-06-21 | 2023-09-27 | 4500537928 | 2023-06-22 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
2485964 | 2023-06-24 | 2023-09-28 | 4500538419 | 2023-07-01 | On Time | Follow up with the supplier | Production Stage
36000834 | 2023-04-20 | 2023-07-24 | 4500532757 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
40561678 | 2023-04-19 | 2023-07-24 | 4500532759 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
40561836 | 2023-04-20 | 2023-07-26 | 4500532761 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
40561847 | 2023-04-20 | 2023-07-29 | 4500532762 | 2023-04-26 | On Time | nominate the forwarder | Nomination Stage
40561874 | 2023-04-20 | 2023-07-24 | 4500532764 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
40561882 | 2023-04-20 | 2023-07-24 | 4500532765 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
40561888 | 2023-04-20 | 2023-07-30 | 4500532766 | 2023-04-26 | On Time | nominate the forwarder | Nomination Stage
40561894 | 2023-04-20 | 2023-07-24 | 4500532767 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
40561902 | 2023-04-20 | 2023-07-24 | 4500532768 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
40562514 | 2023-04-26 | 2023-07-31 | 4500532770 | 2023-04-26 | On Time | nominate the forwarder | Nomination Stage
40563634 | 2023-05-01 | 2023-08-05 | 4500533697 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40563655 | 2023-05-01 | 2023-08-06 | 4500533698 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40563754 | 2023-05-02 | 2023-08-05 | 4500533699 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40563760 | 2023-05-02 | 2023-08-06 | 4500533700 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40563829 | 2023-05-02 | 2023-08-03 | 4500533701 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40563830 | 2023-05-02 | 2023-08-03 | 4500533702 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40563836 | 2023-05-02 | 2023-08-03 | 4500533703 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40564011 | 2023-05-03 | 2023-08-07 | 4500533704 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40564019 | 2023-05-03 | 2023-08-06 | 4500533705 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40564215 | 2023-05-04 | 2023-08-06 | 4500533706 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40564219 | 2023-05-04 | 2023-08-07 | 4500533707 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
40564577 | 2023-05-06 | 2023-08-10 | 4500533708 | 2023-05-08 | On Time | nominate the forwarder | Nomination Stage
40565096 | 2023-05-09 | 2023-08-10 | 4500534212 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
40565098 | 2023-05-09 | 2023-08-10 | 4500534218 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
40565120 | 2023-05-09 | 2023-08-10 | 4500534219 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
40565238 | 2023-05-10 | 2023-08-12 | 4500534221 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
40565241 | 2023-05-10 | 2023-08-12 | 4500534222 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
40565257 | 2023-05-10 | 2023-08-13 | 4500534223 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
40565956 | 2023-05-14 | 2023-08-15 | 4500534612 | 2023-05-18 | On Time | Follow up with the supplier | Production Stage
40566326 | 2023-05-16 | 2023-08-21 | 4500534556 | 2023-05-18 | On Time | nominate the forwarder | Nomination Stage
40566528 | 2023-05-17 | 2023-08-20 | 4500534557 | 2023-05-18 | On Time | nominate the forwarder | Nomination Stage
40566603 | 2023-05-17 | 2023-08-23 | 4500534616 | 2023-05-18 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
40566606 | 2023-05-17 | 2023-08-23 | 4500534558 | 2023-05-18 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
40566789 | 2023-05-18 | 2023-08-24 | 4500536347 | 2023-06-05 | On Time | Follow up with the supplier | Production Stage
40566796 | 2023-05-18 | 2023-08-27 | 4500535060 | 2023-05-23 | On Time | nominate the forwarder | Nomination Stage
40567097 | 2023-05-21 | 2023-08-28 | 4500535637 | 2023-05-27 | On Time | nominate the forwarder | Nomination Stage
40567098 | 2023-05-21 | 2023-08-23 | 4500535639 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
40567143 | 2023-05-21 | 2023-08-23 | 4500535640 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
40567400 | 2023-05-22 | 2023-08-23 | 4500535641 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
40567441 | 2023-05-22 | 2023-08-31 | 4500536063 | 2023-05-31 | On Time | Follow up with the supplier | Production Stage
40567589 | 2023-05-23 | 2023-08-26 | 4500535654 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
40567640 | 2023-05-23 | 2023-08-24 | 4500535655 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
40567702 | 2023-05-24 | 2023-09-02 | 4500535656 | 2023-05-27 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
40567748 | 2023-05-24 | 2023-09-23 | 4500535657 | 2023-05-27 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
40567836 | 2023-05-24 | 2023-08-26 | 4500535658 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
40567931 | 2023-05-25 | 2023-08-27 | 4500535659 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
40568635 | 2023-05-29 | 2023-08-30 | 4500536061 | 2023-05-31 | On Time | Follow up with the supplier | Production Stage
40568641 | 2023-05-29 | 2023-08-30 | 4500536064 | 2023-05-31 | On Time | Follow up with the supplier | Production Stage
40568657 | 2023-05-29 | 2023-08-31 | 4500536068 | 2023-05-31 | On Time | Follow up with the supplier | Production Stage
40568781 | 2023-05-30 | 2023-09-02 | 4500536070 | 2023-05-31 | On Time | nominate the forwarder | Nomination Stage
40568809 | 2023-05-30 | 2023-09-03 | 4500536395 | 2023-06-06 | On Time | Follow up with the supplier | Production Stage
40568903 | 2023-05-31 | 2023-09-07 | 4500536348 | 2023-06-05 | On Time | nominate the forwarder | Nomination Stage
40568914 | 2023-05-31 | 2023-09-02 | 4500536350 | 2023-06-05 | On Time | Follow up with the supplier | Production Stage
40569166 | 2023-06-01 | 2023-09-03 | 4500536351 | 2023-06-05 | On Time | Follow up with the supplier | Production Stage
40569548 | 2023-06-03 | 2023-09-04 | 4500536352 | 2023-06-05 | On Time | Follow up with the supplier | Production Stage
40569551 | 2023-06-03 | 2023-09-04 | 4500536353 | 2023-06-05 | On Time | Follow up with the supplier | Production Stage
40569613 | 2023-06-04 | 2023-09-09 | 4500536354 | 2023-06-05 | On Time | nominate the forwarder | Nomination Stage
40569822 | 2023-06-05 | 2023-09-07 | 4500536355 | 2023-06-05 | On Time | nominate the forwarder | Nomination Stage
40569865 | 2023-06-05 | 2023-09-07 | 4500536356 | 2023-06-05 | On Time | nominate the forwarder | Nomination Stage
40569878 | 2023-06-05 | 2023-09-06 | 4500536626 | 2023-06-10 | On Time | Follow up with the supplier | Production Stage
40569895 | 2023-06-05 | 2023-09-06 | 4500536627 | 2023-06-10 | On Time | Follow up with the supplier | Production Stage
40569896 | 2023-06-05 | 2023-09-06 | 4500536628 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40569898 | 2023-06-05 | 2023-09-13 | 4500536629 | 2023-06-11 | On Time | nominate the forwarder | Nomination Stage
40569955 | 2023-06-05 | 2023-09-06 | 4500536630 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40569956 | 2023-06-05 | 2023-09-06 | 4500536631 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40569958 | 2023-06-05 | 2023-09-13 | 4500536632 | 2023-06-11 | On Time | nominate the forwarder | Nomination Stage
40569959 | 2023-06-05 | 2023-09-13 | 4500536633 | 2023-06-11 | On Time | nominate the forwarder | Nomination Stage
40569964 | 2023-06-05 | 2023-09-07 | 4500536634 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570053 | 2023-06-06 | 2023-09-07 | 4500536639 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570102 | 2023-06-06 | 2023-09-09 | 4500536640 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570108 | 2023-06-06 | 2023-09-09 | 4500536641 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570117 | 2023-06-06 | 2023-09-09 | 4500536642 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570118 | 2023-06-06 | 2023-09-07 | 4500536643 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570280 | 2023-06-07 | 2023-09-09 | 4500536644 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570293 | 2023-06-07 | 2023-09-12 | 4500536645 | 2023-06-11 | On Time | nominate the forwarder | Nomination Stage
40570327 | 2023-06-07 | 2023-09-09 | 4500536646 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570337 | 2023-06-07 | 2023-09-09 | 4500536647 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570338 | 2023-06-07 | 2023-09-09 | 4500536648 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
40570738 | 2023-06-10 | 2023-09-16 | 4500536810 | 2023-06-12 | On Time | nominate the forwarder | Nomination Stage
40570843 | 2023-06-10 | 2023-09-11 | 4500536807 | 2023-06-12 | On Time | Follow up with the supplier | Production Stage
40571284 | 2023-06-12 | 2023-09-13 | 4500537075 | 2023-06-14 | On Time | Follow up with the supplier | Production Stage
40571391 | 2023-06-13 | 2023-09-17 | 4500537078 | 2023-06-14 | On Time | nominate the forwarder | Nomination Stage
40571396 | 2023-06-13 | 2023-09-17 | 4500537079 | 2023-06-14 | On Time | nominate the forwarder | Nomination Stage
40571577 | 2023-06-13 | 2023-09-14 | 4500537080 | 2023-06-14 | On Time | Follow up with the supplier | Production Stage
40571643 | 2023-06-14 | 2023-09-16 | 4500537320 | 2023-06-18 | On Time | Follow up with the supplier | Production Stage
40571683 | 2023-06-14 | 2023-09-16 | 4500537321 | 2023-06-18 | On Time | Follow up with the supplier | Production Stage
40571788 | 2023-06-15 | 2023-09-18 | 4500537323 | 2023-06-18 | On Time | Follow up with the supplier | Production Stage
40571883 | 2023-06-15 | 2023-09-17 | 4500537325 | 2023-06-18 | On Time | Follow up with the supplier | Production Stage
40571884 | 2023-06-15 | 2023-09-17 | 4500537324 | 2023-06-18 | On Time | Follow up with the supplier | Production Stage
40572080 | 2023-06-17 | 2023-09-18 | 4500537327 | 2023-06-18 | On Time | Follow up with the supplier | Production Stage
40572789 | 2023-06-20 | 2023-09-21 | 4500537927 | 2023-06-22 | On Time | Follow up with the supplier | Production Stage
40573152 | 2023-06-22 | 2023-09-25 | 4500537931 | 2023-06-22 | On Time | nominate the forwarder | Nomination Stage
40573154 | 2023-06-22 | 2023-09-25 | 4500537932 | 2023-06-22 | On Time | nominate the forwarder | Nomination Stage
40573171 | 2023-06-22 | 2023-09-26 | 4500537930 | 2023-06-22 | On Time | nominate the forwarder | Nomination Stage
40573486 | 2023-06-24 | 2023-09-30 | 4500538418 | 2023-07-01 | On Time | Follow up with the supplier | Production Stage
40573536 | 2023-06-24 | 2023-09-27 | 4500538422 | 2023-07-01 | On Time | Follow up with the supplier | Production Stage
40573538 | 2023-06-24 | 2023-09-30 | 4500538421 | 2023-07-01 | On Time | Follow up with the supplier | Production Stage
40573548 | 2023-06-24 | 2023-09-25 | 4500538420 | 2023-07-01 | On Time | Follow up with the supplier | Production Stage
40573627 | 2023-06-25 | 2023-09-26 | 4500538423 | 2023-07-01 | On Time | Follow up with the supplier | Production Stage
40573660 | 2023-06-25 | 2023-10-01 | 4500538425 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
40573664 | 2023-06-25 | 2023-10-01 | 4500538424 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
40573667 | 2023-06-25 | 2023-10-02 | 4500538426 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
40573743 | 2023-06-25 | 2023-09-26 | 4500538427 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
40573876 | 2023-06-26 | 2023-09-27 | 4500538432 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
40573917 | 2023-06-26 | 2023-10-01 | 4500538435 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
40574011 | 2023-06-26 | 2023-09-27 | 4500538437 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
40574137 | 2023-06-29 | 2023-09-30 | 4500538438 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
40574243 | 2023-06-29 | 2023-10-02 | 4500538439 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
40574477 | 2023-07-01 | 2023-10-02 | 4500538440 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
73222121 | 2023-03-16 | 2023-08-24 | 4500536803 | 2023-06-12 | On Time | Follow up with the supplier | Production Stage
73250432 | 2023-03-29 | 2023-08-10 | 4500538391 | 2023-06-27 | 23 Days Delay | Create a ticket to report the delay of (23) days | (-23)
73282662 | 2023-05-02 | 2023-08-05 | 4500533709 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
73287425 | 2023-05-09 | 2023-08-10 | 4500534224 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
73292050 | 2023-05-16 | 2023-08-17 | 4500535061 | 2023-05-23 | On Time | Follow up with the supplier | Production Stage
73294410 | 2023-05-20 | 2023-08-24 | 4500535062 | 2023-05-23 | On Time | nominate the forwarder | Nomination Stage
301768062 | 2023-02-05 | 2023-04-29 | 4500532755 | 2023-04-26 | 64 Days Delay | Create a ticket to report the delay of (64) days | (-64)
301768070 | 2023-02-05 | 2023-04-29 | 4500532772 | 2023-04-26 | 64 Days Delay | Create a ticket to report the delay of (64) days | (-64)
301839526 | 2023-04-20 | 2023-07-25 | 4500532774 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
301861129 | 2023-05-31 | 2023-08-31 | 4500536374 | 2023-06-06 | On Time | Follow up with the supplier | Production Stage
301861210 | 2023-05-31 | 2023-09-19 | 4500536373 | 2023-06-06 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
301870813 | 2023-06-19 | 2023-09-25 | 4500537686 | 2023-06-20 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
301870817 | 2023-06-19 | 2023-09-25 | 4500537687 | 2023-06-20 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
391189301 | 2023-02-04 | 2023-05-06 | 4500536059 | 2023-05-31 | 92 Days Delay | Create a ticket to report the delay of (92) days | (-92)
391201403 | 2023-02-25 | 2023-08-02 | 4500536083 | 2023-05-31 | 4 Days Delay | Create a ticket to report the delay of (4) days | (-4)
391243234 | 2023-04-17 | 2023-07-16 | 4500532775 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
391244372 | 2023-04-18 | 2023-07-17 | 4500532776 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
391246161 | 2023-04-22 | 2023-07-23 | 4500532778 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
391256338 | 2023-05-15 | 2023-08-15 | 4500534553 | 2023-05-18 | On Time | Follow up with the supplier | Production Stage
391256356 | 2023-05-15 | 2023-08-15 | 4500534554 | 2023-05-18 | On Time | Follow up with the supplier | Production Stage
391258518 | 2023-05-21 | 2023-08-14 | 4500535647 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
391258522 | 2023-05-21 | 2023-08-21 | 4500535648 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
391258526 | 2023-05-21 | 2023-08-22 | 4500535649 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
391265125 | 2023-06-06 | 2023-09-06 | 4500536638 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
391269139 | 2023-06-17 | 2023-09-16 | 4500537326 | 2023-06-18 | On Time | Follow up with the supplier | Production Stage
810082311 | 2023-04-17 | 2023-07-22 | 4500532779 | 2023-04-26 | On Time | Follow up with the supplier | Production Stage
810082579 | 2023-05-01 | 2023-08-03 | 4500533710 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
810082591 | 2023-05-01 | 2023-08-07 | 4500533711 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
810082594 | 2023-05-01 | 2023-08-06 | 4500533712 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
810082596 | 2023-05-01 | 2023-08-06 | 4500533713 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
810082610 | 2023-05-02 | 2023-08-05 | 4500533714 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
810082619 | 2023-05-02 | 2023-08-07 | 4500533715 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
810082670 | 2023-05-04 | 2023-08-10 | 4500533716 | 2023-05-08 | On Time | nominate the forwarder | Nomination Stage
810082672 | 2023-05-04 | 2023-08-08 | 4500533717 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
810082787 | 2023-05-08 | 2023-08-12 | 4500533718 | 2023-05-08 | On Time | nominate the forwarder | Nomination Stage
810082788 | 2023-05-08 | 2023-08-12 | 4500533719 | 2023-05-08 | On Time | nominate the forwarder | Nomination Stage
810082789 | 2023-05-08 | 2023-08-12 | 4500533720 | 2023-05-08 | On Time | nominate the forwarder | Nomination Stage
810082799 | 2023-05-08 | 2023-08-14 | 4500534227 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
810082826 | 2023-05-09 | 2023-08-13 | 4500534228 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
810082827 | 2023-05-09 | 2023-08-12 | 4500534229 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
810082963 | 2023-05-13 | 2023-08-14 | 4500534559 | 2023-05-18 | On Time | Follow up with the supplier | Production Stage
810083027 | 2023-05-15 | 2023-08-19 | 4500534561 | 2023-05-18 | On Time | nominate the forwarder | Nomination Stage
810083189 | 2023-05-21 | 2023-08-24 | 4500535660 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
810083205 | 2023-05-22 | 2023-08-26 | 4500535661 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
810083221 | 2023-05-23 | 2023-08-24 | 4500535662 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
810083327 | 2023-05-28 | 2023-08-30 | 4500536074 | 2023-05-31 | On Time | Follow up with the supplier | Production Stage
810083477 | 2023-06-03 | 2023-09-30 | 4500536357 | 2023-06-05 | On Time | Follow up with Forwarder and Update ETA | Shipping Stage
810083665 | 2023-06-08 | 2023-09-12 | 4500536649 | 2023-06-11 | On Time | nominate the forwarder | Nomination Stage
810083737 | 2023-06-11 | 2023-09-13 | 4500536805 | 2023-06-12 | On Time | nominate the forwarder | Nomination Stage
810083826 | 2023-06-14 | 2023-09-17 | 4500537322 | 2023-06-18 | On Time | Follow up with the supplier | Production Stage
810083949 | 2023-06-18 | 2023-09-19 | 4500537329 | 2023-06-18 | On Time | nominate the forwarder | Nomination Stage
810083950 | 2023-06-18 | 2023-09-19 | 4500537330 | 2023-06-18 | On Time | nominate the forwarder | Nomination Stage
810083957 | 2023-06-18 | 2023-09-19 | 4500537333 | 2023-06-18 | On Time | nominate the forwarder | Nomination Stage
810084172 | 2023-06-26 | 2023-09-27 | 4500538430 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
810084173 | 2023-06-26 | 2023-09-27 | 4500538431 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
810084195 | 2023-06-26 | 2023-09-27 | 4500538433 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
910120339 | 2023-04-15 | 2023-07-19 | 4500532025 | 2023-04-17 | On Time | nominate the forwarder | Nomination Stage
910121229 | 2023-05-02 | 2023-08-05 | 4500533722 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
910121276 | 2023-05-03 | 2023-08-05 | 4500533723 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
910121325 | 2023-05-04 | 2023-08-07 | 4500533724 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
910121347 | 2023-05-04 | 2023-08-07 | 4500533726 | 2023-05-08 | On Time | Follow up with the supplier | Production Stage
910121455 | 2023-05-07 | 2023-08-12 | 4500533727 | 2023-05-08 | On Time | nominate the forwarder | Nomination Stage
910121606 | 2023-05-09 | 2023-08-12 | 4500534231 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
910121694 | 2023-05-11 | 2023-08-13 | 4500534233 | 2023-05-14 | On Time | Follow up with the supplier | Production Stage
910121699 | 2023-05-11 | 2023-08-13 | 4500534310 | 2023-05-15 | On Time | Follow up with the supplier | Production Stage
910121799 | 2023-05-13 | 2023-08-14 | 4500534564 | 2023-05-18 | On Time | Follow up with the supplier | Production Stage
910122007 | 2023-05-16 | 2023-08-17 | 4500534566 | 2023-05-18 | On Time | Follow up with the supplier | Production Stage
910122053 | 2023-05-17 | 2023-08-20 | 4500534571 | 2023-05-18 | On Time | nominate the forwarder | Nomination Stage
910122057 | 2023-05-17 | 2023-08-19 | 4500534572 | 2023-05-18 | On Time | nominate the forwarder | Nomination Stage
910122099 | 2023-05-18 | 2023-08-20 | 4500535069 | 2023-05-23 | On Time | Follow up with the supplier | Production Stage
910122211 | 2023-05-21 | 2023-08-22 | 4500535663 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
910122269 | 2023-05-22 | 2023-08-23 | 4500535664 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
910122331 | 2023-05-23 | 2023-08-26 | 4500535665 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
910122369 | 2023-05-24 | 2023-08-27 | 4500535666 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
910122415 | 2023-05-25 | 2023-08-27 | 4500535667 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
910122421 | 2023-05-25 | 2023-08-23 | 4500535668 | 2023-05-27 | On Time | Follow up with the supplier | Production Stage
910122595 | 2023-05-29 | 2023-08-30 | 4500536077 | 2023-05-31 | On Time | Follow up with the supplier | Production Stage
910122603 | 2023-05-29 | 2023-08-30 | 4500536078 | 2023-05-31 | On Time | Follow up with the supplier | Production Stage
910122611 | 2023-05-29 | 2023-08-30 | 4500536359 | 2023-06-05 | On Time | Follow up with the supplier | Production Stage
910122651 | 2023-05-30 | 2023-08-31 | 4500536080 | 2023-05-31 | On Time | Follow up with the supplier | Production Stage
910122781 | 2023-06-01 | 2023-09-05 | 4500536360 | 2023-06-05 | On Time | Follow up with the supplier | Production Stage
910122887 | 2023-06-03 | 2023-09-05 | 4500536361 | 2023-06-05 | On Time | Follow up with the supplier | Production Stage
910122988 | 2023-06-05 | 2023-09-06 | 4500536363 | 2023-06-05 | On Time | nominate the forwarder | Nomination Stage
910123193 | 2023-06-08 | 2023-09-11 | 4500536650 | 2023-06-11 | On Time | Follow up with the supplier | Production Stage
910123409 | 2023-06-12 | 2023-09-13 | 4500537081 | 2023-06-14 | On Time | Follow up with the supplier | Production Stage
910123410 | 2023-06-12 | 2023-09-14 | 4500537082 | 2023-06-14 | On Time | Follow up with the supplier | Production Stage
910123413 | 2023-06-12 | 2023-09-14 | 4500537084 | 2023-06-14 | On Time | Follow up with the supplier | Production Stage
910123467 | 2023-06-13 | 2023-09-16 | 4500537083 | 2023-06-14 | On Time | nominate the forwarder | Nomination Stage
910123686 | 2023-06-17 | 2023-09-18 | 4500537328 | 2023-06-18 | On Time | Follow up with the supplier | Production Stage
910123760 | 2023-06-18 | 2023-09-19 | 4500537331 | 2023-06-18 | On Time | nominate the forwarder | Nomination Stage
910123761 | 2023-06-18 | 2023-09-19 | 4500537332 | 2023-06-18 | On Time | nominate the forwarder | Nomination Stage
910123813 | 2023-06-19 | 2023-09-20 | 4500537689 | 2023-06-20 | On Time | Follow up with the supplier | Production Stage
910123816 | 2023-06-19 | 2023-09-20 | 4500537691 | 2023-06-20 | On Time | Follow up with the supplier | Production Stage
910123855 | 2023-06-20 | 2023-09-21 | 4500537692 | 2023-06-20 | On Time | nominate the forwarder | Nomination Stage
910123878 | 2023-06-20 | 2023-09-21 | 4500537693 | 2023-06-20 | On Time | nominate the forwarder | Nomination Stage
910123880 | 2023-06-20 | 2023-09-21 | 4500537694 | 2023-06-20 | On Time | nominate the forwarder | Nomination Stage
910123930 | 2023-06-21 | 2023-09-24 | 4500537929 | 2023-06-22 | On Time | nominate the forwarder | Nomination Stage
910124195 | 2023-06-25 | 2023-09-27 | 4500538428 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
910124221 | 2023-06-26 | 2023-09-27 | 4500538429 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
910124251 | 2023-06-26 | 2023-09-27 | 4500538434 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage
910124252 | 2023-06-26 | 2023-09-27 | 4500538436 | 2023-07-02 | On Time | Follow up with the supplier | Production Stage

## Data_1
Instructions
-999 | Create a ticket to report the delay of
1 | Follow up with the supplier
26 | nominate the forwarder
30 | Follow up with Forwarder and Update ETA
65 | Check with Clearance Team
76 | Check with Warehouse Team
Order Stage
1 | Production Stage
26 | Nomination Stage
30 | Shipping Stage
56 | Clearance Stage
67 | Receiving Stage
90 | Critical stage

## Sheet2
Sales Doc. | Created On | Req.dlv.dt | PO | PO CREATION
2462369 | 2023-04-19 | 2023-07-24 | 4500532753 | 2023-04-26
2468406 | 2023-05-02 | 2023-08-05 | 4500533693 | 2023-05-08
2468408 | 2023-05-02 | 2023-08-05 | 4500533694 | 2023-05-08
2469059 | 2023-05-04 | 2023-11-11 | 4500533695 | 2023-05-08
2470424 | 2023-05-08 | 2023-08-17 | 4500533696 | 2023-05-08
2472392 | 2023-05-14 | 2023-08-17 | 4500534548 | 2023-05-18
2472395 | 2023-05-14 | 2023-08-15 | 4500534549 | 2023-05-18
2474735 | 2023-05-21 | 2023-08-31 | 4500535642 | 2023-05-27
2475010 | 2023-05-22 | 2023-08-30 | 4500535643 | 2023-05-27
2475077 | 2023-05-22 | 2023-08-22 | 4500536041 | 2023-05-31
2475585 | 2023-05-24 | 2023-08-30 | 4500535644 | 2023-05-27
2475596 | 2023-05-24 | 2023-08-30 | 4500535645 | 2023-05-27
2475881 | 2023-05-25 | 2023-09-03 | 4500536054 | 2023-05-31
2476580 | 2023-05-27 | 2023-08-31 | 4500535646 | 2023-05-27
2477444 | 2023-05-29 | 2023-09-23 | 4500536056 | 2023-05-31
2477985 | 2023-05-31 | 2023-09-09 | 4500536375 | 2023-06-06
2480045 | 2023-06-06 | 2023-09-11 | 4500536625 | 2023-06-10
2480046 | 2023-06-06 | 2023-09-12 | 4500536635 | 2023-06-11
2480706 | 2023-06-08 | 2023-09-14 | 4500536636 | 2023-06-11
2481448 | 2023-06-10 | 2023-09-16 | 4500536637 | 2023-06-11
2485063 | 2023-06-21 | 2023-09-27 | 4500537928 | 2023-06-22
2485964 | 2023-06-24 | 2023-09-28 | 4500538419 | 2023-07-01
36000834 | 2023-04-20 | 2023-07-24 | 4500532757 | 2023-04-26
40561678 | 2023-04-19 | 2023-07-24 | 4500532759 | 2023-04-26
40561836 | 2023-04-20 | 2023-07-26 | 4500532761 | 2023-04-26
40561847 | 2023-04-20 | 2023-07-29 | 4500532762 | 2023-04-26
40561874 | 2023-04-20 | 2023-07-24 | 4500532764 | 2023-04-26
40561882 | 2023-04-20 | 2023-07-24 | 4500532765 | 2023-04-26
40561888 | 2023-04-20 | 2023-07-30 | 4500532766 | 2023-04-26
40561894 | 2023-04-20 | 2023-07-24 | 4500532767 | 2023-04-26
40561902 | 2023-04-20 | 2023-07-24 | 4500532768 | 2023-04-26
40562514 | 2023-04-26 | 2023-07-31 | 4500532770 | 2023-04-26
40563634 | 2023-05-01 | 2023-08-05 | 4500533697 | 2023-05-08
40563655 | 2023-05-01 | 2023-08-06 | 4500533698 | 2023-05-08
40563754 | 2023-05-02 | 2023-08-05 | 4500533699 | 2023-05-08
40563760 | 2023-05-02 | 2023-08-06 | 4500533700 | 2023-05-08
40563829 | 2023-05-02 | 2023-08-03 | 4500533701 | 2023-05-08
40563830 | 2023-05-02 | 2023-08-03 | 4500533702 | 2023-05-08
40563836 | 2023-05-02 | 2023-08-03 | 4500533703 | 2023-05-08
40564011 | 2023-05-03 | 2023-08-07 | 4500533704 | 2023-05-08
40564019 | 2023-05-03 | 2023-08-06 | 4500533705 | 2023-05-08
40564215 | 2023-05-04 | 2023-08-06 | 4500533706 | 2023-05-08
40564219 | 2023-05-04 | 2023-08-07 | 4500533707 | 2023-05-08
40564577 | 2023-05-06 | 2023-08-10 | 4500533708 | 2023-05-08
40565096 | 2023-05-09 | 2023-08-10 | 4500534212 | 2023-05-14
40565098 | 2023-05-09 | 2023-08-10 | 4500534218 | 2023-05-14
40565120 | 2023-05-09 | 2023-08-10 | 4500534219 | 2023-05-14
40565238 | 2023-05-10 | 2023-08-12 | 4500534221 | 2023-05-14
40565241 | 2023-05-10 | 2023-08-12 | 4500534222 | 2023-05-14
40565257 | 2023-05-10 | 2023-08-13 | 4500534223 | 2023-05-14
40565956 | 2023-05-14 | 2023-08-15 | 4500534612 | 2023-05-18
40566326 | 2023-05-16 | 2023-08-21 | 4500534556 | 2023-05-18
40566528 | 2023-05-17 | 2023-08-20 | 4500534557 | 2023-05-18
40566603 | 2023-05-17 | 2023-08-23 | 4500534616 | 2023-05-18
40566606 | 2023-05-17 | 2023-08-23 | 4500534558 | 2023-05-18
40566789 | 2023-05-18 | 2023-08-24 | 4500536347 | 2023-06-05
40566796 | 2023-05-18 | 2023-08-27 | 4500535060 | 2023-05-23
40567097 | 2023-05-21 | 2023-08-28 | 4500535637 | 2023-05-27
40567098 | 2023-05-21 | 2023-08-23 | 4500535639 | 2023-05-27
40567143 | 2023-05-21 | 2023-08-23 | 4500535640 | 2023-05-27
40567400 | 2023-05-22 | 2023-08-23 | 4500535641 | 2023-05-27
40567441 | 2023-05-22 | 2023-08-31 | 4500536063 | 2023-05-31
40567589 | 2023-05-23 | 2023-08-26 | 4500535654 | 2023-05-27
40567640 | 2023-05-23 | 2023-08-24 | 4500535655 | 2023-05-27
40567702 | 2023-05-24 | 2023-09-02 | 4500535656 | 2023-05-27
40567748 | 2023-05-24 | 2023-09-23 | 4500535657 | 2023-05-27
40567836 | 2023-05-24 | 2023-08-26 | 4500535658 | 2023-05-27
40567931 | 2023-05-25 | 2023-08-27 | 4500535659 | 2023-05-27
40568635 | 2023-05-29 | 2023-08-30 | 4500536061 | 2023-05-31
40568641 | 2023-05-29 | 2023-08-30 | 4500536064 | 2023-05-31
40568657 | 2023-05-29 | 2023-08-31 | 4500536068 | 2023-05-31
40568781 | 2023-05-30 | 2023-09-02 | 4500536070 | 2023-05-31
40568809 | 2023-05-30 | 2023-09-03 | 4500536395 | 2023-06-06
40568903 | 2023-05-31 | 2023-09-07 | 4500536348 | 2023-06-05
40568914 | 2023-05-31 | 2023-09-02 | 4500536350 | 2023-06-05
40569166 | 2023-06-01 | 2023-09-03 | 4500536351 | 2023-06-05
40569548 | 2023-06-03 | 2023-09-04 | 4500536352 | 2023-06-05
40569551 | 2023-06-03 | 2023-09-04 | 4500536353 | 2023-06-05
40569613 | 2023-06-04 | 2023-09-09 | 4500536354 | 2023-06-05
40569822 | 2023-06-05 | 2023-09-07 | 4500536355 | 2023-06-05
40569865 | 2023-06-05 | 2023-09-07 | 4500536356 | 2023-06-05
40569878 | 2023-06-05 | 2023-09-06 | 4500536626 | 2023-06-10
40569895 | 2023-06-05 | 2023-09-06 | 4500536627 | 2023-06-10
40569896 | 2023-06-05 | 2023-09-06 | 4500536628 | 2023-06-11
40569898 | 2023-06-05 | 2023-09-13 | 4500536629 | 2023-06-11
40569955 | 2023-06-05 | 2023-09-06 | 4500536630 | 2023-06-11
40569956 | 2023-06-05 | 2023-09-06 | 4500536631 | 2023-06-11

## Sheet3
Sales Doc. | Created On | Req.dlv.dt | PO | PO CREATION
40563830 | 2023-05-02 | 2023-08-03 | 4500533702 | 2023-05-08
40563836 | 2023-05-02 | 2023-08-03 | 4500533703 | 2023-05-08
40564011 | 2023-05-03 | 2023-08-07 | 4500533704 | 2023-05-08
40564019 | 2023-05-03 | 2023-08-06 | 4500533705 | 2023-05-08
40564215 | 2023-05-04 | 2023-08-06 | 4500533706 | 2023-05-08
40564219 | 2023-05-04 | 2023-08-07 | 4500533707 | 2023-05-08
40564577 | 2023-05-06 | 2023-08-10 | 4500533708 | 2023-05-08
40565096 | 2023-05-09 | 2023-08-10 | 4500534212 | 2023-05-14
40565098 | 2023-05-09 | 2023-08-10 | 4500534218 | 2023-05-14
40565120 | 2023-05-09 | 2023-08-10 | 4500534219 | 2023-05-14
40565238 | 2023-05-10 | 2023-08-12 | 4500534221 | 2023-05-14
40565241 | 2023-05-10 | 2023-08-12 | 4500534222 | 2023-05-14
2475585 | 2023-05-10 | 2023-08-13 | 4500534223 | 2023-05-14
40565956 | 2023-05-14 | 2023-08-15 | 4500534612 | 2023-05-18
40566326 | 2023-05-16 | 2023-08-21 | 4500534556 | 2023-05-18
40566528 | 2023-05-17 | 2023-08-20 | 4500534557 | 2023-05-18
40566603 | 2023-05-17 | 2023-08-23 | 4500534616 | 2023-05-18
40566606 | 2023-05-17 | 2023-08-23 | 4500534558 | 2023-05-18
40566789 | 2023-05-18 | 2023-08-24 | 4500536347 | 2023-06-05
40566796 | 2023-05-18 | 2023-08-27 | 4500535060 | 2023-05-23
40567097 | 2023-05-21 | 2023-08-28 | 4500535637 | 2023-05-27
40567098 | 2023-05-21 | 2023-08-23 | 4500535639 | 2023-05-27
40567143 | 2023-05-21 | 2023-08-23 | 4500535640 | 2023-05-27
40567400 | 2023-05-22 | 2023-08-23 | 4500535641 | 2023-05-27
40567441 | 2023-05-22 | 2023-08-31 | 4500536063 | 2023-05-31
40567589 | 2023-05-23 | 2023-08-26 | 4500535654 | 2023-05-27
40567640 | 2023-05-23 | 2023-08-24 | 4500535655 | 2023-05-27
40567702 | 2023-05-24 | 2023-09-02 | 4500535656 | 2023-05-27
40567748 | 2023-05-24 | 2023-09-23 | 4500535657 | 2023-05-27
40567836 | 2023-05-24 | 2023-08-26 | 4500535658 | 2023-05-27
40567931 | 2023-05-25 | 2023-08-27 | 4500535659 | 2023-05-27
40568635 | 2023-05-29 | 2023-08-30 | 4500536061 | 2023-05-31
40568641 | 2023-05-29 | 2023-08-30 | 4500536064 | 2023-05-31
40568657 | 2023-05-29 | 2023-08-31 | 4500536068 | 2023-05-31
40568781 | 2023-05-30 | 2023-09-02 | 4500536070 | 2023-05-31
40568809 | 2023-05-30 | 2023-09-03 | 4500536395 | 2023-06-06
40568903 | 2023-05-31 | 2023-09-07 | 4500536348 | 2023-06-05
40568914 | 2023-05-31 | 2023-09-02 | 4500536350 | 2023-06-05
40569166 | 2023-06-01 | 2023-09-03 | 4500536351 | 2023-06-05
40569548 | 2023-06-03 | 2023-09-04 | 4500536352 | 2023-06-05
40569551 | 2023-06-03 | 2023-09-04 | 4500536353 | 2023-06-05
40569613 | 2023-06-04 | 2023-09-09 | 4500536354 | 2023-06-05
40569822 | 2023-06-05 | 2023-09-07 | 4500536355 | 2023-06-05
40569865 | 2023-06-05 | 2023-09-07 | 4500536356 | 2023-06-05
40569878 | 2023-06-05 | 2023-09-06 | 4500536626 | 2023-06-10
40569895 | 2023-06-05 | 2023-09-06 | 4500536627 | 2023-06-10
40569896 | 2023-06-05 | 2023-09-06 | 4500536628 | 2023-06-11
2475585 | 2023-06-05 | 2023-09-13 | 4500536629 | 2023-06-11
40569955 | 2023-06-05 | 2023-09-06 | 4500536630 | 2023-06-11
40569956 | 2023-06-05 | 2023-09-06 | 4500536631 | 2023-06-11
40569958 | 2023-06-05 | 2023-09-13 | 4500536632 | 2023-06-11
40569959 | 2023-06-05 | 2023-09-13 | 4500536633 | 2023-06-11
40569964 | 2023-06-05 | 2023-09-07 | 4500536634 | 2023-06-11
40570053 | 2023-06-06 | 2023-09-07 | 4500536639 | 2023-06-11
40570102 | 2023-06-06 | 2023-09-09 | 4500536640 | 2023-06-11
40570108 | 2023-06-06 | 2023-09-09 | 4500536641 | 2023-06-11
40570117 | 2023-06-06 | 2023-09-09 | 4500536642 | 2023-06-11
40570118 | 2023-06-06 | 2023-09-07 | 4500536643 | 2023-06-11
40570280 | 2023-06-07 | 2023-09-09 | 4500536644 | 2023-06-11
40570293 | 2023-06-07 | 2023-09-12 | 4500536645 | 2023-06-11
40570327 | 2023-06-07 | 2023-09-09 | 4500536646 | 2023-06-11
40570337 | 2023-06-07 | 2023-09-09 | 4500536647 | 2023-06-11
40570338 | 2023-06-07 | 2023-09-09 | 4500536648 | 2023-06-11
40570738 | 2023-06-10 | 2023-09-16 | 4500536810 | 2023-06-12
40570843 | 2023-06-10 | 2023-09-11 | 4500536807 | 2023-06-12
40571284 | 2023-06-12 | 2023-09-13 | 4500537075 | 2023-06-14
40571391 | 2023-06-13 | 2023-09-17 | 4500537078 | 2023-06-14
40571396 | 2023-06-13 | 2023-09-17 | 4500537079 | 2023-06-14
40571577 | 2023-06-13 | 2023-09-14 | 4500537080 | 2023-06-14
40571643 | 2023-06-14 | 2023-09-16 | 4500537320 | 2023-06-18
40571683 | 2023-06-14 | 2023-09-16 | 4500537321 | 2023-06-18
40571788 | 2023-06-15 | 2023-09-18 | 4500537323 | 2023-06-18
40571883 | 2023-06-15 | 2023-09-17 | 4500537325 | 2023-06-18
40571884 | 2023-06-15 | 2023-09-17 | 4500537324 | 2023-06-18
40572080 | 2023-06-17 | 2023-09-18 | 4500537327 | 2023-06-18
40572789 | 2023-06-20 | 2023-09-21 | 4500537927 | 2023-06-22
40573152 | 2023-06-22 | 2023-09-25 | 4500537931 | 2023-06-22
40573154 | 2023-06-22 | 2023-09-25 | 4500537932 | 2023-06-22
40573171 | 2023-06-22 | 2023-09-26 | 4500537930 | 2023-06-22
40573486 | 2023-06-24 | 2023-09-30 | 4500538418 | 2023-07-01
40573536 | 2023-06-24 | 2023-09-27 | 4500538422 | 2023-07-01
40573538 | 2023-06-24 | 2023-09-30 | 4500538421 | 2023-07-01
40573548 | 2023-06-24 | 2023-09-25 | 4500538420 | 2023-07-01
40573627 | 2023-06-25 | 2023-09-26 | 4500538423 | 2023-07-01
40573660 | 2023-06-25 | 2023-10-01 | 4500538425 | 2023-07-02
40573664 | 2023-06-25 | 2023-10-01 | 4500538424 | 2023-07-02
40573667 | 2023-06-25 | 2023-10-02 | 4500538426 | 2023-07-02
40573743 | 2023-06-25 | 2023-09-26 | 4500538427 | 2023-07-02
40573876 | 2023-06-26 | 2023-09-27 | 4500538432 | 2023-07-02
40573917 | 2023-06-26 | 2023-10-01 | 4500538435 | 2023-07-02
40574011 | 2023-06-26 | 2023-09-27 | 4500538437 | 2023-07-02
40574137 | 2023-06-29 | 2023-09-30 | 4500538438 | 2023-07-02
40574243 | 2023-06-29 | 2023-10-02 | 4500538439 | 2023-07-02
40574477 | 2023-07-01 | 2023-10-02 | 4500538440 | 2023-07-02
73222121 | 2023-03-16 | 2023-08-24 | 4500536803 | 2023-06-12
73250432 | 2023-03-29 | 2023-08-10 | 4500538391 | 2023-06-27
73282662 | 2023-05-02 | 2023-08-05 | 4500533709 | 2023-05-08
73287425 | 2023-05-09 | 2023-08-10 | 4500534224 | 2023-05-14
73292050 | 2023-05-16 | 2023-08-17 | 4500535061 | 2023-05-23
73294410 | 2023-05-20 | 2023-08-24 | 4500535062 | 2023-05-23
301768062 | 2023-02-05 | 2023-04-29 | 4500532755 | 2023-04-26
301768070 | 2023-02-05 | 2023-04-29 | 4500532772 | 2023-04-26
301839526 | 2023-04-20 | 2023-07-25 | 4500532774 | 2023-04-26
301861129 | 2023-05-31 | 2023-08-31 | 4500536374 | 2023-06-06
301861210 | 2023-05-31 | 2023-09-19 | 4500536373 | 2023-06-06
301870813 | 2023-06-19 | 2023-09-25 | 4500537686 | 2023-06-20
301870817 | 2023-06-19 | 2023-09-25 | 4500537687 | 2023-06-20
391189301 | 2023-02-04 | 2023-05-06 | 4500536059 | 2023-05-31
391201403 | 2023-02-25 | 2023-08-02 | 4500536083 | 2023-05-31
391243234 | 2023-04-17 | 2023-07-16 | 4500532775 | 2023-04-26
391244372 | 2023-04-18 | 2023-07-17 | 4500532776 | 2023-04-26
391246161 | 2023-04-22 | 2023-07-23 | 4500532778 | 2023-04-26
391256338 | 2023-05-15 | 2023-08-15 | 4500534553 | 2023-05-18
391256356 | 2023-05-15 | 2023-08-15 | 4500534554 | 2023-05-18
391258518 | 2023-05-21 | 2023-08-14 | 4500535647 | 2023-05-27
391258522 | 2023-05-21 | 2023-08-21 | 4500535648 | 2023-05-27
391258526 | 2023-05-21 | 2023-08-22 | 4500535649 | 2023-05-27
391265125 | 2023-06-06 | 2023-09-06 | 4500536638 | 2023-06-11
391269139 | 2023-06-17 | 2023-09-16 | 4500537326 | 2023-06-18
810082311 | 2023-04-17 | 2023-07-22 | 4500532779 | 2023-04-26
810082579 | 2023-05-01 | 2023-08-03 | 4500533710 | 2023-05-08
810082591 | 2023-05-01 | 2023-08-07 | 4500533711 | 2023-05-08
810082594 | 2023-05-01 | 2023-08-06 | 4500533712 | 2023-05-08
810082596 | 2023-05-01 | 2023-08-06 | 4500533713 | 2023-05-08
810082610 | 2023-05-02 | 2023-08-05 | 4500533714 | 2023-05-08
810082619 | 2023-05-02 | 2023-08-07 | 4500533715 | 2023-05-08
810082670 | 2023-05-04 | 2023-08-10 | 4500533716 | 2023-05-08
810082672 | 2023-05-04 | 2023-08-08 | 4500533717 | 2023-05-08
810082787 | 2023-05-08 | 2023-08-12 | 4500533718 | 2023-05-08
810082788 | 2023-05-08 | 2023-08-12 | 4500533719 | 2023-05-08
810082789 | 2023-05-08 | 2023-08-12 | 4500533720 | 2023-05-08
810082799 | 2023-05-08 | 2023-08-14 | 4500534227 | 2023-05-14
810082826 | 2023-05-09 | 2023-08-13 | 4500534228 | 2023-05-14
810082827 | 2023-05-09 | 2023-08-12 | 4500534229 | 2023-05-14
810082963 | 2023-05-13 | 2023-08-14 | 4500534559 | 2023-05-18
810083027 | 2023-05-15 | 2023-08-19 | 4500534561 | 2023-05-18
810083189 | 2023-05-21 | 2023-08-24 | 4500535660 | 2023-05-27
810083205 | 2023-05-22 | 2023-08-26 | 4500535661 | 2023-05-27
810083221 | 2023-05-23 | 2023-08-24 | 4500535662 | 2023-05-27
810083327 | 2023-05-28 | 2023-08-30 | 4500536074 | 2023-05-31
810083477 | 2023-06-03 | 2023-09-30 | 4500536357 | 2023-06-05
810083665 | 2023-06-08 | 2023-09-12 | 4500536649 | 2023-06-11
810083737 | 2023-06-11 | 2023-09-13 | 4500536805 | 2023-06-12
810083826 | 2023-06-14 | 2023-09-17 | 4500537322 | 2023-06-18
810083949 | 2023-06-18 | 2023-09-19 | 4500537329 | 2023-06-18
810083950 | 2023-06-18 | 2023-09-19 | 4500537330 | 2023-06-18
810083957 | 2023-06-18 | 2023-09-19 | 4500537333 | 2023-06-18
810084172 | 2023-06-26 | 2023-09-27 | 4500538430 | 2023-07-02
810084173 | 2023-06-26 | 2023-09-27 | 4500538431 | 2023-07-02
810084195 | 2023-06-26 | 2023-09-27 | 4500538433 | 2023-07-02
910120339 | 2023-04-15 | 2023-07-19 | 4500532025 | 2023-04-17
910121229 | 2023-05-02 | 2023-08-05 | 4500533722 | 2023-05-08
910121276 | 2023-05-03 | 2023-08-05 | 4500533723 | 2023-05-08
910121325 | 2023-05-04 | 2023-08-07 | 4500533724 | 2023-05-08
910121347 | 2023-05-04 | 2023-08-07 | 4500533726 | 2023-05-08
910121455 | 2023-05-07 | 2023-08-12 | 4500533727 | 2023-05-08
910121606 | 2023-05-09 | 2023-08-12 | 4500534231 | 2023-05-14
910121694 | 2023-05-11 | 2023-08-13 | 4500534233 | 2023-05-14
910121699 | 2023-05-11 | 2023-08-13 | 4500534310 | 2023-05-15
910121799 | 2023-05-13 | 2023-08-14 | 4500534564 | 2023-05-18
910122007 | 2023-05-16 | 2023-08-17 | 4500534566 | 2023-05-18
910122053 | 2023-05-17 | 2023-08-20 | 4500534571 | 2023-05-18
910122057 | 2023-05-17 | 2023-08-19 | 4500534572 | 2023-05-18
910122099 | 2023-05-18 | 2023-08-20 | 4500535069 | 2023-05-23
910122211 | 2023-05-21 | 2023-08-22 | 4500535663 | 2023-05-27
910122269 | 2023-05-22 | 2023-08-23 | 4500535664 | 2023-05-27
910122331 | 2023-05-23 | 2023-08-26 | 4500535665 | 2023-05-27
910122369 | 2023-05-24 | 2023-08-27 | 4500535666 | 2023-05-27
910122415 | 2023-05-25 | 2023-08-27 | 4500535667 | 2023-05-27
910122421 | 2023-05-25 | 2023-08-23 | 4500535668 | 2023-05-27
910122595 | 2023-05-29 | 2023-08-30 | 4500536077 | 2023-05-31
910122603 | 2023-05-29 | 2023-08-30 | 4500536078 | 2023-05-31
910122611 | 2023-05-29 | 2023-08-30 | 4500536359 | 2023-06-05
910122651 | 2023-05-30 | 2023-08-31 | 4500536080 | 2023-05-31
910122781 | 2023-06-01 | 2023-09-05 | 4500536360 | 2023-06-05
910122887 | 2023-06-03 | 2023-09-05 | 4500536361 | 2023-06-05
910122988 | 2023-06-05 | 2023-09-06 | 4500536363 | 2023-06-05
910123193 | 2023-06-08 | 2023-09-11 | 4500536650 | 2023-06-11
910123409 | 2023-06-12 | 2023-09-13 | 4500537081 | 2023-06-14
910123410 | 2023-06-12 | 2023-09-14 | 4500537082 | 2023-06-14
910123413 | 2023-06-12 | 2023-09-14 | 4500537084 | 2023-06-14
910123467 | 2023-06-13 | 2023-09-16 | 4500537083 | 2023-06-14
910123686 | 2023-06-17 | 2023-09-18 | 4500537328 | 2023-06-18
910123760 | 2023-06-18 | 2023-09-19 | 4500537331 | 2023-06-18
910123761 | 2023-06-18 | 2023-09-19 | 4500537332 | 2023-06-18
910123813 | 2023-06-19 | 2023-09-20 | 4500537689 | 2023-06-20
910123816 | 2023-06-19 | 2023-09-20 | 4500537691 | 2023-06-20
910123855 | 2023-06-20 | 2023-09-21 | 4500537692 | 2023-06-20
910123878 | 2023-06-20 | 2023-09-21 | 4500537693 | 2023-06-20
910123880 | 2023-06-20 | 2023-09-21 | 4500537694 | 2023-06-20
910123930 | 2023-06-21 | 2023-09-24 | 4500537929 | 2023-06-22
910124195 | 2023-06-25 | 2023-09-27 | 4500538428 | 2023-07-02
910124221 | 2023-06-26 | 2023-09-27 | 4500538429 | 2023-07-02
910124251 | 2023-06-26 | 2023-09-27 | 4500538434 | 2023-07-02