## Sheet1
Order Validity | Ord Status | LN SO# | Pos | Proj No | Committed | Machine # | Client Name | Project Name | Item Description | System/PO | DIA1 | DIA2 | Ends | System | Pressure | Order Qty | Pro Qty | Bal Qty | Transfer Qty | Rate/shift [pcs] | # of Shifts | Total Rate [pcs/day] | Duratin Numeric | Duration | Start | Finish
[6 empty] | Rotating Machine 1 (3 Shift) | Rotating Machine 1 (3 Shift) | ELBOWS (25Ø-125Ø) - | [15 empty] | 327.96 days | 2025-03-25
[16 empty] | 764 | 132 | 632 | 93 | 3.62 | 3 | 6 | 86.83 | 86.83 days | Wed 29/01/25 | Fri 09/05/25
| CA |  |  | 40M001333 |  | Rotating Machine 1 |  | Linde - Wesseling_14 | Elb 80R1.5/90 EST32 TBTB | [6 empty] | 150 | 111 | 39 | 0 | 3 | 3 | 9 | 4.3333 | 4.83 days | 2025-03-25 | 2025-03-29 08:00
| CA |  |  | 40P000358 |  | Rotating Machine 1 |  | B107/2 Vessel | Elb 100R1.5/30 EMT50/16 CBCB | [6 empty] | 7 | 0 | 7 | 0 | 1 | 3 | 3 | 2.3333 | 4.83 days | 2025-03-29 08:00 | 2025-03-31 16:00
| CA |  |  | 40P000358 |  | Rotating Machine 1 |  | B107/2 Vessel | Elb 100R1.5/45 EMT50/16 CBCB | [6 empty] | 10 | 0 | 10 | 0 | 1 | 3 | 3 | 3.3333 | 4.83 days | 2025-03-31 16:00 | 2025-04-04
| CA |  |  | 40P000358 |  | Rotating Machine 1 |  | B107/2 Vessel | Elb 65R1.5/90 EMT50/16 CBCB | [6 empty] | 1 | 0 | 1 | 0 | 1 | 3 | 3 | 0.33333 | 4.83 days | 2025-04-04 | 2025-04-04 08:00
| CA |  |  | 40P000356 |  | Rotating Machine 1 |  | B107/1Vessel | Elb 100R1.5/30 EMT50/16 CBCB | [6 empty] | 7 | 0 | 7 | 0 | 1 | 3 | 3 | 2.3333 | 4.83 days | 2025-04-04 08:00 | 2025-04-06 16:00
| CA |  |  | 40P000356 |  | Rotating Machine 1 |  | B107/1Vessel | Elb 100R1.5/45 EMT50/16 CBCB | [6 empty] | 10 | 0 | 10 | 0 | 1 | 3 | 3 | 3.3333 | 4.83 days | 2025-04-06 16:00 | 2025-04-10
| CA |  |  | 40P000356 |  | Rotating Machine 1 |  | B107/1Vessel | Elb 100R1.5/90 EMT50/16 CBCB | [6 empty] | 14 | 0 | 14 | 0 | 2 | 3 | 6 | 2.3333 | 4.83 days | 2025-04-10 | 2025-04-12 08:00
| CA |  |  | 40P000304 |  | Rotating Machine 1 |  | 6331 | Elb 125R1.5/15 EST25 CBCB | [6 empty] | 1 | 0 | 1 | 0 | 1 | 3 | 3 | 0.33333 | 4.83 days | 2025-04-12 08:00 | 2025-04-12 16:00
| CH |  |  | 16P000744 |  | Rotating Machine 1 |  | Ohaji South Project | Elbow 100R1.5/90° (Molded) EST25 Bar TBTB | [6 empty] | 35 | 0 | 35 | 0 | 2 | 3 | 6 | 5.8333 | 4.83 days | 2025-04-12 16:00 | 2025-04-18 12:00
| CH |  |  | 16P000744 |  | Rotating Machine 1 |  | Ohaji South Project | Elbow 50R1.5/90° (Molded) EST40 Bar TBTB | [6 empty] | 18 | 0 | 18 | 0 | 2 | 3 | 6 | 3 | 4.83 days | 2025-04-18 12:00 | 2025-04-21 12:00
| CH |  |  | 16P000744 |  | Rotating Machine 1 |  | Ohaji South Project | Elbow 80R1.5/90° (Molded) EST32 Bar TBTB | [6 empty] | 25 | 0 | 25 | 0 | 2 | 3 | 6 | 4.1667 | 4.83 days | 2025-04-21 12:00 | 2025-04-25 16:00
| CH |  |  | 16P000744 |  | Rotating Machine 1 |  | Ohaji South Project | Elbow 25R1.5/90° (Molded) EST50 Bar TBTB | [6 empty] | 6 | 0 | 6 | 0 | 2 | 3 | 6 | 1 | 4.83 days | 2025-04-25 16:00 | 2025-04-26 16:00
| CH |  |  | 16P000744 |  | Rotating Machine 1 |  | Ohaji South Project | Elbow 100R1.5/45° (Molded) EST25 Bar TBTB | [6 empty] | 2 | 0 | 2 | 0 | 2 | 3 | 6 | 0.33333 | 4.83 days | 2025-04-26 16:00 | 2025-04-27
| CH |  |  | 16P000641 |  | Rotating Machine 1 |  | Supply &install GRE Connection | Elbow 100R1.5/90° (Molded) EST25 Bar TBTB | [6 empty] | 2 | 0 | 2 | 0 | 2 | 3 | 6 | 0.33333 | 4.83 days | 2025-04-27 | 2025-04-27 08:00
| CH |  |  | 16P000882 |  | Rotating Machine 1 |  | GPC Alhamd Station | Elb 80R1.5/45 EST32 TBTB | [6 empty] | 4 | 0 | 4 | 0 | 2 | 3 | 6 | 0.66667 | 4.83 days | 2025-04-27 08:00 | 2025-04-28
| CH |  |  | 16P000882 |  | Rotating Machine 1 |  | GPC Alhamd Station | Elb 100R1.5/90 EST25 TBTB | [6 empty] | 7 | 0 | 7 | 0 | 2 | 3 | 6 | 1.1667 | 4.83 days | 2025-04-28 | 2025-04-29 04:00
| CH |  |  | 16P000882 |  | Rotating Machine 1 |  | GPC Alhamd Station | Elb 80R1.5/90 EST32 TBTB | [6 empty] | 38 | 0 | 38 | 0 | 2 | 3 | 6 | 6.3333 | 4.83 days | 2025-04-29 04:00 | 2025-05-05 12:00
| CH |  |  | 16P000882 |  | Rotating Machine 1 |  | GPC Alhamd Station | Elb 50R1.5/90 EST40 TBTB | [6 empty] | 24 | 0 | 24 | 0 | 2 | 3 | 6 | 4 | 4.83 days | 2025-05-05 12:00 | 2025-05-09 12:00
[11 empty] | 219.39 | 0 |  |  |  | 361 | 111 | 250 | 0 |  |  |  | 45.5 | 219.35 days | 2025-03-25 | 2025-05-09 12:00
[6 empty] | Rotating Machine 2 (3 Shift) | Rotating Machine 1 (3 Shift) | Couplers - Reducers (25Ø-900Ø) -
| CA |  |  | 40M001333 |  | Rotating Machine 2 |  | Linde - Wesseling_14 | RedEcc 80x50 EST32 TBTB | [6 empty] | 10 | 9 | 1 |  | 1 | 3 | 3 | 0.33333 | 5 days | 2025-03-25 | 2025-03-25 08:00
| CA |  |  | 40M001333 |  | Rotating Machine 2 |  | Linde - Wesseling_14 | RedEcc 300x200 EST16 TBTB | [6 empty] | 30 | 28 | 2 |  | 1 | 3 | 3 | 0.66667 | 5 days | 2025-03-25 08:00 | 2025-03-26
| CA |  |  | 40P000351 |  | Rotating Machine 2 |  | Chantiers E35 | Coupler 65 EMT50/16 CBCB | [6 empty] | 2 | 0 | 2 |  | 1 | 3 | 3 | 0.66667 | 5 days | 2025-03-26 | 2025-03-26 16:00
| CA |  |  | 40P000351 |  | Rotating Machine 2 |  | Chantiers E35 | Coupler 150 EMT50/16 CBCB | [6 empty] | 3 | 0 | 3 |  | 1 | 3 | 3 | 1 | 5 days | 2025-03-26 16:00 | 2025-03-27 16:00
| CA |  |  | 40P000351 |  | Rotating Machine 2 |  | Chantiers E35 | Coupler 200 EMT20/10 CBCB | [6 empty] | 1 | 0 | 1 |  | 1 | 3 | 3 | 0.33333 | 5 days | 2025-03-27 16:00 | 2025-03-28
GEI | CH | 01R016072 | 38 | 16P000744 | 2025-02-15 | Rotating Machine 2 |  | Ohaji South Project | Concentric Reducer 100x50 EST25 Bar TBTB | D65023436 | [5 empty] | 1 | 0 | 1 | 0 | 1 | 3 | 3 | 0.33333 | 0.25 days | 2025-03-28 | 2025-03-28 08:00
AUH | CH | 01E012284 | 11 | 16P000744 | 2025-02-20 | Rotating Machine 2 |  | Ohaji South Project | Concentric Reducer 100x80 EST25 Bar TBTB | D65023406 | [5 empty] | 1 | 0 | 1 | 0 | 1 | 3 | 3 | 0.33333 | 0.5 days | 2025-03-28 08:00 | 2025-03-28 16:00
GEI | CH | 01R015959 | 16 | 16P000882 | 2025-03-10 | Rotating Machine 2 |  | GPC Alhamd Station | RedCon 100x50 EST25 TBTB | D65023354 | [5 empty] | 4 | 0 | 4 | 0 | 1 | 3 | 3 | 1.3333 | 5 days | 2025-03-28 16:00 | 2025-03-30
KSA | CH | 01E012280 | 3 | 16P000882 | 2025-03-10 | Rotating Machine 2 |  | GPC Alhamd Station | RedCon 100x80 EST25 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 1 | 3 | 3 | 0.66667 | 3 days | 2025-03-30 | 2025-03-30 16:00
GEI | CH | 01R015959 | 16 | 16P000882 | 2025-03-15 | Rotating Machine 2 |  | GPC Alhamd Station | Coupler 50 EST40 TBTB | [6 empty] | 7 | 0 | 7 | 0 | 1 | 3 | 3 | 2.3333 | 5 days | 2025-03-30 16:00 | 2025-04-02
GEI | CH | 01R015959 | 16 | 16P000882 | 2025-03-20 | Rotating Machine 2 |  | GPC Alhamd Station | Coupler 50 EST40 TBTB | [6 empty] | 6 | 0 | 6 | 0 | 1 | 3 | 3 | 2 | 5 days | 2025-04-02 | 2025-04-04
GEI | CH | 01R015959 | 16 | 16P000882 | 2025-03-25 | Rotating Machine 2 |  | GPC Alhamd Station | Coupler 50 EST40 TBTB | [6 empty] | 4 | 0 | 4 | 0 | 1 | 3 | 3 | 1.3333 | 2.5 days | 2025-04-04 | 2025-04-05 08:00
KSA | CH | 01E012280 | 3 | 16P000882 | 2025-03-20 | Rotating Machine 2 |  | GPC Alhamd Station | Coupler 50 EST40 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 1 | 3 | 3 | 0.66667 | 3.13 days | 2025-04-05 08:00 | 2025-04-06
GEI | CH | 01R016110 | 39 | 16P000882 | 5-Mar -15April | Rotating Machine 2 |  | Produced Water Treatment | Coupler 80 EST32 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 1 | 3 | 3 | 0.66667 | 1.25 days | 2025-04-06 | 2025-04-06 16:00
GEI | CH | 01R016110 | 40 | 16P000882 | 5-Mar -15April | Rotating Machine 2 |  | GPC Alhamd Station | Coupler 100 EST25 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 1 | 3 | 3 | 0.66667 | 0.25 days | 2025-04-06 16:00 | 2025-04-07 08:00
GEI | CH | 01R016110 | 41 | 16P000882 | 5-Mar -15April | Rotating Machine 2 |  | Produced Water Treatment | Coupler 25 EST50 TBTB | [6 empty] | 20 | 0 | 20 | 0 | 1 | 3 | 3 | 6.6667 | 0.75 days | 2025-04-07 08:00 | 2025-04-14
2025-01-30 | CH |  |  | 16P000882 | 2025-03-15 | Rotating Machine 2 |  | Produced Water Treatment | Coupler 25 EST50 TBTB | [6 empty] | 10 | 0 | 10 | 0 | 1 | 3 | 3 | 3.3333 | 25 days | 2025-04-14 | 2025-04-17 08:00
2025-02-15 | CH |  |  | 16P000882 | 2025-04-30 | Rotating Machine 2 |  | Produced Water Treatment | Coupler 25 EST50 TBTB | [6 empty] | 5 | 0 | 5 | 0 | 1 | 3 | 3 | 1.6667 | 1 day | 2025-04-17 08:00 | 2025-04-19
GEI | CH |  |  | 16P000882 |  | Rotating Machine 2 |  | Produced Water Treatment | Coupler 25 EST50 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 1 | 3 | 3 | 0.66667 | 29.75 days | 2025-04-19 | 2025-04-19 16:00
GEI | CH | 01B000629 | 216 | 16P000882 |  | Rotating Machine 2 |  | GPC Alhamd Station | Coupler 80 EST32 TBTB | [6 empty] | 9 | 0 | 9 | 0 | 1 | 3 | 3 | 3 | 6.88 days | 2025-04-19 16:00 | 2025-04-22 16:00
[16 empty] | 77 | 0 | 77 | 0 |  |  |  | 28.6667 | 327.96 days | 2025-03-25 | 2025-04-22 16:00
[6 empty] | Rotating Machine 3 (3 Shift) | Rotating Machine 2 (3 Shift) | ELBOWS (150 Ø-250Ø) -
| CA |  |  | 40M001333 |  | Rotating Machine 3 |  | Linde - Wesseling_14 | Elb 150R1.5/90 EST20 TBTB | [6 empty] | 70 | 66 | 4 | 0 | 2 | 3 | 6 | 0.66667 | 16 days | 2025-03-25 | 2025-03-25 16:00
| CA |  |  | 40M001333 |  | Rotating Machine 3 |  | Linde - Wesseling_14 | Elb 200R1.0/90 EST20 TBTB | [6 empty] | 30 | 15 | 15 | 0 | 2 | 3 | 6 | 2.5 | 16 days | 2025-03-25 16:00 | 2025-03-28 04:00
| CA |  |  | 40M001333 |  | Rotating Machine 3 |  | Linde - Wesseling_14 | Elb 250R1.0/90 EST16 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 1 | 3 | 3 | 0.66667 | 16 days | 2025-03-28 04:00 | 2025-03-28 20:00
| CA |  |  | 40P000351 |  | Rotating Machine 3 |  | Chantiers E35 | Elb 150R1.5/90 EMT50/16 CBCB | [6 empty] | 1 | 0 | 1 | 0 | 2 | 3 | 6 | 0.16667 | 16 days | 2025-03-28 20:00 | 2025-03-29
| CA |  |  | 40P000351 |  | Rotating Machine 3 |  | Chantiers E35 | Elb 200R1.5/90 EMT20/10 CBCB | [6 empty] | 1 | 0 | 1 | 0 | 1 | 3 | 3 | 0.33333 | 16 days | 2025-03-29 | 2025-03-29 08:00
GEI | CH | 01B000865 | 32 | 16P000834 |  | Rotating Machine 3 |  | Agiba | Elbow 250R1.5/90° (Molded) EST20 Bar TBTB | [6 empty] | 10 | 0 | 10 | 0 | 2 | 3 | 6 | 1.6667 | 1.6 days | 2025-03-29 08:00 | 2025-03-31
GEI | CH | 01B000906 | 242 | 16P000834 |  | Rotating Machine 3 |  | Agiba | Elbow 250R1.5/45° (Molded) EST25 Bar TBTB | [6 empty] | 6 | 0 | 6 | 0 | 2 | 3 | 6 | 1 | 16 days | 2025-03-31 | 2025-04-01
GEI | CH | 01B001022 | 28 | 16P000641 |  | Rotating Machine 3 |  | Supply &install GRE Connection | Elbow 150R1.5/90° (Molded) EST20 Bar TBTB | [6 empty] | 4 | 0 | 4 | 0 | 3 | 3 | 9 | 0.44444 | 1 day | 2025-04-01 | 2025-04-01 10:40
GEI | CH | 01B001022 | 29 | 16P000882 |  | Rotating Machine 3 |  | GPC Alhamd Station | Elb 200R1.5/45 EST20 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 3 | 3 | 9 | 0.22222 | 8.5 days | 2025-04-01 10:40 | 2025-04-01 16:00
GEI | CH | 01B001022 | 30 | 16P000882 |  | Rotating Machine 3 |  | Produced Water Treatment | Elb 250R1.5/45 EST16 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 2 | 3 | 6 | 0.33333 | 1 day | 2025-04-01 16:00 | 2025-04-02
GEI | CH | 01B001033 | 22 | 16P000882 |  | Rotating Machine 3 |  | GPC Alhamd Station | Elb 200R1.5/90 EST20 TBTB | [6 empty] | 41 | 0 | 41 | 0 | 3 | 3 | 9 | 4.5556 | 0.4 days | 2025-04-02 | 2025-04-06 13:20
GEI | CH | 01B001033 | 24 | 16P000882 |  | Rotating Machine 3 |  | GPC Alhamd Station | Elb 150R1.5/45 EST20 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 3 | 3 | 9 | 0.22222 | 0.4 days | 2025-04-06 13:20 | 2025-04-06 18:40
GEI | CH | 01B001048 | 61 | 16P000882 |  | Rotating Machine 3 |  | GPC Alhamd Station | Elb 250R1.5/90 EST16 TBTB | [6 empty] | 25 | 0 | 25 | 0 | 2 | 3 | 6 | 4.1667 | 0.4 days | 2025-04-06 18:40 | 2025-04-10 22:40
GEI | CH | 01B001052 | 28 | 16P000882 |  | Rotating Machine 3 |  | GPC Alhamd Station | Elb 150R1.5/90 EST20 TBTB | [6 empty] | 32 | 0 | 32 | 0 | 3 | 3 | 9 | 3.5556 | 0.2 days | 2025-04-10 22:40 | 2025-04-14 12:00
[16 empty] | 124 | 0 | 124 | 0 |  |  |  | 20.5 | 327.96 days | 2025-03-25 | 2025-04-14 12:00
[6 empty] | Rotating Machine 4 (3 Shift) | Rotating Machine 2 (3 Shift) | ELBOWS (300 Ø-400Ø) -
| CA |  |  | 40M001333 |  | Rotating Machine 4 |  | Linde - Wesseling_14 | Elb 300R1.0/90 EST16 TBTB | [6 empty] | 30 | 12 | 18 |  | 1 | 3 | 3 | 6 | 2 days | 2025-03-25 | 2025-03-31
| CA |  |  | 40M001333 |  | Rotating Machine 4 |  | Linde - Wesseling_14 | Elb 350R1.0/90 EST16 TBTB | [6 empty] | 10 | 9 | 1 |  | 1 | 3 | 3 | 0.33333 | 2 days | 2025-03-31 | 2025-03-31 08:00
| CA |  |  | 40M001333 |  | Rotating Machine 4 |  | Linde - Wesseling_14 | Elb 400R1.5/90 EST16 TBTB | [6 empty] | 10 | 6 | 4 |  | 1 | 3 | 3 | 1.3333 | 2 days | 2025-03-31 08:00 | 2025-04-01 16:00
| CA |  |  | 40P000304 |  | Rotating Machine 4 |  | 6331 | Elb 400R1.5/15 EST8 CBCB | [6 empty] | 1 | 0 | 1 |  | 1 | 3 | 3 | 0.33333 | 2 days | 2025-04-01 16:00 | 2025-04-02
GEI | CH | 01R012504 | 1 | 16P000849 |  | Rotating Machine 4 |  | Fertial Annaba- UAN ligne | Elbow 350R1.5/45° (Mitered) EST20 Bar PLPL | [6 empty] | 30 | 0 | 30 | 0 | 1 | 3 | 3 | 10 | 2 days | 2025-04-02 | 2025-04-12
GEI | CH | 01B001033 | 23 | 16P000882 |  | Rotating Machine 4 |  | GPC Alhamd Station | Elb 300R1.5/90 EST16 TBTB | [6 empty] | 26 | 0 | 26 | 0 | 2 | 3 | 6 | 4.3333 | 0.9 days | 2025-04-12 | 2025-04-16 08:00
[16 empty] | 355 | 27 | 328 | 0 | 1 | 3 | 3 | 22.3333 |  | 2025-03-25 | 2025-04-16 08:00
[6 empty] | Rotating Machine 5 (3 Shift) | Rotating Machine 2 (3 Shift) | ELBOWS (450Ø-600Ø) -
AUH | [5 empty] | Rotating Machine 5 |  |  |  | D65023190 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 days | #REF! | #REF!
GEI | [5 empty] | Rotating Machine 5 |  |  |  | D65023435 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 day | #REF! | #REF!
[16 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 226.5 days | 2025-03-25 | 2025-03-25
[6 empty] | Rotating Machine 6 (3 Shift) | Rotating Machine 2 (3 Shift) | Tees ( 25 Ø-200 Ø)
| CA |  |  | 40P000358 |  | Rotating Machine 6 |  | B107/2 Vessel | Tee 100x65 EMT50/16 CBCB | [6 empty] | 1 | 0 | 1 |  | 1 | 3 | 3 | 0.33333 | 2 days | 2025-03-25 | 2025-03-25 08:00
| CA |  |  | 40P000358 |  | Rotating Machine 6 |  | B107/2 Vessel | Tee 65x65 EMT50/16 CBCB | [6 empty] | 2 | 0 | 2 |  | 1 | 3 | 3 | 0.66667 | 0.75 days | 2025-03-25 08:00 | 2025-03-26
| CA |  |  | 40P000356 |  | Rotating Machine 6 |  | B107/1Vessel | Tee 100x100 EMT50/16 CBCB | [6 empty] | 10 | 3 | 7 |  | 1 | 3 | 3 | 2.3333 | 0.75 days | 2025-03-26 | 2025-03-28 08:00
| CA |  |  | 40P000356 |  | Rotating Machine 6 |  | B107/1Vessel | Tee 100x65 EMT50/16 CBCB | [6 empty] | 1 | 0 | 1 |  | 1 | 3 | 3 | 0.33333 | 0.75 days | 2025-03-28 08:00 | 2025-03-28 16:00
2025-03-30 | CH |  |  | 16P000744 |  | Rotating Machine 6 |  | Ohaji South Project | Tee 80x50 EST32 Bar TBTB | [6 empty] | 6 | 0 | 6 | 0 | 1 | 3 | 3 | 2 | 0.75 days | 2025-03-28 16:00 | 2025-03-30 16:00
GEI | CH |  |  | 16P000744 |  | Rotating Machine 6 |  | Ohaji South Project | Tee 80x25 EST32 Bar TBTB | [6 empty] | 3 | 0 | 3 | 0 | 1 | 3 | 3 | 1 | 7 days | 2025-03-30 16:00 | 2025-03-31 16:00
2025-06-30 | CH |  |  | 16P000744 |  | Rotating Machine 6 |  | Ohaji South Project | Tee 100x100 EST25 Bar TBTB | [6 empty] | 5 | 0 | 5 | 0 | 1 | 3 | 3 | 1.6667 | 0.25 days | 2025-03-31 16:00 | 2025-04-02 08:00
2025-06-30 | CH |  |  | 16P000744 |  | Rotating Machine 6 |  | Ohaji South Project | Tee 100x80 EST25 Bar TBTB | [6 empty] | 1 | 0 | 1 | 0 | 1 | 3 | 3 | 0.33333 | 0.25 days | 2025-04-02 08:00 | 2025-04-02 16:00
GEI | CH |  |  | 16P000744 |  | Rotating Machine 6 |  | Ohaji South Project | Tee 80x80 EST32 Bar TBTB | [6 empty] | 5 | 0 | 5 | 0 | 1 | 3 | 3 | 1.6667 | 2.5 days | 2025-04-02 16:00 | 2025-04-04 08:00
GEI | CH |  |  | 16P000641 |  | Rotating Machine 6 |  | Supply &install GRE Connection | Tee 150x100 EST20 Bar TBTB | [6 empty] | 1 | 0 | 1 | 0 | 1 | 3 | 3 | 0.33333 | 2.5 days | 2025-04-04 08:00 | 2025-04-04 16:00
GEI | CH |  |  | 16P000882 |  | Rotating Machine 6 |  | GPC Alhamd Station | Tee 80x80 EST32 TBTB | Not to be released | [5 empty] | 1 | 0 | 1 | 0 | 1 | 3 | 3 | 0.33333 | 0.5 days | 2025-04-04 16:00 | 2025-04-05
GEI | CH |  |  | 16P000882 |  | Rotating Machine 6 |  | GPC Alhamd Station | Tee 150x80 EST20 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 1 | 3 | 3 | 0.66667 | 1 day | 2025-04-05 | 2025-04-05 16:00
GEI | CH |  |  | 16P000882 |  | Rotating Machine 6 |  | GPC Alhamd Station | Tee 200x200 EST20 TBTB | [6 empty] | 3 | 0 | 3 | 0 | 1 | 3 | 3 | 1 | 2.25 days | 2025-04-05 16:00 | 2025-04-06 16:00
GEI | CH |  |  | 16P000882 |  | Rotating Machine 6 |  | Produced Water Treatment | Tee 80x50 EST32 TBTB | [6 empty] | 15 | 0 | 15 | 0 | 1 | 3 | 3 | 5 | 3.75 days | 2025-04-06 16:00 | 2025-04-11 16:00
GEI | CH |  |  | 16P000882 |  | Rotating Machine 6 |  | Produced Water Treatment | Tee 200x80 EST20 TBTB | [6 empty] | 9 | 0 | 9 | 0 | 1 | 3 | 3 | 3 | 2.25 days | 2025-04-11 16:00 | 2025-04-14 16:00
GEI | CH |  |  | 16P000882 |  | Rotating Machine 6 |  | GPC Alhamd Station | Tee 150x150 EST20 TBTB | [6 empty] | 8 | 0 | 8 | 0 | 1 | 3 | 3 | 2.6667 | 2.5 days | 2025-04-14 16:00 | 2025-04-17 08:00
GEI | CH |  |  | 16P000882 |  | Rotating Machine 6 |  | GPC Alhamd Station | Tee 200x100 EST20 TBTB | [6 empty] | 7 | 0 | 7 | 0 | 1 | 3 | 3 | 2.3333 | 2 days | 2025-04-17 08:00 | 2025-04-19 16:00
[16 empty] | 80 | 3 | 77 | 0 |  |  |  | 25.6667 |  | 2025-03-25 08:00 | 2025-04-20
[6 empty] | Rotating Machine 7 (3 Shift) | Rotating Machine 2 (3 Shift) | Tees ( 250 Ø- 600 Ø)
| CA |  |  | 40P000351 |  | Rotating Machine 7 |  | Chantiers E35 | Tee 250x150 EMT20/10 CBCB | [6 empty] | 1 | 0 | 1 |  | 1 | 3 | 3 | 0.33333 | 0.25 days | 2025-03-25 | 2025-03-25 08:00
AUH | CH |  |  | 16P000882 |  | Rotating Machine 7 |  | Produced Water Treatment | Tee 250x80 EST16 TBTB | [6 empty] | 8 | 0 | 8 | 0 | 1 | 3 | 3 | 2.6667 | 0.25 days | 2025-03-25 08:00 | 2025-03-28
GEI | CH |  |  | 16P000882 |  | Rotating Machine 7 |  | GPC Alhamd Station | Tee 300x200 EST16 TBTB | [6 empty] | 10 | 0 | 10 | 0 | 1 | 3 | 3 | 3.3333 | 1.5 days | 2025-03-28 | 2025-03-31 08:00
GEI | CH |  |  | 16P000882 |  | Rotating Machine 7 |  | Produced Water Treatment | Tee 250x200 EST16 TBTB | [6 empty] | 2 | 0 | 2 | 0 | 1 | 3 | 3 | 0.66667 | 0.25 days | 2025-03-31 08:00 | 2025-04-01
GEI | CH |  |  | 16P000882 |  | Rotating Machine 7 |  | GPC Alhamd Station | Tee 300x150 EST16 TBTB | [6 empty] | 3 | 0 | 3 | 0 | 1 | 3 | 3 | 1 | 0.25 days | 2025-04-01 | 2025-04-02
GEI | CH |  |  | 16P000882 |  | Rotating Machine 7 |  | Produced Water Treatment | Tee 300x250 EST16 TBTB | [6 empty] | 1 | 0 | 1 | 0 | 1 | 3 | 3 | 0.33333 | 1.75 days | 2025-04-02 | 2025-04-02 08:00
GEI | CH |  |  | 16P000882 |  | Rotating Machine 7 |  | GPC Alhamd Station | Tee 250x250 EST16 TBTB | [6 empty] | 11 | 0 | 11 | 0 | 1 | 3 | 3 | 3.6667 | 3.5 days | 2025-04-02 08:00 | 2025-04-06
GEI | CH |  |  | 16P000882 |  | Rotating Machine 7 |  | GPC Alhamd Station | Tee 300x300 EST16 TBTB | [6 empty] | 4 | 0 | 4 | 0 | 1 | 3 | 3 | 1.3333 | 22.25 days | 2025-04-06 | 2025-04-07 08:00
[11 empty] | 96.18 | 0 |  |  |  | 40 | 0 | 40 | 0 |  |  |  | 13.3333 | 168.92 days | 2025-03-25 | 2025-04-07 08:00
[6 empty] | Rotating Machine 8 (3 Shift) | Rotating Machine 2 (3 Shift) | Flanges (25Ø-250Ø) - |  |  | 78.97 | 0
| CA |  |  | 40M001333 |  | Rotating Machine 8 |  | Linde - Wesseling_14 | FL 50 EST40 FLTB PN40 | [6 empty] | 60 | 55 | 5 |  | 3 | 3 | 9 | 0.55556 | 0.17 days | 2025-03-25 | 2025-03-25 13:20
| CA |  |  | 40M001333 |  | Rotating Machine 8 |  | Linde - Wesseling_14 | FL 150 EST20 FLTB PN16 | [6 empty] | 110 | 57 | 53 |  | 3 | 3 | 9 | 5.8889 |  | 2025-03-25 13:20 | 2025-03-31 10:40
| CA |  |  | 40M001333 |  | Rotating Machine 8 |  | Linde - Wesseling_14 | FL 200 EST20 FLTB PN16 | [6 empty] | 40 | 36 | 4 |  | 3 | 3 | 9 | 0.44444 |  | 2025-03-31 10:40 | 2025-03-31 21:20
| CA |  |  | 40M001333 |  | Rotating Machine 8 |  | Linde - Wesseling_14 | FL Blnd 80 EST32 FLFL PN40 | [6 empty] | 50 | 0 | 50 |  | 10 | 3 | 30 | 1.6667 |  | 2025-03-31 21:20 | 2025-04-02 13:20
| CA |  |  | 40M001333 |  | Rotating Machine 8 |  | Linde - Wesseling_14 | FL 50 EST40 FLTB PN40 | [6 empty] | 70 | 0 | 70 |  | 3 | 3 | 9 | 7.7778 |  | 2025-04-02 13:20 | 2025-04-10 08:00
| CA |  |  | 40M001333 |  | Rotating Machine 8 |  | Linde - Wesseling_14 | FL 80 EST32 FLTB PN40 | [6 empty] | 120 | 10 | 110 |  | 3 | 3 | 9 | 12.2222 |  | 2025-04-10 08:00 | 2025-04-22 13:20
| CA |  |  | 40M001333 |  | Rotating Machine 8 |  | Linde - Wesseling_14 | FL 150 EST20 FLTB PN16 | [6 empty] | 140 | 0 | 140 |  | 3 | 3 | 9 | 15.5556 |  | 2025-04-22 13:20 | 2025-05-08 02:40
| CA |  |  | 40M001333 |  | Rotating Machine 8 |  | Linde - Wesseling_14 | FL 200 EST20 FLTB PN16 | [6 empty] | 20 | 0 | 20 |  | 3 | 3 | 9 | 2.2222 |  | 2025-05-08 02:40 | 2025-05-10 08:00
| CA |  |  | 40M001333 |  | Rotating Machine 8 |  | Linde - Wesseling_14 | FL 250 EST16 FLTB PN16 | [6 empty] | 10 | 8 | 2 |  | 3 | 3 | 9 | 0.22222 |  | 2025-05-10 08:00 | 2025-05-10 13:20
| CA |  |  | 40P000358 |  | Rotating Machine 8 |  | B107/2 Vessel | FL 100 EMT50/16 FLCB PN16 | [6 empty] | 48 | 9 | 39 |  | 3 | 3 | 9 | 4.3333 |  | 2025-05-10 13:20 | 2025-05-14 21:20
| CA |  |  | 40P000358 |  | Rotating Machine 8 |  | B107/2 Vessel | FL 65 EMT516 FLCB spec. | [6 empty] | 7 | 5 | 2 |  | 3 | 3 | 9 | 0.22222 |  | 2025-05-14 21:20 | 2025-05-15 02:40
| CA |  |  | 40P000356 |  | Rotating Machine 8 |  | B107/1Vessel | FL 100 EMT50/16 FLCB PN16 | [6 empty] | 48 | 0 | 48 |  | 3 | 3 | 9 | 5.3333 |  | 2025-05-15 02:40 | 2025-05-20 10:40
| CA |  |  | 40P000356 |  | Rotating Machine 8 |  | B107/1Vessel | FL 65 EMT516 FLCB spec. | [6 empty] | 7 | 0 | 7 |  | 3 | 3 | 9 | 0.77778 |  | 2025-05-20 10:40 | 2025-05-21 05:20
| CA |  |  | 40P000351 |  | Rotating Machine 8 |  | Chantiers E35 | FL Stub 200 EMT20/10 FLCB PN10 | [6 empty] | 1 | 0 | 1 |  | 3 | 3 | 9 | 0.11111 |  | 2025-05-21 05:20 | 2025-05-21 08:00
| CA |  |  | 40P000351 |  | Rotating Machine 8 |  | Chantiers E35 | FL Stub 250 EMT20/10 FLCB PN10 | [6 empty] | 1 | 0 | 1 |  | 3 | 3 | 9 | 0.11111 |  | 2025-05-21 08:00 | 2025-05-21 10:40
| CH |  |  | 16P000834 |  | Rotating Machine 8 |  | Agiba | Flange 250 EST20 Bar FLTB ASA 150 | [6 empty] | 10 | 0 | 10 | 0 | 3 | 3 | 9 | 1.1111 | 0.17 days | 2025-05-21 10:40 | 2025-05-22 13:20
| CH |  |  | 16P000820 |  | Rotating Machine 8 |  | Desalination Plant El Alamein | FL 150 EST20 FLPL PN10 | [6 empty] | 5 | 0 | 5 | 0 | 3 | 3 | 9 | 0.55556 | 0.17 days | 2025-05-22 13:20 | 2025-05-23 02:40
| CH |  |  | 16P000820 |  | Rotating Machine 8 |  | Desalination Plant El Alamein | FL 250 EST12.5 FLPL PN10 | [6 empty] | 6 | 0 | 6 | 0 | 3 | 3 | 9 | 0.66667 | 0.17 days | 2025-05-23 02:40 | 2025-05-23 18:40
| CH |  |  | 16P000744 |  | Rotating Machine 8 |  | Ohaji South Project | Flange 50 EST40 Bar FLTB ASA 150 | [6 empty] | 19 | 0 | 19 | 0 | 3 | 3 | 9 | 2.1111 | 0.17 days | 2025-05-23 18:40 | 2025-05-25 21:20
| CH |  |  | 16P000744 |  | Rotating Machine 8 |  | Ohaji South Project | Flange 100 EST25 Bar FLTB ASA 150 | [6 empty] | 14 | 0 | 14 | 0 | 3 | 3 | 9 | 1.5556 | 0.17 days | 2025-05-25 21:20 | 2025-05-27 10:40
| CH |  |  | 16P000744 |  | Rotating Machine 8 |  | Ohaji South Project | Flange Blind 50 EST32 Bar FLFL ASA 150 | [6 empty] | 1 | 0 | 1 | 0 | 3 | 3 | 9 | 0.11111 | 0.17 days | 2025-05-27 10:40 | 2025-05-27 13:20
| CH |  |  | 16P000744 |  | Rotating Machine 8 |  | Ohaji South Project | Flange Blind 25 EST32 Bar FLFL ASA 150 | [6 empty] | 8 | 0 | 8 | 0 | 3 | 3 | 9 | 0.88889 | 0.17 days | 2025-05-27 13:20 | 2025-05-28 10:40
| CH |  |  | 16P000744 |  | Rotating Machine 8 |  | Ohaji South Project | Flange 80 EST32 Bar FLTB ASA 150 | [6 empty] | 29 | 0 | 29 | 0 | 3 | 3 | 9 | 3.2222 | 0.17 days | 2025-05-28 10:40 | 2025-05-31 16:00
| CH |  |  | 16P000744 |  | Rotating Machine 8 |  | Ohaji South Project | Flange 25 EST50 Bar FLTB ASA 150 | [6 empty] | 4 | 0 | 4 | 0 | 3 | 3 | 9 | 0.44444 | 0.17 days | 2025-05-31 16:00 | 2025-06-01 02:40
| CH |  |  | 16P000641 |  | Rotating Machine 8 |  | Supply &install GRE Connection | Flange 150 EST20 Bar FLTB ASA 150 | [6 empty] | 2 | 0 | 2 | 0 | 3 | 3 | 9 | 0.22222 | 0.17 days | 2025-06-01 02:40 | 2025-06-01 08:00
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL Blnd 80 EST32 FLFL AS150 | [6 empty] | 2 | 0 | 2 | 0 | 3 | 3 | 9 | 0.22222 | 0.17 days | 2025-06-01 08:00 | 2025-06-01 13:20
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | Produced Water Treatment | FL Blnd 200 EST16 FLFL AS150 | [6 empty] | 1 | 0 | 1 | 0 | 3 | 3 | 9 | 0.11111 | 0.17 days | 2025-06-01 13:20 | 2025-06-01 16:00
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | Produced Water Treatment | FL Blnd 250 EST16 FLFL AS150 | [6 empty] | 4 | 0 | 4 | 0 | 3 | 3 | 9 | 0.44444 | 0.17 days | 2025-06-01 16:00 | 2025-06-02 02:40
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL Blnd 150 EST20 FLFL AS150 | [6 empty] | 1 | 0 | 1 | 0 | 3 | 3 | 9 | 0.11111 | 0.17 days | 2025-06-02 02:40 | 2025-06-02 05:20
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL 200 EST16 FLTB AS150 | [6 empty] | 109 | 0 | 109 | 0 | 3 | 3 | 9 | 12.1111 | 0.17 days | 2025-06-02 05:20 | 2025-06-14 08:00
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL 50 EST40 FLTB AS150 | [6 empty] | 66 | 0 | 66 | 0 | 3 | 3 | 9 | 7.3333 | 0.17 days | 2025-06-14 08:00 | 2025-06-21 16:00
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL 150 EST20 FLTB AS150 | [6 empty] | 57 | 0 | 57 | 0 | 3 | 3 | 9 | 6.3333 | 0.17 days | 2025-06-21 16:00 | 2025-06-28
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL 250 EST16 FLTB AS150 | [6 empty] | 96 | 0 | 96 | 0 | 3 | 3 | 9 | 10.6667 | 0.17 days | 2025-06-28 | 2025-07-08 16:00
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL 80 EST32 FLTB AS150 | [6 empty] | 70 | 0 | 70 | 0 | 3 | 3 | 9 | 7.7778 | 0.17 days | 2025-07-08 16:00 | 2025-07-16 10:40
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL 100 EST25 FLTB AS150 | [6 empty] | 15 | 0 | 15 | 0 | 3 | 3 | 9 | 1.6667 | 0.17 days | 2025-07-16 10:40 | 2025-07-18 02:40
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL 25 EST50 FLTB AS150 | [6 empty] | 45 | 0 | 45 | 0 | 3 | 3 | 9 | 5 | 0.17 days | 2025-07-18 02:40 | 2025-07-23 02:40
| CH |  |  | 16P000882 |  | Rotating Machine 8 |  | GPC Alhamd Station | FL Blnd 25 EST32 FLFL AS150 | [6 empty] | 21 | 0 | 21 | 0 | 3 | 3 | 9 | 2.3333 | 0.17 days | 2025-07-23 02:40 | 2025-07-25 10:40
[16 empty] | 1317 | 180 | 1137 | 0 |  |  |  | 122.4444 |  | 2025-03-25 | 2025-07-25 10:40
[6 empty] | Rotating Machine 9(3 Shift) | Rotating Machine 2 (3 Shift) | Flanges (300 Ø-600Ø) - |  |  |  | 0
| CA |  |  | 40M001333 |  | Rotating Machine 9 |  | Linde - Wesseling_14 | FL 300 EST16 FLTB PN16 | [6 empty] | 10 | 2 | 8 |  | 1 | 3 | 3 | 2.6667 | 4.36 days | 2025-03-25 | 2025-03-27 16:00
| CA |  |  | 40M001333 |  | Rotating Machine 9 |  | Linde - Wesseling_14 | FL 400 EST16 FLTB PN16 | [6 empty] | 10 | 7 | 3 |  | 1 | 3 | 3 | 1 | 4.36 days | 2025-03-27 16:00 | 2025-03-28 16:00
| CA |  |  | 40P000304 |  | Rotating Machine 9 |  | 6331 | FL 300 EST12.5 FLCB PN6 | [6 empty] | 1 | 0 | 1 |  | 1 | 3 | 3 | 0.33333 | 4.36 days | 2025-03-28 16:00 | 2025-03-29
AUH | CH | 01E012173 | 3 | 16P000849 | 2025-01-30 | Rotating Machine 9 |  | Fertial Annaba- UAN ligne | Flange STD 350 EST20 Bar FLCB PN 10 | D65022977 | [5 empty] | 20 | 0 | 20 | 0 | 1 | 3 | 3 | 6.6667 | 4.36 days | 2025-03-29 | 2025-04-04 16:00
AUH | CH | 01E012173 | 1 | 16P000820 | 2025-02-05 | Rotating Machine 9 |  | Desalination Plant El Alamein | FL 300 EST12.5 FLPL PN10 | D65022986 | [5 empty] | 3 | 0 | 3 | 0 | 1 | 3 | 3 | 1 | 2.86 days | 2025-04-04 16:00 | 2025-04-05 16:00
AUH | CH | 01E012173 | 4 | 16P000882 | 2025-02-07 | Rotating Machine 9 |  | Produced Water Treatment | FL Blnd 300 EST16 FLFL AS150 | D65022988 | [5 empty] | 6 | 0 | 6 | 0 | 1 | 3 | 3 | 2 | 5.71 days | 2025-04-05 16:00 | 2025-04-07 16:00
AUH | CH | 01E012173 | 4 | 16P000882 | 2025-02-20 | Rotating Machine 9 |  | GPC Alhamd Station | FL 300 EST16 FLTB AS150 | D65022989 | [5 empty] | 43 | 0 | 43 | 0 | 1 | 3 | 3 | 14.3333 | 7.14 days | 2025-04-07 16:00 | 2025-04-22
[16 empty] | 93 | 9 | 84 | 0 | 1 | 3 | 3 | 28 |  | 2025-03-25 | 2025-04-22
Formulas:
Start = [Finish, row above]
Finish = [Start]+[Duratin Numeric]