## Sheet3
Develop Project Charter
Identify Stakeholders
Develop Project Management Plan
Collect Requirements
Define Scope
Create WBS
Plan Risk Management |  |  |  | Define Activities
Identify Risks |  |  |  | Estimate Activity Resources |  |  | Develop H.R Plan | Estimate Costs
Perform Qualitative Risk Analysis |  |  |  | Estimate Activity Duration |  |  | Plan Quality | Determine Budget
Perform Quantitative Risk Analysis |  |  |  | Sequence Activities |  |  | Plan Comm.
Plan Risk Response |  |  |  | Develop Schedule |  |  | Plan Procurements
| Direct and Manage Project Execution | [5 empty] | Perform Integrated Change Control | Monitor and Control Project Work
Acquire Project Team | Conduct Procurements |  | Perform Quality Assurance |  | Verify Scope |  |  | Perform Quality Control
Develop Project Team |  |  | Distribute Information |  | Control Scope |  |  | Report Performance
Manage Project Team |  |  | Manage Stakeholders Expectations |  | Control Schedule |  |  | Monitor and Control Risks
[5 empty] | Control Costs |  |  | Administer Procurements
|  | Close Procurements |  |  |  | Close Project or phase

## Sheet1
S.N | Process | INPUTS | Tools and Techniques | OUTPUTS
1 | Develop Project Charter | Project statement of work | Expert Judgment | Project Charter
Business case
Contract
Enterprise Environmental Factors
Organization Process assets
2 | Identify Stakeholders | Project Charter | Stakeholder Analysis | Stakeholder Register
Procurement Documents
|  | Enterprise Environmental Factors | Expert Judgment | Stakeholder Management Strategy
Organization Process assets
3 | Develop Project Management Plan | Project Charter | Expert Judgment | Project Management Plan
Outputs From Planning Process
Enterprise Environmental Factors
Organization Process assets
4 | Collect Requirements | Project Charter | Interviews | Requirement Documentation
|  | Stakeholder Register | Focus Groups | Requirement Management Plan
|  |  | Facilitated Workshops | Requirements Traceability Matrix
Group Creativity Techniques
Group Decision Making Techniques
Questionnaires and Surveys
Observations
Prototypes
5 | Define Scope | Project Charter | Expert Judgment | Project Scope Statement
|  | Requirement Documentation | Product analysis | Project Document Updates
|  | Organization Process assets | Alternatives Identification
Facilitated Workshops
6 | Create WBS | Project Scope Statement | Decomposition | WBS
|  | Requirement Documentation |  | WBS Dictionary
|  | Organization Process assets |  | Scope Baseline
Project Document Updates
7 | Define Activities | Scope Baseline | Decomposition | Activity List
|  | Enterprise Environmental Factors | Rolling Wave Planning | Activity Attributes
|  | Organization Process assets | Templates | Milestone List
Expert Judgment
8 | Estimate Activity Resources | Activity List | Expert Judgment | Activity Resource Requirements
|  | Activity Attributes | Alternatives Analysis | Resource Breakdown Structure
|  | Resource Calendars | Published Estimating Data | Project Document Updates
Bottom-Up Estimating
Project Management Software
9 | Estimate Activity Duration | Activity List | Expert Judgment | Activity Duration Estimate
|  | Activity Attributes | Analogous Estimating | Project Document Updates
|  | Activity Resource Requirements | Parametric Estimating
|  | Resource Calendars | Three-Point Estimates
|  | Project Scope Statement | Reserve Analysis
Enterprise Environmental Factors
Organization Process assets
10 | Sequence Activities | Activity List | Precedence Diagramming Method (PDM) | Project Schedule Network Diagram
|  | Activity Attributes | Dependency Determination | Project Document Updates
|  | Milestone List | Applying Leads and Lags
|  | Project Scope Statement | Schedule Network Templates
Organization Process assets
11 | Develop Schedule | Activity List | Schedule Network Analysis | Project Schedule
|  | Activity Attributes | Critical Path Method | Schedule Baseline
|  | Project Schedule Network Diagram | Critical Chain Method | Schedule Data
|  | Activity Resource Requirements | Resource Leveling | Project Document Updates
|  | Resource Calendars | What-if Scenario Analysis
|  | Activity Duration Estimate | Applying Leads and Lags
|  | Project Scope Statement | Schedule Compression
|  | Enterprise Environmental Factors | Scheduling Tool
Organization Process assets
12 | Develop Human Resource Plan | Activity Resource Requirements | Organization Chart and Position Description | Human Resource Plan
|  | Enterprise Environmental Factors | Networking
|  | Organization Process assets | Organization Theory
13 | Plan Communications | Stakeholder Register | Communication Requirements Analysis | Communication Management Plan
|  | Stakeholder Management Strategy | Communication Technology | Project Document Updates
|  | Enterprise Environmental Factors | Communication Models
|  | Organization Process assets | Communication Methods
14 | Estimate Costs | Scope Baseline | Expert Judgment | Activity Cost Estimate
|  | Project Schedule | Analogous Estimating | Basis Of Estimate
|  | Human Resource Plan | Parametric Estimating | Project Document Updates
|  | Risk Register | Bottom-Up Estimating
|  | Enterprise Environmental Factors | Three-Point Estimates
|  | Organization Process assets | Reserve Analysis
Cost of Quality
Project Management Estimating Software
Vendor Bid Analysis
15 | Determine Budget | Activity Cost Estimate | Cost Aggregation | Cost Performance Baseline
|  | Basis Of Estimate | Reserve Analysis | Project Funding Requirements
|  | Scope Baseline | Expert Judgment | Project Document Updates
|  | Project Schedule | Historical Relationships
|  | Resource Calendars | Funding Limit Reconciliation
Contract
Organization Process assets
16 | Plan Quality | Scope Baseline | Cost-Benefit Analysis | Quality Management Plan
|  | Stakeholder Register | Cost of Quality | Quality Metrics
|  | Cost Performance Baseline | Control Charts | Quality Checklists
|  | Schedule Baseline | Benchmarking | Process Improvement Plan
|  | Risk Register | Design of Experiments | Project Document Updates
|  | Enterprise Environmental Factors | Statical Sampling
|  | Organization Process assets | Flowcharting
Proprietary quality Management Methodology
Additional Quality Planning Tools
17 | Plan Risk Management | Project Scope Statement | Planning Meetings and Analysis | Risk Management Plan
Cost Management Plan
Schedule Management Plan
Communication Management Plan
Enterprise Environmental Factors
Organization Process assets
18 | Identify Risks | Risk Management Plan | Documentation Reviews | Risk Register
|  | Activity Cost Estimate | Information Gathering Techniques
|  | Activity Duration Estimate | Checklist Analysis
|  | Scope Baseline | Assumption Analysis
|  | Stakeholder Register | Diagramming Techniques
|  | Cost Management Plan | SWOT Analysis
|  | Schedule Management Plan | Expert Judgment
Quality Management Plan
Project Documents
Enterprise Environmental Factors
Organization Process assets
19 | Perform Qualitative Risk Analysis | Risk Register | Risk Probability and Impact Assessment | Risk Register Update
|  | Risk Management Plan | Probability and Impact Matrix
|  | Project Scope Statement | Risk Data Quality Assessment
|  | Organization Process assets | Risk Categorization
Risk Urgency Assessment
Expert Judgment
20 | Perform Quantitative Risk Analysis | Risk Register | Data Gathering and Representation Techniques | Risk Register Update
|  | Risk Management Plan | Quantitative Risk Analysis and Modeling Techniques
|  | Cost Management Plan | Expert Judgment
Schedule Management Plan
Organization Process assets
21 | Plan Risk Response | Risk Register | Strategies For Negative Risk or Threats | Risk Register Update
|  | Risk Management Plan | Strategies For Positive Risk or Opportunities | Risk-Related Contract Decision
|  |  | Contingent Response Strategies | Project Management Plan Update
|  |  | Expert Judgment | Project Document Updates
22 | Plan Procurements | Scope Baseline | Make-or-Buy Analysis | Procurement Management Plan
|  | Requirement Documentation | Expert Judgment | Procurement Statement Of Work
|  | Teaming Agreements | Contract Types | Make-Or-Buy Decision
|  | Risk Register |  | Procurement Documents
|  | Risk-Related Contract Decision |  | Source Selection Criteria
|  | Activity Resource Requirements |  | Change Request
Project Schedule
Activity Cost Estimate
Cost Performance Baseline
Enterprise Environmental Factors
Organization Process assets
23 | Direct and Manage Project Execution | Project Management Plan | Expert Judgment | Deliverables
|  | Approved Change Request | Project Management Information System | Work Performance Information
|  | Enterprise Environmental Factors |  | Change Request
|  | Organization Process assets |  | Project Management Plan Update
Project Document Updates
24 | Perform Quality Assurance | Project Management Plan | Plan Quality and Perform Quality Control Tools and Techniques | Organization Process assets Update
|  | Quality Metrics |  | Change Request
|  | Work Performance Information | Quality Audits | Project Management Plan Update
|  | Quality Control Measurements | Process Analysis | Project Document Updates
25 | Acquire Project Team | Project Management Plan | Pre-assignment | Project Staff assignment
|  | Enterprise Environmental Factors | Negotiation | Resource Calendars
|  | Organization Process assets | Acquisition | Project Management Plan Update
Virtual Teams
26 | Develop Project Team | Project Staff assignment | Interpersonal Skills | Team Performance Assessment
|  | Project Management Plan | Training | Enterprise Environmental Factors Updates
|  | Resource Calendars | Team-Building Activities
Ground Rules
Co-Location
Recognition and Reward
27 | Manage Project Team | Project Staff assignment | Observation and Conversation | Enterprise Environmental Factors Updates
|  | Project Management Plan | Project Performance Appraisals | Organization Process assets Update
|  | Team Performance Assessment | Conflict Management | Change Request
|  | Performance Reports | Issue Log | Project Management Plan Update
|  | Organization Process assets | Interpersonal Skills
28 | Distribute Information | Project Management Plan | Communication Methods | Organization Process assets Update
|  | Performance Reports | Information Distribution Tools
Organization Process assets
29 | Manage Stakeholders Expectation | Stakeholder Register | Communication Methods | Organization Process assets Update
|  | Stakeholders Management strategy | Interpersonal Skills | Change Request
|  | Project Management Plan | Management Skills | Project Management Plan Update
|  | Issue Log |  | Project Document Updates
Change Log
Organization Process assets
30 | Conduct Procurement | Project Management Plan | Bidder Conferences | Selected Sellers
|  | Procurement Documents | Proposal Evaluation Techniques | Procurement Contract Award
|  | Source Selection Criteria | Independent Estimates | Resource Calendars
|  | Qualified Seller List | Expert Judgment | Change Request
|  | Sellers Proposals | Advertising | Project Management Plan Update
|  | Project Documents | Internet search | Project Document Updates
|  | Make-Or-Buy Decision | Procurement Negotiation
Teaming Agreements
Organization Process assets
31 | Monitor and Control Project Work | Project Management Plan | Expert Judgment | Change Request
|  | Performance Reports | Project Management Information System | Project Management Plan Update
|  | Enterprise Environmental Factors |  | Project Document Updates
Organization Process assets
32 | Perform Integrated Change Control | Project Management Plan | Expert Judgment | Change Request Status Update
|  | Work Performance Information | Change Control Meeting | Project Management Plan Update
|  | Change Request |  | Project Document Updates
Enterprise Environmental Factors
Organization Process assets
33 | Verify Scope | Project Management Plan | Inspection | Accepted Deliverables
|  | Requirement Documentation |  | Change Request
|  | Requirement Traceability Matrix |  | Project Document Updates
Validated Deliverables
34 | Control Scope | Project Management Plan | Variance Analysis | Work Performance Measurement
|  | Work Performance Information |  | Organization Process assets Update
|  | Requirement Documentation |  | Change Request
|  | Requirement Traceability Matrix |  | Project Management Plan Update
|  | Organization Process assets |  | Project Document Updates
35 | Control Schedule | Project Management Plan | Performance Review | Work Performance Measurement
|  | Project Schedule | Variance Analysis | Organization Process assets Update
|  | Work Performance Information | Project Management Software | Change Request
|  | Organization Process assets | Resource Leveling | Project Management Plan Update
|  |  | What-if Scenario Analysis | Project Document Updates
Adjusting Leads and Lags
Schedule Compression
Scheduling Tool
36 | Control Cost | Project Management Plan | Earned Value Management | Work Performance Measurement
|  | Project Funding Requirements | Forecasting | Budget Forecast
|  | Work Performance Information | To-Complete Performance Index | Organization Process assets Update
|  | Organization Process assets | Performance Review | Change Request
|  |  | Variance Analysis | Project Management Plan Update
|  |  | Project Management Software | Project Document Updates
37 | Perform Quality Control | Project Management Plan | Cause and Effect Diagram | Quality Control Measurements
|  | Quality Metrics | Control Charts | Validated Changes
|  | Quality Checklists | Flowcharting | Validated Deliverables
|  | Work Performance Measurement | Histograms | Organization Process assets Update
|  | Approved Change Request | Pareto Charts | Change Request
|  | Deliverables | Run chart | Project Management Plan Update
|  | Organization Process assets | Scatter Diagram | Project Document Updates
Statical Sampling
Inspection
Approved Change Request Review
38 | Report Performance | Project Management Plan | Variance Analysis | Performance Reports
|  | Work Performance Information | Forecasting Methods | Organization Process assets Update
|  | Work Performance Measurement | Communication Methods | Change Request
|  | Budget Forecast | Reporting System
Organization Process assets
39 | Monitor and Control Risks | Risk Register | Risk Reassessment | Risk Register Update
|  | Project Management Plan | Risk Audits | Organization Process assets Update
|  | Work Performance Information | Variance and Trend Analysis | Change Request
|  | Performance Reports | Technical Performance Measurement | Project Management Plan Update
|  |  | Reserve Analysis | Project Document Updates
Status Meetings
40 | Administer Procurements | Procurement Documents | Contract Change Control System | Procurement Documentation
|  | Project Management Plan | Procurement Performance Reviews | Organization Process assets Update
|  | Contract | Inspections and Audits | Change Request
|  | Performance Reports | Performance Reporting | Project Management Plan Update
|  | Approved Change Request | Payment Systems
|  | Work Performance Information | Claims administration
Record Management System
41 | Close Project Or Phase | Project Management Plan | Expert Judgment | Final Product, Service or Result Transition
|  | Accepted Deliverables |  | Organization Process assets Update
Organization Process assets
42 | Close Procurement | Project Management Plan | Procurement Audits | Closed Procurements
|  | Procurement Documents | Negotiation Settlement | Organization Process assets Update
Record Management System