## Summary
|  | PMBOK 4th Edition - Processes | 1 | 28 | 2 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 18 | 19 | 21 | 24 | 29 | 33 | 34 | 35 | 36 | 37 | 39 | 3 | 22 | 25 | 26 | 27 | 30 | 31 | 40 | 4 | 5 | 10 | 11 | 17 | 20 | 23 | 32 | 38 | 41 | 6 | 42
|  | Based on PMBOK® 4th Edition | 4.1 | 10.1 | 4.2 | 5.1 | 5.2 | 5.3 | 6.1 | 6.2 | 6.3 | 6.4 | 6.5 | 7.1 | 7.2 | 8.1 | 9.1 | 10.2 | 11.1 | 11.2 | 11.3 | 11.4 | 11.5 | 12.1 | 4.3 | 8.2 | 9.2 | 9.3 | 9.4 | 10.3 | 10.4 | 12.2 | 4.4 | 4.5 | 5.4 | 5.5 | 6.6 | 7.3 | 8.3 | 10.5 | 11.6 | 12.3 | 4.6 | 12.4
|  | PMBOK is a registered Mark of the Project Mangagement Institure, Inc. | Integ. | Comm. | Integ. | Scope | Scope | Scope | Time | Time | Time | Time | Time | Cost | Cost | Quality | HR | Comm. | Risk | Risk | Risk | Risk | Risk | Proc. | Integ. | Quality | HR | HR | HR | Comm. | Comm. | Proc. | Integ. | Integ. | Scope | Scope | Time | Cost | Quality | Comm. | Risk | Proc. | Integ. | Proc.
|  | Process Group | Initiating | Initiating | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Planning | Executing | Executing | Executing | Executing | Executing | Executing | Executing | Executing | M&C | M&C | M&C | M&C | M&C | M&C | M&C | M&C | M&C | M&C | Closing | Closing
ALL | Type | Process I , T&T , O | •4.1 Dev. Project Charter | •10.1 Idetify Stakeholders | •4.2 Develop Project Management Plan | •5.1 Collect Requirements | •5.2 Define Scope | •5.3 Create WBS | •6.1 Define Activities | •6.2 Sequence Activities | •6.3 Estimate Activity Resources | •6.4 Estimate Activity Durations | •6.5 Develop Schedule | •7.1 Estimate Costs | •7.2 Determine Budget | •8.1 Plan Quality | •9.1 Develop Human Resource Plan | •10.2 Plan Communications | •11.1 Plan Risk Management | •11.2 Identify Risks | •11.3 Perform Qualitative Risk Analysis | •11.4 Perform Quantitative Risk Analysis | •11.5 Plan Risk Responses | •12.1 Plan Procurements | •4.3 Direct and Manage Project Execution | •8.2 Perform Quality Assurance | •9.2 Acquire Project Team | •9.3 Develop Project Team | •9.4 Manage Project Team | •10.3 Distribute Information | •10.4 Manage Stakeholder Expectations | •12.2 Conduct Procurements | •4.4 Monitor and Control Project Work | •4.5 Peform Integrated Change Control | •5.4 Verify Scope | •5.5 Control Scope | •6.6 Control Schedule | •7.3 Control Costs | •8.3 Perform Quality Control | •10.5 Report Performance | •11.6 Monitor and Control Risks | •12.3 Administer Procurements | •4.6 Close Project or Phase | •12.4 Close Procurments | Int | Scope | Time | Cost | Quality | HR | Comm | Risk | Procurement
I | Inputs | Project Statement of Work | I | [41 empty] | I
I | Inputs | Business Case | I | [41 empty] | I
II | Inputs | Contract | I | [38 empty] | I |  |  | I | [7 empty] | I
I | Inputs | Contracts | [12 empty] | I | [32 empty] | I
IIIIIIIIIIIIIIIIUUII | Inputs | Enterprise Environemental Factors | I | I | I |  |  |  | I |  | I | I | I | I |  | I | I | I | I | I |  |  |  | I | I |  | I | U | U |  |  |  | I | I | [10 empty] | IIIII |  | IIII | I | I | IIUU | II | II | I
IIIIIIIIIIIIIIIIIIIIIUIIUIUIUIIIIUIUIUIUIUUUIUU | Inputs | Organization Process Assets | I | I | I |  | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |  | I | I | U | I |  | IU | IU | IU | I | I | I |  | IU | IU | IU | IU | IU | U | U | IU | U | IIIIIIU | IIIU | IIIIIIU | IIIU | IUIU | IIIU | IIIUIUIU | IIIIU | IIUU
II | Inputs | Teaming Agreements | [21 empty] | I | [7 empty] | I | [20 empty] | II
I | Inputs | Change Log | [28 empty] | I | [19 empty] | I
I | Inputs | Issue Log | [28 empty] | I | [19 empty] | I
I | Inputs | Qualified Seller List | [29 empty] | I | [20 empty] | I
I | Inputs | Seller Proposals | [29 empty] | I | [20 empty] | I
OIIII | Output | Project Chater | O | I | I | I | I | [37 empty] | OI | II |  |  |  |  | I
OIIIII | Output | Stakeholder Register |  | O |  | I | [9 empty] | I |  | I |  | I | [10 empty] | I | [14 empty] | I |  |  | I |  | OII | I
OII | Output | Stakeholder Mamagement Strategy |  | O | [13 empty] | I | [12 empty] | I | [19 empty] | OII
OUIUIUIUIIUIIUIUIUIUIIUIUIUIUIIUIUII | Output | Project Management Plan |  |  | O | [17 empty] | U |  | IU | IU | IU | I | IU | I | IU | IU | IU | IU | I | IU | IU | IU | IU | I | IU | IU | I | I | OIUIUIUI | IIU | IU | IU | IUIU | IUIIU | IIUI | UIU | IUIUI
OIII | Output | Schedule Management Plan |  |  | O | [13 empty] | I | I |  | I | [22 empty] | O | [6 empty] | III
OIII | Output | Cost Management Plan |  |  | O | [13 empty] | I | I |  | I | [22 empty] | O | [6 empty] | III
I | Output | Outputs from Planning Processes |  |  | I | [39 empty] | I
O | Output | Requirements Management Plan |  |  |  | O | [39 empty] | O
OIIIII | Output | Requirements Documentaion |  |  |  | O | I | I | [15 empty] | I | [10 empty] | I | I | [9 empty] | OIIII | [6 empty] | I
OII | Output | Reqiurments traceability matrix |  |  |  | O | [28 empty] | I | I | [9 empty] | OII
OIIIIII | Output | Project Scope Statement |  |  |  |  | O | I |  | I |  | I | I | [5 empty] | I |  | I | [24 empty] | OI | III |  |  |  |  | II
O | Output | WBS | [5 empty] | O | [37 empty] | O
O | Output | WBS Dictionary | [5 empty] | O | [37 empty] | O
OIIIIII | Output | Scope Baseline | [5 empty] | O | I |  |  |  |  | I | I | I |  |  |  | I |  |  |  | I | [21 empty] | O | I | II | I |  |  | I | I
OIIII | Output | Activity Attributes | [6 empty] | O | I | I | I | I | [33 empty] | OIIII
OI | Output | Milestone List | [6 empty] | O | I | [36 empty] | OI
OIIII | Output | Activity List | [6 empty] | O | I | I | I | I | [33 empty] | OIIII
OI | Output | Project Schedule Network Diagram | [7 empty] | O |  |  | I | [33 empty] | OI
O | Output | Resource Breakdown Struture | [8 empty] | O | [35 empty] | O
OIIII | Output | Activiy Resource Requirements | [8 empty] | O | I | I |  |  |  | I | [6 empty] | I | [22 empty] | OII |  |  | I |  |  | I
OII | Output | Activity Duration Estimate | [9 empty] | O | I | [6 empty] | I | [26 empty] | OI |  |  |  |  | I
OIIII | Output | Project Schedule | [10 empty] | O | I | I | [8 empty] | I | [12 empty] | I | [9 empty] | OI | II |  |  |  |  | I
OI | Output | Schedule Baseline | [10 empty] | O |  |  | I | [30 empty] | O |  | I
O | Output | Schedule Data | [10 empty] | O | [33 empty] | O
OIII | Output | Activity Cost Estimates | [11 empty] | O | I |  |  |  |  | I |  |  |  | I | [23 empty] | OI |  |  |  | I | I
OI | Output | Basis for Estimate | [11 empty] | O | I | [32 empty] | OI
OII | Output | Cost Performance Basseline | [12 empty] | O | I | [7 empty] | I | [23 empty] | O | I |  |  |  | I
OI | Output | Project Funding Requirements | [12 empty] | O | [22 empty] | I | [9 empty] | OI
OI | Output | Quality checklists | [13 empty] | O | [22 empty] | I | [9 empty] | OI
OI | Output | Quality Management Plan | [13 empty] | O |  |  |  | I | [28 empty] | O |  |  | I
O | Output | Process Improvement Plan | [13 empty] | O | [32 empty] | O
OII | Output | Quality metrics | [13 empty] | O | [9 empty] | I | [12 empty] | I | [9 empty] | OII
IO | Output | Human Resource Plan | [11 empty] | I |  |  | O | [30 empty] | I |  | O
OI | Output | Communications Management Plan | [15 empty] | O | I | [31 empty] | O | I
OIIII | Output | Risk Management Plan | [16 empty] | O | I | I | I | I | [28 empty] | OIIII
IIOIUIUIUIIU | Output | Risk Register | [11 empty] | I |  | I |  |  |  | O | IU | IU | IU | I | [16 empty] | IU | [6 empty] | I | I |  |  | OIUIUIUIU | I
OI | Output | Risk-related Contract decisions | [20 empty] | O | I | [27 empty] | O | I
OI | Output | Source Selection Criteria | [21 empty] | O | [7 empty] | I | [20 empty] | OI
OI | Output | Make or Buy decisions | [21 empty] | O | [7 empty] | I | [20 empty] | OI
IOII | Output | Procurement Documents |  | I | [19 empty] | O | [7 empty] | I | [9 empty] | I | [8 empty] | I |  | OII
O | Output | Procurement Management Plan | [21 empty] | O | [28 empty] | O
O | Output | Procurement Statements of work | [21 empty] | O | [28 empty] | O
OIIIIIIII | Output | Work Performance Information | [22 empty] | O | I | [7 empty] | I |  | I | I | I |  | I | I | I |  |  | OI | I | I | I | I |  | I | I | I
OI | Output | Deliverables | [22 empty] | O | [13 empty] | I | [5 empty] | O |  |  |  | I
OOOOOOOIOOOOOOOO | Output | Change Requests | [21 empty] | O | O | O |  |  | O |  | O | O | O | I | O | O | O | O | O | O | O | O |  |  | OOI | OO | O | O | OO | O | OO | O | OOO
IOII | Output | Approved Change Requests | [22 empty] | I | [7 empty] | O | [5 empty] | I |  |  | I |  |  | IO |  |  |  | I |  |  |  | I
OII | Output | Project Staff Assignement | [24 empty] | O | I | I | [20 empty] | OII
IIIIOIO | Output | Resource Calendars | [8 empty] | I | I | I |  | I | [11 empty] | O | I |  |  |  | O | [14 empty] | III | I |  | OI |  |  | O
OI | Output | Team Perfroamance Assessement | [25 empty] | O | I | [20 empty] | OI
O | Output | Selected Sellers | [29 empty] | O | [20 empty] | O
O | Output | Procurement Contract Award | [29 empty] | O | [20 empty] | O
OI | Output | Accepted Deliverables | [32 empty] | O | [7 empty] | I |  | I | O
OOOII | Output | Work Performance Measurements | [33 empty] | O | O | O | I | I | [5 empty] | O | O | O | I |  | I
OI | Output | Budget Forecasts | [35 empty] | O |  | I | [7 empty] | O |  |  | I
IO | Output | Validated Deliverables | [32 empty] | I |  |  |  | O | [6 empty] | I |  |  | O
IO | Output | Quality Control Measurements | [23 empty] | I | [12 empty] | O | [9 empty] | IO
O | Output | Validated Changes | [36 empty] | O | [9 empty] | O
IIIOII | Output | Perfroamance Reports | [26 empty] | I | I |  |  | I | [6 empty] | O | I | I |  |  | I |  |  |  |  | I | IO | I | I
OI | Output | Procurement Documentation | [39 empty] | O |  | I | [8 empty] | OI
O | Output | Final Product, servise, or result transition | [40 empty] | O |  | O
O | Output | Closed Procurements | [41 empty] | O | [8 empty] | O
U | Output | Change Request Status Updates | [31 empty] | U | [10 empty] | U
UUUUUUUUUUIUUUUIUUUUUUUUU | Output | Project Documents |  |  |  |  | U | U |  | U | U | U | U | U | U | U |  | U |  | I |  |  | U |  | U | U |  |  |  |  | U | IU | U | U | U | U | U | U | U |  | U |  |  |  | UUU | UUUU | UUUUU | UUU | UUU |  | UU | IUU | IU
TTTTTTTTTTTTTTTTTTT | T&T | Expert Judgment | T | T | T |  | T |  | T |  | T | T |  | T | T |  |  |  |  | T | T | T | T | T | T | [6 empty] | T | T | T | [8 empty] | T |  | TTTTTT | T | TTT | TT |  |  | T | TTTT | TT
T | T&T | Stakeholder Analysis |  | T | [46 empty] | T
T | T&T | Group Creativity Techniques |  |  |  | T | [39 empty] | T
T | T&T | Group Decision Making Techniques |  |  |  | T | [39 empty] | T
T | T&T | Interviews |  |  |  | T | [39 empty] | T
T | T&T | Observations |  |  |  | T | [39 empty] | T
T | T&T | Prototypes |  |  |  | T | [39 empty] | T
T | T&T | Questionaires and Surveys |  |  |  | T | [39 empty] | T
TT | T&T | Facilitated Workshops |  |  |  | T | T | [38 empty] | TT
T | T&T | Focus Groups |  |  |  | T | [39 empty] | T
T | T&T | Product Analysis |  |  |  |  | T | [38 empty] | T
T | T&T | Alternative Identification |  |  |  |  | T | [38 empty] | T
TT | T&T | Decomposition | [5 empty] | T | T | [36 empty] | T | T
T | T&T | Rolling Wave Planning | [6 empty] | T | [37 empty] | T
T | T&T | Templates | [6 empty] | T | [37 empty] | T
T | T&T | Precedence Diagramming Method (PDM) | [7 empty] | T | [36 empty] | T
T | T&T | Dependency Determination | [7 empty] | T | [36 empty] | T
TT | T&T | Applying Leads and Lags | [7 empty] | T |  |  | T | [33 empty] | TT
T | T&T | Schedule Network Templates | [7 empty] | T | [36 empty] | T
TTT | T&T | Project Management Software | [8 empty] | T | [25 empty] | T | T | [8 empty] | TT | T
T | T&T | Published Estimating Data | [8 empty] | T | [35 empty] | T
T | T&T | Alternative Analysis | [8 empty] | T | [35 empty] | T
TT | T&T | Analogous estimating | [9 empty] | T |  | T | [32 empty] | T | T
TT | T&T | Parametric estimating | [9 empty] | T |  | T | [32 empty] | T | T
TT | T&T | Bottom-up Estimating | [8 empty] | T |  |  | T | [32 empty] | T | T
TT | T&T | Three-point estimates | [9 empty] | T |  | T | [32 empty] | T | T
TTTT | T&T | Reserve analysis | [9 empty] | T |  | T | T | [25 empty] | T | [5 empty] | T | TT |  |  |  | T
TT | T&T | Cost of Quality | [11 empty] | T |  | T | [31 empty] | T | T
TT | T&T | Resource Leveling | [10 empty] | T | [23 empty] | T | [9 empty] | TT
TT | T&T | Schedule Compression | [10 empty] | T | [23 empty] | T | [9 empty] | TT
T | T&T | Schedule Network Analysis | [10 empty] | T | [33 empty] | T
TT | T&T | Scheduling Tool | [10 empty] | T | [23 empty] | T | [9 empty] | TT
TT | T&T | What-if Scenario analysis | [10 empty] | T | [23 empty] | T | [9 empty] | TT
T | T&T | Critical Chain Method | [10 empty] | T | [33 empty] | T
T | T&T | Critical Path Method (CPM) | [10 empty] | T | [33 empty] | T
T | T&T | Project Management Estimating Software | [11 empty] | T | [33 empty] | T
T | T&T | Vendor Bid Analysis | [11 empty] | T | [33 empty] | T
T | T&T | Cost Aggregation | [12 empty] | T | [32 empty] | T
T | T&T | Funding Limit reconciliation | [12 empty] | T | [32 empty] | T
T | T&T | Historical Relatioships | [12 empty] | T | [32 empty] | T
T | T&T | Proprietary Quality Mgmt Methodologies | [13 empty] | T | [32 empty] | T
TT | T&T | Statistical sampling | [13 empty] | T | [22 empty] | T | [9 empty] | TT
TT | T&T | Flowcharting | [13 empty] | T | [22 empty] | T | [9 empty] | TT
T | T&T | Cost Benefot Analysis | [13 empty] | T | [32 empty] | T
T | T&T | Design of Eperiments | [13 empty] | T | [32 empty] | T
TT | T&T | Control Charts | [13 empty] | T | [22 empty] | T | [9 empty] | TT
T | T&T | Additional Quality Planning Tools | [13 empty] | T | [32 empty] | T
T | T&T | Benshmarking | [13 empty] | T | [32 empty] | T
T | T&T | Networking | [14 empty] | T | [32 empty] | T
T | T&T | Organization charts and position descriptions | [14 empty] | T | [32 empty] | T
T | T&T | Organizational Theory | [14 empty] | T | [32 empty] | T
TTTT | T&T | Communication Methods | [15 empty] | T | [11 empty] | T | T | [8 empty] | T | [10 empty] | TTTT
T | T&T | Communications Models | [15 empty] | T | [32 empty] | T
T | T&T | Communications Requirements Analysis | [15 empty] | T | [32 empty] | T
T | T&T | Communications Technology | [15 empty] | T | [32 empty] | T
T | T&T | Planning Meetings and Analysis | [16 empty] | T | [32 empty] | T
T | T&T | Diagramming Techniques | [17 empty] | T | [31 empty] | T
T | T&T | Documentation Reviews | [17 empty] | T | [31 empty] | T
T | T&T | SWOT Analsysis | [17 empty] | T | [31 empty] | T
T | T&T | Information Gathering Techniques | [17 empty] | T | [31 empty] | T
T | T&T | Assumption Analysis | [17 empty] | T | [31 empty] | T
T | T&T | Checklist analysis | [17 empty] | T | [31 empty] | T
T | T&T | Risk Categorization | [18 empty] | T | [30 empty] | T
T | T&T | Risk Data Quality Assessement | [18 empty] | T | [30 empty] | T
T | T&T | Risk Probability and impact assessement | [18 empty] | T | [30 empty] | T
T | T&T | Risk Urgency assessement | [18 empty] | T | [30 empty] | T
T | T&T | Probalility and Impact Matrix | [18 empty] | T | [30 empty] | T
T | T&T | Quantitave Risk Analysis and Modeling Techs. | [19 empty] | T | [29 empty] | T
T | T&T | Data Gathering and represention techniques | [19 empty] | T | [29 empty] | T
T | T&T | Strategies for negative risks or threats | [20 empty] | T | [28 empty] | T
T | T&T | Strategies for positive risks or opportunities | [20 empty] | T | [28 empty] | T
T | T&T | Contingent Response strategies | [20 empty] | T | [28 empty] | T
T | T&T | contract types | [21 empty] | T | [28 empty] | T
T | T&T | Make-or-buy analysis | [21 empty] | T | [28 empty] | T
T | T&T | PM Information Systems | [22 empty] | T | [19 empty] | T
T | T&T | Plan Quality & Perform QC Tools & Techs. | [23 empty] | T | [22 empty] | T
T | T&T | Quality Audits | [23 empty] | T | [22 empty] | T
T | T&T | Process Analysis | [23 empty] | T | [22 empty] | T
T | T&T | Virtual Teams | [24 empty] | T | [22 empty] | T
T | T&T | Pre-assignment | [24 empty] | T | [22 empty] | T
T | T&T | Negotiation | [24 empty] | T | [22 empty] | T
T | T&T | Acquisition | [24 empty] | T | [22 empty] | T
T | T&T | Team-Building Activities | [25 empty] | T | [21 empty] | T
T | T&T | Training | [25 empty] | T | [21 empty] | T
T | T&T | Recongnition and rewards | [25 empty] | T | [21 empty] | T
T | T&T | Ground Rules | [25 empty] | T | [21 empty] | T
TTT | T&T | Interpersonal Skills | [25 empty] | T | T |  | T | [18 empty] | TT | T
T | T&T | Co-location | [25 empty] | T | [21 empty] | T
T | T&T | Conflict Management | [26 empty] | T | [20 empty] | T
T | T&T | Project Performance Appraisals | [26 empty] | T | [20 empty] | T
T | T&T | Observation and conversation | [26 empty] | T | [20 empty] | T
T | T&T | Issue Log | [26 empty] | T | [20 empty] | T
T | T&T | Information Distribution Tools | [27 empty] | T | [20 empty] | T
T | T&T | Management Skills | [28 empty] | T | [19 empty] | T
T | T&T | Internet Search | [29 empty] | T | [20 empty] | T
T | T&T | Procurement negotiations | [29 empty] | T | [20 empty] | T
T | T&T | Proposal Evaluation Techniques | [29 empty] | T | [20 empty] | T
T | T&T | Independent Estimates | [29 empty] | T | [20 empty] | T
T | T&T | Advertising | [29 empty] | T | [20 empty] | T
T | T&T | Bidder conference | [29 empty] | T | [20 empty] | T
T | T&T | Change control Meetings | [31 empty] | T | [10 empty] | T
TT | T&T | Inspection | [32 empty] | T |  |  |  | T | [6 empty] | T |  |  | T
TTTT | T&T | Varriance Analysis | [33 empty] | T | T | T |  | T | [5 empty] | T | T | T |  |  | T
T | T&T | Adjusting Leads and Lags | [34 empty] | T | [9 empty] | T
TT | T&T | Performance Reviews | [34 empty] | T | T | [8 empty] | T | T
T | T&T | Earned Value Management | [35 empty] | T | [9 empty] | T
T | T&T | Forecasting | [35 empty] | T | [9 empty] | T
T | T&T | To Complete performance index | [35 empty] | T | [9 empty] | T
T | T&T | Run Chart | [36 empty] | T | [9 empty] | T
T | T&T | Scatter Diagram | [36 empty] | T | [9 empty] | T
T | T&T | Approved change request review | [36 empty] | T | [9 empty] | T
T | T&T | Cause and Effect Diagram | [36 empty] | T | [9 empty] | T
T | T&T | Histogram | [36 empty] | T | [9 empty] | T
T | T&T | Pareto Chart | [36 empty] | T | [9 empty] | T
T | T&T | Reporting Systems | [37 empty] | T | [10 empty] | T
T | T&T | Forecasting Methods | [37 empty] | T | [10 empty] | T
T | T&T | Risk resasessment | [38 empty] | T | [10 empty] | T
T | T&T | Risk audits | [38 empty] | T | [10 empty] | T
T | T&T | Varriance and trend analysis | [38 empty] | T | [10 empty] | T
T | T&T | Technical Performance measurement | [38 empty] | T | [10 empty] | T
T | T&T | Status meeting | [38 empty] | T | [10 empty] | T
T | T&T | Claims Administration | [39 empty] | T | [10 empty] | T
T | T&T | Contract Change Control System | [39 empty] | T | [10 empty] | T
T | T&T | Inspections and audits | [39 empty] | T | [10 empty] | T
T | T&T | Payment Systems | [39 empty] | T | [10 empty] | T
T | T&T | Performance Reporting | [39 empty] | T | [10 empty] | T
T | T&T | Procurement Performance Reviews | [39 empty] | T | [10 empty] | T
TT | T&T | Records Management Systems | [39 empty] | T |  | T | [8 empty] | TT
T | T&T | Negotiated Settlements | [41 empty] | T | [8 empty] | T
T | T&T | Procurement Audits | [41 empty] | T | [8 empty] | T
Information used as Input to Processes
| Input | Inputs to PM Processes | [7 empty] | I | Input
| Documents & Information Generated From the Processes | [8 empty] | O | Otput
| Output | Outputs | [7 empty] | IU | Input & Updated as Output
| Output | Outputs - PM Plan | [7 empty] | U | Updated as output only
Tools & Techniques
| T&T | Tools & Techniques | [7 empty] | T | Tools & Techniques