## Sheet1
Plant Crusher repair and Commissioning
Step | Cost | Period
Step 1 is Transferring Generator 1000 kVA from Camp TO crusher site
Step 2 -inspection and serviced the generator
Step 3 Place generator to the Power house
Step 4 Connect the generator to the Crusher control room
Period for all above steps is 1 week
Cost of the above work is $ 3,066.74
step 5 Metso Technician inspection and material estimation Period 3 days Cost Euro 6600
STEP 6 request parts , quotations , purchase order , deliver the parts , receive the parts Period 2 months Cost unknown
Step 7 Fix the received parts by Metso technician 15 DAYS period 15 DAYS sorry , period 1 week cost Euro 15400
Days
Step | Period | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85
# 1 is Transferring Generator 1000 kVA from Camp TO crusher site | 2 | bar: Days 1 to Days 2
# 2 inspection and serviced the generator | 2 | bar: Days 3 to Days 4
# 3 Place generator to the Power house | 2 | bar: Days 5 to Days 6
# 4 Connect the generator to the Crusher control room | 1 | bar: Days 7
# 5 Metso Technician inspection and material estimation | 3 | bar: Days 8 to Days 10
# 6 request parts , quotations , purchase order , deliver the parts , receive the parts | 60 | bar: Days 11 to Days 70
# 7 Fix the received parts by Metso technician | 15 | bar: Days 71 to Days 85