## ملخص
District Code | (الكل)
Exchange Code | (الكل)
Design Forecast Date | (الكل)
حالة الطلبات | حالة الطلبات في التصميم
نوع المشاريع | الطلبات المصممة | إجمالي الطلبات
OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 1 | 1
OSP PROGRAM HELD ORDER ( HO ) FOR HBU -2013 | 1 | 1
OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 8 | 8
إجمالي الطلبات | 10 | 10
District Code | (الكل)
Exchange Code | (الكل)
NI Forecast Date | (الكل)
حالة الطلبات | حالة الطلبات في التنفيذ
نوع المشاريع | منفذ | جاري التنفيذ | تحتاج مقاول | Not In NFTS | إجمالي الطلبات
OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 1 |  |  |  | 1
OSP PROGRAM HELD ORDER ( HO ) FOR HBU -2013 | 1 |  |  |  | 1
OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 5 | 1 | 2 |  | 8
(فارغ)
إجمالي الطلبات | 7 | 1 | 2 |  | 10
تحويل نص التاريخ من يوم شهر سنة الى شهر سنة بحيث لا يتكرر الشهر والسنة
مثال 2014-04
تحويل نص التاريخ من يوم شهر سنة الى شهر سنة بحيث لا يتكرر الشهر والسنة
مثال 2014-06

## SOU
OSP Number | Project | Project Year | Service Order Number | HBU Priority | Reason Code | SO Status | SO Type | Surveyor Status | Reason | OSP Status | SO Remarks | HO Type | CAB | DP | BSW | FDT | FAT | TB | Design Job Type | Design WO ID | Prime WO | Design WO | Job Status | Approved Status | Approved Status Date | RFW Number | Request Origin | RFW Status | NFTS WO Status | Design Completed Date | Design Forecast Date | NI Forecast Date | Held Order Date | Design Contractor | RFW Stage | Surveyor | Senior Designer | Designer | Imp HQ Reject Status | Imp HQ Reject Reason | Imp HQ Reject Remarks | Imp Dist. Reject Status | Imp Dist. Reject Reason | Imp Dist. Reject Remarks | WO Assigned Date | Region | District Code | ICMS Eng. Work Order | Exchange Code | Account Number | Cabinet Number or Building Name | Switch Code | Analysis Code | First Name | Last Name | Contact # 1 | Contact # 2 | Service Order Type | Customet Address | Customer Address 2
31464 | OSP PROGRAM HELD ORDER ( HO ) FOR HBU -2013 | 2013 | 02177964 | High | 6 | Issue RFW | New | Completed | Covered by Existing Work Order | Completed | Issued RFW FROM SWAT WO based on the ICMS Eng. Work Order | [7 empty] | Secondary | 0724003069_31464 | Checked | 0724003069 | Completed | Approved |  | 1000056911 | ICMS | Completed | Completed | 03/03/2009 | 2013-09-30 | 2014-03-20 | 2009-01-19 |  | Design Completed | ICMS024 (Asir) | 24_SD ASIR | 24_DD ASIR | [6 empty] | 24/03/2013 | South | 24 | 0724003069 | ABHGA | 0301400721 | ABHA 065:0067
31383 | OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 2013 | 06322912 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 093 | 040 | 3 & 4 |  |  |  | Secondary | 1327000236 | Checked | 1327000236 | Completed | Approved | 05/05/2013 | 1304249090 | ICMS | Completed | Under Assign | 05/05/2013 | 2014-04-24 | 2014-06-08 | 2011-07-05 |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 24/04/2013 | South | 27 |  | ABAR | 2008707513 | ABAR 093:0046
31384 | OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 2013 | 06325575 | High | 7 | Assign | Covered by DWO | Completed | BSW Work | Completed |  | Copper | 093 | 040 | 3 & 4 |  |  |  | Secondary | 1327000236 | Checked | 1327000236 | Completed | Approved | 05/05/2013 | 1304249090 | ICMS | Completed | Under Assign | 05/05/2013 | 2014-04-26 | 2014-06-10 | 2011-07-05 |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 24/04/2013 | South | 27 |  | ABAR | 2008707734 | ABAR 093:0046
1500 | OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 2013 | 03600394 | High | 6 | Issue RFW | New | Completed | Covered by Existing Work Order | Completed | [8 empty] | Secondary | 1327000232 | Checked | 1327000232 | Completed | Approved | 01/05/2013 | 1304299582 | ICMS | Completed | In Progress | 01/05/2013 | 2013-06-06 | 2013-07-06 | 2011-09-06 |  | Design Completed |  | Hasan Ghashim | Cecilio Bactol | [6 empty] | 29/04/2013 | South | 27 |  | ABAR | 2009650000 | ABAR 022:0067
77430 | OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 2013 | 03944667 | High | 6 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 011 | 009 | 000 |  |  |  | Secondary | 1325000177 | Checked | 1325000177 | Completed | Approved | 11/06/2013 | 1305060376 | ICMS | Completed | Completed | 11/06/2013 | 2013-07-03 | 2013-08-02 | 2012-06-18 |  | Design Completed | ICMS025 (BAHA) | Mohammed Al Zahrani | Mohammed Saed Alzahrani | [6 empty] | 06/05/2013 | South | 25 |  | AQQ2A | 2014722605 | AQIQ 011:0010
192390 | OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 2013 | 05357866 | High | 6 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 011 | 009 | 000 |  |  |  | Secondary | 1325000177 | Checked | 1325000177 | Completed | Approved | 11/06/2013 | 1305060376 | ICMS | Completed | Completed | 11/06/2013 | 2013-07-03 | 2013-08-02 | 2013-01-27 |  | Design Completed | ICMS025 (BAHA) | Mohammed Al Zahrani | Mohammed Saed Alzahrani | [6 empty] | 06/05/2013 | South | 25 |  | AQQ2A | 2018403288 | AQIQ 011:0010
222256 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03092957 | High | 7 | Issue RFW | New | Completed | Covered by Existing Work Order | Completed |  | Copper | 215 | 002-005 | IN DOOR DP |  |  |  | Secondary | 1324000525 | Checked | 1224000836 | Completed | Approved | 13/05/2013 | 1305070480 | ICMS | Completed | Completed | 13/05/2013 | 2013-04-30 |  | 5/26/2012 |  | Design Completed | Ali al-hasanieh | ahmed Alasere | Ali al-hasanieh | [6 empty] | 07/05/2013 | South | 24 |  | KHMII | 0300338186 | KHAM 099:0082
83904 | OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 2013 | 03752603 | High | 6 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 050 | 0086 | 3+4 |  |  |  | Secondary | 1326000112 | Checked | 1326000112 | Completed | Approved | 14/05/2013 | 1305131005 | ICMS | Completed | Completed | 14/05/2013 | 2013-08-01 | 2013-09-11 | 2012-05-29 |  | Design Completed | ICMS026 (Najran) | Ali almayed | Ibrahim Ali Almahmady | [6 empty] | 13/05/2013 | South | 26 |  | FAI6C | 2014387156 | FAIS 050:0086
83905 | OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 2013 | 02551444 | High | 1 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 051 | 0025+0026 | 9+10+11 |  |  |  | Secondary | 1326000111 | Checked | 1326000111 | Completed | Approved | 14/05/2013 | 1305131002 | ICMS | Completed | Completed | 14/05/2013 | 2013-08-01 | 2013-09-20 | 2012-06-05 |  | Design Completed | ICMS026 (Najran) | Ali almayed | Ibrahim Ali Almahmady | [6 empty] | 13/05/2013 | South | 26 |  | FAI5A | 2014498934 | FAIS 051:0027
152177 | OSP PROGRAM HELD ORDER ( HO ADDITIONAL) FOR HBU- 2013 | 2013 | 04133070 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 022 | 088 | 3 |  |  |  | Secondary | 1325000138 | Checked | 1325000138 | Completed | Approved | 04/06/2013 | 1305252072 | ICMS | Completed | Completed | 04/06/2013 | 2013-07-01 | 2013-07-31 | 2012-09-18 |  | Design Completed | ICMS025 (BAHA) | Mohammed Al Zahrani | KHALID A. ALGHAMDI | [6 empty] | 25/05/2013 | South | 25 |  | BAHA | 2016081658 | BAHA 022:0088