## Overall
Sr. | Priority | T.P No | AG/UG | Signed by Engg. | name | action | Comm. | Test Pack Punching CMC | Test Pack Punching EPM MECH | Test Pack Punching EPM ENGG | Test Pack Punching COMPANY | Test Pack Preparation EPM Engineering Approval | Flushing & Cleanliness CMC Construction | Flushing & Cleanliness EPC Commissioning | Flushing & Cleanliness Company | Hydrotest CMC Construction | action
1 | 1.1 | 92-WO-344 | UG | 2013-05-10 | user 01 | Req. | CP-06-61-355 | 2010-09-19 | 2011-04-26 | 2011-03-02 | 2011-04-26 | 2011-04-26 | 2010-07-19 | 2010-08-08 | 2010-09-15 | 2010-07-19 | Req.
2 | 1.1 | 92-WO-345 | AG | 2013-05-11 | user 02 | N/A | CP-09-61-361 | 2011-04-30 | 2011-05-11 | 2011-05-11 | 2011-05-11 | 2011-05-11 | 2010-08-22 | 2010-08-31 | 2011-06-12 | 2010-07-19 | N/A
3 | 1.1 | 92-WO-355 | AG | 2013-05-12 | user 03 | N/A | CP-06-61-355 | 2011-04-30 | 2011-05-11 | 2011-05-11 | 2011-05-11 |  | 2010-07-19 | 2010-09-19 | 2010-08-22 | 2010-07-19 | N/A
4 | 1.1 | 92-WO-356 | AG | 2013-05-13 | user 04 | N/A | CP-07-61-359 |  | 2011-05-11 |  |  | 2011-05-11 | 2010-07-19 | 2010-09-19 | 2010-08-22 | 2010-08-05 | N/A
5 | 1.1 | 92-WO-357 | UG | 2013-05-14 | user 05 | N/A | CP-06-61-355 | 2011-04-30 | 2011-05-11 | 2011-05-11 | 2011-05-11 | 2011-05-11 | 2010-07-19 | 2010-08-08 | 2010-08-21 | 2010-08-05 | N/A
6 | 1.1 | 92-WO-358 | UG | 2013-05-15 | user 06 | Req. | CP-06-61-355 | 2011-04-30 | 2011-05-10 | 2011-05-10 | 2011-05-10 | 2011-05-10 | 2010-07-19 | 2010-08-15 | 2010-08-21 | 2011-05-31 | Req.
7 | 1.1 | 92-WO-359 | UG | 2013-05-16 | user 07 | N/A | CP-06-61-355 | 2010-09-18 | 2011-03-22 | 2011-02-16 | 2011-03-22 | 2011-03-26 | 2010-08-05 | 2010-08-15 | 2010-08-21 | 2010-08-22 | N/A
8 | 1.1 | 92-WO-363 | UG | 2013-05-17 | user 08 | N/A | CP-06-61-355 | 2010-09-13 | 2011-03-31 | 2011-02-20 | 2011-03-31 | 2011-04-03 | 2010-08-05 | 2010-08-15 | 2010-08-24 | 2010-08-31 | N/A
9 | 1.1 | 92-WO-371 | AG | 2013-05-18 | user 09 | N/A | CP-06-61-355 | 2010-02-09 | 2010-05-31 |  | 2010-06-03 | 2010-06-12 | 2011-05-31 | 2010-08-15 | 2010-08-24 | 2010-08-31 | N/A
10 | 1.1 | 92-WO-372 | AG | 2013-05-19 | user 10 | Req. | CP-06-61-355 | 2010-02-23 | 2010-04-18 | 2010-04-18 | 2010-04-18 | 2010-05-06 | 2010-08-22 | 2010-08-14 | 2010-08-24 | 2010-08-03 | Req.
11 | 1.2 | 92-WO-373 | AG | 2013-05-20 | user 11 | Req. | CP-06-61-355 | 2010-02-23 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-08-31 | 2010-08-14 | 2010-08-24 | 2011-05-31 | Req.
12 | 1.2 | 92-WO-374 | AG | 2012-02-10 | user 12 | Req. | CP-06-61-355 | 2010-02-23 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-08-31 | 2010-08-14 | 2010-08-24 | 2010-08-03 | Req.
13 | 1.2 | 92-WO-375 | UG | 2012-02-10 | user 13 | Req. | CP-06-61-355 | 2010-02-01 | 2010-04-29 | 2010-04-27 | 2010-04-28 | 2010-05-20 | 2010-08-03 | 2010-08-14 | 2010-08-24 | 2010-07-24 | Req.
14 | 1.2 | 92-WO-514 | UG | 2012-02-10 | user 14 | N/A | CP-06-61-355 | 2010-02-16 | 2010-10-05 | 2010-04-18 | 2010-10-05 | na | 2011-05-31 | 2010-08-14 | 2010-08-24 | 2010-08-03 | Req.
15 | 1.2 | 92-WR-033 | UG | 2012-02-10 | user 15 | N/A | CP-06-61-355 | 2010-02-15 | 2010-09-01 | 2010-04-18 | 2010-09-01 | 2010-09-05 | 2010-08-03 | 2010-08-15 | 2010-08-30 | 2010-08-05 | N/A
16 | 1.2 | 92-WR-034 | UG | 2012-02-10 | user 16 | Req. | CP-06-61-355 | 2010-02-23 | 2010-06-12 | 2010-04-18 | 2010-06-12 | 2010-06-26 | 2010-07-24 | 2010-08-14 | 2010-08-24 | 2010-08-04 | N/A
17 | 1.2 | 92-WR-034A | UG | 2012-02-10 | user 17 | Req. | CP-06-61-355 | 2010-02-23 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-08-03 | 2010-08-14 | 2010-08-24 | 2010-08-04 | N/A
18 | 1.2 | 92-WR-036 | UG | 2012-02-10 | user 18 | Req. | CP-06-61-355 | 2010-02-23 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-08-05 | 2010-09-13 | 2010-09-13 | 2010-08-04 | N/A
19 | 1.2 | 92-WR-051 | UG | 2010-10-19 | user 19 | Req. | CP-06-61-355 | 2010-01-31 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-05-05 | 2010-08-04 | 2010-08-15 | 2010-08-24 | 2010-08-04 | Req.
20 | 1.2 | 92-WR-361 | UG | 2010-10-12 | user 20 | Req. | CP-06-61-355 | 2010-03-07 | 2010-05-27 | 2010-05-27 | 2010-05-27 | 2010-06-06 | 2010-08-04 | 2010-08-14 | 2010-09-13 | 2010-08-05 | Req.
21 | 1.2 | 92-WR-362 | UG | 2010-10-12 | user 21 | Req. | CP-06-61-355 | 2010-03-04 | 2010-06-07 | 2010-06-07 | 2010-06-07 | 2010-06-24 | 2010-08-04 | 2010-08-14 | 2010-08-24 | 2010-07-19 | Req.
22 | 2 | 92-WR-507 | UG | 2011-01-31 | user 22 | N/A | CP-06-61-355 | 2010-03-01 | 2010-05-13 | 2010-04-18 | na | 2010-05-22 | 2010-08-04 | 2010-08-15 | 2010-09-13 | 2010-07-19 | N/A
23 | 2 | 92-WR-510 | UG | 2011-01-31 | user 23 | N/A | CP-08-61-357 | 2010-04-13 | 2010-05-26 | 2010-05-26 | 2010-05-26 | 2010-06-24 | 2010-08-05 | 2010-08-18 | 2010-09-13 | 2010-07-19 | N/A
24 | 2 | 92-WS-001 | UG | 2010-08-11 | user 24 | N/A | CP-07-61-359 | 2010-04-13 | 2010-05-27 | 2010-05-27 | 2010-05-27 | 2010-06-12 | 2010-08-04 | 2010-08-15 | 2010-08-30 | 2010-08-05 | N/A
25 | 2 | 92-WS-002 | UG | 2011-01-27 | user 25 | N/A | CP-07-61-359 | 2010-09-29 | signed | signed | signed | signed | 2010-08-04 | 2010-08-24 | 2010-08-24 | 2010-08-05 | N/A
26 | 2 | 92-WS-003 | UG | 2011-03-02 | user 26 | N/A | CP-06-61-355 | 2010-03-07 | 2010-05-13 | 2010-04-18 | na | 2010-06-14 | 2010-07-24 | 2011-01-16 | 2010-08-24 | 2011-05-31 | N/A
27 | 2 | 92-WS-004 | UG | 2010-08-29 | user 27 | Req. | CP-07-61-359 | 2010-03-04 | 2010-05-05 | 2010-05-05 | 2010-05-05 | 2010-06-06 | 2010-08-08 | 2010-09-14 | 2010-09-18 | 2010-08-22 | Req.
28 | 2 | 92-WS-005 | UG | 2010-08-24 | user 28 | Req. | CP-07-61-358 | 2010-03-04 | 2010-05-29 | 2010-05-29 | 2010-05-05 | 2010-06-06 | 2011-03-15 | 2010-08-15 | 2010-08-24 | 2010-08-31 | Req.
29 | 2 | 92-WS-006 | UG | 2010-08-24 | user 29 | Req. | CP-07-61-358 | 2010-03-06 | signed | signed | signed | signed | 2010-08-05 | 2010-08-14 | 2010-08-24 | 2010-08-31 | Req.
30 | 2 | 92-WS-007 | UG | 2010-12-05 | user 30 | Req. | CP-07-61-358 | 2010-03-06 | signed | signed | signed | signed | 2010-08-08 | 2010-08-24 | 2010-08-24 | 2010-08-03 | Req.
31 | 2 | 92-WS-008 | UG | 2011-12-30 | user 31 | Req. | CP-07-61-358 | 2010-11-30 | signed | 2010-12-12 | signed | signed | 2010-07-24 | 2010-08-24 | 2010-08-30 | 2011-05-31 | Req.
32 | 2 | 92-WS-009 | UG | 2010-08-21 | user 32 | Req. | CP-07-61-358 | 2010-04-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-17 | 2010-06-19 | 2010-08-24 | 2010-08-24 | 2010-08-03 | Req.
33 | 2 | 92-WS-010 | UG | 2010-11-06 | user 33 | N/A | CP-07-61-359 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-17 | 2010-05-04 | 2010-08-30 | 2010-08-30 | 2010-07-24 | Req.
34 | 2 | 92-WS-011 | UG | 2010-10-15 | user 34 | N/A | CP-07-61-359 | 2010-03-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-29 | 2010-08-04 | 2010-08-30 | 2010-08-29 | 2010-08-03 | N/A
35 | 3 | 92-WS-012 | UG | 2010-11-08 | user 35 | N/A | CP-07-61-359 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-17 | 2010-08-04 | 2010-08-14 | 2010-08-29 | 2010-08-05 | N/A
36 | 3 | 92-WS-013 | UG | 2010-07-19 | user 36 | Req. | CP-07-61-359 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-15 | 2010-08-03 | 2010-09-13 | 2010-08-29 | 2010-08-04 | N/A
37 | 3 | 92-WS-014 | UG | 2010-08-05 | user 37 | Req. | CP-06-61-355 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-22 | 2010-08-05 | 2010-08-14 | 2010-08-29 | 2010-08-04 | N/A
38 | 3 | 92-WS-015 | UG | 2010-08-05 | user 38 | Req. | CP-07-61-359 | 2010-03-06 | signed | signed | signed | 2010-07-22 | 2010-08-05 | 2010-08-15 | 2010-08-29 | 2010-08-04 | N/A
39 | 3 | 92-WS-016 | UG | 2011-05-31 | user 39 | Req. | CP-07-61-359 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-02-10 | 2010-08-05 | 2010-08-15 | 2010-08-29 | 2010-08-04 | Req.
40 | 3 | 92-WS-017 | UG | 2010-08-22 | user 40 | N/A | CP-07-61-359 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-08-18 | 2010-07-25 | 2010-08-15 | 2010-08-31 | 2010-08-05 | N/A
41 | 3 | 92-WS-018 | UG | 2010-08-31 | user 41 | N/A | CP-07-61-359 | 2010-02-18 | 2010-05-06 | 2010-04-10 | 2010-05-09 | 2010-02-23 | 2010-08-05 | 2010-08-15 | 2010-09-09 | 2010-07-19 | N/A
42 | 3.1 | 92-WS-019 | UG | 2010-08-31 | user 42 | N/A | CP-07-61-359 | 2010-02-13 | 2010-09-21 | 2010-04-10 | 2010-09-26 | 2010-02-09 | 2010-08-05 | 2010-08-14 | 2010-08-24 | 2010-07-19 | N/A
43 | 3.1 | 92-WS-020 | UG | 2010-08-03 | user 43 | N/A | CP-07-61-359 | 2010-02-15 | 2010-08-16 | 2010-04-10 | 2010-08-16 | 2010-02-09 | 2010-08-05 | 2010-08-14 | 2010-08-24 | 2010-07-19 | N/A
44 | 3.1 | 92-WS-021 | UG | 2011-05-31 | user 44 | N/A | CP-07-61-359 | 2010-02-22 | 2010-04-20 | 2010-04-20 | 2010-04-20 | 2010-07-29 | 2010-05-04 | 2010-09-14 | 2010-08-24 | 2010-08-05 | N/A
45 | 3.2 | 92-WS-023 | UG | 2010-08-03 | user 45 | N/A | CP-07-61-359 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-24 | 2010-06-26 | 2011-01-16 | 2010-08-24 | 2010-08-05 | N/A
46 | 3.2 | 92-WS-024 | UG | 2010-07-24 | user 46 | N/A | CP-07-61-359 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-24 | 2010-08-05 | 2010-08-31 | 2010-08-24 | 2011-05-31 | N/A
47 | 3.2 | 92-WS-025 | UG | 2010-08-03 | user 47 | N/A | CP-07-61-358 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-24 | 2010-08-05 | 2010-09-13 | 2010-08-24 | 2010-08-22 | N/A
48 | 3.2 | 92-WS-026 | UG | 2010-08-05 | user 48 | Req. | CP-07-61-358 | 2010-02-18 | 2010-05-06 | 2010-04-10 | 2010-05-09 | 2010-07-13 | 2010-08-05 | 2010-08-14 | 2010-08-24 | 2010-08-31 | Req.
49 | 3.2 | 92-WS-027 | UG | 2010-08-04 | user 49 | Req. | CP-07-61-358 | 2010-02-13 | 2010-09-21 | 2010-04-10 | 2010-09-26 | 2010-04-24 | 2010-08-05 |  | 2010-08-24 | 2010-08-31 | Req.
50 | 3.2 | 92-WS-028 | UG | 2010-08-04 | user 50 | Req. | CP-07-61-358 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-04-24 | 2010-08-05 | 2010-08-14 | 2010-08-24 | 2010-08-03 | Req.
51 | 3.2 | 92-WS-029 | UG | 2010-08-04 | user 51 | Req. | CP-07-61-358 | 2010-03-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-04-25 | 2010-08-05 | 2010-08-14 | 2010-08-24 | 2011-05-31 | Req.
52 | 3.3 | 92-WS-030 | UG | 2010-08-04 | user 52 | Req. | CP-07-61-358 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 |  | 2010-08-05 | 2010-05-03 | 2010-08-24 | 2010-08-03 | Req.
53 | 3.3 | 92-WS-030A | UG | 2010-08-05 | user 53 | Req. | CP-08-61-364 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-24 | 2010-07-25 | 2010-05-08 | 2010-09-06 | 2010-07-24 | Req.
54 | 3.3 | 92-WS-031 | UG | 2010-08-04 | user 54 | Req. | CP-08-61-364 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-24 | 2010-08-05 | 2010-08-14 | 2010-08-24 | 2010-08-03 | Req.
55 | 3.3 | 92-WS-033 | UG | 2010-08-04 | user 55 | Req. | CP-09-61-361 | 2010-03-06 | signed | signed | signed | 2010-07-24 | 2010-08-14 | 2010-08-31 | 2010-09-15 | 2010-08-05 | Req.
56 | 3.3 | 92-WS-034 | UG | 2010-07-19 | user 56 | Req. | CP-08-61-364 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-24 | 2010-06-14 | 2010-08-14 | 2010-09-14 | 2010-08-04 | N/A
57 | 3.3 | 92-WS-035 | UG | 2010-08-05 | user 57 | Req. | CP-08-61-364 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-07-24 | 2011-02-01 | 2010-08-14 | 2010-08-24 | 2010-08-04 | N/A
58 | 3.3 | 92-WS-055 | UG | 2010-08-05 | user 58 | Req. | CP-09-61-361 | 2010-02-18 | 2010-05-06 | 2010-04-10 | 2010-05-09 | 2010-07-08 | 2011-02-02 | 2010-08-14 | 2010-08-18 | 2010-08-04 | Req.
59 | 4 | 92-WS-521 | UG | 2011-05-31 | user 59 | Req. | CP-09-61-361 | 2010-02-13 | 2010-09-21 |  | 2010-09-26 | 2010-05-03 | 2011-02-02 | 2010-08-14 | 2010-08-18 | 2010-08-04 | Req.
60 | 4 | 92-WS-525 | UG | 2010-08-22 | user 60 | Req. | CP-09-61-361 | 2010-02-15 | 2010-08-16 | 2010-04-10 | 2010-08-16 | 2010-07-24 | 2011-02-02 | 2010-08-29 | 2010-09-02 | 2010-08-05 | Req.
61 | 4 | 92-WS-526 | UG | 2010-08-31 | user 61 | Req. | CP-08-61-364 | 2010-02-22 | 2010-04-20 | 2010-04-20 | 2010-04-20 | 2010-07-13 | 2011-02-01 | 2010-09-09 | 2010-08-29 | 2010-07-19 | Req.
62 | 4 | 92-WS-528 | UG | 2010-08-31 | user 62 | Req. | CP-08-61-364 |  | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-04-25 | 2011-02-01 | 2010-08-14 | 2010-08-29 | 2010-07-19 | Req.
63 | 4 | 92-WS-532 | UG | 2010-08-03 | user 63 | N/A | CP-08-61-364 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-08 | 2011-02-01 | 2010-09-06 | 2010-08-29 | 2010-07-19 | N/A
64 | 4 | 92-WS-533 | UG | 2011-05-31 | user 64 | N/A | CP-08-61-364 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-05-01 | 2011-02-02 | 2010-09-07 | 2010-08-29 | 2010-08-05 | N/A
65 | 4 | 92-WS-537 | UG | 2010-08-03 | user 65 | N/A | CP-08-61-364 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-24 | 2011-02-02 | 2010-08-14 | 2010-08-29 | 2010-08-05 | N/A
66 | 4 | 92-WW-035 | UG | 2010-07-24 | user 66 | N/A | CP-08-61-356 | 2010-03-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-08 | 2010-08-14 | 2010-08-15 | 2010-08-29 | 2011-05-31 | N/A
67 | 4 | 92-WW-039 | UG | 2010-08-03 | user 67 | N/A | CP-08-61-357 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-17 | 2010-07-13 | 2010-08-14 | 2010-09-04 | 2010-08-22 | N/A
68 | 4 | 92-WW-043 | UG | 2010-08-05 | user 68 | N/A | CP-08-61-364 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-07 | 2010-07-24 | 2011-03-02 | 2010-09-07 | 2010-08-31 | N/A
69 | 4 | 92-WW-092 | UG | 2010-08-04 | user 69 | Req. | CP-08-61-364 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-04-17 | 2010-07-24 | 2010-08-14 | 2010-08-29 | 2010-08-31 | Req.
70 | 4 | 92-WW-093 | UG | 2010-08-04 | user 70 | Req. | CP-10-61-368 | 2010-03-06 | signed | signed | signed | 2010-07-07 | 2010-08-14 | 2010-08-14 | 2010-08-29 | 2010-08-03 | Req.
71 | 5 | 92-WW-096 | UG | 2010-08-04 | user 71 | N/A | CP-09-61-362 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-18 | 2010-06-03 | 2010-08-14 | 2010-09-04 | 2011-05-31 | N/A
72 | 5 | 92-WW-129 | UG | 2010-08-04 | user 72 | N/A | CP-09-61-361 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-04-20 | 2010-06-03 | 2010-08-14 | 2010-09-04 | 2010-08-03 | N/A
73 | 5 | 92-WW-149 | UG | 2010-08-05 | user 73 | N/A | CP-09-61-365 | 2010-02-09 | 2010-05-20 | 2010-05-16 | 2010-05-20 | 2010-07-19 | 2010-06-03 | 2010-09-19 | 2010-08-29 | 2010-07-24 | N/A
74 | 5 | 92-WW-290 | UG | 2010-08-04 | user 74 | N/A | CP-09-61-365 | 2010-02-18 | 2010-05-06 | 2010-04-10 | 2010-05-09 | 2010-07-24 | 2010-06-12 | 2011-06-10 | 2011-03-16 | 2010-08-03 | N/A
75 | 5 | 92-WW-291 | UG | 2010-08-04 | user 75 | N/A | CP-09-61-362 | 2010-02-13 | 2010-09-21 | 2010-04-10 | 2010-09-26 | 2010-07-24 | 2010-08-15 | 2011-06-10 | 2010-06-26 | 2010-08-05 | N/A
76 | 5 | 92-WW-293 | UG | 2010-07-19 | user 76 | N/A | CP-08-61-356 | 2010-02-15 | 2010-08-16 | 2010-04-10 | 2010-08-16 | 2010-07-24 | 2011-04-01 | 2011-06-17 | 2010-06-27 | 2010-08-04 | N/A
77 | 5 | 92-WW-295 | UG | 2010-08-05 | user 77 | N/A | CP-09-61-361 | 2010-02-22 | 2010-04-20 | 2010-04-20 | 2010-04-20 | 2010-09-12 | 2011-04-03 | 2010-08-14 |  | 2010-08-04 | N/A
78 | 5 | 92-WW-297 | UG | 2010-08-05 | user 78 | Req. | CP-09-61-365 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-09-12 | 2010-08-15 | 2010-09-09 | 2011-04-24 | 2010-08-04 | Req.
79 | 5 | 92-WW-367 | UG | 2011-05-31 | user 79 | Req. | CP-08-61-356 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-24 | 2010-08-14 | 2010-09-12 | 2011-04-30 | 2010-08-04 | Req.
80 | 5 | 92-WW-377 | UG | 2010-08-22 | user 80 | Req. | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-24 | 2010-08-08 | 2010-08-18 | 2010-06-07 | 2010-08-05 | Req.
81 | 5 | 92-WW-385 | UG | 2010-08-31 | user 81 | Req. | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-20 |  | 2010-08-31 | 2010-07-22 | 2010-07-19 | Req.
82 | 5 | 92-WW-508 | UG | 2010-08-31 | user 82 | Req. | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-19 | 2010-08-08 | 2010-08-30 | 2010-11-02 | 2010-07-19 | N/A
83 | 5 | 92-WW-509 | UG | 2010-08-03 | user 83 | Req. | CP-08-61-357 | 2010-03-06 | 2010-05-30 | 2010-05-30 |  | 2010-07-19 | 2010-08-08 | 2010-09-07 | 2010-09-06 | 2010-07-19 | Req.
84 | 5 | 92-WW-517 | UG | 2011-05-31 | user 84 | Req. | CP-09-61-365 | 2010-03-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-19 | 2010-08-08 | 2011-02-24 | 2011-06-13 | 2010-08-05 | Req.
85 | 5 | 93-WP-031 | UG | 2010-08-03 | user 85 | Req. | CP-09-61-365 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-19 | 2010-08-14 | 2011-06-10 | 2010-08-18 | 2010-08-05 | Req.
86 | 5 | 93-WP-039 | UG | 2010-07-24 | user 86 | N/A | CP-09-61-365 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-19 | 2010-08-08 | 2010-08-15 | 2010-08-18 | 2011-05-31 | N/A
87 | 5 | 93-WP-040 | UG | 2010-08-03 | user 87 | N/A | CP-08-61-358 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-19 | 2010-08-08 | 2010-08-15 | 2010-08-14 | 2010-08-22 | N/A
88 | 5 | 93-WP-041 | UG | 2010-08-05 | user 88 | N/A | CP-09-61-365 | 2010-03-06 | signed | signed | signed | 2010-07-19 | 2010-08-08 | 2010-08-18 | 2011-02-24 | 2010-08-31 | N/A
89 | 5 | 93-WP-501 | UG | 2010-08-04 | user 89 | N/A | CP-09-61-365 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-19 | 2010-08-08 | 2010-08-18 | 2010-08-18 | 2010-08-31 | N/A
90 | 5 | 93-WP-501A | UG | 2010-08-04 | user 90 | N/A | CP-09-61-365 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-07-19 | 2010-08-08 | 2010-08-18 | 2010-09-06 | 2010-08-03 | N/A
91 | 5 | 93-WP-502 | UG | 2010-08-04 | user 91 | N/A | CP-08-61-359 | 2010-02-09 |  | 2010-05-16 | 2010-05-20 | 2010-07-19 | 2010-09-14 | 2010-09-13 | 2010-09-18 | 2011-05-31 | N/A
92 | 6 | 93-WP-502A | UG | 2010-07-19 | user 92 | Req. | CP-09-61-365 | 2010-02-18 | 2010-05-06 | 2010-04-10 | 2010-05-09 | 2010-07-19 | 2011-05-31 | 2011-05-25 | 2010-08-18 | 2010-08-03 | Req.
93 | 6 | 93-WP-503 | UG | 2010-08-05 | user 93 | Req. | CP-09-61-365 | 2010-02-13 | 2010-09-21 | 2010-04-10 | 2010-09-26 | 2010-07-20 | 2010-08-31 | 2010-08-21 | 2010-08-18 | 2010-07-24 | Req.
94 | 6 | 93-WP-504 | UG | 2010-08-05 | user 94 | Req. | CP-09-61-365 | 2010-02-15 | 2010-08-16 | 2010-04-10 | 2010-08-16 | 2010-07-20 | 2010-08-08 | 2010-08-29 | 2010-08-18 | 2010-08-03 | Req.
95 | 6 | 93-WP-505 | UG | 2011-05-31 | user 95 | Req. | CP-08-61-360 | 2010-02-22 | 2010-04-20 | 2010-04-20 | 2010-04-20 | 2010-07-20 | 2011-01-25 | 2010-08-21 | 2010-08-18 | 2010-08-05 | N/A
96 | 6 | 93-WP-506 | UG | 2010-08-22 | user 96 | Req. | CP-09-61-365 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-22 | 2010-08-14 | 2010-08-29 | 2010-08-29 | 2010-08-04 | N/A
97 | 6 | 93-WP-507 | UG | 2010-08-31 | user 97 | Req. | CP-09-61-365 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-22 | 2010-08-08 | 2010-09-07 | 2010-08-24 | 2010-08-04 | Req.
98 | 6 | 93-WP-508 | UG | 2010-08-31 | user 98 | Req. | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-22 | 2010-09-14 | 2011-01-16 | 2010-08-21 | 2010-08-04 | Req.
99 | 6 | 93-WP-509 | UG | 2010-08-03 | user 99 | Req. | CP-08-61-361 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-20 | 2010-08-29 | 2010-08-21 | 2010-08-24 | 2010-08-04 | Req.
100 | 6 | 93-WP-510 | UG | 2011-05-31 | user 100 | Req. | CP-09-61-365 |  | 2010-05-04 |  | 2010-05-04 | 2010-07-20 | 2010-08-31 | 2011-04-15 | 2010-08-24 | 2010-08-05 | Req.
101 | 6 | 93-WP-511 | UG | 2010-08-03 | user 101 | N/A | CP-09-61-365 | 2010-02-13 | 2010-09-21 | 2010-04-10 | 2010-09-26 | 2010-07-20 | 2010-08-18 | 2010-08-30 | 2010-08-24 | 2010-07-19 | N/A
102 | 6 | 93-WP-512 | UG | 2010-07-24 | user 102 | N/A | CP-09-61-365 | 2010-02-15 | 2010-08-16 | 2010-04-10 | 2010-08-16 | 2010-07-22 | 2010-08-14 | 2010-08-21 | 2010-09-28 | 2010-07-19 | N/A
103 | 6 | 93-WP-513 | UG | 2010-08-03 | user 103 | N/A | CP-08-61-362 | 2010-02-22 | 2010-04-20 | 2010-04-20 | 2010-04-20 | 2010-07-22 | 2011-01-16 | 2010-09-13 | 2010-08-22 | 2010-07-19 | N/A
104 | 6 | 93-WP-514 | UG | 2010-08-05 | user 104 | N/A | CP-09-61-365 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-22 | 2010-08-05 | 2011-06-11 | 2010-09-12 | 2010-08-05 | N/A
105 | 6 | 93-WP-515 | UG | 2010-08-04 | user 105 | N/A | CP-09-61-365 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-22 | 2010-08-14 | 2010-09-01 | 2010-09-08 | 2010-08-05 | N/A
106 | 6 | 93-WP-516 | UG | 2010-08-04 | user 106 | N/A | CP-09-61-365 | 2010-02-01 | 2010-05-04 |  | 2010-05-04 | 2010-07-22 | 2010-08-18 | 2010-08-18 | 2010-08-21 | 2011-05-31 | N/A
107 | 6 | 93-WP-517 | UG | 2010-08-04 | user 107 | Req. | CP-08-61-363 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-04-24 | 2011-01-16 | 2010-09-14 | 2010-09-14 | 2010-08-22 | Req.
108 | 6 | 93-WP-518 | UG | 2010-08-04 | user 108 | Req. | CP-09-61-365 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-04-22 | 2010-09-14 | 2010-08-21 | 2010-09-13 | 2010-08-31 | N/A
109 | 6 | 93-WP-519 | UG | 2010-08-05 | user 109 | Req. | CP-09-61-365 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-22 |  | 2011-01-16 |  | 2010-08-31 | N/A
110 | 6 | 93-WP-520 | UG | 2010-08-04 | user 110 | Req. | CP-09-61-365 | 2010-03-06 | signed | signed | signed | 2010-07-22 | 2010-08-14 | 2010-08-21 | 2010-08-29 | 2010-08-03 | Req.
111 | 6 | 93-WP-521 | UG | 2010-08-04 | user 111 | Req. | CP-08-61-364 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-24 | 2010-08-21 | 2011-01-16 | 2010-08-24 | 2011-05-31 | Req.
112 | 6 | 93-WP-522 | UG | 2010-07-19 | user 112 | Req. | CP-09-61-365 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-12-15 | 2011-04-06 | 2010-08-21 | 2010-08-24 | 2010-08-03 | Req.
113 | 6 | 93-WP-523 | UG | 2010-08-05 | user 113 | Req. | CP-09-61-365 | 2010-02-09 | 2010-05-20 | 2010-05-16 | 2010-05-20 | 2010-07-22 | 2010-08-14 | 2010-08-21 | 2010-08-24 | 2010-07-24 | Req.
114 | 6 | 93-WP-524 | UG | 2010-08-05 | user 114 | N/A | CP-09-61-365 | 2010-02-18 | 2010-05-06 | 2010-04-10 | 2010-05-09 | 2010-07-22 | 2010-08-08 | 2010-08-21 | 2010-09-12 | 2010-08-03 | N/A
115 | 6 | 93-WP-525 | UG | 2011-05-31 | user 115 | N/A | CP-08-61-365 | 2010-02-13 | 2010-09-21 | 2010-04-10 | 2010-09-26 | 2010-07-22 | 2010-09-18 | 2010-08-21 | 2010-09-12 | 2010-08-05 | N/A
116 | 6 | 93-WP-526 | UG | 2010-08-22 | user 116 | N/A | CP-09-61-365 | 2010-02-15 | 2010-08-16 | 2010-04-10 | 2010-08-16 | 2010-07-24 |  | 2010-09-09 | 2010-09-12 | 2010-08-04 | N/A
117 | 6 | 93-WP-527 | UG | 2010-08-31 | user 117 | N/A | CP-09-61-365 | 2010-02-22 | 2010-04-20 | 2010-04-20 | 2010-04-20 | 2010-07-22 | 2011-05-04 | 2010-08-22 |  | 2010-08-04 | N/A
118 | 6 | 93-WP-528 | UG | 2010-08-31 | user 118 | N/A | CP-09-61-365 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-12-06 | 2010-08-24 | 2010-09-06 | 2010-09-17 | 2010-08-04 | N/A
119 | 6 | 93-WP-529 | UG | 2010-08-03 | user 119 | N/A | CP-08-61-366 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-24 | 2010-08-08 | 2010-08-14 | 2010-09-12 | 2010-08-04 | N/A
120 | 6 | 93-WP-530 | UG | 2011-05-31 | user 120 | Req. | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-15 | 2010-12-07 | 2010-09-07 | 2010-09-06 | 2010-08-05 | Req.
121 | 6 | 93-WP-531 | UG | 2010-08-03 | user 121 | Req. | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-15 | 2010-09-07 | 2010-08-14 | 2010-09-01 | 2010-07-19 | N/A
122 | 6 | 93-WP-532 | UG | 2010-07-24 | user 122 | Req. | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-10-03 | 2010-08-14 | 2010-08-14 | 2010-08-31 | 2010-07-19 | Req.
123 | 7 | 93-WP-533 | UG | 2010-08-03 | user 123 | Req. | CP-08-61-367 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-24 | 2010-10-04 | 2010-09-06 | 2010-08-29 | 2010-07-19 | Req.
124 | 7 | 93-WP-534 | UG | 2010-08-05 | user 124 | Req. | CP-09-61-365 | 2010-04-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-04-20 | 2010-08-08 | 2010-09-06 | 2010-08-30 | 2010-08-05 | Req.
125 | 7 | 93-WP-535 | UG | 2010-08-04 | user 125 | N/A | CP-09-61-365 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-04-20 | 2010-08-15 | 2010-08-24 | 2010-09-14 | 2010-08-05 | N/A
126 | 7 | 93-WP-536 | UG | 2010-08-04 | user 126 | N/A | CP-09-61-365 | 2010-03-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-04-19 | 2010-08-14 | 2010-08-16 | 2010-09-14 | 2011-05-31 | N/A
127 | 7 | 93-WP-537 | UG | 2010-08-04 | user 127 | N/A | CP-08-61-368 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-04-18 | 2010-08-14 | 2011-04-26 | 2010-09-13 | 2010-08-22 | N/A
128 | 7 | 93-WP-538 | UG | 2010-08-04 | user 128 | N/A | CP-09-61-365 | 2010-03-07 | 2010-05-29 |  | 2010-05-29 | 2010-04-24 | 2010-08-14 | 2011-05-22 | 2010-07-19 | 2010-08-31 | N/A
129 | 7 | 93-WP-539 | UG | 2010-08-05 | user 129 | N/A | CP-09-61-365 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-04-24 | 2010-08-14 | 2010-08-21 | 2010-07-19 | 2010-08-31 | N/A
130 | 7 | 93-WP-540 | UG | 2010-08-04 | user 130 | N/A | CP-09-61-365 | 2010-03-06 |  |  |  | 2010-04-24 | 2010-09-01 | 2010-08-18 | 2010-07-19 | 2010-08-03 | N/A
131 | 7 | 93-WP-541 | UG | 2010-08-04 | user 131 | N/A | CP-08-61-369 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-05-03 | 2010-08-14 | 2010-08-18 | 2010-08-05 | 2011-05-31 | N/A
132 | 7 | 93-WP-542 | UG | 2010-07-24 | user 132 | Req. | CP-09-61-365 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-05-02 | 2010-08-15 | 2010-08-18 | 2010-08-05 | 2010-08-03 | Req.
133 | 7 | 93-WP-543 | UG | 2010-08-14 | user 133 | Req. | CP-09-61-365 | 2010-02-09 | 2010-05-20 | 2010-05-16 | 2010-05-20 | 2010-07-24 | 2010-08-14 | 2010-08-18 | 2011-05-31 | 2010-07-24 | Req.
134 | 7 | 93-WP-544 | UG | 2010-08-18 | user 134 | Req. | CP-09-61-365 | 2010-02-18 | 2010-05-06 | 2010-04-10 | 2010-05-09 | 2010-07-13 | 2010-08-18 | 2010-08-18 | 2010-08-22 | 2010-08-03 | Req.
135 | 7 | 93-WP-545 | UG | 2010-08-14 | user 135 | Req. | CP-08-61-370 | 2010-02-13 | 2010-09-21 | 2010-04-10 | 2010-09-26 | 2010-07-24 | 2010-08-14 | 2010-08-18 | 2010-08-31 | 2010-08-05 | N/A
136 | 7 | 93-WP-546 | UG | 2010-08-14 | user 136 | Req. | CP-09-61-365 | 2010-02-15 | 2010-08-16 | 2010-04-10 | 2010-08-16 | 2010-08-03 | 2010-08-14 | 2010-08-21 | 2010-08-31 | 2010-08-04 | N/A
137 | 7 | 93-WP-547 | UG | 2010-08-14 | user 137 | Req. | CP-09-61-365 | 2010-02-22 |  | 2010-04-20 | 2010-04-20 | 2010-08-04 | 2010-08-14 |  | 2010-08-03 | 2010-08-04 | Req.
138 | 7 | 93-WP-548 | UG | 2010-08-15 | user 138 | N/A | CP-09-61-365 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-07-19 | 2010-08-15 | 2010-08-22 | 2011-05-31 | 2010-08-04 | N/A
139 | 7 | 93-WP-549 | UG | 2010-08-08 | user 139 | N/A | CP-08-61-371 | 2010-02-22 | 2010-03-30 | 2010-03-30 | 2010-03-30 | 2010-02-04 | 2010-08-08 | 2010-08-22 | 2010-08-03 | 2010-08-04 | N/A
140 | 7 | 93-WP-550 | UG | 2010-08-08 | user 140 | N/A | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-02-04 | 2010-08-08 | 2011-01-16 | 2010-07-24 | 2010-08-05 | N/A
141 | 7 | 93-WP-551 | UG | 2010-08-08 | user 141 | N/A | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-08-03 | 2010-08-08 | 2010-08-14 | 2010-08-03 | 2010-07-19 | N/A
142 | 7 | 93-WP-552 | UG | 2010-08-15 | user 142 | N/A | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-08-04 | 2010-08-15 | 2010-08-31 | 2010-08-05 | 2010-07-19 | N/A
143 | 7 | 93-WP-553 | UG | 2010-08-21 | user 143 | N/A | CP-08-61-372 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-08-04 | 2010-08-21 | 2010-08-31 | 2010-08-04 | 2010-07-19 | N/A
144 | 7 | 93-WP-554 | UG | 2011-03-10 | user 144 | N/A | CP-09-61-365 | 2010-02-01 | 2010-05-04 | 2010-05-04 | 2010-05-04 | 2010-07-24 | 2011-03-10 | 2010-08-31 | 2010-08-04 | 2010-08-05 | N/A
145 | 7 | 93-WP-555 | UG | 2010-08-08 | user 145 | Req. | CP-09-61-365 | 2010-04-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-17 | 2010-08-08 | 2010-08-21 | 2010-08-04 | 2010-08-05 | Req.
146 | 7 | 93-WP-556 | UG | 2010-08-14 | user 146 | Req. | CP-09-61-365 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-17 | 2010-09-06 | 2010-08-21 | 2010-08-04 | 2011-05-31 | Req.
147 | 7 | 93-WP-557 | UG | 2010-08-18 | user 147 | Req. | CP-08-61-373 | 2010-03-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-17 | 2010-09-06 | 2010-08-21 | 2010-08-05 | 2010-08-22 | Req.
148 | 7 | 93-WP-558 | UG | 2010-08-14 | user 148 | Req. | CP-09-61-365 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-17 | 2010-07-19 | 2010-08-21 | 2010-07-19 | 2010-08-31 | N/A
149 | 7 | 93-WP-559 | UG | 2010-08-14 | user 149 | Req. | CP-09-61-365 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-17 | 2010-07-19 | 2010-08-21 | 2010-07-19 | 2010-08-31 | Req.
150 | 7 | 93-WP-560 | UG | 2010-08-14 | user 150 | N/A | CP-09-61-365 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-17 | 2010-07-19 | 2010-08-21 | 2010-07-19 | 2010-08-03 | N/A
151 | 7 | 93-WP-561 | UG | 2010-08-15 | user 151 | N/A | CP-08-61-374 | 2010-03-06 | signed |  |  | 2010-07-17 | 2010-08-05 | 2010-08-18 | 2010-08-05 | 2011-05-31 | N/A
152 | 7 | 93-WP-562 | UG | 2010-08-08 | user 152 | N/A | CP-09-61-365 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-17 | 2010-08-05 | 2010-08-18 | 2010-08-05 | 2010-08-03 | N/A
153 | 7 | 93-WP-563 | UG | 2010-08-08 | user 153 | N/A | CP-09-61-365 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-07-17 | 2011-05-31 | 2010-08-22 | 2011-05-31 | 2010-07-24 | N/A
154 | 7 | 93-WP-564 | UG | 2010-08-08 | user 154 | N/A | CP-09-61-365 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-07-17 | 2010-08-22 | 2010-08-22 | 2010-08-22 | 2010-08-03 | N/A
155 | 7 | 93-WP-565 | UG | 2010-08-15 | user 155 | N/A | CP-08-61-375 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-07-17 | 2010-08-31 | 2010-08-18 | 2010-08-31 | 2010-08-05 | N/A
156 | 7 | 93-WP-566 | UG | 2010-08-21 | user 156 | N/A | CP-08-61-357 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-07-17 | 2010-08-31 | 2010-08-18 | 2010-08-31 | 2010-08-04 | N/A
157 | 7 | 93-WP-567 | UG | 2011-03-10 | user 157 | N/A | CP-09-61-365 | 2010-04-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-06-28 | 2010-08-03 | 2010-08-24 | 2010-08-03 | 2010-08-04 | N/A
158 | 7 | 93-WP-568 | UG | 2010-08-08 | user 158 | Req. | CP-09-61-365 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-06-28 | 2011-05-31 | 2010-08-24 | 2011-05-31 | 2010-08-04 | Req.
159 | 7 | 93-WP-569 | UG | 2010-08-14 | user 159 | Req. | CP-09-61-365 | 2010-03-07 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-06-28 | 2010-08-03 | 2010-08-24 | 2010-08-03 | 2010-08-04 | Req.
160 | 7 | 93-WP-570 | UG | 2010-08-18 | user 160 | Req. | CP-08-61-358 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-18 | 2010-07-24 | 2010-08-24 | 2010-07-24 | 2010-08-05 | N/A
161 | 7 | 93-WP-571 | UG | 2010-08-14 | user 161 | Req. | CP-09-61-365 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-18 | 2010-08-03 | 2010-08-21 | 2010-08-03 | 2010-08-06 | N/A
162 | 7 | 93-WP-572 | UG | 2010-08-14 | user 162 | Req. | CP-09-61-365 | 2010-03-07 | 2010-05-29 | 2010-05-28 | 2010-05-29 | 2010-07-18 | 2010-08-05 | 2010-08-21 | 2010-08-05 | 2010-08-07 | Req.
163 | 7 | 93-WP-573 | UG | 2010-08-14 | user 163 | Req. | CP-09-61-365 | 2010-03-06 | signed | signed |  |  |  |  | 2010-08-04 | 2010-08-08 | Req.
164 | 7 | 93-WP-574 | UG | 2010-08-15 | user 164 | Req. | CP-08-61-359 | 2010-03-06 | 2010-05-30 | 2010-05-30 | 2010-05-30 | 2010-07-18 | 2010-08-04 | 2010-08-15 | 2010-08-04 | 2010-08-09 | Req.
165 | 7 | 93-WP-575 | UG | 2010-08-08 | user 165 | N/A | CP-09-61-365 | 2010-08-24 | 2010-09-10 | 2010-09-13 | 2010-09-13 | 2010-07-18 | 2010-08-04 | 2010-08-21 | 2010-08-04 | 2010-08-10 | N/A
166 | 7 | 93-WP-576 | UG | 2010-08-08 | user 166 | N/A | CP-09-61-365 | 2010-02-09 | 2010-05-20 | 2010-05-16 | 2010-05-20 | 2010-07-18 | 2010-08-04 | 2010-08-21 | 2010-08-04 | 2010-08-11 | N/A
167 | 7 | 93-WP-577 | UG | 2010-08-08 | user 167 | N/A | CP-09-61-365 | 2010-02-09 | 2010-05-20 | 2010-05-16 | 2010-05-20 | 2010-07-13 | 2010-08-05 | 2011-01-10 | 2010-08-05 | 2010-08-12 | N/A
168 | 7 | 93-WP-578 | AG | 2010-08-15 | user 168 | N/A | CP-08-61-360 | 2010-02-09 | 2010-05-20 | 2010-05-16 | 2010-05-20 | 2010-07-08 | 2010-08-06 | 2010-08-18 | 2010-08-05 | 2010-08-13 | N/A

## Summary AG
AG |  |  |  | Summary of Test Packages ( AG )
| Priority | Test Pack Punching CMC | Test Pack Punching EPM MECH | Test Pack Punching EPM ENGG | Test Pack Punching COMPANY | Test Pack Preparation EPM Engineering Approval
| 1 | 0 | 0 | 0 | 0 | 0
| 1.1 | 4 | 5 | 3 | 4 | 4
| 1.2 | 2 | 2 | 2 | 2 | 2
| 2 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0 | 0 | 0 | 0
| 3.1 | 0 | 0 | 0 | 0 | 0
| 3.2 | 0 | 0 | 0 | 0 | 0
| 3.3 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0 | 0 | 0 | 0
| 5 | 0 | 0 | 0 | 0 | 0
| 6 | 0 | 0 | 0 | 0 | 0
| 7 | 1 | 1 | 1 | 1 | 1
| Total | 7 | 8 | 6 | 7 | 7
السلام عليكم
الارقام اللى موجوده فى الصف الاول دى انا حاسبها يدوى باستخدام الفلتر
برجاء عمل معادله تجيب نفس البيانات من الصفحه الرئيسيه
الفكره هى ان كل عمود من الاعمده دى موجود فى الصفحه الرئيسيه و مطلوب يجمع عدد الخلايا اللى فيها
تاريخ مقابل كل سطر بريورتى
مع الاخذ فى الاعتبار الشرط فى العمود ( دى ) لازم يكون ( اى جى )
بارك الله فيكم مقدما

## Summary UG (hidden)
Summary of Test Packages ( UG )
Priority | Test Packages Assigned by Engg. | Total Test Packages Submitted | Test Packages Signed by Engg. | Test Pack Punching CMC | Test Pack Punching EPM MECH | Test Pack Punching EPM ENGG | Test Pack Punching COMPANY | Test Pack Preparation EPM Engineering Approval
1
1.1
1.2
2
3
3.1
3.2
3.3
4
5
6
7
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0