## JZN
Job WorkOrder | PO Number | Contractor Name | Planned Start Date | Planned End Date | Exchange | Project Type | Sub Project | District Status | WO Objective | Job AsBuilt Cost | InvoicedFNI | Control Remarks | District Remarks | STC Inspector | RFS Date | Received By Contractor | Design Cost
1027000239 | 75745 | Mohemmed Bin Gerboo EST. | 2010-05-01 | 2010-05-15 | SBYA | cable replacement | Cable Replacement | completed | 2011 objective not in the design master sheet | 0 |  |  | as per appved by Ali on 30-10-2010 with MOT project | ali m. gobain | 2010-11-02 | 2010-11-01 | 0
1027000282 | 75745 | Mohemmed Bin Gerboo EST. | 2010-05-01 | 2010-06-15 | SBYA | cable replacement | Cable Replacement | completed | 2011 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | ali m. gobain | 2011-08-06 | 2010-10-23 | 0
1027000286 | 75745 | Mohemmed Bin Gerboo EST. | 2010-05-01 | 2010-05-15 | SBYA | cable replacement | Cable Replacement | completed | 2011 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | ali m. gobain | 2011-08-06 | 2010-10-23 | 0
1127000289 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-20 | 2011-08-04 | SBYA | cable replacement | Cable Replacement 2011 | completed | 2011 objective design issued | 1631533.9952 | DM In Progress |  |  | agobain | 2013-03-20 | 2011-06-13 | 2499030.272
1127000536 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-11 | 2012-02-17 | JIZA | cable replacement | Cable Replacement 2011 | completed | 2012 objective not in the design master sheet | 46471.54 | DM In Progress |  |  | lscarboz | 2012-01-14 | 2011-12-27 | 24043.2
1127000347 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-18 | 2011-08-31 | SBYA | cable replacement | Cable Replacement 2011 | completed | 2011 objective design issued | 21343.42 | Yes |  |  | ali gobain | 2012-03-20 | 2011-07-17 | 20255.88
1127000183 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-09 | 2011-08-19 | SHUQ | cable replacement | Cable Replacement 2011 | completed | 2011 objective design issued | 142354.79 | Yes |  |  | jomeel g. antonio | 2012-03-24 | 2011-07-09 | 172180.16
1127000265 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-12 | 2011-07-20 | ABAR | cable replacement | Cable Replacement 2011 | completed | 2011 objective design issued |  |  |  | MOT project Customer Job Pending with MOT to locate the new center of the new road | ali gobain | 2013-01-01 | 2011-06-01 | 0
1127000045 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-03-01 | 2011-03-31 | TWAL | cable replacement | Cable Replacement 2011 | completed | 2011 objective design issued | 51219 | Yes |  |  | ernesto e. lai | 2011-05-17 | 2011-02-26 | 53848
1127000025 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-27 | 2011-06-10 | JIZA | cable replacement | Cable Replacement 2011 | completed | 2011 objective design issued | 7813.5 | Yes |  |  | lari carboz | 2011-08-15 | 2011-04-27 | 7585.5
1127000047 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-03-01 | 2011-03-31 | SBYA | cable replacement | Cable Replacement 2011 | completed | 2011 objective design issued | 0 |  |  | Customer Job | alfies benjamin | 2013-01-01 | 2011-02-28 | 0
0927000260 | 75745 | Mohemmed Bin Gerboo EST. | 2011-12-11 | 2012-01-25 | SBYA | cable replacement | Cable Replacement 2011 | cancelled | 2012 objective not in the design master sheet |  |  |  | Redesign | ali m. gobain |  | 2011-12-11 | 0
1127000403 | 75745 | Mohemmed Bin Gerboo EST. | 2011-10-12 | 2011-11-25 | SBYA | cable replacement | Cable Replacement 2011 | in progress | 2011 objective design issued |  |  |  | SBYA TO QOZ Pending with MOT to locate the new center of the new road | ali gobain |  | 2011-10-13 | 0
1127000188 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-03 | 2011-06-17 | JIZA | cable replacement | Cable Replacement 2011 | cancelled | 2011 objective design issued |  |  |  | waiting cost approval from baladyah to start implementation | lari carboz |  | 2011-05-03 | 0
1127000201 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-03 | 2011-06-17 | JIZA | cable replacement | Cable Replacement 2011 | cancelled | 2011 objective design issued |  |  |  | waiting cost approval from baladyah to start implementation | lari carboz |  | 2011-05-03 | 0
1227W00007 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-12-01 | 2012-12-31 | SLHD | cable replacement | Cable Replacement 2013 | completed | 2013 objective design issued | 7551.36 | CM In Progress |  | DETCON Saudia Co. (Data_SAD) | elai | 2013-01-01 | 2012-12-01 | 6912
1227000006 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-09-17 | 2012-10-24 | KWBH | cable replacement | Cable Replacement 2013 | completed | 2013 objective design issued | 275909.8468 | Yes |  |  | ernesto e. lai | 2012-04-04 | 2012-01-08 | 353584.02
1027000509 |  |  | 2011-06-29 | 2011-08-02 | JIZA | copper cabinet | Copper Cabinet 2011 | cancelled | 2011 objective design issued |  |  | job wo cancelled | Cancelled by planning | lari carboz |  | 2011-06-29 | 19666
1027000503 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-12-15 | 2011-02-15 | JIZA | copper cabinet | Copper Cabinet 2011 | completed | 2011 objective design issued | 3189.2 | Yes |  |  | lari carboz | 2011-01-01 | 2010-12-13 | 3002.9
0827000546 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-11-10 | 2009-04-06 | JIZA | copper cabinet | Copper Cabinet 2011 | completed | 2011 objective design issued | 3457.3 | Yes |  | Email From: Abdulmoti A. Dahlawi Sent: Monday, February 23, 2009 11:02 | lari carboz | 2009-04-06 | 2008-11-10 | 4097.3
1327000711 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-18 | 2014-01-18 | JIZA | copper cabinet | Copper Cabinet 2013 | in progress | 2013 objective design issued |  |  | need scope of work |  | lari carboz |  | 2013-12-18 | 1991.38
1327000730 |  |  |  |  | DARB | relocation | Customer's Job | not assigned | 2013 objective design issued |  |  |  | DETCON Saudia Co. (Data_SAD) | jomeel g. antonio |  | 2014-01-16 | 1789284.24
1327000023 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-25 | 2013-06-30 | SBYA | relocation | Customer's Job | completed | 2013 objective design issued |  |  | zero job design cost | Done | ali gobain | 2014-01-14 | 2013-05-25 | 0
1327000029 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-25 | 2013-06-30 | SBYA | relocation | Customer's Job | completed | 2013 objective design issued |  |  | zero job design cost | Done | ali gobain | 2014-01-14 | 2013-05-25 | 0
1327000728 |  |  |  |  | SBYA | relocation | Customer's Job | not assigned | 2013 objective design issued |  |  |  | DETCON Saudia Co. (Data_SAD) |  |  |  | 879912.04
1327000729 |  |  |  |  | SBYA | relocation | Customer's Job | not assigned | 2013 objective design issued |  |  |  | Mohemmed Bin Gerboo EST. |  |  |  | 572028.84
1427000003 |  |  |  |  | SBYA | relocation | Customer's Job | not assigned | 2013 objective design issued | [7 empty] | 9546.1
1327000482 | 80206 | ISSA AL ISSA FOR contracting EST. | 2013-10-02 | 2013-11-14 | JIZA | cable replacement | Disaster Recovery | completed | 2013 objective design issued | 0 |  |  |  | laary | 2014-01-06 | 2013-10-02 | 28039.34
1327000399 | 80206 | ISSA AL ISSA FOR contracting EST. | 2013-10-03 | 2013-11-14 | ABAR | cable replacement | Disaster Recovery | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-10-03 | 31069.44
1127000215 | 76677 | Mohemmed Bin Gerboo EST. | 2011-06-04 | 2011-07-15 | JIZA | key account | EBU-EMRG-AD11 | completed | 2011 objective design issued | 113046.15 | DM In Progress | pu price adjustment with bat/pcc |  | lscarboz | 2011-10-01 | 2011-06-04 | 83167.75
1127000283 | 76677 | Mohemmed Bin Gerboo EST. | 2011-06-13 | 2011-07-13 | JIZA | key account | EBU-EMRG-AD11 | completed | 2011 objective design issued | 33666.84 | DM In Progress |  |  | lscarboz | 2011-09-01 | 2011-06-13 | 22362.7
1127000361 | 75745 | Mohemmed Bin Gerboo EST. | 2011-08-15 | 2011-09-29 | JIZA | key account | EBU-EMRG-AD11 | completed | 2011 objective design issued | 130242.68 | Yes |  |  | lari carboz | 2011-10-01 | 2011-08-15 | 148000
1127000227 | 76677 | Mohemmed Bin Gerboo EST. | 2011-06-04 | 2011-07-15 | JIZA | key account | EBU-EMRG-AD11 | completed | 2011 objective design issued | 138223.92 | Yes | pu price adjustment with bat/pcc |  | lari carboz | 2011-10-01 | 2011-07-15 | 101522.72
1127000221 | 76677 | Mohemmed Bin Gerboo EST. | 2011-06-04 | 2011-07-15 | JIZA | key account | EBU-EMRG-AD11 | completed | 2011 objective design issued | 97114.42 | Yes | pu price adjustment with bat/pcc |  | lari carboz | 2011-10-01 | 2011-06-04 | 62318.6
1127000544 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-11-27 | 2012-01-10 | ABAR | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 18196.572 | PM In Progress |  |  | abenjamin | 2012-04-21 | 2011-11-26 | 20524.4
1127000547 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-26 | 2012-04-10 | SBYA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 15573.51 | CM In Progress |  |  | agobain | 2012-07-07 | 2012-02-26 | 16898.31
1127000565 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-26 | 2012-04-10 | JIZA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 7847.92 | DM In Progress |  |  | lscarboz | 2012-06-12 | 2012-02-26 | 7972.72
1127000562 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-26 | 2012-04-10 | JIZA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 25012.53 |  |  |  | lscarboz | 2012-06-12 | 2012-02-26 | 28539.41
1127000543 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-26 | 2012-04-10 | JIZA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 21205.804 | DM In Progress |  |  | lscarboz | 2012-07-07 | 2012-02-26 | 24504.16
1127000563 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-05 | 2012-04-18 | JIZA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 28012.056 | CM In Progress |  | customer issue | lscarboz | 2013-06-24 | 2012-03-05 | 28050.4
1127000567 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-05 | 2012-04-18 | JIZA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 20981.712 | DM In Progress |  |  | lscarboz | 2012-07-07 | 2012-03-05 | 21771.16
1127000577 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-12 | 2012-03-28 | JIZA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 8877.25 | CM In Progress |  |  | lscarboz | 2012-09-07 | 2012-02-12 | 7871.26
1227000048 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-29 | 2012-04-12 | ABAR | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 3233.25 | DM In Progress |  | key account | abenjamin | 2012-07-31 | 2012-02-19 | 3145.9
1127000335 | 76677 | Mohemmed Bin Gerboo EST. | 2011-07-09 | 2011-08-09 | JIZA | key account | Ethernet Switch | completed | 2011 objective design issued | 17755.7 | DM In Progress |  | issued to ALJARBOO | lscarboz | 2011-09-10 | 2011-07-04 | 15112.02
1127000548 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-11-27 | 2012-01-10 | SBYA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 9407.45 | Yes |  |  | jomeel g. antonio | 2012-04-09 | 2011-11-26 | 23599.6
1127000545 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-11-27 | 2012-01-10 | SBYA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 81134.3 | Yes |  |  | ali gobain | 2012-04-09 | 2011-11-26 | 98579.88
1127000546 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-11-27 | 2012-01-10 | JIZA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 33778.53 | Yes |  |  | laary | 2012-03-18 | 2011-11-26 | 33338.8
1127000269 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-18 | 2011-07-18 | JIZA | key account | Ethernet Switch | completed | 2011 objective design issued | 43999.28 | Yes |  |  | lari carboz | 2011-10-01 | 2011-06-12 | 49546.16
1127000620 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-01-08 | 2012-02-15 | SBYA | key account | Ethernet Switch | completed | 2012 objective not in the design master sheet | 1401.6 | Yes |  |  | ali gobain | 2012-02-21 | 2012-01-08 | 1401.6
1027000195 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | key account | Ethernet Switch | completed | 2010 objective design issued | 120981.95 | Yes |  |  | lari carboz | 2011-03-20 | 2010-06-07 | 141515.6
1027000208 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | key account | Ethernet Switch | completed | 2010 objective design issued | 63653.4 | Yes |  |  | lari carboz | 2010-10-03 | 2010-06-07 | 31445
1027000209 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | key account | Ethernet Switch | completed | 2010 objective design issued | 53137.6 | Yes |  |  | lari carboz | 2010-10-03 | 2010-06-07 | 53310.8
1027000378 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-02 | 2010-12-31 | ABAR | key account | Ethernet Switch | completed | 2010 objective design issued | 12663.2 | Yes |  | LAND ARMY FOC | alfies benjamin | 2011-03-09 | 2010-10-02 | 5613
1127000549 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-01 | 2013-06-30 | JIZA | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 104308.56 | PCC In Progress |  | Done Jizan University Girls building | lari carboz | 2013-08-08 | 2013-05-20 | 110597.08
1127000564 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-01 | 2013-06-30 | JIZA | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 295364.301 | PCC In Progress |  | Done Jizan University - Community College for Girls - | lari carboz | 2013-08-10 | 2012-06-26 | 289503.288
1127000569 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-01 | 2013-06-30 | JIZA | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 136148.948 | PCC In Progress |  | Done (Jizan University - FACULTY OF HEALTH and SCIENCES) | lari carboz | 2013-08-17 | 2012-06-26 | 137562.128
1127000594 | 80388 | Mohemmed Bin Gerboo EST. | 2013-05-14 | 2013-06-28 | JIZA | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 329431.52 |  |  | Technical Education and Vocational - Jizan | lari carboz | 2013-08-01 | 2012-06-26 | 303037.44
1127000590 | 80388 | Mohemmed Bin Gerboo EST. | 2013-05-14 | 2013-06-28 | JIZA | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 34682.66 |  |  | Technical Education and Vocational - Jizan | lari carboz | 2013-08-01 | 2012-03-05 | 32325.1
1227000265 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | DMAD | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 0 |  |  | Done | alfies benjamin | 2013-12-08 | 2013-05-19 | 68080.04
1227000249 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-05-06 | 2013-06-14 | BAYS | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 15540.988 |  |  | SAMIS-CIP (Baysh) | jomeel g. antonio | 2013-09-18 | 2013-05-06 | 91227.14
1227000207 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-05-07 | 2013-06-16 | BAYS | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 0 |  |  | Done | jomeel g. antonio | 2013-12-04 | 2013-05-07 | 33507.17
1227000206 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-05-06 | 2013-06-14 | ABAR | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 0 |  |  | Completed LAND FORCES - JIZAN | alfies benjamin | 2013-09-30 | 2013-05-06 | 70194
1227000189 | 80230 | DETCON Saudia Co. (Data_SAD) | 2012-09-12 | 2012-10-22 | BAYS | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 76024.28 | Con/Insp In Progress |  | DETCON Saudia Co. (Data_SAD) | jomeel g. antonio | 2013-01-07 | 2012-08-12 | 129122.4
1227000188 | 80230 | DETCON Saudia Co. (Data_SAD) | 2012-09-12 | 2012-10-22 | BAYS | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 772488.96 | Con/Insp In Progress |  | DETCON Saudia Co. (Data_SAD) | jomeel g. antonio | 2013-01-07 | 2012-09-12 | 804152.8
1227000145 | 80230 | DETCON Saudia Co. (Data_SAD) | 2012-09-17 | 2012-10-24 | DAMD | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2012-09-24 | 2012-09-17 | 44213.156
1227000152 | 80230 | DETCON Saudia Co. (Data_SAD) | 2012-05-27 | 2012-06-30 | SBYA | key account | Ethernet Switch | completed | 2013 objective design issued - ho | 19290.04 |  |  |  | ali gobain | 2013-01-07 | 2012-05-27 | 59952.336
1327000210 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-15 | 2013-05-30 | SBYA | key account | Ethernet Switch | completed | 2013 objective design issued | 0 |  |  | MINISTRY OF HEALTH - DAER HOSPITAL Completed | ali gobain | 2013-09-03 | 2013-04-15 | 1184
1327000199 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-15 | 2013-05-30 | DARB | key account | Ethernet Switch | completed | 2013 objective design issued | 23247.58 |  |  | Darb Hospital | jomeel g. antonio | 2013-07-14 | 2013-04-15 | 34679.12
1327000291 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | BAYS | key account | Ethernet Switch | completed | 2013 objective design issued | 47197.94 |  |  |  | jomeel g. antonio | 2013-09-18 | 2013-05-27 | 68983.76
1327000226 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-05 | 2013-06-16 | BAYS | key account | Ethernet Switch | completed | 2013 objective design issued | 73530.4 |  |  | Done Vocational Training Institute | jomeel g. antonio | 2013-10-03 | 2013-05-05 | 75375.62
1127000374 | 80012 | DETCON Saudia Co. (Data_SAD) | 2011-08-08 | 2011-09-22 | JIZA | key account | Ethernet Switch | completed | 2011 objective design issued | 183790.852 | Con/Insp In Progress |  |  | lari carboz | 2011-12-12 | 2011-08-08 | 178574.4
1327000722 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-12-26 | 2013-12-26 | JIZA | key account | Ethernet Switch | completed | 2013 objective design issued | 0 |  |  | Done | laary | 2013-12-26 | 2013-12-16 | 29974.16
1027000406 | OSP12006 | Jeel AlFursan Est. FOR TRADING &CO | 2010-10-16 | 2010-12-31 | JIZA | key account | Ethernet Switch | completed | 2010 objective design issued | 59828.8 |  |  |  | lari carboz | 2010-12-18 | 2010-10-16 | 17043.6
1127000078 | OSP12006 | Jeel AlFursan Est. FOR TRADING &CO | 2011-03-01 | 2011-03-31 | DAMD | key account | Ethernet Switch | completed | 2011 objective design issued | 0 |  |  |  | alfies benjamin | 2011-04-16 | 2011-02-23 | 81662
1027000022 | 73822 | Middle Sea for Telecommunication Establishment | 2010-02-04 | 2010-03-21 | JIZA | key account | Ethernet Switch | completed | 2010 objective design issued | 5460.8 | Yes |  |  | lari carboz | 2010-03-28 | 2010-02-20 | 53738.3
1027000404 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-10-16 | 2010-12-31 | JIZA | key account | Ethernet Switch | completed | 2010 objective design issued | 50733.35 | Yes |  |  | lari carboz | 2010-12-18 | 2010-10-16 | 37432
1027000491 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-12-15 | 2011-02-15 | JIZA | key account | Ethernet Switch | completed | 2011 objective design issued | 42160.8 | Yes |  |  | lari carboz | 2011-01-05 | 2010-12-13 | 45588.1
0927000669 | 73803 | Mohemmed Bin Gerboo EST. | 2009-12-08 | 2009-12-20 | JIZA | key account | Ethernet Switch | completed | 2010 objective design issued | 51054.09 | Yes |  | Email From: Abdulmoti A. Dahlawi Sent to Aljarboo | lari carboz | 2009-12-08 | 2009-12-08 | 51979.74
1327000479 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-10-08 | 2013-11-21 | SBYA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 810.3 | CM In Progress |  |  | agobain | 2013-11-26 | 2013-10-07 | 810.3
1327000434 |  | Mohemmed Bin Gerboo EST. | 2013-08-21 | 2013-10-02 | SLHD | fttm | Fiber PBU 2013 | cancelled | 2013 objective design issued - lead |  |  |  | ZJZ549-Not added in NPTS cancelled :Out of scope | ernesto e. lai |  | 2013-08-21 | 59322
1327000520 |  | Mohemmed Bin Gerboo EST. | 2013-10-28 | 2013-10-31 | SLHD | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead |  |  |  | Done-Job Implemented by Mohemmed Bin Gerboo Est. | ernesto e. lai | 2013-12-23 | 2013-10-15 | 831.02
1327000521 |  | Mohemmed Bin Gerboo EST. | 2013-10-28 | 2013-10-31 | ABAR | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead |  |  |  | Done-Job implemented by Mohemmed Bin Gerboo Est. | alfies benjamin | 2013-12-23 | 2013-10-15 | 837.02
1327000664 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-12-01 | 2014-01-15 | SBYA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | agobain | 2014-01-14 | 2013-11-21 | 28182.75
1327000653 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-12-01 | 2014-01-15 | SBYA | fttm | Fiber PBU 2013 | in progress | 2013 objective design issued - lead | 0 |  |  |  | agobain |  | 2013-11-21 | 39247.67
1327000656 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-12-01 | 2014-01-15 | SBYA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | agobain | 2013-12-24 | 2013-11-21 | 74659.15
1327000658 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-12-01 | 2014-01-15 | SBYA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | agobain | 2013-12-24 | 2013-11-21 | 23812.88
1327000700 | 81127 | Majd AlJanoub for general Contracting Ltd. | 2013-12-01 | 2014-01-15 | SLHD | fttm | Fiber PBU 2013 | in progress | 2013 objective design issued - lead | 0 |  |  |  | ernesto e. lai |  | 2013-12-01 | 96207.31
1327000522 | 81127 | Majd AlJanoub for general Contracting Ltd. | 2013-11-03 | 2013-12-17 | JIZA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | lari carboz | 2014-01-01 | 2013-10-27 | 94910.06
1327000674 | 81127 | Majd AlJanoub for general Contracting Ltd. | 2013-12-01 | 2014-01-14 | SLHD | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | ernesto e. lai | 2014-01-26 | 2013-11-21 | 61672.74
1327000527 | 81127 | Majd AlJanoub for general Contracting Ltd. | 2013-11-20 | 2013-12-31 | JIZA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | lari carboz | 2013-12-19 | 2013-11-20 | 11157.995
1327000540 | 81127 | Majd AlJanoub for general Contracting Ltd. | 2013-11-20 | 2013-12-31 | 703-00-000 | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | lari carboz | 2013-12-10 | 2013-11-19 | 10559.82
1327000649 | 81128 | DETCON Saudia Co. (Data_SAD) | 2013-11-24 | 2014-01-07 | SBYA | fttm | Fiber PBU 2013 | in progress | 2013 objective design issued - lead | 0 |  |  |  | agobain |  | 2013-11-21 | 36908.24
1327000523 | 81128 | DETCON Saudia Co. (Data_SAD) | 2013-10-27 | 2013-11-27 | SBYA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | agobain | 2013-11-12 | 2013-10-27 | 3399.04
1327000725 | 81128 | DETCON Saudia Co. (Data_SAD) | 2014-01-12 | 2014-02-26 | ABAR | fttm | Fiber PBU 2013 | in progress | 2013 objective design issued - lead | 0 |  |  |  | alfies benjamin |  | 2014-01-08 | 14186.81
1327000278 | 79722 | Mohemmed Bin Gerboo EST. | 2013-05-29 | 2013-06-30 | BAYS | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | jomeel g. antonio | 2013-09-07 | 2013-05-29 | 2528
1327000321 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-16 | 2013-08-29 | 703-00-000 | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 41754.66 |  |  | Completed | lari carboz | 2013-09-30 | 2013-07-16 | 39309.6
1327000324 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-16 | 2013-08-29 | SLHD | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Completed | ernesto e. lai | 2013-09-30 | 2013-07-16 | 198238.6
1327000203 | 79722 | Mohemmed Bin Gerboo EST. | 2013-05-29 | 2013-06-30 | ABAR | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 628 |  |  | Mohemmed Bin Gerboo EST. | alfies benjamin | 2013-07-14 | 2013-05-29 | 560
1327000227 | 79722 | Mohemmed Bin Gerboo EST. | 2013-05-29 | 2013-06-30 | JIZA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 3901.3 |  |  | Done | lari carboz | 2013-08-26 | 2013-05-29 | 3522
1327000218 | 79722 | Mohemmed Bin Gerboo EST. | 2013-05-29 | 2013-06-30 | SLHD | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  |  | ernesto e. lai | 2013-07-14 | 2013-05-29 | 816
1327000258 | 79722 | Mohemmed Bin Gerboo EST. | 2013-05-29 | 2013-06-30 | DARB | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 1795.74 |  |  |  | jomeel g. antonio | 2013-07-15 | 2013-05-29 | 1728
1327000262 | 79722 | Mohemmed Bin Gerboo EST. | 2013-05-29 | 2013-06-30 | SBYA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 4379.5 |  |  | Done | ali gobain | 2013-07-29 | 2013-05-29 | 4464
1327000339 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-22 | 2013-09-04 | JIZA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 11620 |  |  |  | lari carboz | 2013-09-02 | 2013-07-22 | 12136
1327000345 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-22 | 2013-09-04 | SBYA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 817.02 |  |  |  | ali gobain | 2013-08-20 | 2013-07-22 | 816
1327000346 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-22 | 2013-09-04 | JIZA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 9174.44 |  |  | ZJZA001 Done | lari carboz | 2013-08-26 | 2013-07-22 | 10513
1327000294 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-22 | 2013-09-04 | ABAR | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | alfies benjamin | 2013-09-02 | 2013-07-21 | 936
1327000381 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-18 | 2013-08-29 | ABAR | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 2920.41 |  |  |  | alfies benjamin | 2013-08-21 | 2013-07-18 | 2847.2
1327000379 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-15 | 2013-08-15 | SBYA | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 748 |  |  |  | ali gobain | 2013-08-20 | 2013-07-15 | 432
1327000476 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-10-08 | 2013-11-21 | ABAR | fttm | Fiber PBU 2013 | in progress | 2013 objective design issued - lead | 0 |  |  |  | alfies benjamin |  | 2013-10-07 | 61500.11
1327000695 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-12-22 | 2014-02-05 | 703-00-000 | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 0 |  |  | Done | lari carboz | 2014-02-02 | 2013-12-03 | 105366.64
1327000726 | 79738 | ISSA AL ISSA FOR contracting EST. | 2014-01-12 | 2014-02-26 | SBYA | fttm | Fiber PBU 2013 | in progress | 2013 objective design issued - lead | 0 |  |  |  | agobain |  | 2014-01-05 | 27147.52
1227000162 | 79722 | Mohemmed Bin Gerboo EST. | 2012-09-17 | 2012-10-31 | BAYS | fttm | Fiber PBU 2013 | completed | 2013 objective design issued - lead | 2024.58 |  |  |  | jomeel g. antonio | 2013-08-28 | 2013-08-29 | 2024.58
1327000483 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-09-25 | 2013-10-27 | JIZA | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 1219.25 | CM In Progress |  | DONE | lscarboz | 2013-10-22 | 2013-09-25 | 1187.25
1327000470 | 79722 | Mohemmed Bin Gerboo EST. | 2013-09-17 | 2013-09-17 | ABAR | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 764.496 | Director In Progress |  | Done | abenjamin | 2013-10-10 | 2013-09-17 | 684
1327000462 | 79722 | Mohemmed Bin Gerboo EST. | 2013-09-18 | 2013-10-31 | JIZA | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 512.224 | Director In Progress |  | Done | lscarboz | 2013-10-09 | 2013-09-09 | 396
1327000303 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-15 | 2013-08-15 | JIZA | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 6913 | Director In Progress |  |  | lscarboz | 2013-08-22 | 2013-07-15 | 7664
1327000306 | 79722 | Mohemmed Bin Gerboo EST. | 2013-07-15 | 2013-08-15 | JIZA | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 1628 | Director In Progress |  |  | lscarboz | 2013-08-22 | 2013-07-15 | 167.2
1327000471 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-11-30 | 2014-01-14 | ABAR | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 0 |  |  | Done | alfies benjamin | 2013-12-16 | 2013-10-30 | 579.25
1327000646 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-11-24 | 2014-01-07 | SBYA | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 0 |  |  | Done | agobain | 2013-12-16 | 2013-12-01 | 76
1327000647 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-11-24 | 2014-01-07 | JIZA | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 0 |  |  | Done | lari carboz | 2013-12-17 | 2013-11-21 | 76
1327000648 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-11-24 | 2014-01-07 | JIZA | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 0 |  |  | Done | lari carboz | 2013-12-23 | 2013-11-21 | 76
1327000644 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-12-01 | 2014-01-15 | ABAR | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 0 |  |  | Done | alfies benjamin | 2013-12-16 | 2013-11-24 | 76
1327000645 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-12-01 | 2014-01-14 | ABAR | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 0 |  |  | Done | alfies benjamin | 2013-12-16 | 2013-12-01 | 76
1327000475 | 79722 | Mohemmed Bin Gerboo EST. | 2013-09-17 | 2013-10-17 | ABAR | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 0 |  |  | Done | alfies benjamin | 2013-11-17 | 2013-09-17 | 676
1327000478 | 79722 | Mohemmed Bin Gerboo EST. | 2013-09-17 | 2013-10-17 | JIZA | held order | FTTH HO – LEAD | completed | 2013 objective design issued - lead | 0 |  |  | Done | lari carboz | 2013-11-04 | 2013-09-17 | 908
1227000065 |  |  | 2012-03-24 | 2012-04-30 | SBYA | fttx | FTTX EBU-FDT | cancelled | 2013 objective design issued - lead |  |  | job wo cancelled | cancelled-The end of the agreement | ali gobain |  | 2012-03-24 | 258105.25
1227000010 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-09-17 | 2012-10-24 | JIZA | fttx | FTTX EBU-ONT | completed | 2012 objective design issued | 6706.644 | CM In Progress |  |  | lscarboz | 2013-05-23 | 2012-09-17 | 10576.7746
1227000009 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-09-17 | 2012-10-24 | JIZA | fttx | FTTX EBU-ONT | completed | 2012 objective design issued | 69920.74 | CM In Progress |  | key account | lscarboz | 2012-11-13 | 2012-09-17 | 31410.292
1127000609 | 78382 | Majd AlJanoub for general Contracting Ltd. | 2012-06-26 | 2012-08-10 | SLHD | fttx | FTTX EBU-ONT | completed | 2012 objective design issued | 70970.28 | Yes |  | key account | ernesto e. lai | 2012-12-01 | 2012-06-26 | 71066.5
1127000614 | 78382 | Majd AlJanoub for general Contracting Ltd. | 2012-10-16 | 2012-11-14 | SLHD | fttx | FTTX EBU-ONT | completed | 2012 objective design issued | 297266.304 | Yes |  | key account | ernesto e. lai | 2012-12-26 | 2012-06-26 | 291369.2
1227000008 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-22 | 2012-02-29 | SBYA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 137990.5 | DM In Progress |  | FTTH SBYA F064 | agobain | 2012-10-20 | 2012-01-22 | 146763.36
1227000241 |  | Mohemmed Bin Gerboo EST. | 2013-01-16 | 2013-02-28 | ABAR | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead |  |  | district contractor over budget | No PO, completed FTTH project ABAR 057-2 (Fiber Job) | alfies benjamin | 2013-12-18 | 2012-11-03 | 32405.75
1227000240 |  | Mohemmed Bin Gerboo EST. | 2013-01-16 | 2013-02-28 | ABAR | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead |  |  | district contractor over budget | No PO, completed FTTH project ABAR 057-1 (Fiber Job) | alfies benjamin | 2013-12-18 | 2012-11-03 | 41174
1227000227 |  | Mohemmed Bin Gerboo EST. | 2013-01-16 | 2013-02-28 | SBYA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead |  |  | to be assign under lead only | No PO, completed FTTH project SBYA 117-1 (Civil Works) | ali gobain | 2013-12-18 | 2012-11-03 | 16859.2
1227000228 |  | Mohemmed Bin Gerboo EST. | 2013-01-16 | 2013-02-28 | SBYA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead |  |  | to be assign under lead only | No PO, completed FTTH SBYA FDT 117-1 (fiber) | ali gobain | 2013-12-23 | 2012-11-03 | 45407.75
1227000224 |  | Mohemmed Bin Gerboo EST. | 2013-01-16 | 2013-02-28 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead |  |  | to be assign under lead only | No PO, completed FTTH project JIZA FDT 062-1 (Fiber Job) | lari carboz | 2013-12-18 | 2012-10-08 | 59384
1227000237 |  | Mohemmed Bin Gerboo EST. | 2013-01-16 | 2013-02-28 | SBYA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead |  |  | to be assign under lead only | No PO, completed FTTH project SBYA 064-1 (Civil Works) | lari carboz | 2013-12-18 | 2012-11-03 | 35206.4
1227000247 |  | Mohemmed Bin Gerboo EST. | 2013-01-16 | 2013-02-28 | SBYA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead |  |  | to be assign under lead only | No PO, completed FTTH project SBYA 064-1 (Fiber Job) | ali gobain | 2013-12-18 | 2012-11-03 | 67741
1127000551 |  | Mohemmed Bin Gerboo EST. | 2011-10-29 | 2011-12-13 | JIZA | fttx | FTTX-FDT BF | cancelled | 2012 objective design issued - lead |  |  | job wo cancelled | Cancelled By Scope-Jiza FDT023 | lari carboz |  | 2011-10-29 | 312266.08
1127000552 |  | Mohemmed Bin Gerboo EST. | 2011-10-29 | 2011-12-13 | JIZA | fttx | FTTX-FDT BF | cancelled | 2012 objective design issued - lead |  |  | job wo cancelled | Cancelled By Scope | laary |  | 2011-10-29 | 82820
1127000554 |  | Mohemmed Bin Gerboo EST. | 2011-10-29 | 2011-12-13 | JIZA | fttx | FTTX-FDT BF | cancelled | 2012 objective design issued - lead |  |  | job wo cancelled | Cancelled By Scope | laary |  | 2011-10-29 | 3739.92
1127000558 |  | Mohemmed Bin Gerboo EST. | 2011-11-13 | 2011-11-28 | JIZA | fttx | FTTX-FDT BF | cancelled | 2012 objective design issued - lead |  |  | job wo cancelled | Cancelled by planning | laary |  | 2011-11-13 | 201473.84
1127000639 |  | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead |  |  |  | No PO, completed - Feeder Fiber - FTTH JIZA F041 042 - 045 - 061- 041 . | lari carboz | 2013-12-18 | 2013-12-01 | 30540
1127000550 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-29 | 2011-12-13 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 640057.984 | Yes |  | FTTH JIZA F062 | laary | 2012-03-18 | 2011-10-29 | 516282.24
1127000555 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-29 | 2011-12-13 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 60472.5 |  |  | FTTH JIZA F062 | laary | 2013-01-02 | 2011-10-29 | 84204
1127000556 | 76677 | Mohemmed Bin Gerboo EST. | 2011-11-13 | 2011-11-28 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 0 |  |  | FTTH JIZA F062 | laary | 2013-01-02 | 2011-11-13 | 2161.68
1127000641 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | SBYA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 61152.1 |  |  | FTTH SBYA F117 | ali gobain | 2012-10-20 | 2012-01-09 | 84154.56
1127000642 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | SBYA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 16451.06 |  |  | FTTH SBYA F117+064 | ali gobain | 2013-03-13 | 2012-01-09 | 16968.05
1127000634 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 407484.08 | Yes |  | FTTH JIZA F042 | lari carboz | 2012-04-30 | 2012-01-09 | 343905.52
1127000638 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | SBYA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 596919.84 | Yes |  | FTTH SBYA F117 | ali gobain | 2012-10-08 | 2012-01-09 | 485035.2
1127000645 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 86266.9 | Yes |  | FTTH JIZA F061 | lari carboz | 2012-10-20 | 2012-01-09 | 108832
1127000636 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 857277.04 | Yes |  | FTTH JIZA F043 | lari carboz | 2012-04-30 | 2012-01-09 | 585520.72
1127000640 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 694616.96 | Yes |  | FTTH JIZA F061 | lari carboz | 2012-10-08 | 2012-01-09 | 533638
1127000643 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 132914.2 | Yes |  | FTTH JIZA F043 | lari carboz | 2012-10-20 | 2012-01-09 | 73244
1127000644 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-22 | 2012-02-29 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 0 |  |  | FTTH JIZA F043 | laary | 2012-12-03 | 2012-01-22 | 19872
1127000648 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-22 | 2012-02-29 | ABAR | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 48192 |  |  | FTTH ABAR F057+089 | alfies benjamin | 2012-12-03 | 2012-01-22 | 110790.64
1227000001 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-22 | 2012-02-29 | ABAR | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 1415611.36 | Yes |  | FTTH ABAR F057 | alfies benjamin | 2012-10-08 | 2012-01-22 | 1259223.6
1227000002 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-22 | 2012-02-29 | ABAR | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 154373.3 | Yes |  | FTTH ABAR F057 | alfies benjamin | 2012-10-20 | 2012-01-22 | 517236
1227000004 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-22 | 2012-02-29 | ABAR | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 832253.44 | Yes |  | FTTH ABAR F089 | alfies benjamin | 2012-12-03 | 2012-01-22 | 666240.88
1227000005 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-22 | 2012-02-29 | ABAR | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 167811.6 |  |  | FTTH ABAR F089 | alfies benjamin | 2012-10-20 | 2012-01-22 | 171601.6
1227000007 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-22 | 2012-02-29 | SBYA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 716738.64 | Yes |  | FTTH SBYA F064 | ali gobain | 2013-02-09 | 2012-01-22 | 671740.16
1127000646 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 101063 | Yes |  | FTTH JIZA F045 | laary | 2012-10-20 | 2012-01-09 | 116780
1127000635 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 95095.5 | Yes |  | FTTH JIZA F041 | laary | 2012-10-20 | 2012-01-09 | 61120
1127000637 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 86767.5 | Yes |  | FTTH JIZA F042 | lari carboz | 2012-10-20 | 2012-01-09 | 65552
1127000632 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 452692.4 | Yes |  | FTTH JIZA F041 | lari carboz | 2012-03-18 | 2012-01-09 | 363424
1127000633 | 76677 | Mohemmed Bin Gerboo EST. | 2012-01-09 | 2012-02-15 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 711614.76 | Yes |  | FTTH JIZA F045 | laary | 2012-10-08 | 2012-01-09 | 434416
1227000217 | 79722 | Mohemmed Bin Gerboo EST. | 2012-10-03 | 2012-11-10 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 60655.6 | Yes |  |  | laary | 2013-02-12 | 2012-10-03 | 62384
1227000225 | 79722 | Mohemmed Bin Gerboo EST. | 2012-10-03 | 2012-11-10 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 44697.5 |  |  |  | laary | 2013-03-02 | 2012-10-03 | 38324
1227000216 | 79722 | Mohemmed Bin Gerboo EST. | 2012-10-03 | 2012-11-10 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 4471.04 | Yes |  |  | laary | 2013-02-09 | 2012-10-03 | 4360
1227000218 | 79722 | Mohemmed Bin Gerboo EST. | 2012-10-03 | 2012-11-10 | JIZA | fttx | FTTX-FDT BF | completed | 2012 objective design issued - lead | 3231.92 | Yes |  |  | laary | 2013-02-09 | 2012-10-03 | 3619.2
0927000609 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held order | completed | 2009 objective design issued | 1919 | Yes |  |  | lari carboz | 2011-08-20 | 2010-06-07 | 1935
0727000110 |  |  | 2007-07-24 | 2007-08-01 | ABAR | held order | Held Order | cancelled | tbd |  |  |  |  | mohammed ---- bablumiah |  | 2007-07-24 | 2300
0927000532 | STC_2010 | STC CREW | 2009-12-12 | 2010-01-26 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) |  | 2009-10-04 | 2009-10-04 | 100.3
0927000088 | STC_2008 | STC CREW | 2009-02-08 | 2009-02-18 | JIZA | held order | Held Order | completed | 2009 objective design issued |  |  |  | STC CREW | lari carboz | 2009-02-23 | 2009-02-08 | 144.1
0827000569 | STC_2010 | STC CREW | 2008-11-24 | 2009-04-08 | JIZA | held order | Held Order | completed | 2007 backlog |  |  |  | Covered by cab 060 | lari carboz | 2009-04-08 | 2008-11-24 | 7076
0827000636 | STC_2010 | STC CREW | 2008-12-31 | 2009-04-05 | SBYA | held order | Held Order | completed | 2007 backlog |  |  |  | <3000 | ali m. gobain | 2009-04-05 | 2008-12-31 | 283.5
0927000398 | STC_2010 | STC CREW | 2009-07-04 | 2009-09-22 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 3000 SAR (STC CREW) | lari carboz | 2009-08-23 | 2009-07-04 | 1020
0927000294 | STC_2010 | STC CREW | 2006-05-20 | 2009-05-19 | SLHD | held order | Held Order | completed | 2009 objective not in the design master sheet | [5 empty] | 2009-05-19 | 2009-05-16 | 340.2
1027000033 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | DAMD | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | alfies benjamin | 2010-05-05 | 2010-03-30 | 125
1027000146 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | ABAR | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | alfies benjamin | 2010-09-27 | 2010-08-21 | 82.1
1027000102 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | SAMI | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | ernesto e. lai | 2010-08-28 | 2010-08-21 | 125
0927000638 | STC_2010 | STC CREW | 2009-12-23 | 2010-01-04 | DAMD | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | alfies benjamin | 2010-01-02 | 2009-12-23 | 82.1
0927000644 | STC_2010 | STC CREW | 2009-12-23 | 2010-01-04 | DAMD | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | alfies benjamin | 2010-01-02 | 2009-12-23 | 56.7
0927000684 | STC_2010 | STC CREW | 2009-12-23 | 2010-01-26 | ABAR | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | alfies benjamin | 2009-12-30 | 2009-12-23 | 82.1
0927000689 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | DAMD | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | alfies benjamin | 2010-05-05 | 2010-03-30 | 125
0927000500 | STC_2010 | STC CREW | 2009-08-16 | 2009-09-16 | ABAR | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 3000 SAR (STC CREW) | alfies benjamin | 2009-09-05 | 2009-08-16 | 56.7
0927000530 | STC_2010 | STC CREW | 2009-12-12 | 2010-01-26 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) |  | 2009-10-03 | 2009-09-30 | 138.3
0927000513 | STC_2008 | STC CREW | 2009-09-05 | 2009-09-20 | JIZA | held order | Held Order | completed | 2009 objective design issued |  |  |  | less than 100 SAR (STC CREW) | lari carboz | 2009-09-12 | 2009-09-27 | 47
0927000266 | STC_2008 | STC CREW | 2009-05-01 | 2009-06-30 | BAYS | held order | Held Order | completed | 2009 objective design issued |  |  |  | VIP |  | 2009-05-17 | 2009-05-10 | 3663.2
0927000541 | STC_2010 | STC CREW | 2009-12-12 | 2010-01-26 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) |  | 2009-10-03 | 2009-09-30 | 100.3
0927000557 | STC_2010 | STC CREW | 2009-10-25 | 2009-12-20 | DAMD | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | ernesto e. lai | 2009-12-05 | 2009-10-25 | 84.3
0927000600 | STC_2010 | STC CREW | 2009-12-23 | 2010-01-26 | ABAR | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | alfies benjamin | 2009-12-30 | 2009-12-23 | 100.3
0927000607 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | ABAR | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | alfies benjamin | 2010-05-05 | 2010-03-30 | 146.1
0927000608 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | SAMI | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | ernesto e. lai | 2010-04-13 | 2010-03-30 | 125
0927000613 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | SAMI | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | ernesto e. lai | 2010-04-13 | 2010-03-30 | 109
0927000621 | STC_2010 | STC CREW | 2009-12-21 | 2009-12-30 | FRSN | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | alfies benjamin | 2009-12-27 | 2009-12-21 | 124.4
0927000623 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | ABAR | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | alfies benjamin | 2010-05-05 | 2010-03-30 | 115
0927000571 | STC_2010 | STC CREW | 2009-10-24 | 2009-12-20 | FRSN | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | alfies benjamin | 2009-12-27 | 2009-10-24 | 108.4
1027000198 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | SLHD | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | ernesto e. lai | 2010-08-28 | 2010-08-21 | 243
1027000192 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | SAMI | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | ernesto e. lai | 2010-08-28 | 2010-08-21 | 121.4
1027000296 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | SAMI | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | ernesto e. lai | 2010-08-28 | 2010-08-21 | 170.1
1027000268 | STC_2010 | STC CREW | 2010-06-26 | 2010-06-30 | FRSN | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | alfies benjamin | 2010-06-30 | 2010-06-26 | 597.2
1027000308 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | TWAL | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | ernesto e. lai | 2010-08-28 | 2010-08-21 | 170.5
1027000306 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | SAMI | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | ernesto e. lai | 2010-08-28 | 2010-08-21 | 243
0827000457 | STC_2010 | STC CREW | 2008-10-25 | 2009-04-08 | JIZA | held order | Held Order | completed | 2007 backlog |  |  |  | Covered by cab 060 | lari carboz | 2009-04-08 | 2008-10-25 | 1856.3
1027000079 | STC_2010 | STC CREW | 2010-03-04 | 2010-03-15 | SBYA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | ali m. gobain | 2010-03-14 | 2010-03-04 | 375.7
1027000068 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | lari carboz | 2010-03-31 | 2010-03-30 | 100.3
1027000129 | STC_2010 | STC CREW | 2010-03-27 | 2010-03-29 | SHUQ | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | jomeel g. antonio | 2010-03-28 | 2010-03-27 | 250.3
1027000104 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | SBYA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | ali m. gobain | 2010-10-06 | 2010-08-21 | 147.3
1027000093 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | SBYA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | ali m. gobain | 2010-04-07 | 2010-03-30 | 100.3
1027000158 | STC_2010 | STC CREW | 2010-05-02 | 2010-05-12 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | lari carboz | 2010-05-05 | 2010-05-02 | 597.7
1027000173 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | lari carboz | 2010-11-29 | 2010-08-21 | 435.7
1027000174 | STC_2010 | STC CREW | 2010-11-02 | 2010-11-03 | SBYA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC JR | ali m. gobain | 2010-11-03 | 2010-11-02 | 452
1027000241 | STC_2010 | STC CREW | 2010-06-27 | 2010-07-03 | SLHD | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | jomeel g. antonio | 2010-07-03 | 2010-06-27 | 1701
1027000237 | STC_2010 | STC CREW | 2010-06-21 | 2010-06-22 | SBYA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | ali m. gobain | 2010-06-22 | 2010-06-21 | 200.8
1027000171 | STC_2010 | STC CREW | 2010-04-22 | 2010-05-12 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | jomeel g. antonio | 2010-04-27 | 2010-04-22 | 5116.4
1027000164 | STC_2010 | STC CREW | 2010-04-25 | 2010-04-28 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | jomeel g. antonio | 2010-04-26 | 2010-04-25 | 30.7
1027000137 | STC_2010 | STC CREW | 2010-04-11 | 2010-04-17 | BAYS | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | jomeel g. antonio | 2010-04-25 | 2010-04-11 | 30.7
1027000138 | STC_2010 | STC CREW | 2010-04-20 | 2010-04-24 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | ali m. gobain | 2010-04-24 | 2010-04-20 | 719.2
0927000699 | STC_2010 | STC CREW | 2009-12-22 | 2010-01-02 | SBYA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | ali m. gobain | 2009-12-26 | 2009-12-22 | 100.3
0927000674 | STC_2010 | STC CREW | 2010-03-09 | 2010-03-19 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | lari carboz | 2010-03-31 | 2010-03-05 | 131
0927000676 | STC_2010 | STC CREW | 2009-12-23 | 2010-01-04 | DARB | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | jomeel g. antonio | 2010-01-02 | 2009-12-23 | 30.7
0927000679 | STC_2010 | STC CREW | 2009-12-23 | 2010-01-04 | DARB | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | jomeel g. antonio | 2010-01-02 | 2009-12-23 | 100.3
0927000691 | STC_2010 | STC CREW | 2009-12-08 | 2009-12-12 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | (STC CREW) | lari carboz | 2009-12-09 | 2009-12-08 | 189.2
0927000632 | STC_2010 | STC CREW | 2009-12-23 | 2010-01-26 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | lari carboz | 2010-01-26 | 2009-12-23 | 30.7
0927000633 | STC_2010 | STC CREW | 2009-12-11 | 2009-12-12 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | (STC CREW) | lari carboz | 2009-12-12 | 2009-12-11 | 443.8
0927000647 | STC_2010 | STC CREW | 2010-02-21 | 2010-02-25 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | Done By STC CREW & Baladyah | lari carboz | 2010-02-24 | 2010-02-21 | 14254.6
0927000555 | STC_2010 | STC CREW | 2009-10-25 | 2009-10-30 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | lari carboz | 2009-10-25 | 2009-10-25 | 484.3
0927000601 | STC_2010 | STC CREW | 2009-12-21 | 2010-01-26 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | ?STC CREW | lari carboz | 2010-01-10 | 2009-12-21 | 1681
0927000580 | STC_2010 | STC CREW | 2009-12-23 | 2010-01-26 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | lari carboz | 2010-01-18 | 2009-12-23 | 100.3
0927000587 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | BAYS | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | jomeel g. antonio | 2010-05-12 | 2010-03-30 | 143.2
0927000569 | STC_2010 | STC CREW | 2009-10-25 | 2009-12-20 | SBYA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | ali m. gobain | 2009-10-26 | 2009-10-25 | 100.3
0927000560 | STC_2010 | STC CREW | 2009-10-20 | 2009-12-20 | SBYA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | ali m. gobain | 2009-10-21 | 2009-10-20 | 100.3
0927000564 | STC_2010 | STC CREW | 2009-10-25 | 2009-12-20 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | lari carboz | 2009-12-29 | 2009-10-25 | 100.3
0927000566 | STC_2010 | STC CREW | 2009-10-25 | 2009-12-20 | BAYS | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | jomeel g. antonio | 2009-12-21 | 2009-10-25 | 100.3
0927000595 | STC_2010 | STC CREW | 2010-03-30 | 2010-04-30 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | jomeel g. antonio | 2010-04-10 | 2010-03-30 | 138.3
0927000575 | STC_2010 | STC CREW | 2009-10-24 | 2009-12-20 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | lari carboz | 2009-12-29 | 2009-10-24 | 100.3
0927000547 | STC_2010 | STC CREW | 2009-10-25 | 2009-12-20 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | less than 100 SAR (STC CREW) | lari carboz | 2010-01-18 | 2009-10-25 | 30.7
1027000288 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | lari carboz | 2010-10-31 | 2010-08-21 | 719.2
1027000236 | STC_2010 | STC CREW | 2010-06-21 | 2010-06-22 | SBYA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | ali m. gobain | 2010-06-22 | 2010-06-21 | 443.8
1027000204 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | DARB | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | jomeel g. antonio | 2010-10-31 | 2010-08-21 | 157
1027000218 | STC_2010 | STC CREW | 2010-06-12 | 2010-06-14 | SBYA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | ali m. gobain | 2010-06-14 | 2010-06-12 | 37.7
1027000225 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | lari carboz | 2010-08-29 | 2010-08-21 | 203.6
1027000226 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | lari carboz | 2010-08-28 | 2010-08-21 | 203.6
1027000269 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | lari carboz | 2010-08-29 | 2010-08-21 | 100.3
1027000272 | STC_2010 | STC CREW | 2010-08-07 | 2010-08-09 | JIZA | held order | Held Order | completed | 2009 objective design issued |  |  |  | STC CREW | lari carboz | 2010-08-08 | 2010-10-23 | 370.9
1027000285 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | lari carboz | 2010-08-28 | 2010-08-21 | 30.7
1027000324 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | SBYA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | ali m. gobain | 2010-10-06 | 2010-08-21 | 100.3
1027000290 | STC_2010 | STC CREW | 2010-08-21 | 2010-10-31 | SBYA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW JR | ali m. gobain | 2010-10-06 | 2010-08-21 | 303.9
1027000468 | STC_2010 | STC CREW | 2010-12-19 | 2010-12-21 | JIZA | held order | Held Order | completed | 2010 objective not in the design master sheet |  |  |  | STC CREW | lari carboz | 2010-12-21 | 2010-12-19 | 31.4
0927000177 | STC_2010 | STC CREW | 2009-03-08 | 2009-03-11 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | New<3000 | lari carboz | 2009-03-11 | 2009-03-08 | 168.4
0927000162 | STC_2010 | STC CREW | 2009-03-01 | 2009-05-02 | JIZA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  |  | lari carboz | 2009-05-02 | 2009-04-29 | 2948.4
0927000052 | STC_2010 | STC CREW | 2009-02-02 | 2009-03-02 | SBYA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW | ali m. gobain | 2009-03-02 | 2009-02-02 | 5670
0927000210 | STC_2010 | STC CREW | 2009-04-01 | 2009-04-01 | SAMI | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW |  | 2009-04-01 | 2009-03-30 | 125
0927000185 | STC_2010 | STC CREW | 2009-03-23 | 2009-04-12 | DAMD | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW |  | 2009-04-12 | 2009-03-23 | 41.9
0927000086 | STC_2010 | STC CREW | 2009-02-09 | 2009-02-25 | SBYA | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW |  | 2009-02-25 | 2009-02-09 | 144.1
0927000022 | STC_2010 | STC CREW | 2009-01-17 | 2009-02-17 | SLHD | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW |  | 2009-02-17 | 2009-01-17 | 2948.4
0927000208 | STC_2010 | STC CREW | 2009-03-23 | 2009-03-29 | SAMI | held order | Held Order | completed | 2009 objective not in the design master sheet |  |  |  | STC CREW |  | 2009-03-29 | 2009-03-23 | 453.6
1127000254 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-05-26 | 2012-06-09 | BAYS | held order | Held Order - EBU | completed | 2012 objective design issued | 6058.56 | PM In Progress |  |  | jgantonio | 2012-07-03 | 2012-05-23 | 6120.6
1127000397 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-03 | 2012-04-13 | JIZA | held order | Held Order - EBU | completed | 2011 objective design issued | 568.59 | DM In Progress |  |  | lscarboz | 2012-11-26 | 2011-08-23 | 1022.96
1227000042 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-05-05 | 2012-06-15 | SBYA | held order | Held Order - EBU | completed | 2012 objective design issued | 5066.82 | DM In Progress |  |  | lscarboz | 2012-11-26 | 2012-05-05 | 6206.59
1127000621 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-09 | 2012-05-23 | JIZA | held order | Held Order - EBU | completed | 2011 objective design issued | 7528.754 | CM In Progress |  |  | lscarboz | 2012-07-25 | 2012-04-09 | 7906.28
1227000135 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-05-13 | 2012-06-23 | JIZA | held order | Held Order - EBU | completed | 2012 objective design issued | 7884.024 | PM In Progress |  | Jeel AlFursan Est. FOR TRADING &CO Completed | lscarboz | 2012-07-03 | 2012-05-13 | 8412.4
1127000649 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-04-30 | 2012-06-06 | DARB | held order | Held Order - EBU | completed | 2012 objective design issued | 7200 | PM In Progress |  | Jeel AlFursan Est. FOR TRADING &CO | jgantonio | 2012-10-31 | 2012-04-30 | 7200
1227000052 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-04-14 | 2012-05-24 | FRSN | held order | Held Order - EBU | completed | 2012 objective design issued | 529.72 | PM In Progress |  |  | abenjamin | 2012-07-04 | 2012-04-11 | 1007.8
1227000167 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2013-04-15 | 2013-05-30 | JIZA | held order | Held Order - EBU | cancelled | 2012 objective design issued | 0 |  |  |  | laary |  | 2013-04-15 | 1115.4
1127000044 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-18 | 2011-06-30 | JIZA | held order | Held Order - EBU | completed | 2012 objective design issued | 118350.4 | Yes |  |  | lari carboz | 2011-07-02 | 2011-04-24 | 146434.4
1127000210 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-10 | 2011-05-31 | JIZA | held order | Held Order - EBU | completed | 2012 objective design issued | 300 | Yes |  |  | lari carboz | 2011-09-28 | 2011-05-10 | 300
1027000205 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2010-04-07 | 2010-09-10 | ABAR | held order | Held Order - EBU | completed | 2012 objective design issued |  |  |  | CUSTOMERT JOP | alfies benjamin | 2010-07-11 | 2010-04-07 | 0
1127000170 | 80013 | Mohemmed Bin Gerboo EST. | 2013-04-13 | 2013-05-28 | JIZA | held order | Held Order - EBU | in progress | 2011 objective design issued | 0 |  |  |  | lari carboz |  | 2011-04-05 | 5508.46
1227000151 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | JIZA | held order | Held Order - EBU | in progress | 2012 objective design issued | 0 |  |  |  | lari carboz |  | 2013-04-17 | 14162.19
0927000364 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2010-08-09 | 2010-09-23 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 3971.44 | PM In Progress |  | VIP6 | lscarboz | 2013-04-07 | 2010-08-09 | 3625.84
1127000125 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-27 | 2011-09-07 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 11158.368 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-04-07 | 2011-07-27 | 8240.1
1127000132 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-27 | 2011-09-10 | FRSN | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2298.24 | PM In Progress |  |  | abenjamin | 2011-10-26 | 2011-07-27 | 2160
1127000411 | 76677 | Mohemmed Bin Gerboo EST. | 2011-08-23 | 2011-09-23 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2595.89 | DM In Progress | pu price adjustment with bat/pcc |  | lscarboz | 2011-09-11 | 2011-08-23 | 2212
1027000537 | 76677 | Mohemmed Bin Gerboo EST. | 2011-08-06 | 2011-08-20 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 4650.21 | DM In Progress |  |  | lscarboz | 2011-08-06 | 2011-08-06 | 2496
1127000588 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-01-25 | 2012-02-29 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6681.6 |  |  |  | lscarboz | 2012-11-26 | 2012-01-25 | 8179.2
1127000421 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-09-19 | 2011-10-31 | DAMD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 8603.034 | DM In Progress |  | DETCON | abenjamin | 2012-02-08 | 2011-09-13 | 9160.51
1127000576 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-11-22 | 2011-12-30 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 46923.36 | DM In Progress |  |  | agobain | 2012-04-04 | 2011-11-22 | 51280.58
1127000599 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-01-22 | 2012-02-29 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2895.36 | DM In Progress |  |  | lscarboz | 2012-11-26 | 2012-01-22 | 2922.16
1127000589 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-01-22 | 2012-02-29 | ABAR | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 13757.71 | DM In Progress |  |  | abenjamin | 2012-12-05 | 2012-01-22 | 15414.07
1227000036 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-07 | 2012-03-21 | ABAR | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2489.24 | DM In Progress |  | Completed | abenjamin | 2012-06-02 | 2012-02-07 | 2489.24
1227000089 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-05-05 | 2012-06-15 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 9533.046 | DM In Progress |  |  | lscarboz | 2012-05-21 | 2012-05-05 | 9533.046
1127000627 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-27 | 2012-04-11 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 18419.4 | DM In Progress |  |  | agobain | 2012-04-07 | 2012-02-27 | 18419.4
1227000013 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-19 | 2012-04-01 | ARDH | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 31372.34 | CM In Progress |  |  | abenjamin | 2012-11-24 | 2012-02-19 | 41770.12
1127000622 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-19 | 2012-04-01 | ARDH | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 7285.4 | CM In Progress |  |  | abenjamin | 2012-11-23 | 2012-02-19 | 15073.9
1227000076 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-02 | 2012-05-15 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 22733.74 | DM In Progress |  |  | agobain | 2012-05-27 | 2012-04-02 | 26054.1
1127000629 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-20 | 2012-04-25 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 7923.36 |  |  |  | agobain | 2012-11-26 | 2012-03-20 | 7923.36
1227000058 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-20 | 2012-04-25 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 11284.1 | DM In Progress |  |  | agobain | 2012-05-26 | 2012-03-20 | 13165.7
1127000626 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-28 | 2012-04-11 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6527.8 | DM In Progress |  |  | agobain | 2013-01-06 | 2012-02-28 | 6527.8
1227000045 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-27 | 2012-04-11 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 55591.306 | DM In Progress |  |  | lscarboz | 2012-05-27 | 2012-02-27 | 76392.66
1227000044 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-12 | 2012-04-12 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2641.932 | DM In Progress |  |  | lscarboz | 2012-05-27 | 2012-03-12 | 3059.9
1227000080 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-02 | 2012-05-15 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 302.32 | DM In Progress |  |  | lscarboz | 2012-11-26 | 2012-04-02 | 302.32
1227000046 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-27 | 2012-04-11 | SAMI | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6658.38 | DM In Progress |  |  | elai | 2012-05-08 | 2012-02-27 | 6520.14
1227000075 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-02 | 2012-05-15 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 19301.2 |  |  |  | lscarboz | 2012-11-26 | 2012-04-02 | 19819.6
1227000148 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-06-11 | 2012-07-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 25859.87 | CM In Progress |  |  | lscarboz | 2012-07-21 | 2012-05-27 | 24907.57
1127000370 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-27 | 2011-09-10 | FRSN | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6480 | PM In Progress |  |  | abenjamin | 2012-02-05 | 2011-07-27 | 5760
1127000386 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-30 | FRSN | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 19829.18 | PM In Progress |  |  | abenjamin | 2012-02-06 | 2011-08-23 | 18953.66
1127000396 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-23 | DARB | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 10992 | PM In Progress |  |  | jgantonio | 2013-01-27 | 2011-08-23 | 10472.93
1127000420 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-23 | FRSN | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 10700.3 | PM In Progress |  |  | abenjamin | 2011-10-26 | 2011-08-23 | 9908.44
1127000500 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-10-26 | 2011-12-10 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 346.56 | PM In Progress |  |  | agobain | 2011-12-03 | 2011-10-10 | 346.56
1127000446 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-10-12 | 2011-11-25 | DARB | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 5314.48 | PM In Progress |  |  | jgantonio | 2013-01-27 | 2011-10-12 | 5945.24
1127000368 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-26 | 2011-09-06 | DAMD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6622.63 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-02-10 | 2011-07-26 | 8831.32
1127000312 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-29 | 2011-07-29 | BAYS | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 3141.46 | PM In Progress |  |  | jgantonio | 2013-03-19 | 2011-06-29 | 3014.18
1227000072 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-03-20 | 2012-03-29 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 150.72 | Yes |  |  | laary | 2012-03-20 | 2012-03-20 | 150.72
1227000003 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-03-18 | 2012-03-18 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 5009.024 | Yes |  |  | laary | 2012-04-03 | 2012-03-18 | 274.54
1227000061 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-03-12 | 2012-04-25 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2636.08 | Yes |  |  | lari carboz | 2012-09-08 | 2012-03-12 | 2582.32
1227000067 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-03-18 | 2012-04-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 95.02 | Yes |  |  | laary | 2012-04-07 | 2012-03-18 | 95.02
1227000063 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-03-12 | 2012-04-25 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 5918.6 | Yes |  |  | laary | 2012-05-29 | 2012-03-12 | 9712.5
1227000153 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-06-12 | 2012-07-20 | BAYS | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 4477.28 | Yes |  | Ministry of Education | jomeel g. antonio | 2012-07-09 | 2012-06-12 | 5216.48
1227000094 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-04-23 | 2012-05-31 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 194.8 | Yes |  |  | laary | 2012-05-05 | 2012-04-23 | 308.1
1127000437 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-23 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 12131.72 | Yes |  |  | ali gobain | 2012-06-23 | 2011-08-23 | 10456.54
1127000422 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-03 | 2011-09-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 241.14 | Yes |  |  | laary | 2011-09-12 | 2011-08-22 | 241.14
1127000409 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-10-07 | SHUQ | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 11201.328 | Yes |  |  | jomeel g. antonio | 2012-02-14 | 2011-08-23 | 21781.94
1127000334 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-09 | 2011-08-19 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 323.37 | Yes |  |  | lari carboz | 2011-08-14 | 2011-07-09 | 254.25
1127000504 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-10-26 | 2011-12-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 1814.24 | Yes |  |  | lari carboz | 2011-12-21 | 2011-10-10 | 1814.24
1127000204 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-18 | 2011-05-31 | SBYA | held order | Held Order - EBU - 2012 | cancelled | 2012 objective design issued | 0 |  |  | Cancelled By Custemr | ali gobain |  | 2011-05-18 | 2246.78
1127000346 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-18 | 2011-08-31 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 4237.77 | Yes |  |  | ali m. gobain | 2012-03-26 | 2011-07-18 | 3531.42
1127000310 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-29 | 2011-07-31 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 148.77 | Yes |  |  | lari carboz | 2011-08-14 | 2011-06-29 | 148.77
1127000358 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-26 | 2011-09-05 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 636.48 | Yes |  |  | laary | 2011-08-14 | 2011-07-26 | 420.48
1127000173 |  | Mohemmed Bin Gerboo EST. | 2011-04-06 | 2011-04-20 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued |  |  | need cr |  | lari carboz | 2012-07-03 | 2011-04-06 | 1796.95
1127000276 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-13 | 2011-06-23 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 263.97 | Yes |  |  | ali gobain | 2011-07-09 | 2011-06-13 | 263.97
1127000280 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-13 | 2011-07-13 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 23587.364 | Yes |  |  | ali gobain | 2011-09-05 | 2011-06-13 | 58859.96
1127000344 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-07-18 | 2011-08-31 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 10703.33 | Yes |  | Completed in 04/07/2011 by harthi | lari carboz | 2011-08-22 | 2011-07-17 | 10703.33
1127000574 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-10-31 | 2011-11-17 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 317.7 | Yes |  |  | laary | 2012-02-13 | 2011-10-31 | 317.7
1127000179 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-05-07 | 2011-06-07 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 21742.099 | Yes |  |  | lari carboz | 2011-08-15 | 2011-05-07 | 34797.18
1127000475 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-09-27 | 2011-10-31 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2579.34 | Yes |  |  | lari carboz | 2011-12-20 | 2011-09-27 | 653.76
1127000380 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-07-26 | 2011-08-26 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 145.03 | Yes |  |  | ernesto e. lai | 2011-08-07 | 2011-07-26 | 145.03
1127000631 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-01-08 | 2012-02-15 | DARB | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2374.04 | Yes |  |  | jomeel g. antonio | 2012-02-18 | 2012-01-08 | 5945.24
1127000441 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-09-04 | 2011-10-15 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 1246.26 | Yes |  |  | ali gobain | 2011-10-30 | 2011-09-04 | 2863.8
1227000069 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-20 | 2012-04-25 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 322.52 | Yes |  |  | laary | 2012-05-27 | 2012-03-20 | 399.02
1127000104 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-21 | 2011-06-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 411 | Yes |  |  | lari carboz | 2011-05-31 | 2011-05-21 | 411
1127000075 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-27 | 2011-09-08 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 555 | Yes |  |  | lari carboz | 2011-10-31 | 2011-07-27 | 555
1127000393 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-07 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 46 | Yes |  |  | lari carboz | 2011-09-13 | 2011-08-23 | 46
1127000407 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-10 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 145 | Yes |  |  | ali gobain | 2011-09-19 | 2011-08-23 | 145
1127000412 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-22 | 2011-09-30 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 83187.2 | Yes |  |  | ernesto e. lai | 2011-10-16 | 2011-08-22 | 85349.2
1127000413 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-09 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 147 | Yes |  |  | lari carboz | 2011-09-13 | 2011-08-23 | 147
1127000419 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-23 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 5976 | Yes |  |  | ali gobain | 2011-11-16 | 2011-08-23 | 5895
1127000423 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-03 | 2011-09-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 11136.3 | Yes |  |  | laary | 2011-10-24 | 2011-08-22 | 9508
1127000432 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-23 | SAMI | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6004.6 | Yes |  |  | ernesto e. lai | 2011-10-12 | 2011-08-23 | 5642.2
1127000433 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-23 | 2011-09-23 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 23724.2 | Yes |  |  | lari carboz | 2011-11-28 | 2011-08-23 | 25054
1127000534 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-10-12 | 2011-11-25 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 8176 | Yes |  |  | ali gobain | 2011-11-19 | 2011-10-12 | 8176
1127000246 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-29 | 2011-06-30 | BAYS | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 30 | Yes |  |  | jomeel g. antonio | 2011-06-20 | 2011-05-29 | 30
1127000261 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-29 | 2011-06-30 | ARDH | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 3797.64 | Yes |  |  | alfies benjamin | 2011-09-07 | 2011-05-29 | 19656
1127000256 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-29 | 2011-06-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 19212.2 | Yes |  |  | laary | 2011-08-02 | 2011-05-29 | 812
1127000226 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-21 | 2011-06-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 3930 | Yes |  |  | lari carboz | 2011-12-07 | 2011-05-21 | 3405
1127000219 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-21 | 2011-06-30 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 4878 | Yes |  | Completed in 21/06/2011 by harthi | ernesto e. lai | 2011-06-21 | 2011-05-21 | 4933.1
1127000213 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-10 | 2011-06-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 40388.2 | Yes |  |  | lari carboz | 2011-09-13 | 2011-05-10 | 39963.8
1127000216 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-10 | 2011-05-31 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 457 | Yes |  |  | lari carboz | 2011-09-19 | 2011-05-10 | 457
1127000200 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-18 | 2011-05-28 | SAMI | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 207 | Yes |  | Completed in 21-06/2011 By Harthi | ernesto e. lai | 2011-08-22 | 2011-05-18 | 207
1127000203 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-10 | 2011-05-31 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 11975 | Yes |  |  | lari carboz | 2011-07-30 | 2011-05-10 | 9365
1127000305 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-29 | 2011-07-15 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 170 | Yes |  |  | lari carboz | 2011-08-24 | 2011-06-29 | 170
1127000307 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-29 | 2011-07-29 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2738 | Yes |  |  | lari carboz | 2011-12-06 | 2011-06-29 | 2738
1127000320 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-18 | 2011-08-31 | ABAR | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 7320 | Yes |  |  | alfies benjamin | 2011-09-27 | 2011-07-18 | 7998
1127000323 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-16 | 2011-08-19 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 3046 | Yes |  |  | lari carboz | 2011-09-28 | 2011-07-09 | 681
1127000317 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-18 | 2011-08-31 | ABAR | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 3651 | Yes |  |  | alfies benjamin | 2011-09-27 | 2011-07-18 | 3430
1127000354 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-18 | 2011-08-31 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 46 | Yes |  |  | ali gobain | 2011-10-09 | 2011-07-18 | 46
1127000340 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-18 | 2011-08-31 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2445.5 | Yes |  |  | lari carboz | 2011-11-26 | 2011-07-18 | 2040
1027000520 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-07-27 | 2011-08-27 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 8188 | Yes |  |  | ernesto e. lai | 2011-08-23 | 2011-07-27 | 8448
1127000002 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-07-27 | 2011-09-07 | BAYS | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6397 | Yes |  |  | jomeel g. antonio | 2012-01-24 | 2011-07-27 | 6372
1127000349 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-07-12 | 2011-08-26 | KWBH | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 210 | Yes |  |  | ernesto e. lai | 2011-07-23 | 2011-07-12 | 315
1127000350 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-07-12 | 2011-08-26 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 451 | Yes |  |  | lari carboz | 2011-08-06 | 2011-07-12 | 467
1127000297 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-19 | 2011-07-09 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 383 | Yes |  |  | lari carboz | 2011-06-27 | 2011-06-19 | 383
1127000231 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-07-27 | 2011-09-07 | DAMD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 22197 | Yes |  |  | alfies benjamin | 2011-10-29 | 2011-07-27 | 25797
1127000241 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-07-27 | 2011-09-07 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 3908.5 | Yes |  |  | ali gobain | 2012-01-11 | 2011-07-27 | 10099.2
1127000268 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-07-27 | 2011-09-07 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 159 | Yes |  |  | ali gobain | 2011-08-10 | 2011-07-27 | 159
1127000096 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-30 | 2011-06-03 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 10867.2 | Yes |  |  | ali gobain | 2011-09-03 | 2011-04-30 | 10867.2
1127000099 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-30 | 2011-06-03 | BAYS | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 10530 | Yes |  |  | jomeel g. antonio | 2011-05-15 | 2011-04-30 | 10530
1127000126 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-07-27 | 2011-09-07 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6759.4 | Yes |  |  | ernesto e. lai | 2011-12-24 | 2011-07-27 | 8981
1127000176 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-18 | 2011-05-08 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 487 | Yes |  |  | lari carboz | 2011-07-13 | 2011-04-18 | 216
1127000182 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-18 | 2011-05-08 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 119 | Yes |  |  | lari carboz | 2011-04-25 | 2011-04-18 | 119
1127000178 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-18 | 2011-05-08 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 394.5 | Yes |  |  | lari carboz | 2011-09-11 | 2011-04-18 | 394.5
1127000177 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-18 | 2011-05-08 | SHUQ | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 282.8 | Yes |  |  | jomeel g. antonio | 2011-06-20 | 2011-04-18 | 297
1127000163 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-04-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 34874.2 | Yes |  |  | lari carboz | 2011-05-24 | 2011-03-20 | 36044
1127000169 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-26 | 2011-04-30 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 1394 | Yes |  |  | agobain | 2011-04-24 | 2011-03-26 | 1274
1127000167 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-05 | 2011-04-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 8274 | Yes |  |  | lari carboz | 2011-05-10 | 2011-04-05 | 8589
1127000121 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-05 | 2011-05-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 12555 | Yes |  |  | lari carboz | 2011-11-19 | 2011-04-05 | 11430
1127000140 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-05 | 2011-04-30 | ABAR | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2985.58 | Yes |  |  | alfies benjamin | 2011-08-06 | 2011-04-05 | 1966
1127000097 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 4500 | Yes |  |  | agobain | 2011-11-19 | 2011-04-13 | 4830
1127000084 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 207 | Yes |  |  | lari carboz | 2011-09-19 | 2011-04-13 | 207
1127000071 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-06 | 2011-04-20 | DARB | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2625 | Yes |  |  | jomeel g. antonio | 2011-10-24 | 2011-04-06 | 2657
1127000028 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-06 | 2011-04-20 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 318 | Yes |  |  | lari carboz | 2011-04-19 | 2011-04-06 | 129
1127000024 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-06 | 2011-04-20 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 293 | Yes |  |  | lari carboz | 2011-04-11 | 2011-04-06 | 295
1127000042 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-06 | 2011-04-26 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 9478.1 | Yes |  |  | ernesto e. lai | 2011-06-20 | 2011-04-06 | 12425.1
1127000056 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-06 | 2011-04-26 | SAMI | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 4955.6 | Yes |  |  | ernesto e. lai | 2011-06-13 | 2011-04-06 | 6678.2
1027000006 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 35879.6 | Yes |  | Held Order Master Sheet | lari carboz | 2010-10-02 | 2010-06-07 | 79568
0927000581 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 129 | Yes |  | Held Order Master Sheet | lari carboz | 2010-06-14 | 2010-06-07 | 207
1027000050 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 1767.9 | Yes |  | Held Order Master Sheet | lari carboz | 2010-10-02 | 2010-06-07 | 1724
1027000167 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6389.6 | Yes |  | Held Order Master Sheet | lari carboz | 2010-11-06 | 2010-06-07 | 6240
1027000554 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-09 | 2011-04-09 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 1199 | Yes |  |  | ali gobain | 2011-04-19 | 2011-03-09 | 1700
1027000262 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-26 | 2010-07-20 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 128879.7 | Yes |  |  | lari carboz | 2010-07-17 | 2010-06-26 | 128893.7
1027000182 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | ABAR | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 2362.5 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-07-12 | 2010-06-07 | 3000
1027000546 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-26 | 2011-09-06 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 764.16 | Yes |  |  | lari carboz | 2011-09-28 | 2011-07-26 | 764.16
1027000487 | 90711 | STC CREW | 2010-12-25 | 2011-01-20 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued |  |  |  | STC CREW JR | lari carboz | 2011-07-31 | 2010-12-25 | 30
1027000419 | 90711 | STC CREW | 2010-12-01 | 2010-12-07 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued |  |  |  | STC CREW | lari carboz | 2010-12-05 | 2010-12-01 | 46
1127000224 | 90711 | STC CREW | 2011-05-21 | 2011-06-30 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued |  |  |  | done by stc crew | ernesto e. lai | 2011-06-29 | 2011-05-21 | 5266
1127000144 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-27 | 2011-06-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 128.64 | Yes |  |  | lari carboz | 2011-06-27 | 2011-04-27 | 128.64
1027000069 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-05-08 | 2010-06-20 | FRSN | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 730.3 | Yes |  | Approved From Walid Hesham Reshwan | alfies benjamin | 2010-10-10 | 2010-05-01 | 977.4
1027000004 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 170.1 | Yes |  | Email From: Maynah H. Mohammed | ernesto e. lai | 2010-04-07 | 2010-03-17 | 170.1
0927000692 | STC_2008 | STC CREW | 2009-12-22 | 2010-01-04 | ABAR | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued |  |  |  | less than 100 SAR (STC CREW) | alfies benjamin | 2010-01-02 | 2009-12-22 | 56.7
1027000396 | STC_2008 | STC CREW | 2010-10-03 | 2010-10-03 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued |  |  |  | STCM CREW | lari carboz | 2010-10-11 | 2010-10-03 | 127
1027000044 | STC_2008 | STC CREW | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued |  |  |  | STC CREW | lari carboz | 2010-04-28 | 2010-03-17 | 370.9
1027000032 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 170.1 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-04-10 | 2010-03-17 | 200.8
0927000588 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | BAYS | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 1160.1 | Yes |  | Email From: Maynah H. Mohammed | jomeel g. antonio | 2010-04-24 | 2010-03-17 | 1190.8
1027000058 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 810 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-03-31 | 2010-03-17 | 840.7
0927000548 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-17 | 2010-07-28 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 143.2 | Yes |  | Send Email In 2010/03/06 To Riyadh M. Al Hwyde ( less than 3000 SAR) | ali m. gobain | 2010-08-07 | 2010-07-17 | 143.2
1127000008 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-03-02 | 2011-04-02 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 5135.15 | Yes |  |  | ernesto e. lai | 2011-04-30 | 2011-03-01 | 5670
1127000022 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-03-02 | 2011-04-02 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 12081.7 | Yes |  |  | ernesto e. lai | 2011-04-24 | 2011-03-01 | 14697
1127000091 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-03-14 | 2011-03-26 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 9069.5 | Yes |  | Jeel AlFursan Est. Completed | lari carboz | 2011-03-20 | 2011-03-13 | 10677.3
1127000262 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-29 | 2011-06-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 15057.65 | Yes |  |  | lari carboz | 2011-06-14 | 2011-05-29 | 10826.1
1127000238 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-21 | 2011-06-30 | SLHD | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 5862.2 | Yes |  |  | ernesto e. lai | 2011-05-31 | 2011-05-21 | 9102.2
1027000280 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-08-09 | 2010-09-30 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 244.8 | Yes |  |  | lari carboz | 2010-09-27 | 2010-08-24 | 244.8
1027000253 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-06 | 2010-09-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 4470.1 | Yes |  |  | lari carboz | 2011-05-31 | 2010-07-06 | 3568.2
1027000233 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-06 | 2010-09-10 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 313.6 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2010-07-10 | 2010-07-06 | 313.6
1027000259 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-06 | 2010-09-10 | SBYA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 14178 | Yes |  | Email From: Abdulmoti A. Dahlawi | ali m. gobain | 2011-04-17 | 2010-07-06 | 15789.8
1027000135 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-05-15 | 2010-06-30 | ABAR | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 3668.4 | Yes |  | Email From: Abdulmoti A. Dahlawi | alfies benjamin | 2010-06-28 | 2010-05-09 | 3963
0927000696 | 73803 | Mohemmed Bin Gerboo EST. | 2009-12-28 | 2010-01-28 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6799.11 | Yes |  | Email From: Abdulmoti A. Dahlawi Sent to Aljarboo | lari carboz | 2010-01-04 | 2009-12-28 | 7169.45
0927000443 | 73803 | Mohemmed Bin Gerboo EST. | 2010-01-22 | 2010-02-22 | JIZA | held order | Held Order - EBU - 2012 | completed | 2012 objective design issued | 6187.2 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2010-10-06 | 2010-01-17 | 3537.3
1027000523 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 5511.36 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-03-13 | 2011-09-19 | 6480
1027000550 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 877.44 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-02-06 | 2011-09-19 | 916.2
0927000593 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 4463.758 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-02-02 | 2011-09-19 | 7180.28
0927000597 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-03 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 3256.3 | PM In Progress |  |  | elai | 2013-02-10 | 2011-04-13 | 4032
1027000019 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-20 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 10912.64 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | abenjamin | 2013-02-10 | 2011-09-19 | 9058.188
1027000407 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2001.7296 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-02-02 | 2011-09-19 | 4546.42
1027000400 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 3644.16 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-03-03 | 2011-09-19 | 5740.8
1027000274 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-08 | 2011-07-09 | DAMD | held order | Held Order - In Scope | completed | 2011 objective design issued | 6708.248 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | abenjamin | 2013-02-10 | 2011-06-08 | 8620.44
1027000362 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-10-17 | 2011-11-30 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 1198.08 | PM In Progress |  |  | abenjamin | 2013-01-26 | 2011-10-17 | 1198.08
1027000531 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-18 | 2011-10-20 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 10010.78 | PM In Progress |  |  | agobain | 2013-02-10 | 2011-09-18 | 9525.42
1027000260 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-03 | 2011-09-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 7603.2 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-09-03 | 8064
1027000438 | 76677 | Mohemmed Bin Gerboo EST. | 2011-01-01 | 2011-03-15 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 43145.79 | DM In Progress |  |  | elai | 2011-08-10 | 2011-01-01 | 19320
1027000485 | 76677 | Mohemmed Bin Gerboo EST. | 2011-09-18 | 2011-10-20 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 8634.76 | DM In Progress | pu price adjustment with bat/pcc |  | agobain | 2011-11-19 | 2011-09-18 | 4315.2
0927000274 | 76677 | Mohemmed Bin Gerboo EST. | 2011-04-18 | 2011-05-31 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 3201.52 | DM In Progress |  |  | elai | 2011-11-05 | 2011-04-18 | 1922.4
1027000310 | 81343 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-27 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 2296.32 | PM In Progress |  |  | abenjamin | 2011-05-07 | 2011-04-13 | 2496
1027000345 | 81002 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 6349.38 | CM In Progress |  |  | lscarboz | 2013-04-17 | 2010-09-20 | 3582.64
1027000439 | 81002 | Mohemmed Bin Gerboo EST. | 2011-09-20 | 2011-09-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2232.96 | CM In Progress |  | COMPLETED | lscarboz | 2011-09-20 | 2011-09-20 | 452.16
1027000157 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SLHD | held order | Held Order - In Scope | completed | 2011 objective design issued | 3194.88 | PM In Progress |  |  | elai | 2013-03-20 | 2011-09-19 | 4568.46
1027000541 |  | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | BAYS | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  | need cr | Zero Design | jomeel g. antonio | 2011-12-19 | 2011-03-19 | 1288.32
1027000542 |  | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | BAYS | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  | need cr | Zero Design | jomeel g. antonio | 2011-12-19 | 2011-03-19 | 2105.71
1027000341 |  | Mohemmed Bin Gerboo EST. | 2013-04-13 | 2013-05-28 | JIZA | held order | Held Order - In Scope | cancelled | 2010 objective design issued |  |  | job wo cancelled | Cacncelled By Customer | lari carboz |  | 2010-10-16 | 0
1027000194 |  | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  | need cr | Zero Design | agobain | 2011-12-19 | 2011-04-17 | 2558.81
1027000328 |  | Mohemmed Bin Gerboo EST. | 2013-04-13 | 2013-05-28 | SAMI | held order | Held Order - In Scope | cancelled | 2010 objective design issued |  |  | job wo cancelled | Canceled By Customer Saber | ernesto e. lai |  | 2010-10-16 | 0
1027000333 |  | Mohemmed Bin Gerboo EST. | 2011-01-01 | 2011-03-15 | ARDH | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  | need cr | Zero Design | alfies benjamin | 2012-01-03 | 2011-01-01 | 1786.01
1027000340 |  | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  | need cr |  | agobain | 2012-01-03 | 2011-04-17 | 2305.9
1027000425 |  | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  | need cr | Zero Design | ali m. gobain | 2011-12-19 | 2011-04-13 | 198.7
1027000315 |  | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-30 | SHUQ | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  | need cr | Zero Design | jomeel g. antonio | 2012-05-13 | 2011-04-13 | 950.32
1027000478 |  | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  | need cr | Zero Design | ali m. gobain | 2011-12-19 | 2011-04-13 | 246.7
0827000647 |  | Mohemmed Bin Gerboo EST. | 2011-03-09 | 2011-04-09 | SHUQ | Held order | Held Order - In Scope | completed | 2011 objective design issued |  |  | need cr | Zero Design | jomeel g. antonio | 2012-05-13 | 2011-03-09 | 4827.8
0927000441 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 120 | Yes |  | less than 3000 SAR (Big Net) | alfies benjamin | 2009-07-26 | 2009-07-13 | 120
0927000401 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 260 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-07-13 | 2009-07-04 | 312
0927000403 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 387 | Yes |  | less than 3000 SAR (Big Net) | ernesto e. lai | 2009-07-14 | 2009-07-04 | 543
0927000407 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 2886.5 | Yes |  | less than 3000 SAR (Big Net) | ernesto e. lai | 2009-07-18 | 2009-07-04 | 3422.5
0827000589 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 99 | Yes |  | less than 3000 SAR (Big net) | ernesto e. lai | 2009-03-14 | 2008-12-01 | 119
0827000573 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 83 | Yes |  | less than 3000 SAR (Big net) | ernesto e. lai | 2008-12-31 | 2008-11-24 | 235
0827000323 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 6427.7 | Yes |  | Old Progress | alfies benjamin | 2008-12-25 | 2008-10-25 | 6772
0827000196 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-03-12 | 2008-03-19 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 4206 | Yes |  |  | federico ---- aguilar | 2008-12-24 | 2008-04-05 | 4206
0827000195 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 1476.2 | Yes |  |  | federico ---- aguilar | 2008-03-12 | 2008-04-05 | 1476.2
0927000013 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 516 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-04-18 | 2009-01-17 | 461
0927000228 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 333 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-04-18 | 2009-04-15 | 391
0927000342 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 137.1 | Yes |  | less than 3000 SAR (Big net) | ernesto e. lai | 2009-07-01 | 2009-06-22 | 137.1
0927000315 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 225 | Yes |  | less than 3000 SAR (Big net) | ernesto e. lai | 2009-07-01 | 2009-06-29 | 225
0827000602 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 83 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-01-16 | 2008-12-16 | 83
0827000624 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 99 | Yes |  | less than 3000 SAR (Big Net) | lari carboz | 2010-01-20 | 2008-12-22 | 99
0827000628 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 117 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2009-01-22 | 2008-12-22 | 117
0927000012 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 242 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-04-14 | 2009-01-17 | 179
0927000045 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 369 | Yes |  | cover by wo#0927000194 | lari carboz | 2009-04-18 | 2009-02-01 | 369
0627000906 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2007-12-30 | 2008-01-30 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 9925 | Yes |  |  | lari carboz | 2007-08-01 | 2008-04-05 | 9925
0827000242 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2986 | Yes |  |  | lari carboz | 2008-03-28 | 2008-04-05 | 2986
0827000571 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 99 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2008-12-31 | 2008-11-24 | 99
0827000194 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 127 | Yes |  |  | ali m. gobain | 2008-03-15 | 2008-04-05 | 127
0927000428 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 127 | Yes |  | less than 3000 SAR (Big Net) | lari carboz | 2009-07-22 | 2009-07-07 | 157
0927000429 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 3484 | Yes |  | less than 3000 SAR (Big Net) | lari carboz | 2009-08-03 | 2009-07-07 | 1536.5
0927000420 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2504 | Yes |  | Email From: Abdulmoti A. Dahlawi Sent: 3/Oct/2009 10:50 AM | lari carboz | 2009-10-21 | 2009-07-04 | 2504
0927000339 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 411 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2009-07-13 | 2009-06-22 | 411
0927000340 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1125 | Yes |  | less than 3000 SAR (Big Net) | ali m. gobain | 2009-08-19 | 2009-06-22 | 1125
0927000336 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2080 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-06-28 | 2009-06-22 | 2080
0927000337 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 127 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-06-30 | 2009-06-22 | 665
0927000305 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 395 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-06-08 | 2009-06-06 | 395
0927000306 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 476 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-05-31 | 2009-05-30 | 476
0927000307 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 135 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-06-06 | 2009-06-03 | 135
0927000316 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | DARB | held order | Held Order - In Scope | completed | 2010 objective design issued | 555 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2009-06-02 | 2009-05-30 | 555
0927000319 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 117 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-05-27 | 2009-05-25 | 117
0927000295 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 433 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-07-08 | 2009-07-04 | 413
0927000256 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 630 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-05-02 | 2009-04-29 | 630
0927000248 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 99 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2009-05-02 | 2009-04-29 | 99
0927000249 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 99 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-05-02 | 2009-04-29 | 99
1027000429 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-03-19 | 2011-04-30 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 525 | Yes |  |  | alfies benjamin | 2011-10-11 | 2011-03-19 | 525
1027000505 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 30 | Yes |  |  | ali gobain | 2011-10-24 | 2011-09-19 | 30
1027000351 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-03 | 2011-08-12 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 4460.2 | Yes |  |  | alfies benjamin | 2011-10-04 | 2011-07-03 | 5565
1027000376 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 5315 | Yes |  |  | lari carboz | 2011-12-06 | 2011-09-19 | 5315
1027000216 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 9600 | Yes |  |  | ali gobain | 2011-11-21 | 2011-09-19 | 9600
1027000123 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-29 | 2011-07-31 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 2625 | Yes |  |  | alfies benjamin | 2011-09-28 | 2011-06-29 | 3750
1027000281 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-24 | 2011-06-03 | SHUQ | held order | Held Order - In Scope | completed | 2011 objective design issued | 7074.3 | Yes |  |  | jomeel g. antonio | 2011-08-21 | 2011-04-30 | 4919.4
1027000222 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-24 | 2011-06-04 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 5072.1 | Yes |  |  | alfies benjamin | 2011-06-13 | 2011-04-30 | 5432.1
1027000202 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-30 | 2011-06-03 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 6753 | Yes |  |  | agobain | 2011-05-29 | 2011-04-30 | 6880
1027000391 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3670 | Yes |  |  | lari carboz | 2011-05-25 | 2011-04-13 | 3670
1027000357 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | BAYS | held order | Held Order - In Scope | completed | 2011 objective design issued | 2370 | Yes |  |  | jomeel g. antonio | 2011-05-09 | 2011-04-13 | 2370
1027000319 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 2488 | Yes |  |  | alfies benjamin | 2011-06-05 | 2011-04-13 | 2700
1027000317 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2672.5 | Yes |  |  | agobain | 2011-06-25 | 2011-04-13 | 2672.5
1027000325 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2419 | Yes |  |  | agobain | 2011-06-04 | 2011-04-13 | 2419
1027000344 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 9574 | Yes |  | Completed in 04/07/2011 | ernesto e. lai | 2011-08-24 | 2011-04-13 | 14824
1027000452 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-24 | 2011-06-03 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 8117 | Yes |  |  | lari carboz | 2011-06-27 | 2011-04-20 | 8149
1027000420 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2138 | Yes |  |  | agobain | 2011-05-09 | 2011-04-13 | 3471.5
1027000414 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 5458.4 | Yes |  |  | agobain | 2011-05-09 | 2011-04-13 | 4155
1027000410 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3405 | Yes |  |  | lari carboz | 2011-05-14 | 2011-04-13 | 3405
1027000399 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2756 | Yes |  |  | agobain | 2011-05-09 | 2011-04-13 | 3150
1027000395 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3452.5 | Yes |  |  | lari carboz | 2011-05-25 | 2011-04-13 | 3452.5
1027000525 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-30 | 2011-06-03 | BAYS | held order | Held Order - In Scope | completed | 2011 objective design issued | 8098.5 | Yes |  |  | jomeel g. antonio | 2011-06-20 | 2011-04-19 | 8173.5
1027000301 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-24 | 2011-06-04 | SHUQ | held order | Held Order - In Scope | completed | 2011 objective design issued | 10033.4 | Yes |  |  | jomeel g. antonio | 2011-08-21 | 2011-04-30 | 10033.4
1027000052 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-30 | 2011-06-03 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 6443.5 | Yes |  |  | ali m. gobain | 2011-09-14 | 2011-04-30 | 6473.5
0927000271 | 75745 | Mohemmed Bin Gerboo EST. | 2010-12-13 | 2011-02-15 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3102 | Yes |  |  | lari carboz | 2011-05-21 | 2010-12-17 | 3210
0927000365 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 4578.4 | Yes |  |  | ali m. gobain | 2011-09-03 | 2011-04-13 | 3394
0927000431 | 75745 | Mohemmed Bin Gerboo EST. | 2010-07-05 | 2010-08-25 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 24033.8 | Yes |  | By the Technical Notes | jomeel g. antonio | 2010-07-26 | 2010-07-05 | 24099.5
0827000507 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-18 | 2011-05-31 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 5148.5 | Yes |  |  | ali m. gobain | 2011-06-01 | 2011-04-18 | 4318
0827000516 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 4200.6 | Yes |  | Held Order Master Sheet | ali m. gobain | 2010-08-04 | 2010-06-07 | 5974
0827000585 | 75745 | Mohemmed Bin Gerboo EST. | 2008-12-01 | 2008-12-31 | BAYS | Held order | Held Order - In Scope | completed | 2011 objective design issued | 2547 | Yes |  |  | jomeel g. antonio | 2011-10-10 | 2011-03-09 | 2599
1027000538 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 5280 | Yes |  |  | lari carboz | 2011-06-13 | 2011-03-19 | 5280
0927000705 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1422 | Yes |  | Held Order Master Sheet | lari carboz | 2010-06-20 | 2010-06-07 | 1422
0927000698 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 265 | Yes |  | Held Order Master Sheet | ali m. gobain | 2010-06-13 | 2010-06-07 | 265
0927000697 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 113 | Yes |  | Held Order Master Sheet | ali m. gobain | 2010-06-13 | 2010-06-07 | 129
1027000034 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 281 | Yes |  | Held Order Master Sheet | jomeel g. antonio | 2010-06-19 | 2010-06-07 | 265
1027000038 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 6002 | Yes |  | Held Order Master Sheet | lari carboz | 2010-06-28 | 2010-06-07 | 5370
0927000714 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 282 | Yes |  | Held Order Master Sheet | ali m. gobain | 2010-06-13 | 2010-06-07 | 282
0927000666 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1919 | Yes |  | Held Order Master Sheet | ali m. gobain | 2010-07-05 | 2010-06-07 | 1949
0927000650 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 379 | Yes |  | Held Order Master Sheet | lari carboz | 2010-10-02 | 2010-06-07 | 370
0927000653 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 3007.6 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2009-12-15 | 2009-12-09 | 3038
0927000637 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 157 | Yes |  | Held Order Master Sheet | lari carboz | 2011-01-05 | 2010-06-07 | 141
0927000616 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 330 | Yes |  | Add 39M to House By Customer | ali m. gobain | 2010-11-27 | 2010-06-07 | 2112
0927000531 | 75745 | Mohemmed Bin Gerboo EST. | 2010-03-04 | 2010-04-18 | JIZA | Held order | Held Order - In Scope | completed | 2011 objective design issued | 630 | Yes |  | More than 7 times the notice of the Customer to build a wall without response | lari carboz | 2011-04-20 | 2011-03-09 | 345
1027000097 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 10559.2 | Yes |  | Held Order Master Sheet | lari carboz | 2011-02-05 | 2010-06-07 | 2616.6
1027000108 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 595 | Yes |  | Held Order Master Sheet | ali m. gobain | 2010-10-02 | 2010-06-07 | 745
1027000145 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 471 | Yes |  | Held Order Master Sheet | jomeel g. antonio | 2010-06-14 | 2010-06-07 | 471
1027000126 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1350 | Yes |  | Held Order Master Sheet | ali m. gobain | 2010-08-04 | 2010-06-07 | 1155
1027000114 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | Held order | Held Order - In Scope | completed | 2011 objective design issued | 1755 | Yes |  |  | lari carboz | 2011-02-05 | 2010-06-07 | 1155
0827000555 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 3225 | Yes |  | Held Order Master Sheet | ali m. gobain | 2010-07-07 | 2010-06-07 | 3225
1027000161 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1484.3 | Yes |  | Held Order Master Sheet | lari carboz | 2011-02-05 | 2010-06-07 | 922.54
1027000130 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 1980 | Yes |  |  | lari carboz | 2011-05-21 | 2010-10-16 | 1680
1027000133 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 145 | Yes |  | Held Order Master Sheet | lari carboz | 2011-01-08 | 2010-06-07 | 1645
1027000139 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 665 | Yes |  | Held Order Master Sheet | lari carboz | 2010-06-15 | 2010-06-07 | 665
1027000127 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 265 | Yes |  | Held Order Master Sheet | jomeel g. antonio | 2010-06-14 | 2010-06-07 | 265
1027000203 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | DARB | held order | Held Order - In Scope | completed | 2010 objective design issued | 2151.1 | Yes |  |  | jomeel g. antonio | 2011-05-18 | 2010-10-16 | 2045
1027000175 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 928.2 | Yes |  | Held Order Master Sheet | lari carboz | 2010-06-15 | 2010-06-07 | 729.4
1027000177 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 1872 | Yes |  | Held Order Master Sheet | jomeel g. antonio | 2010-10-02 | 2010-06-07 | 2135
1027000187 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | DARB | held order | Held Order - In Scope | completed | 2010 objective design issued | 2211.3 | Yes |  |  | jomeel g. antonio | 2011-05-18 | 2010-06-07 | 77
1027000246 | 75745 | Mohemmed Bin Gerboo EST. | 2010-05-01 | 2010-05-15 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 0 |  |  | as per appved by Ali on 30-10-2010 with MOT project | lari carboz | 2010-11-02 | 2010-11-01 | 0
1027000147 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 444 | Yes |  | Held Order Master Sheet | ali m. gobain | 2010-06-26 | 2010-06-07 | 444
1027000432 | 75745 | Mohemmed Bin Gerboo EST. | 2010-12-01 | 2011-01-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 674 | Yes |  |  | lari carboz | 2011-10-02 | 2010-11-27 | 674
1027000342 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1605 | Yes |  | Need Design | lari carboz | 2010-12-18 | 2010-10-16 | 1530
1027000338 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 600 | Yes |  |  | lari carboz | 2010-11-29 | 2010-10-16 | 1125
1027000457 | 75745 | Mohemmed Bin Gerboo EST. | 2010-12-01 | 2011-01-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 14063.8 | Yes |  |  | lari carboz | 2011-05-07 | 2010-11-27 | 12651.4
1027000381 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 665 | Yes |  |  | lari carboz | 2010-11-06 | 2010-10-16 | 665
1027000393 | 75745 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 7466.8 | Yes |  | NOT YET PERMINATED . WAITING FOR HH . COCTOMER TO PRDVIDE HH . 20-12-2010 | lari carboz | 2010-12-18 | 2010-09-20 | 9075
1027000416 | 75745 | Mohemmed Bin Gerboo EST. | 2010-12-01 | 2011-01-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 4604.4 | Yes |  |  | lari carboz | 2011-05-21 | 2010-11-27 | 13876.5
1027000405 | 75745 | Mohemmed Bin Gerboo EST. | 2010-12-01 | 2011-01-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 6669.38 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2011-01-09 | 2010-11-27 | 7642.4
1027000548 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 411 | Yes |  |  | lari carboz | 2011-09-11 | 2011-04-13 | 411
1027000549 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-16 | 2011-05-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 405 | Yes |  |  | lari carboz | 2011-09-11 | 2011-04-16 | 405
1027000471 | 75745 | Mohemmed Bin Gerboo EST. | 2011-01-01 | 2011-03-15 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 5743.4 | Yes |  | Approved by as per email 25/12/2010 from Walid | ali m. gobain | 2011-03-02 | 2011-01-01 | 3728.2
1027000484 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | JIZA | Held order | Held Order - In Scope | completed | 2011 objective design issued | 1659 | Yes |  |  | lari carboz | 2011-08-07 | 2011-04-17 | 1645
1027000539 | 75745 | Mohemmed Bin Gerboo EST. | 2011-01-01 | 2011-03-15 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 688 | Yes |  | Approved by as per email 25/12/2010 from Walid | lari carboz | 2011-01-30 | 2011-01-01 | 816
1027000372 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 922 | Yes |  | Yehya hkami stc | lari carboz | 2011-03-07 | 2010-10-16 | 290
1027000552 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-16 | 2011-05-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2798 | Yes |  |  | lari carboz | 2011-10-12 | 2011-04-16 | 3818
1027000553 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-16 | 2011-05-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2708 | Yes |  |  | lari carboz | 2011-08-06 | 2011-04-16 | 2630
1027000555 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-16 | 2011-05-30 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2336 | Yes |  |  | ali m. gobain | 2011-05-24 | 2011-04-16 | 2334.6
1027000529 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | DAMD | held order | Held Order - In Scope | completed | 2011 objective design issued | 2928 | Yes |  |  | alfies benjamin | 2011-04-20 | 2011-03-19 | 2236
1027000473 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 3086 | Yes |  |  | alfies benjamin | 2011-05-07 | 2011-03-20 | 2893
1027000474 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 46 | Yes |  |  | ali m. gobain | 2011-05-07 | 2011-04-13 | 46
1027000513 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 2130 | Yes |  |  | jomeel g. antonio | 2011-10-24 | 2011-04-13 | 2581
1027000517 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 193 | Yes |  |  | ernesto e. lai | 2011-05-08 | 2011-04-13 | 235
1027000518 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-13 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2890 | Yes |  |  | ali m. gobain | 2011-05-24 | 2011-04-13 | 2630
1027000519 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 290 | Yes |  |  | ali m. gobain | 2011-06-01 | 2011-04-13 | 290
1027000521 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2860 | Yes |  |  | ali m. gobain | 2011-05-24 | 2011-04-13 | 2630
1027000359 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 342 | Yes |  |  | lari carboz | 2010-11-06 | 2010-10-16 | 342
1027000384 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 99 | Yes |  |  | lari carboz | 2010-10-25 | 2010-10-16 | 99
1027000388 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 99 | Yes |  |  | jomeel g. antonio | 2010-10-25 | 2010-10-16 | 99
1027000367 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 792 | Yes |  |  | lari carboz | 2011-01-31 | 2010-10-16 | 792
1027000312 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 207 | Yes |  | Completed | lari carboz | 2010-12-05 | 2010-10-16 | 207
1027000316 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 411 | Yes |  |  | lari carboz | 2011-01-30 | 2010-10-16 | 411
1027000332 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 980 | Yes |  |  | lari carboz | 2010-11-27 | 2010-10-16 | 980
1027000305 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 46 | Yes |  |  | jomeel g. antonio | 2011-01-30 | 2010-10-16 | 421
1027000334 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 427 | Yes |  |  | lari carboz | 2010-11-29 | 2010-10-16 | 427
1027000318 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-03 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 294 | Yes |  |  | ali m. gobain | 2010-10-06 | 2010-10-03 | 294
1027000330 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2424 | Yes |  |  | lari carboz | 2011-01-08 | 2010-10-16 | 720
1027000250 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 621.6 | Yes |  |  | ali m. gobain | 2011-03-14 | 2010-10-16 | 621.6
1027000263 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 630 | Yes |  |  | jomeel g. antonio | 2011-04-18 | 2010-10-16 | 930
1027000284 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 411 | Yes |  |  | ali m. gobain | 2010-11-06 | 2010-10-16 | 411
1027000298 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 919 | Yes |  |  | lari carboz | 2010-11-29 | 2010-10-16 | 411
1027000299 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 538 | Yes |  |  | ali m. gobain | 2010-11-02 | 2010-10-16 | 411
1027000309 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 207 | Yes |  |  | ali m. gobain | 2011-03-07 | 2010-10-16 | 207
1027000235 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 8248.6 | Yes |  |  | jomeel g. antonio | 2011-05-07 | 2010-10-16 | 725
1027000240 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 830 | Yes |  |  | ali m. gobain | 2010-11-02 | 2010-10-16 | 846
1027000244 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 665 | Yes |  |  | lari carboz | 2011-01-31 | 2010-10-16 | 665
1027000245 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 547 | Yes |  |  | lari carboz | 2011-05-30 | 2010-10-16 | 2965
1027000248 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 411 | Yes |  |  | ali m. gobain | 2010-11-02 | 2010-10-16 | 411
1027000249 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 345 | Yes |  |  | ali m. gobain | 2010-10-25 | 2010-10-16 | 345
1027000247 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 70.2 | Yes |  |  | ali m. gobain | 2010-11-06 | 2010-10-16 | 70.2
1027000252 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1808 | Yes |  |  | lari carboz | 2011-02-05 | 2010-10-16 | 2160
1027000302 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 635 | Yes |  |  | lari carboz | 2011-03-07 | 2010-10-16 | 411
1027000256 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1446.5 | Yes |  | STC CREW | lari carboz | 2011-02-19 | 2010-10-16 | 1446.5
0927000101 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 2363.5 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-07-12 | 2010-06-07 | 3278.08
0827000348 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-18 | 2011-05-31 | BAYS | held order | Held Order - In Scope | completed | 2011 objective design issued | 4623.8 | Yes |  |  | ernesto e. lai | 2011-05-24 | 2011-04-18 | 4774.5
0827000597 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 5458.7 | Yes |  | Held Order Master Sheet | ernesto e. lai | 2010-07-17 | 2010-06-07 | 5470.7
0927000576 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 1575 | Yes |  | Held Order Master Sheet | alfies benjamin | 2011-02-20 | 2010-06-07 | 1146
0927000586 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 8791.2 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-10-16 | 2010-06-07 | 5094
0927000584 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 99 | Yes |  | Held Order Master Sheet | alfies benjamin | 2011-02-17 | 2010-06-07 | 119
0927000677 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 1347 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-10-16 | 2010-06-07 | 1347
1027000023 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 99 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-06-15 | 2010-06-07 | 119
1027000028 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 1709.2 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-07-12 | 2010-06-07 | 2002
1027000064 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 2496 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-06-15 | 2010-06-07 | 1976
1027000077 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 6805 | Yes |  | Held Order Master Sheet | ernesto e. lai | 2010-09-26 | 2010-06-07 | 9808
1027000132 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | SLHD | held order | Held Order - In Scope | completed | 2011 objective design issued | 4357 | Yes |  |  | ernesto e. lai | 2011-05-25 | 2011-04-17 | 4458.7
1027000370 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-03-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 99 | Yes |  |  | lari carboz | 2011-04-11 | 2011-03-19 | 99
1027000397 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 665 | Yes |  |  | lari carboz | 2011-09-11 | 2011-04-13 | 665
1027000408 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 836 | Yes |  |  | lari carboz | 2011-04-23 | 2011-04-13 | 1145
1027000411 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 810 | Yes |  |  | lari carboz | 2011-04-30 | 2011-04-13 | 405
1027000412 | 75745 | Mohemmed Bin Gerboo EST. | 2010-12-01 | 2011-01-31 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 7435.1 | Yes |  |  | ernesto e. lai | 2011-06-13 | 2010-11-27 | 11349.2
1027000418 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 1905 | Yes |  |  | lari carboz | 2011-10-18 | 2011-04-13 | 1905
1027000445 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3212.1 | Yes |  |  | lari carboz | 2011-08-16 | 2011-04-13 | 2695.5
1027000422 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 206 | Yes |  |  | lari carboz | 2011-04-19 | 2011-04-13 | 1585
1027000427 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-26 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 681 | Yes |  |  | ali m. gobain | 2011-05-11 | 2011-04-13 | 681
1027000431 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 2775 | Yes |  |  | jomeel g. antonio | 2011-05-18 | 2011-04-13 | 1820
1027000433 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | BAYS | held order | Held Order - In Scope | completed | 2011 objective design issued | 2912 | Yes |  |  | jomeel g. antonio | 2011-06-01 | 2011-04-13 | 2630
1027000483 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | BAYS | held order | Held Order - In Scope | completed | 2011 objective design issued | 4408.6 | Yes |  |  | agobain | 2011-05-30 | 2011-04-13 | 3995
1027000440 | 75745 | Mohemmed Bin Gerboo EST. | 2011-01-01 | 2011-03-15 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 1397.6 | Yes |  |  | alfies benjamin | 2011-05-21 | 2011-01-01 | 2656
1027000467 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 3910.9 | Yes |  |  | ernesto e. lai | 2011-05-21 | 2011-04-13 | 3687.5
1027000469 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 413.1 | Yes |  |  | ernesto e. lai | 2011-07-09 | 2011-04-13 | 413.1
1027000453 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 3976.5 | Yes |  |  | alfies benjamin | 2011-05-07 | 2011-04-13 | 4576.8
1027000454 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 5118.5 | Yes |  |  | lari carboz | 2011-07-09 | 2011-03-19 | 5051
1027000456 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 520 | Yes |  |  | alfies benjamin | 2011-06-26 | 2011-04-13 | 260
1027000488 | 75745 | Mohemmed Bin Gerboo EST. | 2010-12-25 | 2011-01-20 | JIZA | Held order | Held Order - In Scope | completed | 2011 objective design issued | 87 | Yes |  |  | lari carboz | 2011-04-20 | 2010-12-25 | 121
1027000489 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 30 | Yes |  |  | lari carboz | 2011-04-19 | 2011-04-13 | 255
1027000490 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 30 | Yes |  |  | lari carboz | 2011-04-16 | 2011-04-13 | 186
1027000495 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3480 | Yes |  |  | lari carboz | 2011-10-18 | 2011-04-13 | 2655
1027000501 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 381 | Yes |  |  | lari carboz | 2011-04-23 | 2011-04-13 | 411
1027000502 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2880 | Yes |  |  | lari carboz | 2011-10-02 | 2011-04-13 | 2880
1027000498 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3846.9 | Yes |  |  | lari carboz | 2011-11-19 | 2011-04-13 | 3761
1027000499 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3154.3 | Yes |  |  | lari carboz | 2011-08-06 | 2011-04-13 | 3803
1027000507 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2428 | Yes |  |  | ali m. gobain | 2011-09-03 | 2011-04-13 | 2447
1027000331 | 75745 | Mohemmed Bin Gerboo EST. | 2010-09-25 | 2010-10-25 | DAMD | held order | Held Order - In Scope | completed | 2011 objective design issued | 14530.4 | Yes |  | Email From: Abdulmoti A. Dahlawi | alfies benjamin | 2010-10-24 | 2010-09-25 | 18445
1027000353 | 75745 | Mohemmed Bin Gerboo EST. | 2010-12-01 | 2011-01-31 | TWAL | held order | Held Order - In Scope | completed | 2011 objective design issued | 691 | Yes |  | Email From :Abdulmoti A. Dahlawi | ernesto e. lai | 2011-01-25 | 2010-11-27 | 691
1027000366 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 4551 | Yes |  |  | jomeel g. antonio | 2011-05-21 | 2011-03-19 | 3502.4
1027000390 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2340 | Yes |  |  | lari carboz | 2011-10-10 | 2011-04-13 | 2370
1027000172 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 3783.6 | Yes |  |  | jomeel g. antonio | 2011-05-21 | 2011-04-17 | 3643.8
1027000180 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 3529 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-06-15 | 2010-06-07 | 3338.1
1027000184 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 911.9 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-06-15 | 2010-06-07 | 1070
1027000185 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 207 | Yes |  |  | alfies benjamin | 2010-10-25 | 2010-10-16 | 207
1027000189 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 197.1 | Yes |  | Held Order Master Sheet | ernesto e. lai | 2010-06-14 | 2010-06-07 | 197.1
1027000190 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | SLHD | held order | Held Order - In Scope | completed | 2011 objective design issued | 3928.1 | Yes |  |  | ernesto e. lai | 2011-06-25 | 2011-04-17 | 4178.7
1027000186 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 4344.1 | Yes |  |  | alfies benjamin | 2011-05-07 | 2011-04-13 | 6817
1027000232 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 150 | Yes |  | Completed | alfies benjamin | 2010-12-05 | 2010-10-16 | 150
1027000234 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 4350 | Yes |  |  | alfies benjamin | 2011-10-10 | 2011-04-17 | 2860
1027000264 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 3083.7 | Yes |  |  | jomeel g. antonio | 2011-10-24 | 2011-04-17 | 3080.9
1027000270 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 372 | Yes |  |  | alfies benjamin | 2010-11-29 | 2010-10-16 | 356
1027000278 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-27 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 4525 | Yes |  |  | agobain | 2011-09-03 | 2011-04-17 | 4422.5
1027000287 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-03 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 1456 | Yes |  |  | alfies benjamin | 2011-05-07 | 2011-04-13 | 1456
1027000430 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-01-25 | 2011-02-25 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 28.8 | Yes |  |  | ali m. gobain | 2011-06-29 | 2011-01-25 | 28.8
1027000461 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-18 | 2011-07-08 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 2931.6476 | Yes |  |  | alfies benjamin | 2011-07-12 | 2011-06-18 | 3906.2
0927000630 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-12-24 | 2012-01-20 | DAMD | held order | Held Order - In Scope | completed | 2012 objective design issued | 2736 | Yes |  | Send Email In 2010/01/16 To Riyadh M. Al Hwyde (more than 3000 SAR) | alfies benjamin | 2012-02-19 | 2010-03-06 | 3840
1027000497 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-18 | 2011-07-18 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 5948.12 | Yes |  |  | jomeel g. antonio | 2011-09-13 | 2011-06-18 | 5948.12
1027000297 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-04-20 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 2188.8 | Yes |  |  | lari carboz | 2011-07-31 | 2011-04-13 | 2188.8
1027000106 | 90711 | STC CREW | 2010-08-21 | 2010-10-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  |  | STC CREW JR | lari carboz | 2011-06-29 | 2010-08-21 | 550
1027000515 | 90711 | STC CREW | 2011-01-04 | 2011-01-31 | TWAL | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  |  | DONE BY STC CREW | ernesto e. lai | 2011-01-24 | 2011-04-17 | 11772
0827000146 | 90711 | STC CREW | 2008-02-27 | 2008-03-08 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  |  | lari carboz | 2008-03-20 | 2008-04-05 | 2625
0827000634 | 90711 | STC CREW | 2011-06-05 | 2011-06-05 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  |  | ali m. gobain | 2011-06-05 | 2011-06-05 | 143
1027000371 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-03 | 2011-08-10 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 5806 | Yes |  |  | ali gobain | 2012-10-15 | 2011-07-03 | 5586.22
1027000379 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-18 | 2011-07-18 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 4917.12 | Yes |  |  | lari carboz | 2011-08-14 | 2011-06-18 | 4917.12
1027000449 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 7588.8 | Yes |  |  | lari carboz | 2011-12-07 | 2011-09-19 | 7228.8
0927000565 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-13 | BAYS | held order | Held Order - In Scope | completed | 2011 objective design issued | 5649.08 | Yes |  |  | jomeel g. antonio | 2012-06-16 | 2011-04-13 | 5649.08
0927000645 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-13 | DAMD | held order | Held Order - In Scope | completed | 2011 objective design issued | 4169.52 | Yes |  |  | alfies benjamin | 2011-07-11 | 2011-04-13 | 4562.16
1027000516 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3869.52 | Yes |  |  | lari carboz | 2012-01-08 | 2011-09-19 | 5831.02
1027000522 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-20 | 2011-10-20 | SBYA | held order | Held Order - In Scope | cancelled | 2011 objective design issued | 0 |  |  | Cancelled By Customer | ali m. gobain |  | 2011-09-20 | 95.02
0927000391 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-13 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 6961.93 | Yes |  |  | ali m. gobain | 2011-07-23 | 2011-04-13 | 8925.52
1027000350 | 90711 | STC CREW | 2011-04-13 | 2011-05-27 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  |  |  | alfies benjamin | 2011-09-27 | 2011-04-13 | 8537.4
1027000337 | 90711 | STC CREW | 2010-11-08 | 2010-11-09 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  |  | Completed By STC CREW | ali m. gobain | 2010-11-09 | 2010-11-08 | 1560
1027000421 | 90711 | STC CREW | 2011-04-13 | 2011-04-20 | SLHD | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  |  | done by stc crew | ernesto e. lai | 2011-06-29 | 2011-04-12 | 109.2
1027000424 | 90711 | STC CREW | 2011-04-13 | 2011-04-20 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued |  |  |  | STC CREW | lari carboz | 2011-06-29 | 2011-04-13 | 135
0927000503 | STC_2008 | STC CREW | 2009-08-16 | 2009-09-16 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  | less than 100 SAR (STC CREW) | alfies benjamin | 2009-09-12 | 2009-08-16 | 66.1
1027000382 | STC_2008 | STC CREW | 2010-09-01 | 2010-09-10 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  | STC CREW | ernesto e. lai | 2010-09-21 | 2010-09-01 | 243
1027000091 | STC_2008 | STC CREW | 2010-02-28 | 2010-03-18 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  | BSW WO Assign for South LESS THAN 2500 SR | lari carboz | 2010-03-16 | 2010-03-17 | 47
0927000711 | STC_2008 | STC CREW | 2010-03-21 | 2010-05-05 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  | STC CREW | jomeel g. antonio | 2010-04-28 | 2010-03-17 | 436.3
0927000643 | STC_2008 | STC CREW | 2010-02-02 | 2010-02-15 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  | BSW WO Assign for South LESS THAN 2500 SR | lari carboz | 2010-02-07 | 2010-03-17 | 192.7
1027000013 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 3944.15 | Yes |  | Email From: Maynah H. Mohammed | alfies benjamin | 2010-05-05 | 2010-03-17 | 583.3
0927000675 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 1174.5 | Yes |  | Email From: Maynah H. Mohammed | ernesto e. lai | 2010-04-11 | 2010-03-17 | 1174.5
0927000640 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 1707.5 | Yes |  | Email From: Maynah H. Mohammed | alfies benjamin | 2010-04-07 | 2010-03-17 | 1608.6
0927000700 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 418.1 | Yes |  | Email From: Maynah H. Mohammed | alfies benjamin | 2010-03-24 | 2010-03-17 | 418.1
0827000649 | 73822 | Middle Sea for Telecommunication Establishment | 2009-01-07 | 2009-01-30 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 0 |  |  | (MOT) Relocation For Road Widen Projector | alfies benjamin | 2010-12-18 | 2009-01-07 | 0
1027000039 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 436.3 | Yes |  | Email From: Maynah H. Mohammed | ali m. gobain | 2010-04-07 | 2010-03-17 | 436.3
1027000035 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 275.4 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-04-05 | 2010-03-17 | 918.3
1027000014 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1360.8 | Yes |  | Email From: Maynah H. Mohammed | ali m. gobain | 2010-03-23 | 2010-03-17 | 1278.1
1027000026 | 73822 | Middle Sea for Telecommunication Establishment | 2010-02-23 | 2010-03-23 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1504 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2010-04-11 | 2010-02-23 | 1655.5
0927000624 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 413.1 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-04-11 | 2010-03-17 | 443.8
0927000659 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 5613.3 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-05-08 | 2010-03-17 | 370.9
0927000574 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 439.2 | Yes |  | Email From: Maynah H. Mohammed | ali m. gobain | 2010-03-29 | 2010-03-17 | 455.5
0927000559 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 443.8 | Yes |  | Email From: Maynah H. Mohammed | ali m. gobain | 2010-04-05 | 2010-03-17 | 443.8
0927000556 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 435.7 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-04-10 | 2010-03-17 | 597.7
0927000567 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 1782 | Yes |  | Email From: Maynah H. Mohammed | jomeel g. antonio | 2010-04-25 | 2010-03-17 | 1650.7
0927000599 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1020.6 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-03-24 | 2010-03-17 | 1051.3
0927000585 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 443.8 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-03-31 | 2010-03-17 | 443.8
0927000553 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 840.7 | Yes |  | Email From: Maynah H. Mohammed | ali m. gobain | 2010-04-05 | 2010-03-17 | 840.7
0927000611 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | DARB | held order | Held Order - In Scope | completed | 2010 objective design issued | 688.5 | Yes |  | Email From: Maynah H. Mohammed | jomeel g. antonio | 2010-04-14 | 2010-03-17 | 688.5
0927000612 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2097.9 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-03-31 | 2010-03-17 | 1812.7
0927000620 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 972 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-04-14 | 2010-03-17 | 443.8
1027000087 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 856.9 | Yes |  | Email From: Maynah H. Mohammed | ali m. gobain | 2010-03-29 | 2010-03-17 | 856.9
1027000089 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1620 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-04-04 | 2010-03-17 | 1245.7
1027000092 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-08 | 2010-04-22 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 401.5 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2010-03-31 | 2010-03-08 | 515.5
1027000100 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 992.25 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-03-31 | 2010-03-17 | 711.1
1027000096 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 340.8 | Yes |  | Email From: Maynah H. Mohammed | jomeel g. antonio | 2010-04-04 | 2010-03-17 | 340.8
1027000101 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 581.5 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-03-31 | 2010-03-17 | 612.2
1027000082 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 443.8 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-03-31 | 2010-03-17 | 443.8
1027000073 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 567 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-04-10 | 2010-03-17 | 370.9
1027000078 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 1037.4 | Yes |  | Email From: Maynah H. Mohammed | jomeel g. antonio | 2010-04-25 | 2010-03-17 | 776.5
1027000065 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 1377 | Yes |  | Email From: Maynah H. Mohammed | jomeel g. antonio | 2010-04-24 | 2010-03-17 | 1407.7
1027000045 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 776.5 | Yes |  | Email From: Maynah H. Mohammed | lari carboz | 2010-03-31 | 2010-03-17 | 436.3
0927000549 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 1871.1 | Yes |  | Email From: Maynah H. Mohammed | jomeel g. antonio | 2010-04-04 | 2010-03-17 | 1731.7
0927000330 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-06 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 4860 | Yes |  |  | lari carboz | 2011-05-29 | 2010-07-06 | 4860
0927000186 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 16294.4475 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2010-11-08 | 2010-09-26 | 15063.4
0827000232 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-08-09 | 2010-09-23 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 5827.98 | Yes |  |  | jomeel g. antonio | 2010-12-11 | 2010-08-09 | 6516.95
1027000066 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1646.1 | Yes |  | Email From :Abdulmoti A. Dahlawi | agobain | 2010-11-03 | 2010-09-26 | 1735.2
1027000116 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-06-19 | 2010-10-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1265 | Yes |  | Waleed e-mail on 14-Jun-10 | ali m. gobain | 2010-09-18 | 2010-06-19 | 941
1027000154 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-06-19 | 2010-10-31 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3506.6 | Yes |  | Waleed e-mail on 14-Jun-10 | ali m. gobain | 2010-12-08 | 2010-06-19 | 3939.6
1027000136 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-05-08 | 2010-06-20 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 5766.3 | Yes |  | Approved From Walid Hesham Reshwan | ali m. gobain | 2010-10-05 | 2010-05-01 | 5621.8
0927000535 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-10-16 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 238.8 | Yes |  |  | lari carboz | 2010-11-10 | 2010-10-16 | 216
1027000217 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1520 | Yes |  |  | ali m. gobain | 2010-11-27 | 2010-10-16 | 1520
1027000261 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1984.5 | Yes |  |  | ali m. gobain | 2010-11-03 | 2010-10-16 | 2015.2
1027000303 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1194.75 | Yes |  |  | ali m. gobain | 2010-11-03 | 2010-10-16 | 1488.7
1027000271 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 48153.51 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2011-02-19 | 2010-09-26 | 50840.5
1027000291 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 8048.74 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2010-11-27 | 2010-09-26 | 8205.5
1027000320 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-10-03 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2056.4 | Yes |  |  | ali m. gobain | 2010-11-02 | 2010-10-03 | 2056.4
1027000361 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-10-16 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 100.3 | Yes |  |  | ali m. gobain | 2011-05-07 | 2010-10-16 | 100.3
1027000363 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-12-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 5520.9 | Yes |  |  | ali m. gobain | 2010-10-30 | 2010-09-26 | 5520.9
1027000377 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 914.7 | Yes |  |  | lari carboz | 2010-11-27 | 2010-09-26 | 914.7
1027000402 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-10-29 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2015.2 | Yes |  |  | lari carboz | 2010-11-27 | 2010-09-29 | 2865.7
1027000465 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-11-29 | 2010-12-31 | DARB | held order | Held Order - In Scope | completed | 2011 objective design issued | 13360.7 | Yes |  |  | jomeel g. antonio | 2010-12-06 | 2010-11-29 | 14104.3
1027000336 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-12-31 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 87536.15 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2011-01-30 | 2010-09-26 | 82092.4
1027000512 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-03 | SAMI | held order | Held Order - In Scope | completed | 2011 objective design issued | 3917.4 | Yes |  |  | ernesto e. lai | 2011-05-10 | 2011-04-13 | 4030.8
1027000526 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-03 | DAMD | held order | Held Order - In Scope | completed | 2011 objective design issued | 2041.2 | Yes |  |  | alfies benjamin | 2011-04-18 | 2011-04-13 | 2608.2
0927000333 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-05-29 | 2010-06-22 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 2518.5 | Yes |  | Held Order Master Sheet | ernesto e. lai | 2010-11-01 | 2010-05-29 | 2772.1
0927000376 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-05-29 | 2010-06-22 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 7790.9 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-09-26 | 2010-05-29 | 10083.2
0927000363 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-05-15 | 2010-06-30 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 14859.075 | Yes |  | Email From: Abdulmoti A. Dahlawi | alfies benjamin | 2010-11-01 | 2010-05-09 | 8149.2
0927000369 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-05-29 | 2010-06-22 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 9769.4 | Yes |  | Held Order Master Sheet | alfies benjamin | 2010-10-30 | 2010-05-29 | 10457.9
0927000631 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-06-19 | 2010-10-31 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 2470.8 | Yes |  | Waleed e-mail on 14-Jun-10 | alfies benjamin | 2010-08-25 | 2010-06-20 | 2495.5
0927000568 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-04-20 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 2948.4 | Yes |  |  | alfies benjamin | 2011-05-07 | 2011-04-13 | 2835
1027000163 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-02-23 | 2011-03-09 | JIZA | Held order | Held Order - In Scope | completed | 2011 objective design issued | 6012 | Yes |  |  | lari carboz | 2011-03-19 | 2011-02-23 | 5763.45
1027000191 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-06-19 | 2010-10-31 | TWAL | held order | Held Order - In Scope | completed | 2010 objective design issued | 1782.26 | Yes |  | Waleed e-mail on 14-Jun-10 | ernesto e. lai | 2010-11-01 | 2010-06-19 | 2252.1
1027000243 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-10-16 | 2010-12-31 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 2025 | Yes |  |  | alfies benjamin | 2010-11-06 | 2010-10-16 | 1247.4
1027000360 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-12-31 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 680.4 | Yes |  |  | alfies benjamin | 2010-10-10 | 2010-09-26 | 680.4
1027000326 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-09-26 | 2010-12-31 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 6921.53 | Yes |  |  | ernesto e. lai | 2010-10-18 | 2010-09-26 | 6548.8
1027000458 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-17 | 2011-04-30 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 81 | Yes |  |  | alfies benjamin | 2011-05-10 | 2011-04-17 | 81
1027000459 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-24 | 2011-06-30 | DAMD | held order | Held Order - In Scope | completed | 2011 objective design issued | 10391.9 | Yes |  |  | alfies benjamin | 2011-06-18 | 2011-05-24 | 10521.5
1027000460 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-03 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 3284.3 | Yes |  |  | alfies benjamin | 2011-05-10 | 2011-04-13 | 3692.8
1027000472 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-01-05 | 2011-02-15 | DAMD | held order | Held Order - In Scope | completed | 2011 objective design issued | 5380 | Yes |  |  | alfies benjamin | 2011-05-10 | 2011-01-05 | 5380
1027000482 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-01-05 | 2011-02-15 | BAYS | held order | Held Order - In Scope | completed | 2011 objective design issued | 4898.88 | Yes |  |  | jomeel g. antonio | 2011-04-17 | 2011-01-05 | 4702.78
1027000423 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-17 | 2011-04-27 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 153.5 | Yes |  |  | alfies benjamin | 2011-05-21 | 2011-04-17 | 153.5
1027000437 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-04-20 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 567 | Yes |  |  | alfies benjamin | 2011-04-18 | 2011-04-13 | 567
1027000446 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-17 | 2011-04-26 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 100.3 | Yes |  |  | ali m. gobain | 2011-05-21 | 2011-04-17 | 100.3
1027000447 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-17 | 2011-04-26 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 138.3 | Yes |  |  | ali m. gobain | 2011-05-07 | 2011-04-17 | 138.3
1027000343 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 8336.2 | Yes |  | Email From :Abdulmoti A. Dahlawi | alfies benjamin | 2010-12-25 | 2010-09-20 | 7433.5
1027000358 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 5210 | Yes |  | Email From :Abdulmoti A. Dahlawi | ernesto e. lai | 2010-10-12 | 2010-09-20 | 5154.4
1027000156 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 7766.8 | Yes |  | Email From :Abdulmoti A. Dahlawi | alfies benjamin | 2010-10-23 | 2010-09-20 | 3436
0927000402 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-08 | 2010-04-22 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 6046.95 | Yes |  |  | ernesto e. lai | 2010-09-26 | 2010-03-08 | 6821.9
0927000406 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-08 | 2010-04-22 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 5405.4 | Yes |  |  | ernesto e. lai | 2010-04-06 | 2010-03-08 | 8505
0927000159 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-08 | 2010-04-22 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 4669 | Yes |  |  | alfies benjamin | 2010-07-10 | 2010-03-08 | 4522.1
0927000188 | 73803 | Mohemmed Bin Gerboo EST. | 2009-06-30 | 2009-10-04 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 949.3 | Yes |  | Email From: Abdulmoti A. Dahlawi Sent: 3/Oct/2009 10:50 AM | alfies benjamin | 2010-02-27 | 2009-10-04 | 478.1
0927000138 | 73803 | Mohemmed Bin Gerboo EST. | 2011-05-15 | 2011-05-31 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 5649.57 | Yes |  |  | ernesto e. lai | 2011-05-15 | 2011-05-14 | 5896.3
0927000103 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-08 | 2010-04-22 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 12781.8 | Yes |  |  | alfies benjamin | 2010-03-28 | 2010-03-08 | 12781.8
0927000043 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-08 | 2010-04-22 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 3231.9 | Yes |  |  | ernesto e. lai | 2010-05-15 | 2010-03-08 | 4025.7
0927000076 | 73803 | Mohemmed Bin Gerboo EST. | 2009-02-02 | 2009-03-02 | ABAR | held order | Held Order - In Scope | completed | 2011 objective design issued | 5058.05 | Yes |  | The road close by baladyah (Sanitation) | alfies benjamin | 2010-10-02 | 2010-01-03 | 5738.27
0927000006 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-08 | 2010-04-22 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 3117.38 | Yes |  |  | ernesto e. lai | 2010-05-15 | 2010-03-08 | 3251.17
0827000168 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-08 | 2010-04-22 | TWAL | held order | Held Order - In Scope | completed | 2010 objective design issued | 10206 | Yes |  |  | ernesto e. lai | 2010-06-20 | 2010-03-08 | 14345.1
1027000352 | 73803 | Mohemmed Bin Gerboo EST. | 2010-08-14 | 2010-09-30 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 25464.08 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2010-10-02 | 2010-08-14 | 23758.5
1027000295 | 73803 | Mohemmed Bin Gerboo EST. | 2010-08-14 | 2010-09-30 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 5403 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2010-08-21 | 2010-08-14 | 4987.5
1027000383 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 4906.9 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2011-01-17 | 2010-09-20 | 5247.1
1027000348 | 73803 | Mohemmed Bin Gerboo EST. | 2010-08-14 | 2010-09-30 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 12338.6 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2010-10-16 | 2010-08-14 | 8123.7
1027000265 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | DARB | held order | Held Order - In Scope | completed | 2010 objective design issued | 5651.75 | Yes |  | Email From :Abdulmoti A. Dahlawi | jomeel g. antonio | 2010-10-06 | 2010-09-20 | 4798.7
1027000227 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | SBYA | held order | Held Order - In Scope | completed | 2011 objective design issued | 3973.56 | Yes |  | Email From :Abdulmoti A. Dahlawi | ali m. gobain | 2010-11-02 | 2010-09-20 | 4730.9
1027000300 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | DARB | held order | Held Order - In Scope | completed | 2010 objective design issued | 6533.3 | Yes |  | Email From :Abdulmoti A. Dahlawi | jomeel g. antonio | 2010-10-02 | 2010-09-20 | 4472.5
0927000546 | 73803 | Mohemmed Bin Gerboo EST. | 2009-10-12 | 2009-12-12 | JIZA | held order | Held Order - In Scope | completed | 2011 objective design issued | 59257.15 | Yes |  | Email From: Abdulmoti A. Dahlawi Sent: 3/Oct/2009 10:50 AM | lari carboz | 2009-12-22 | 2009-10-12 | 53053.658
0927000614 | 73803 | Mohemmed Bin Gerboo EST. | 2010-05-12 | 2010-06-30 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 3730.86 | Yes |  | Email From :Maynah H. Mohammed | jomeel g. antonio | 2010-06-20 | 2010-04-17 | 3149.2
0927000651 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 4691 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2010-11-29 | 2010-09-20 | 6991.5
0927000655 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 216 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2010-11-29 | 2010-09-20 | 216
1027000027 | 73803 | Mohemmed Bin Gerboo EST. | 2010-09-20 | 2010-12-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 6098.7 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2010-11-29 | 2010-09-20 | 5364
1027000105 | 73803 | Mohemmed Bin Gerboo EST. | 2010-05-12 | 2010-06-30 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 3723.5 | Yes |  | Email From :Maynah H. Mohammed | lari carboz | 2010-08-04 | 2010-04-17 | 3478.4
1027000112 | 73803 | Mohemmed Bin Gerboo EST. | 2010-05-12 | 2010-06-30 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2754 | Yes |  | Email From :Maynah H. Mohammed | ali m. gobain | 2010-08-04 | 2010-04-17 | 2460.7
0827000259 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-08 | 2010-04-22 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 9516.5 | Yes |  |  | ali m. gobain | 2010-06-05 | 2010-03-08 | 7785.2
0827000643 | 73803 | Mohemmed Bin Gerboo EST. | 2011-05-15 | 2011-05-31 | JIZA | Held order | Held Order - In Scope | completed | 2011 objective design issued | 13476.5 | Yes |  |  | lari carboz | 2011-05-15 | 2011-05-14 | 13400.9
0927000235 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-08 | 2010-04-22 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 4509.9 | Yes |  |  | lari carboz | 2010-08-04 | 2010-03-08 | 4509.8
0827000637 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-27 | 2009-05-03 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1927.4 | Yes |  | ? | lari carboz | 2009-05-03 | 2009-05-03 | 2057
0927000211 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-04-12 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1486.9 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-04-12 | 2009-04-09 | 1486.9
0927000224 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-04-12 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2097.9 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-04-12 | 2009-04-09 | 2154.6
0927000216 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-05-20 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 2014.6 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2009-05-20 | 2009-04-15 | 2055.6
0927000234 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-04-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1814.4 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-04-25 | 2009-04-15 | 1944
0927000225 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-04-29 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 7250.9 | Yes |  | Send Email in: 5/Oct/2009 11:41 AM Ahmed A. Al-Harthi To: Riyadh M. Al Hwyde | lari carboz | 2009-04-29 | 2009-04-27 | 7250.9
0927000229 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-04-18 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 270.6 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-04-18 | 2009-04-15 | 270.6
0927000222 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-05-30 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 5913 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-05-30 | 2009-05-27 | 5913
0927000223 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-04-20 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1236.5 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-04-20 | 2009-04-15 | 1238.1
0927000231 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-04-14 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 275.4 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-04-14 | 2009-04-11 | 275.4
0927000191 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-04-11 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 793.2 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2009-04-11 | 2009-04-09 | 908
0927000196 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-01 | 2009-04-15 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 100.3 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-04-15 | 2009-04-13 | 100.3
0927000198 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-01 | 2009-06-09 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 144.1 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-06-09 | 2009-04-15 | 144.1
0927000199 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-01 | 2009-04-30 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 604.7 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-04-30 | 2009-04-13 | 726.2
0927000247 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-05-01 | 2009-05-02 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 30.7 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-05-02 | 2009-04-29 | 30.7
0927000258 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 5353.8975 | Yes |  | VIP2 | ali m. gobain | 2009-07-18 | 2009-06-20 | 5619.7
0927000262 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-05-01 | 2009-06-01 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 268.7 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-06-01 | 2009-05-03 | 268.7
0927000267 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-05-01 | 2009-05-26 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 544.1 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2009-05-26 | 2009-05-03 | 544.1
0927000270 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-05-01 | 2009-07-08 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 368 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-07-08 | 2009-05-10 | 368
0927000272 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-05-01 | 2009-06-30 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 490.8 | Yes |  | List 3 New<3000 | lari carboz | 2009-05-10 | 2009-05-10 | 490.8
0927000273 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-05-05 | 2009-06-06 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 30.7 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-06-06 | 2009-05-10 | 30.7
0927000236 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-20 | 2009-04-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 125 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-04-25 | 2009-04-23 | 125
0927000237 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-20 | 2009-04-30 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 257.5 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-04-30 | 2009-04-20 | 257.5
0927000279 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-05-15 | 2009-05-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 972 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-05-25 | 2009-05-22 | 907.2
0927000280 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-05-15 | 2009-05-24 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 169 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-05-24 | 2009-05-21 | 169
0927000288 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-05-15 | 2009-05-27 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 138.3 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-05-27 | 2009-05-24 | 138.3
0927000293 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2006-05-20 | 2009-05-31 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 100.3 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-05-31 | 2009-05-30 | 100.3
0927000296 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2006-05-20 | 2009-05-25 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 887.6 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-05-25 | 2009-05-22 | 887.6
0927000300 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2006-05-20 | 2009-06-02 | DARB | held order | Held Order - In Scope | completed | 2010 objective design issued | 581.5 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2009-06-02 | 2009-05-30 | 719.2
0927000343 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-06-22 | 2009-06-30 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 581.5 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-06-30 | 2009-06-22 | 719.2
0927000323 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-06-22 | 2009-06-27 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 432.3 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-06-27 | 2009-06-22 | 432.3
0927000324 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2010.2 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-06-29 | 2009-06-22 | 2010.2
0927000388 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-07-07 | 2009-09-07 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1530.9 | Yes |  | less than 3000 SAR (Big Net) | lari carboz | 2009-07-26 | 2009-07-07 | 1701
0927000355 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-06-22 | 2009-09-22 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1377 | Yes |  | less than 3000 SAR (Big Net) | lari carboz | 2009-07-21 | 2009-06-22 | 1296
0927000442 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-07-14 | 2009-09-13 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 162 | Yes |  | less than 3000 SAR (Big Net) | lari carboz | 2009-07-21 | 2009-07-14 | 162
0927000445 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-07-14 | 2009-09-13 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 1620 | Yes |  | less than 3000 SAR (Big Net) | jomeel g. antonio | 2009-08-05 | 2009-07-14 | 2025
0927000424 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-07-07 | 2009-09-07 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 915 | Yes |  | less than 3000 SAR (Big Net) | lari carboz | 2009-08-03 | 2009-07-07 | 833.3
0827000600 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-12-02 | 2008-12-31 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 437 | Yes |  | less than 3000 SAR (Big Net) | lari carboz | 2009-07-25 | 2008-12-02 | 437
0827000420 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-10-25 | 2009-04-25 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 415.2 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-04-25 | 2008-10-25 | 1717.3
0827000172 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-10-18 | 2008-12-18 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 258.9 | Yes |  | <3000 | lari carboz | 2009-03-21 | 2008-10-18 | 258.9
0927000128 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-02-14 | 2009-02-23 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 2385.6 | Yes |  | Halema Yosef | lari carboz | 2009-03-03 | 2009-02-23 | 2467.3
0927000030 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-01-17 | 2009-02-17 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 100.3 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-02-17 | 2009-01-17 | 100.3
0927000036 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-01-19 | 2009-03-30 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 729 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-03-30 | 2009-01-19 | 810
0827000553 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-11-10 | 2009-04-05 | SBYA | held order | Held Order - In Scope | completed | 2010 objective design issued | 303.3 | Yes |  | less than 3000 SAR (Big net) | ali m. gobain | 2009-04-05 | 2008-11-10 | 510.3
0827000493 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-10-25 | 2009-04-12 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued | 1224.4 | Yes |  | less than 3000 SAR (Big net) | lari carboz | 2009-04-12 | 2008-10-25 | 1183.9
0827000645 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-12-31 | 2009-04-11 | BAYS | held order | Held Order - In Scope | completed | 2010 objective design issued | 369.6 | Yes |  | less than 3000 SAR (Big net) | jomeel g. antonio | 2009-04-11 | 2008-12-31 | 369.6
0927000283 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 100.3 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-05-26 | 2009-05-23 | 157
0927000345 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-06-22 | 2009-07-04 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 125 | Yes |  | less than 3000 SAR (Big net) | ernesto e. lai | 2009-07-04 | 2009-06-22 | 125
0927000217 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-06-30 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 634 | Yes |  | less than 3000 SAR (Big Net) | ernesto e. lai | 2009-08-04 | 2009-04-15 | 634
0927000179 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-01 | 2009-04-18 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 2022.246 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-04-18 | 2009-04-15 | 1941.246
0927000209 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-05-05 | ARDH | held order | Held Order - In Scope | completed | 2010 objective design issued | 364.5 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-05-05 | 2009-04-15 | 405
0927000193 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-06-30 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 73 | Yes |  | List 3 New<3000 | alfies benjamin | 2009-04-08 | 2009-04-06 | 73
0927000197 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-01 | 2009-04-26 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 275.4 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-04-26 | 2009-04-15 | 275.4
0927000202 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-09 | 2009-04-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 81 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-04-09 | 2009-04-07 | 81
0927000203 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-01 | 2009-04-25 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued | 1134 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-04-25 | 2009-04-15 | 1134
0927000207 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-04-10 | 2009-06-30 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 401 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-07-13 | 2009-04-15 | 466.1
0827000203 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-07-08 | 2008-07-25 | TWAL | held order | Held Order - In Scope | completed | 2010 objective design issued | 2656.8 | Yes |  |  | ernesto e. lai | 2009-01-30 | 2008-07-08 | 2835
0827000418 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-10-25 | 2009-04-09 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 1708.4 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-04-09 | 2008-10-25 | 1708.4
0827000422 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-07-19 | 2009-07-19 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 1215 | Yes |  | less than 3000 SAR (Big Net) | ernesto e. lai | 2009-07-21 | 2008-10-25 | 1134
0827000508 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-10-25 | 2009-04-15 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 1247.4 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-04-15 | 2008-10-25 | 1304.1
0827000476 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-10-25 | 2008-12-25 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 1749.193 | Yes |  | <3000 | alfies benjamin | 2009-07-06 | 2008-10-25 | 1710.644
0827000474 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-10-22 | 2008-12-22 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 2268 | Yes |  | <3000 | alfies benjamin | 2009-05-05 | 2008-10-22 | 2187
0827000543 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-11-10 | 2009-04-08 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 125 | Yes |  | less than 3000 SAR (STC CREW) | ernesto e. lai | 2009-04-08 | 2008-11-10 | 125
0827000549 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-11-10 | 2009-04-15 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 100.3 | Yes |  | less than 3000 SAR (Big net) | alfies benjamin | 2009-04-15 | 2008-11-10 | 125
0927000435 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 1620 | Yes |  | less than 3000 SAR (Big Net) | alfies benjamin | 2009-08-01 | 2009-07-13 | 1620
0927000404 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2010-06-10 | 2010-09-10 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 2187 | Yes |  | less than 3000 SAR (Big Net) | ernesto e. lai | 2009-07-14 | 2009-07-04 | 2430
0927000394 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2009-06-29 | 2009-09-22 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 170.5 | Yes |  | less than 3000 SAR (Big Net) | alfies benjamin | 2009-07-27 | 2009-06-30 | 170.5
0827000498 | STC_2008 | STC CREW | 2008-10-25 | 2008-12-25 | SBYA | held order | Held Order - In Scope | completed | 2009 objective design issued |  |  |  | From: Saed Zareb Sent: 21/Dec/2008 2:27 PM | ali m. gobain | 2008-12-25 | 2008-10-25 | 8170.1
0927000501 | STC_2008 | STC CREW | 2009-08-16 | 2009-09-16 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  | less than 100 SAR (STC CREW) | lari carboz | 2009-09-01 | 2009-08-24 | 47
0927000498 | STC_2008 | STC CREW | 2009-08-16 | 2009-09-16 | JIZA | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  | less than 100 SAR (STC CREW) | lari carboz | 2009-09-28 | 2009-08-16 | 100.3
0927000371 | STC_2008 | STC CREW | 2009-06-22 | 2009-07-04 | ARDH | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  | STC CREW | alfies benjamin | 2009-07-04 | 2009-06-22 | 247.6
0927000375 | STC_2008 | STC CREW | 2009-08-02 | 2009-08-12 | SLHD | held order | Held Order - In Scope | completed | 2009 objective design issued |  |  |  | STC CREW | ernesto e. lai | 2009-08-09 | 2009-08-06 | 4252.5
1027000008 | STC_2008 | STC CREW | 2010-02-06 | 2010-02-10 | DAMD | held order | Held Order - In Scope | completed | 2010 objective design issued |  |  |  | BSW WO Assign for South LESS THAN 2500 SR |  | 2010-02-07 | 2010-03-17 | 231.8
0927000610 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 1053 | Yes |  | Email From: Maynah H. Mohammed | alfies benjamin | 2010-04-05 | 2010-03-17 | 972
0927000642 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 1842.75 | Yes |  | Email From: Maynah H. Mohammed | ernesto e. lai | 2010-04-11 | 2010-03-17 | 1701
0927000649 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 243 | Yes |  | Email From: Maynah H. Mohammed | ernesto e. lai | 2010-04-07 | 2010-03-17 | 243
0927000663 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SAMI | held order | Held Order - In Scope | completed | 2010 objective design issued | 292.4 | Yes |  | Email From: Maynah H. Mohammed | ernesto e. lai | 2010-04-13 | 2010-03-17 | 278
0927000664 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 1863 | Yes |  | Email From: Maynah H. Mohammed | alfies benjamin | 2010-04-07 | 2010-03-17 | 1863
1027000031 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 2467.3 | Yes |  | Email From: Maynah H. Mohammed | alfies benjamin | 2010-05-05 | 2010-03-17 | 1722
1027000040 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 189.9 | Yes |  | Email From: Maynah H. Mohammed | ernesto e. lai | 2010-04-11 | 2010-03-17 | 261.4
1027000046 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | SLHD | held order | Held Order - In Scope | completed | 2010 objective design issued | 277.2 | Yes |  | Email From: Maynah H. Mohammed | ernesto e. lai | 2010-04-11 | 2010-03-17 | 275.8
1027000025 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-21 | 2010-05-05 | ABAR | held order | Held Order - In Scope | completed | 2010 objective design issued | 688.5 | Yes |  | Email From: Maynah H. Mohammed | alfies benjamin | 2010-04-05 | 2010-03-17 | 688.5
0827000230 | STC_2008 | STC CREW | 2008-07-08 | 2008-07-25 | JIZA | held order | Held Order2008 | completed | 2008 objective design issued |  |  |  | DONE BY STC _ JAZAN CREW | ernesto e. lai | 2008-12-24 | 2008-07-10 | 38
0827000264 | STC_2008 | STC CREW | 2008-04-09 | 2008-04-14 | JIZA | held order | Held Order2008 | completed | 2008 objective design issued |  |  |  |  | ernesto e. lai | 2008-12-24 | 2008-04-09 | 190
0827000298 | STC_2008 | STC CREW | 2008-04-22 | 2008-04-25 | JIZA | held order | Held Order2008 | completed | 2008 objective design issued |  |  |  |  | ernesto e. lai | 2008-12-24 | 2008-04-22 | 178
0827000315 | STC_2008 | STC CREW | 2008-05-07 | 2008-05-08 | KWBH | held order | Held Order2008 | completed | 2008 objective design issued |  |  |  |  | federico ---- aguilar | 2008-05-07 | 2008-05-07 | 2505
0827000280 | STC_2008 | STC CREW | 2008-07-07 | 2008-07-25 | SLHD | held order | Held Order2008 | completed | 2008 objective design issued |  |  |  |  | ernesto e. lai | 2008-09-23 | 2009-01-24 | 2520
0827000305 | STC_2008 | STC CREW | 2008-07-07 | 2008-07-25 | SLHD | held order | Held Order2008 | completed | 2008 objective design issued |  |  |  |  | ernesto e. lai | 2008-12-23 | 2008-08-12 | 2450
0927000046 | STC_2008 | STC CREW | 2009-02-01 | 2009-02-10 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | lari carboz | 2009-02-10 | 2009-02-01 | 405
0927000032 | STC_2008 | STC CREW | 2009-01-17 | 2009-01-20 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | <3000 | lari carboz | 2009-02-17 | 2009-01-17 | 300
0927000011 | STC_2008 | STC CREW | 2009-01-17 | 2009-02-17 | DAMD | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | ali m. gobain | 2009-02-17 | 2009-01-17 | 420
0827000572 | STC_2008 | STC CREW | 2008-12-20 | 2009-01-20 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | <3000 | lari carboz | 2009-01-20 | 2008-12-20 | 124
0827000541 | STC_2008 | STC CREW | 2008-11-10 | 2008-12-10 | DAMD | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | ali m. gobain | 2008-12-10 | 2008-11-10 | 81
0827000545 | STC_2008 | STC CREW | 2008-11-10 | 2008-12-10 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | <3000 | lari carboz | 2009-05-06 | 2008-11-10 | 1275.4
0827000568 | STC_2008 | STC CREW | 2008-11-18 | 2008-11-19 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | lari carboz | 2008-11-19 | 2008-11-18 | 210
0827000410 | STC_2008 | STC CREW | 2008-07-07 | 2008-07-25 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | lari carboz | 2008-07-25 | 2008-07-07 | 323
0827000401 | STC_2008 | STC CREW | 2008-06-23 | 2008-06-24 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  |  | lari carboz | 2008-06-24 | 2008-06-23 | 420
0827000535 | STC_2008 | STC CREW | 2008-10-25 | 2008-12-25 | DAMD | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | ali m. gobain | 2008-12-25 | 2008-10-25 | 2148
0827000488 | STC_2008 | STC CREW | 2008-09-14 | 2008-09-15 | SBYA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | ali m. gobain | 2008-09-15 | 2008-09-14 | 173
0827000482 | STC_2008 | STC CREW | 2008-10-25 | 2008-12-25 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | <3000 | lari carboz | 2008-12-25 | 2008-10-25 | 154
0827000458 | STC_2008 | STC CREW | 2008-10-22 | 2008-12-22 | SBYA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | <3000 | ali m. gobain | 2008-12-22 | 2008-10-22 | 1000
0827000221 | STC_2008 | STC CREW | 2008-07-08 | 2008-07-25 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | lari carboz | 2008-09-27 | 2008-07-08 | 7065
0827000385 | STC_2008 | STC CREW | 2008-06-07 | 2008-06-08 | JIZA | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | ernesto e. lai | 2009-01-07 | 2008-06-07 | 139
0827000317 | STC_2008 | STC CREW | 2008-06-16 | 2008-06-18 | JIZA | held order | Held Order2009 | completed | 2008 objective design issued |  |  |  |  | federico ---- aguilar | 2008-06-18 | 2008-06-17 | 14304
0827000455 | STC_2008 | STC CREW | 2008-10-25 | 2008-12-25 | TWAL | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | FINISH BY STC | federico ---- aguilar | 2008-10-25 | 2008-10-25 | 1717.3
0827000556 | STC_2008 | STC CREW | 2008-11-10 | 2008-12-10 | KWBH | held order | Held Order2009 | completed | 2009 objective design issued |  |  |  | STC CREW | ernesto e. lai | 2008-12-10 | 2008-11-10 | 584
0927000031 | STC_2010 | STC CREW | 2009-01-17 | 2009-06-02 | JIZA | held order | Held Order2009 | completed | 2009 objective not in the design master sheet |  |  |  | <3000 | lari carboz | 2009-06-02 | 2009-01-17 | 405
1227000159 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-08 | 2012-08-20 | BAYS | held order | Held Order-EBU | completed | 2012 objective design issued | 3234.22 | DM In Progress |  |  | jgantonio | 2013-01-05 | 2012-07-08 | 5181.12
1227000175 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-08 | 2012-08-20 | ABAR | held order | Held Order-EBU | completed | 2012 objective design issued | 8614.79 | DM In Progress |  |  | abenjamin | 2012-11-21 | 2012-07-08 | 26432.39
1227000170 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-08 | 2012-08-20 | ARDH | held order | Held Order-EBU | completed | 2012 objective design issued | 27679.714 | DM In Progress |  |  | abenjamin | 2013-06-24 | 2012-07-08 | 26063.96
1227000176 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-08 | 2012-08-20 | ABAR | held order | Held Order-EBU | completed | 2012 objective design issued | 478.08 | DM In Progress |  |  | abenjamin | 2013-02-17 | 2012-07-08 | 478.08
1227000174 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-15 | 2012-08-29 | JIZA | held order | Held Order-EBU | completed | 2012 objective design issued | 278.4 | PM In Progress |  |  | lscarboz | 2012-11-24 | 2012-07-15 | 243.84
1127000532 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-09-17 | 2012-10-24 | JIZA | held order | Held Order-EBU | completed | 2012 objective design issued | 779.12 | PM In Progress |  | Jeel AlFursan Est. FOR TRADING &CO | lscarboz | 2012-10-23 | 2012-07-24 | 5538.8
1327000684 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-28 | 2013-12-13 | JIZA | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | laary |  | 2013-11-28 | 7397.5
1227000182 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-15 | 2012-08-29 | JIZA | held order | Held Order-EBU | completed | 2012 objective design issued | 44794.374 | Yes |  |  | laary | 2012-11-21 | 2012-07-15 | 48553.206
1227000183 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-15 | 2012-08-29 | JIZA | held order | Held Order-EBU | cancelled | 2012 objective design issued | 0 |  |  | Cover By WO# 1227000242 | laary |  | 2012-07-15 | 1288.74
1427000022 |  | DETCON Saudia Co. (Data_SAD) | 2014-01-15 | 2014-02-28 | BAYS | held order | Held Order-EBU | not started | 2013 objective design issued |  |  | contractor over budget |  | jomeel g. antonio |  | 2014-01-15 | 3312
1427000026 |  | DETCON Saudia Co. (Data_SAD) | 2014-01-16 | 2014-02-28 | BAYS | held order | Held Order-EBU | not started | 2013 objective design issued |  |  | contractor over budget |  | jomeel g. antonio |  | 2014-01-16 | 1800
1427000028 |  | DETCON Saudia Co. (Data_SAD) | 2014-01-19 | 2014-02-28 | ARDA2 | held order | Held Order-EBU | not started | 2013 objective design issued |  |  | contractor over budget |  | alfies benjamin |  | 2014-01-19 | 10136.868
1327000697 | 80388 | Mohemmed Bin Gerboo EST. | 2013-12-01 | 2014-01-15 | JIZA | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | lari carboz |  | 2013-12-01 | 7304.68
1327000386 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-15 | 2013-08-25 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 15085.944 |  |  |  | laary | 2013-08-25 | 2013-07-15 | 15343.04
1327000383 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-15 | 2013-08-25 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 141.12 |  |  |  | lari carboz | 2013-07-29 | 2013-07-15 | 141.12
1327000378 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-15 | 2013-08-25 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 116.14 |  |  |  | lari carboz | 2013-07-29 | 2013-07-15 | 116.14
1327000385 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-01 | 2013-11-30 | BRDR | held order | Held Order-EBU | completed | 2013 objective design issued | 12107.288 |  |  |  | ernesto e. lai | 2013-11-03 | 2013-07-29 | 11550.81
1327000438 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-18 | 2013-10-31 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 1845 |  |  |  | lari carboz | 2013-10-28 | 2013-08-26 | 1832.54
1327000243 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-31 | 2013-06-30 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 15498.9 |  |  |  | lari carboz | 2013-08-25 | 2013-05-18 | 7165.51
1327000331 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-24 | 2013-10-31 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | lari carboz | 2013-09-30 | 2013-07-01 | 475.52
1327000657 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-07 | 2013-11-30 | SLHD | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-11-07 | 7279.11
1327000651 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-07 | 2013-11-30 | Dehemah | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-11-07 | 2692.8
1327000481 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-03 | 2013-11-30 | JIZA | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | laary |  | 2013-11-03 | 7200
1327000495 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-03 | 2013-11-30 | SAMI | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-11-03 | 3021.02
1327000468 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-01 | 2013-10-31 | BRDR | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2013-10-21 | 2013-09-17 | 13288.34
1327000488 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-03 | 2013-12-11 | SLHD | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2013-12-19 | 2013-10-03 | 1585.8
1327000499 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-23 | 2013-11-30 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 13683.46 |  |  |  | laary | 2013-12-11 | 2013-10-23 | 15897.49
1327000498 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-03 | 2013-10-31 | SAMI | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2014-01-29 | 2013-10-03 | 9331.2
1227000244 | 80013 | Mohemmed Bin Gerboo EST. | 2014-01-14 | 2014-01-31 | SLHD | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  | need scope of work |  | ernesto e. lai |  | 2014-01-14 | 95.02
1227W00021 | 80013 | Mohemmed Bin Gerboo EST. | 2013-04-15 | 2013-04-30 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 5188.58 |  |  | Mohemmed Bin Gerboo EST. | lari carboz | 2013-04-16 | 2013-04-15 | 26597.72
1327000717 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-18 | 2014-01-24 | JIZA | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | lari carboz |  | 2013-12-18 | 12611.02
1327000699 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-01 | 2013-12-31 | ABAR | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-12-01 | 4780.8
1327000708 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-11 | 2013-12-31 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | lari carboz | 2014-01-29 | 2013-12-11 | 1018.44
1327000707 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-15 | 2013-12-31 | 703-00-000 | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | lari carboz | 2014-01-29 | 2013-12-15 | 8364.32
1327000705 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-12-04 | 2014-01-18 | ARDA2 | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-12-04 | 10239.444
1327000703 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-12-01 | 2013-12-31 | SBYA | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | ali gobain |  | 2013-12-01 | 8571.2
1227000165 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-13 | 2013-05-28 | FRSN | held order | Held Order-EBU | completed | 2013 objective design issued | 7520.02 |  |  |  | alfies benjamin | 2013-08-05 | 2013-03-31 | 7680.36
1227000179 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-12-01 | 2014-01-15 | FRSN | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-12-01 | 23686.05
1327000011 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-27 | 2013-06-09 | ARDA2 | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-04-27 | 19143.93
1327000013 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-27 | 2013-06-09 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 2405.72 |  |  |  | ali gobain | 2013-05-21 | 2013-04-27 | 2405.72
1227W00026 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-17 | 2013-05-31 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | ali gobain | 2013-11-10 | 2013-04-17 | 21077.7
1327000002 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-02-19 | 2013-03-31 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 2966.82 |  |  |  | ali gobain | 2013-02-23 | 2013-02-19 | 2966.82
1327000003 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-02-19 | 2013-03-31 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | ali gobain | 2013-02-23 | 2013-02-19 | 980.16
1327000004 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-02-19 | 2013-03-31 | DARB | held order | Held Order-EBU | completed | 2013 objective design issued | 2797.81 |  |  | DETCON Saudia Co. (Data_SAD) | jomeel g. antonio | 2013-03-02 | 2013-02-19 | 4041.01
1227W00036 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-17 | 2013-05-31 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 1497.6 |  |  |  | ali gobain | 2013-06-22 | 2013-04-17 | 1526.4
1227W00038 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-17 | 2013-05-31 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 11579.91 |  |  |  | ali gobain | 2013-06-22 | 2013-04-17 | 11456.07
1327000030 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-01 | 2013-05-10 | JIZA | held order | Held Order-EBU | completed | 2013 objective design issued | 13840.29 |  |  |  | lari carboz | 2013-05-18 | 2013-03-31 | 13600.34
1227W00042 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-17 | 2013-05-31 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | ali gobain | 2013-12-01 | 2013-04-17 | 15868.8
1227000259 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-25 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 95.02 |  |  |  | ali gobain | 2013-08-22 | 2013-07-15 | 95.02
1327000463 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-30 | DARB | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | jomeel g. antonio | 2013-11-24 | 2013-09-09 | 5669.76
1327000514 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-06 | 2013-12-13 | DAMD | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-10-23 | 898.03
1327000486 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-03 | 2013-10-31 | BAYS | held order | Held Order-EBU | completed | 2013 objective design issued | 2975.02 |  |  |  | jomeel g. antonio | 2013-10-22 | 2013-10-03 | 3138.22
1327000419 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | BAYS | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  | Datasad 6/24/2013 | jomeel g. antonio |  | 2013-08-27 | 2949.55
1327000472 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | SAMI | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  | May-13 | ernesto e. lai |  | 2013-09-17 | 4583.1
1327000466 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | SBYA | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  | 30/05/2013 | ali gobain |  | 2013-09-17 | 10132.97
1327000467 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | SBYA | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  | May-13 | ali gobain |  | 2014-10-01 | 2548.8
1327000458 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | ABAR | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | alfies benjamin | 2013-11-20 | 2013-08-27 | 9313.74
1327000459 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | ABAR | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | alfies benjamin | 2013-11-20 | 2013-08-27 | 11895.76
1327000690 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-28 | 2013-12-13 | BAYS | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | jomeel g. antonio |  | 2013-11-28 | 9608.74
1327000687 | 80012 | DETCON Saudia Co. (Data_SAD) | 2014-02-01 | 2014-02-28 | SBYA | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | ali gobain |  | 2013-11-24 | 6027.1
1327000534 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-03 | 2013-11-30 | ABAR | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-11-03 | 1930.42
1327000519 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-29 | 2013-11-29 | SBYA | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | ali gobain |  | 2013-10-29 | 10439.02
1327000652 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-07 | 2013-11-30 | ABAR | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-11-07 | 167.13
1327000288 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | ABAR | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | alfies benjamin | 2013-07-28 | 2013-05-27 | 4608
1327000330 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-03 | 2013-07-31 | DMAD | held order | Held Order-EBU | completed | 2013 objective design issued | 181.42 |  |  | 02/07/2013 Done | alfies benjamin | 2013-08-21 | 2013-07-03 | 181.42
1327000221 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-27 | 2013-06-09 | BRDR | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2013-10-21 | 2013-04-27 | 42714.04
1327000422 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-01 | 2013-11-30 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | ali gobain | 2013-11-03 | 2013-07-29 | 52.8
1327000376 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-25 | BAYS | held order | Held Order-EBU | completed | 2013 objective design issued | 28.8 |  |  |  | jomeel g. antonio | 2013-10-21 | 2013-07-15 | 28.8
1327000377 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-25 | DARB | held order | Held Order-EBU | in progress | 2013 objective design issued | 0 |  |  |  | jomeel g. antonio |  | 2013-07-15 | 3628.8
1327000362 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-25 | SBYA | held order | Held Order-EBU | completed | 2013 objective design issued | 10200.27 |  |  |  | ali gobain | 2013-09-18 | 2013-07-15 | 12054.01
1327000384 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-25 | DARB | held order | Held Order-EBU | completed | 2013 objective design issued | 699.72 |  |  |  | jomeel g. antonio | 2013-08-04 | 2013-07-15 | 10356
1327000382 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-25 | ABAR | held order | Held Order-EBU | completed | 2013 objective design issued | 0 |  |  |  | alfies benjamin | 2013-12-24 | 2013-07-15 | 156.48
1127000293 |  | WATAD AL ARABIAH | 2014-01-29 | 2014-01-31 | ABAR | held order | Held Order-HBU 2013 | cancelled | 2013 objective design issued |  |  | job wo cancelled | High Cost | alfies benjamin |  | 2014-01-29 | 194916.34
1327000490 |  | DETCON Saudia Co. (Data_SAD) | 2014-01-19 | 2014-02-28 | BAYS | held order | Held Order-HBU 2013 | not started | 2013 objective design issued |  |  | contractor over budget |  | jomeel g. antonio |  | 2014-01-19 | 2496
0927000135 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-05-19 | 2013-06-30 | SBYA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | ali m. gobain |  | 2013-05-19 | 13797.76
1327000205 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-04-17 | 2013-05-31 | SLHD | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  | 15/08/2013 16/08/2013 | ernesto e. lai |  | 2013-04-17 | 4992
0827000275 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-06 | 2013-05-31 | SAMI | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 7001.18 |  |  |  | federico ---- aguilar | 2013-05-20 | 2013-05-06 | 6403.58
0827000601 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-06 | 2013-05-31 | TWAL | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 9146 |  |  |  | ernesto e. lai | 2013-06-24 | 2013-05-06 | 9723.96
0927000348 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-19 | 2013-06-30 | SLHD | held order | Held Order-HBU 2013 | cancelled | 2013 objective design issued | 0 |  |  | Done By anther | ernesto e. lai |  | 2013-05-19 | 5849.85
1027000524 | 80013 | Mohemmed Bin Gerboo EST. | 2013-04-17 | 2013-05-31 | SAMI | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 5189.76 |  |  |  | ernesto e. lai | 2013-06-24 | 2013-04-14 | 5070.81
1127000062 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-28 | 2013-07-12 | ABAR | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 26994.998 |  |  |  | alfies benjamin | 2013-06-02 | 2013-05-19 | 19231.64
1127000094 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-19 | 2013-05-19 | ABAR | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 1174.22 |  |  |  | alfies benjamin | 2013-06-24 | 2013-05-19 | 3899.44
1127000508 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-06 | 2013-05-31 | TWAL | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 2880 |  |  |  | ernesto e. lai | 2013-06-24 | 2013-05-06 | 2635.1
1327000413 | 80013 | Mohemmed Bin Gerboo EST. | 2014-03-01 | 2014-03-30 | BRDR | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Completed | ernesto e. lai |  | 2013-07-29 | 27263.03
1327000420 | 80013 | Mohemmed Bin Gerboo EST. | 2014-01-01 | 2014-01-31 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 0 |  |  |  | lari carboz | 2014-01-05 | 2013-07-29 | 3696
1327000409 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-30 | 2014-01-30 | SAMI | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2014-01-01 | 2013-08-27 | 6504
1327000412 | 80013 | Mohemmed Bin Gerboo EST. | 2013-08-25 | 2013-08-31 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 6261.002 |  |  | 11/30/2013 | laary | 2013-09-01 | 2013-08-25 | 8664
1327000415 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-12 | 2013-10-19 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 25907.882 |  |  | Bin Garboo 10/19/2013 | lari carboz | 2013-10-06 | 2013-08-27 | 12131.238
1327000421 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-31 | 2013-08-31 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 4742.4 |  |  | 11/7/2013 | lari carboz | 2013-09-22 | 2013-07-31 | 5376
1327000430 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-03 | 2013-09-30 | JIZA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  | Bin Garboo 4/14/2014 | lari carboz |  | 2013-09-03 | 8597.76
1327000408 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-25 | 2013-08-31 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 3589.63 |  |  |  | laary | 2013-10-06 | 2013-07-25 | 3984
1327000410 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-01 | 2013-11-30 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 1032.74 |  |  |  | lari carboz | 2013-11-03 | 2013-07-29 | 2579.46
1327000439 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-28 | 2014-01-29 | SAMI | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2014-01-29 | 2013-08-27 | 8029.71
1327000440 | 80013 | Mohemmed Bin Gerboo EST. | 2014-05-01 | 2014-06-04 | SLHD | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Bin Garboo 4/6/2014 | ernesto e. lai |  | 2013-08-27 | 7143.42
1327000441 | 80013 | Mohemmed Bin Gerboo EST. | 2014-02-25 | 2014-03-29 | SLHD | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Bin Garboo 3/29/2014 | ernesto e. lai |  | 2013-08-27 | 6174.81
1327000432 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-01 | 2013-12-01 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 2184 |  |  |  | lari carboz | 2013-12-11 | 2013-09-03 | 2131.2
1327000437 | 80013 | Mohemmed Bin Gerboo EST. | 2014-03-13 | 2014-04-13 | JIZA | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Bin Garboo 4/13/2014 | lari carboz |  | 2013-08-27 | 1881.6
1327000204 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-19 | 2013-06-30 | Dehemah | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 4243.2 |  |  |  | ernesto e. lai | 2013-08-28 | 2013-05-19 | 4581.9
1327000650 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-07 | 2013-11-30 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 5953.36 |  |  |  | laary | 2013-12-11 | 2013-11-07 | 6008.3
1327000662 | 80013 | Mohemmed Bin Gerboo EST. | 2014-01-01 | 2014-01-30 | SAMI | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2014-01-29 | 2013-11-07 | 1550.43
1327000665 | 80013 | Mohemmed Bin Gerboo EST. | 2014-04-01 | 2014-04-30 | SAMI | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Completed | ernesto e. lai |  | 2013-11-12 | 4880.32
1327000675 | 80013 | Mohemmed Bin Gerboo EST. | 2014-04-01 | 2014-04-30 | JIZA | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Completed | lari carboz |  | 2013-11-18 | 7258.95
1327000494 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-20 | 2013-12-31 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 0 |  |  |  | laary | 2014-01-29 | 2013-11-18 | 2572.25
1327000671 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-20 | 2013-12-31 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 5557.48 |  |  |  | laary | 2013-12-11 | 2013-11-18 | 5576.95
1327000669 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-12 | 2013-12-20 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 4946.48 |  |  |  | laary | 2013-12-11 | 2013-11-12 | 4714.3
1327000456 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-14 | 2013-10-14 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 2372.504 |  |  | Bin Garboo 10/14/2013 | lari carboz | 2013-10-07 | 2013-08-27 | 2246.06
1327000477 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-16 | 2013-10-31 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 2880 |  |  |  | lari carboz | 2013-10-28 | 2013-09-16 | 2880
1327000442 | 80013 | Mohemmed Bin Gerboo EST. | 2014-02-18 | 2014-03-22 | SLHD | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Completed | ernesto e. lai |  | 2013-08-27 | 6144
1327000446 | 80013 | Mohemmed Bin Gerboo EST. | 2014-02-20 | 2014-03-25 | SLHD | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Completed | ernesto e. lai |  | 2013-08-27 | 5064
1327000447 | 80013 | Mohemmed Bin Gerboo EST. | 2014-03-15 | 2014-04-15 | BRDR | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Bin Garboo 4/15/2014 | ernesto e. lai |  | 2013-08-27 | 533.76
1327000448 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-15 | 2013-12-20 | KHAW | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-08-27 | 4560
1327000449 | 80013 | Mohemmed Bin Gerboo EST. | 2014-03-14 | 2014-04-18 | SAMI | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Completed | ernesto e. lai |  | 2013-08-27 | 3628.8
1327000451 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-04 | 2014-01-09 | SAMI | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-08-27 | 7224
1327000450 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-18 | 2013-10-31 | SAMI | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 4805.76 |  |  |  | ernesto e. lai | 2013-10-29 | 2013-08-27 | 4529.65
1327000452 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-15 | 2013-12-21 | KHAW | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-08-27 | 5639.55
1327000443 | 80013 | Mohemmed Bin Gerboo EST. | 2014-02-24 | 2014-03-24 | SLHD | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  | Completed | ernesto e. lai |  | 2013-08-27 | 1881.6
1327000444 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-18 | 2013-10-31 | SAMI | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 4177.92 |  |  |  | ernesto e. lai | 2013-10-27 | 2013-08-27 | 4377.6
1327000445 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-05 | 2014-01-10 | SAMI | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  | Bin Garboo 1/10/2014 | ernesto e. lai |  | 2013-08-27 | 6229.46
1327000489 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-01 | 2013-12-30 | 703-00-000 | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 11418.68 |  |  |  | laary | 2013-12-04 | 2013-10-03 | 3301.96
1327000505 | 80013 | Mohemmed Bin Gerboo EST. | 2014-01-01 | 2014-01-30 | SAMI | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  | 27-Jan-14 | ernesto e. lai |  | 2013-10-23 | 5449.8
1227000049 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-19 | 2013-06-30 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 62972.56 |  |  |  | lari carboz | 2013-08-28 | 2013-05-19 | 29641.84
1227000043 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-19 | 2013-06-30 | ABAR | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 2745.6 |  |  |  | alfies benjamin | 2013-06-24 | 2013-05-19 | 2246.4
1127000606 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-19 | 2013-06-30 | DAMD | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 3243.27 |  |  |  | alfies benjamin | 2013-06-24 | 2013-05-19 | 3379.63
1227W00015 | 80013 | Mohemmed Bin Gerboo EST. | 2013-04-01 | 2013-05-14 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 16234.248 |  |  |  | laary | 2013-10-06 | 2013-04-01 | 14813.496
1227W00025 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-19 | 2013-06-30 | Dehemah | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 10036.236 |  |  |  | ernesto e. lai | 2013-08-28 | 2013-05-19 | 13854.81
1227000199 | 80013 | Mohemmed Bin Gerboo EST. | 2013-04-03 | 2013-04-29 | JIZA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 5795.908 |  |  | Mohemmed Bin Gerboo EST. | laary | 2013-04-14 | 2012-10-08 | 3624.76
1227000143 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-19 | 2013-06-30 | ABAR | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 5336.51 |  |  |  | alfies benjamin | 2013-06-24 | 2013-05-19 | 6135.53
1427000002 | 80013 | Mohemmed Bin Gerboo EST. | 2014-01-14 | 2014-01-31 | JIZA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  | need scope of work |  | lari carboz |  | 2014-01-14 | 4630.08
1327000716 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-15 | 2013-12-31 | JIZA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | lari carboz |  | 2013-12-15 | 6662.07
1327000712 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-15 | 2013-12-31 | JIZA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | lari carboz |  | 2013-12-15 | 8027.85
1327000704 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-01 | 2013-12-31 | JIZA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | lari carboz |  | 2013-12-01 | 7447.418
1327000714 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-12-15 | 2013-12-31 | ABAR | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-12-15 | 9640.17
1327000720 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-12-23 | 2014-01-23 | ABAR | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-12-23 | 2215.16
1327000202 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | BAYS | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 2725.16 |  |  |  | jomeel g. antonio | 2013-07-09 | 2013-05-19 | 2986.46
1227W00019 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | SBYA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 8569.02 |  |  |  | ali gobain | 2013-07-03 | 2013-05-19 | 18243.82
1327000014 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | BAYS | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | jomeel g. antonio |  | 2013-05-19 | 7401.4
1227W00010 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | ABAR | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-05-19 | 2520
1327000201 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-17 | 2013-05-31 | BAYS | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 388.8 |  |  |  | jomeel g. antonio | 2013-10-21 | 2013-04-17 | 388.8
1227000243 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-04-19 | 2013-04-20 | DMAD | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 3691.22 |  |  |  | alfies benjamin | 2013-06-09 | 2013-04-06 | 5670.84
1127000630 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | SBYA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 1178.93 |  |  |  | ali gobain | 2013-06-22 | 2013-05-19 | 1308.91
1327000515 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-06 | 2013-12-07 | DAMD | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  | 14-Aug-13 | alfies benjamin |  | 2013-10-23 | 6480
1327000474 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | SBYA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 3484.8 |  |  |  | ali gobain | 2013-10-09 | 2013-09-15 | 4320
1327000455 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | SBYA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 0 |  |  |  | ali gobain | 2013-12-22 | 2013-08-27 | 5126.3
1327000678 | 80012 | DETCON Saudia Co. (Data_SAD) | 2014-04-01 | 2014-04-30 | SQYQ | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  |  | jomeel g. antonio |  | 2013-11-18 | 1248
1327000686 | 80012 | DETCON Saudia Co. (Data_SAD) | 2014-04-01 | 2014-04-30 | SQYQ | held order | Held Order-HBU 2013 | not started | 2013 objective design issued | 0 |  |  |  | jomeel g. antonio |  | 2013-11-24 | 5018.8
1327000539 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-03 | 2013-11-30 | DMAD | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-11-03 | 3751.76
1327000537 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-03 | 2013-11-30 | DMAD | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-11-03 | 5456.12
1327000531 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-07 | 2013-11-30 | DMAD | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  | 6August-13 | alfies benjamin |  | 2013-11-07 | 7573.71
1227000238 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-25 | DMAD | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  | 13/08/2013 | alfies benjamin |  | 2013-07-15 | 7053.38
1327000070 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | DMAD | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 7643.964 |  |  |  | alfies benjamin | 2013-08-21 | 2013-05-19 | 15199.9
1327000367 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-25 | ABAR | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 0 |  |  |  | alfies benjamin | 2014-01-05 | 2013-07-15 | 5984.64
1127000463 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | BAYS | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | jomeel g. antonio |  | 2013-05-19 | 8702.12
1127000494 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | BAYS | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | jomeel g. antonio |  | 2013-05-19 | 2368.44
1127000136 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | SBYA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | ali gobain |  | 2013-05-19 | 12046.12
1127000072 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-15 | SBYA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  | 07/05/2013 08/05/2013 (Data_SAD | ali gobain |  | 2013-07-15 | 4018.95
1127000068 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-15 | SBYA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  | 05/05/2013 06/05/2013 (Data_SAD | ali gobain |  | 2013-07-15 | 394.56
1127000115 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-15 | SBYA | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 1468.8 |  |  |  | agobain | 2013-10-22 | 2013-07-15 | 2188.8
0827000222 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-28 | 2013-07-12 | SHUQ | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-05-19 | 5680.02
0827000303 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-07-15 | 2013-08-15 | SHUQ | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-07-15 | 6142.316
1327000660 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-12-05 | 2013-12-25 | SAMI | held order | Held Order-HBU 2013 | completed | 2013 objective design issued | 3793.92 |  |  |  | ernesto e. lai | 2013-12-09 | 2013-11-07 | 3993.6
1327000727 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2014-01-01 | 2014-01-31 | JIZA | held order | Held Order-HBU 2013 | in progress | 2013 objective design issued | 0 |  |  |  | lari carboz |  | 2014-01-01 | 6852.22
1127000211 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-19 | 2011-07-19 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6977.12 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-06-26 | 2011-06-19 | 7788.92
1127000251 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5302.27 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-04-07 | 2011-09-19 | 4753.9
1227000066 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-08 | 2012-08-20 | BAYS | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 20545.79 | PM In Progress |  |  | jgantonio | 2013-03-03 | 2012-07-08 | 40357.52
1227000059 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-09-17 | 2012-10-24 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2452.78 | PM In Progress |  |  | jgantonio | 2013-03-19 | 2012-09-17 | 260.12
1127000402 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 394.56 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-05-27 | 2011-09-19 | 394.56
1127000426 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 3332.06 | PM In Progress |  |  | lscarboz | 2013-04-14 | 2011-09-19 | 2456.52
1127000531 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 14457.52 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2012-07-10 | 11863.3
1127000318 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-18 | 2011-10-20 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5132 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-06-26 | 2011-09-18 | 9369.6
1127000399 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | Cancelled By customer 0596576970 | laary |  | 2011-09-19 | 434.86
1227000196 |  | DETCON Saudia Co. (Data_SAD) | 2012-10-08 | 2012-11-15 | DAMD | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho |  |  | job wo cancelled | Cancelled By Customer refused | alfies benjamin |  | 2012-10-08 | 6782.98
1127000313 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-08 | 2012-08-20 | ABAR | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | Cancelled By Customer refused | alfies benjamin |  | 2012-07-08 | 13939.16
0827000603 |  | Majd AlJanoub for general Contracting Ltd. | 2013-06-26 | 2013-07-04 | ABAR | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho |  |  | job wo cancelled | High Cost | alfies benjamin |  | 2013-05-07 | 161879.73
1027000018 |  | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | JIZA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho |  |  | job wo cancelled | Canceled By Customer | lari carboz |  | 2013-04-02 | 2473.84
1227000074 |  | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | DARB | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho |  |  | job wo cancelled | High cost + copper cabine | jomeel g. antonio |  | 2013-04-15 | 555392.71
1227W00003 |  | Majd AlJanoub for general Contracting Ltd. | 2013-09-24 | 2013-10-31 | JIZA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho |  |  | job wo cancelled | Customer serveced | lari carboz |  | 2013-07-31 | 19135.68
1427000049 | 80366 | WATAD AL ARABIAH | 2014-01-23 | 2014-02-28 | ABAR | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | alfies benjamin | 2014-02-02 | 2014-01-23 | 5936.488
1427000050 | 80366 | WATAD AL ARABIAH | 2014-01-23 | 2014-02-28 | DMAD | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho |  |  | need scope of work |  | alfies benjamin | 2014-02-02 | 2014-01-23 | 4552.64
1427000042 | 80366 | WATAD AL ARABIAH | 2014-01-23 | 2014-02-28 | ABAR | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | alfies benjamin |  | 2014-01-23 | 4289.33
1327000724 | 80366 | WATAD AL ARABIAH | 2014-01-05 | 2014-01-31 | ARDA2 | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin |  | 2014-01-05 | 5973.88
1427000037 | 80366 | WATAD AL ARABIAH | 2014-01-23 | 2014-02-28 | DMAD | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | alfies benjamin | 2014-02-02 | 2014-01-23 | 6362.51
1427000031 | 80366 | WATAD AL ARABIAH | 2014-01-19 | 2014-02-28 | DMAD | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | alfies benjamin |  | 2014-01-19 | 4555.06
1327000457 | 80366 | WATAD AL ARABIAH | 2014-05-22 | 2014-06-22 | ARDA2 | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | alfies benjamin |  | 2013-08-26 | 2774.4
1327000453 | 80366 | WATAD AL ARABIAH | 2013-08-27 | 2013-09-27 | DMAD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 34253.968 | PCC In Progress |  |  | alfies benjamin | 2013-11-04 | 2013-08-27 | 34919.42
1327000248 | 80366 | WATAD AL ARABIAH | 2013-09-18 | 2013-10-31 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 24720.5152 | PCC In Progress |  |  | alfies benjamin | 2013-10-03 | 2013-09-18 | 19220.4
1327000670 | 80366 | WATAD AL ARABIAH | 2013-11-12 | 2013-12-20 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2014-01-13 | 2013-11-12 | 3043.596
1327000676 | 80366 | WATAD AL ARABIAH | 2013-11-18 | 2013-12-31 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2013-12-11 | 2013-11-18 | 6027.28
1327000663 | 80366 | WATAD AL ARABIAH | 2013-11-12 | 2013-12-20 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2013-12-11 | 2013-11-12 | 3293.66
1327000296 | 80366 | WATAD AL ARABIAH | 2013-07-15 | 2013-08-15 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 8115.274 | PCC In Progress |  |  | alfies benjamin | 2013-09-29 | 2013-06-26 | 7007.32
1327000305 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-30 | DMAD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4222.08 | PCC In Progress |  |  | alfies benjamin | 2013-09-08 | 2013-06-09 | 720
1327000301 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-30 | DMAD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2014-01-01 | 2013-06-09 | 3615.36
1327000256 | 80366 | WATAD AL ARABIAH | 2013-07-14 | 2013-08-25 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4044.4 | PCC In Progress |  |  | alfies benjamin | 2013-09-16 | 2013-07-14 | 4044.4
1327000244 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-30 | ABAR | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2014-01-01 | 2013-06-03 | 7564.54
1327000246 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-30 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 7317.14 | PCC In Progress |  | 19/06/2013 20/06/2013 | alfies benjamin | 2013-09-29 | 2013-06-03 | 8163.176
1327000257 | 80366 | WATAD AL ARABIAH | 2014-05-11 | 2014-06-16 | ABAR | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | alfies benjamin |  | 2013-08-26 | 4330.78
1327000116 | 80366 | WATAD AL ARABIAH | 2013-10-13 | 2013-11-13 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | lari carboz | 2014-01-01 | 2013-08-26 | 532.8
1327000230 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-30 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5236.09 | PCC In Progress |  | 15/06/2013 16/06/2013 | alfies benjamin | 2013-07-30 | 2013-06-03 | 7769.166
1327000232 | 80366 | WATAD AL ARABIAH | 2013-07-14 | 2013-08-25 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 8910.6 | PCC In Progress |  |  | alfies benjamin | 2013-09-29 | 2013-07-14 | 7516.8
1327000233 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-24 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6537.6 | PCC In Progress |  | 11/06/2013 12/06/2013 | alfies benjamin | 2013-09-16 | 2013-06-03 | 6537.6
1327000234 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-24 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4496.26 | PCC In Progress |  | 19/06/2013 20/06/2013 | alfies benjamin | 2013-09-04 | 2013-06-03 | 4265.59
1327000235 | 80366 | WATAD AL ARABIAH | 2013-07-14 | 2013-08-25 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 3371.1 | PCC In Progress |  |  | alfies benjamin | 2013-10-03 | 2013-07-14 | 4295.99
1327000236 | 80366 | WATAD AL ARABIAH | 2014-05-08 | 2014-06-08 | ABAR | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | alfies benjamin |  | 2013-08-26 | 2954.35
1327000237 | 80366 | WATAD AL ARABIAH | 2013-07-14 | 2013-08-25 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 3070.08 | PCC In Progress |  |  | alfies benjamin | 2013-09-08 | 2013-07-14 | 3185.28
1327000238 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-30 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 1413.41 | PCC In Progress |  | 07/06/2013 08/06/2013 | alfies benjamin | 2013-09-04 | 2013-06-03 | 1500.3
1327000239 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-30 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2908.8 | PCC In Progress |  | 21/06/2013 22/06/2013 | alfies benjamin | 2013-09-16 | 2013-06-03 | 2908.8
1327000240 | 80366 | WATAD AL ARABIAH | 2014-05-16 | 2014-06-16 | ABAR | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | alfies benjamin |  | 2013-08-26 | 1631.8
1327000241 | 80366 | WATAD AL ARABIAH | 2014-05-04 | 2014-06-04 | ABAR | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | alfies benjamin |  | 2013-08-26 | 1468.8
1327000242 | 80366 | WATAD AL ARABIAH | 2014-01-02 | 2014-01-30 | ABAR | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin |  | 2013-05-07 | 2908.8
1327000394 | 80366 | WATAD AL ARABIAH | 2013-07-21 | 2013-08-31 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 10266.19 | PCC In Progress |  |  | alfies benjamin | 2013-09-08 | 2013-07-21 | 13387.66
1327000398 | 80366 | WATAD AL ARABIAH | 2013-09-01 | 2013-09-30 | DMAD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2013-12-11 | 2013-07-29 | 5660.28
1327000366 | 80366 | WATAD AL ARABIAH | 2013-07-14 | 2013-08-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | laary | 2013-12-11 | 2013-07-14 | 4536
1327000338 | 80366 | WATAD AL ARABIAH | 2013-06-26 | 2013-07-26 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2014-01-13 | 2013-06-26 | 12981.14
1327000343 | 80366 | WATAD AL ARABIAH | 2013-07-14 | 2013-08-25 | ARDA2 | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2013-12-11 | 2013-07-14 | 14383.71
1227W00020 | 80366 | WATAD AL ARABIAH | 2013-06-24 | 2013-07-30 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 8668.8 | PCC In Progress |  | 19/10/2013 20/10/2013 | alfies benjamin | 2013-07-30 | 2013-06-03 | 9028.8
1227W00009 | 80366 | WATAD AL ARABIAH | 2014-05-01 | 2014-05-23 | ABAR | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | alfies benjamin |  | 2013-08-26 | 6927.91
1227W00012 | 80366 | WATAD AL ARABIAH | 2014-04-01 | 2014-05-01 | ABAR | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | alfies benjamin |  | 2013-08-26 | 3273.6
1327000015 | 80366 | WATAD AL ARABIAH | 2014-01-01 | 2014-01-18 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2014-01-01 | 2013-08-26 | 3072.9
1327000018 | 80366 | WATAD AL ARABIAH | 2013-09-12 | 2013-10-25 | DMAD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2014-01-01 | 2013-08-26 | 2937.6
1327000020 | 80366 | WATAD AL ARABIAH | 2013-09-14 | 2013-10-25 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2014-01-13 | 2013-08-26 | 5879.25
1127000579 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-23 | 2013-04-24 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 7534.08 | Yes |  |  | lari carboz | 2013-05-06 | 2013-04-02 | 8640
1127000540 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-07 | 2013-04-08 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 10227.098 | Yes |  |  | alfies benjamin | 2013-04-27 | 2013-04-02 | 11728.292
1127000529 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-30 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 12885.12 | PCC In Progress |  |  | ernesto e. lai | 2013-06-19 | 2013-04-02 | 13265.37
1127000521 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-27 | 2013-04-28 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 7731.138 | Yes |  |  | lari carboz | 2013-05-13 | 2013-04-02 | 7193.06
1127000510 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 8454.06 | Yes |  |  | laary | 2013-05-06 | 2013-05-04 | 6581.4
1127000497 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6003.4 | PCC In Progress |  |  | agobain | 2013-07-21 | 2013-05-04 | 6003.4
1127000511 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 1485.82 | Yes |  |  | ernesto e. lai | 2013-05-06 | 2013-04-02 | 764.16
1127000459 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6143.55 | Yes |  |  | ali gobain | 2013-05-08 | 2013-04-02 | 4912.28
1127000472 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2750.57 | Yes |  |  | ernesto e. lai | 2013-05-25 | 2013-05-04 | 3050.76
1127000492 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 12340.21 | Yes |  |  | ali gobain | 2013-06-01 | 2013-04-02 | 10676.77
1127000487 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 807.36 | Yes |  |  | ernesto e. lai | 2013-05-06 | 2013-04-02 | 133.62
1127000471 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-15 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 20651.49 | Yes |  |  | ali gobain | 2013-06-01 | 2013-04-02 | 20356.85
1127000479 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-25 | 2013-04-26 | JIZA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | Covered by FTTH | lari carboz |  | 2013-04-02 | 135.34
1127000453 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 11089.688 | PCC In Progress |  |  | agobain | 2013-06-12 | 2013-04-02 | 5469.94
1127000470 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-13 | 2013-04-30 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-08 | 2013-04-13 | 180.46
1127000478 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-19 | 2013-04-20 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 638.4 | Yes |  | Completed | lari carboz | 2013-04-27 | 2013-04-02 | 638.4
1127000359 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SHUQ | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  | see Dependencies | jomeel g. antonio |  | 2013-05-04 | 16588.74
1127000438 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 12511.03 | Yes |  |  | ali gobain | 2013-06-01 | 2013-05-04 | 11058.62
1127000430 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-03 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 10591.864 | Yes |  |  | lari carboz | 2013-04-14 | 2013-04-02 | 7214.98
1127000442 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-03 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5052.076 | Yes |  |  | lari carboz | 2013-04-14 | 2013-04-02 | 4899.58
1127000436 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-03 | 2013-04-04 | ABAR | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | Cover by WO 1327000217 | alfies benjamin |  | 2013-04-02 | 16924.84
1127000315 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-11 | 2013-04-12 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4824 | PCC In Progress |  |  | ernesto e. lai | 2013-06-02 | 2013-04-03 | 9753.6
1127000337 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-06 | 2013-04-30 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 9256.32 | Yes |  |  | laary | 2013-04-07 | 2013-04-03 | 5520
1127000288 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-15 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6264.98 | Yes |  |  | lari carboz | 2013-04-27 | 2013-04-02 | 6480
1127000270 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-03 | 2013-04-15 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6758.668 | PCC In Progress |  |  | ernesto e. lai | 2013-06-15 | 2013-04-03 | 7031.04
1127000248 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 8739.82 | Yes |  |  | alfies benjamin | 2013-06-08 | 2013-05-04 | 10808.62
1127000236 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-17 | 2013-04-18 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6382.04 | Yes |  |  | laary | 2013-05-18 | 2013-04-02 | 6378.16
1127000260 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-21 | 2013-04-22 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 8963.79 | Yes |  |  | lari carboz | 2013-04-27 | 2013-04-02 | 7537.92
1127000079 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-03 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2824.32 | Yes |  |  | alfies benjamin | 2013-05-06 | 2013-04-02 | 3494.4
1127000033 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | TWAL | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 7048.86 | PCC In Progress |  |  | ernesto e. lai | 2013-05-25 | 2013-04-02 | 11745.37
1127000032 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-03 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4118.97 | Yes |  |  | alfies benjamin | 2013-04-27 | 2013-04-02 | 5459.4
1127000041 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-03 | ARDH | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5958.94 | Yes |  |  | alfies benjamin | 2013-04-27 | 2013-04-02 | 5867.74
1127000026 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-16 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4032 | PCC In Progress |  |  | ernesto e. lai | 2013-06-02 | 2013-04-02 | 2880
1127000124 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 9609.58 | PCC In Progress |  |  | lari carboz | 2013-05-20 | 2013-05-04 | 6851.5
1127000119 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2664 | PCC In Progress |  |  | ernesto e. lai | 2013-05-25 | 2013-05-04 | 5040
1127000151 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2200.2 | Yes |  |  | agobain | 2013-05-25 | 2013-05-04 | 2188.8
0927000010 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | coverd By Wo | ali m. gobain |  | 2013-05-04 | 5470.44
0927000145 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-11 | 2013-04-12 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 3144.43 | PCC In Progress |  |  | jomeel g. antonio | 2013-06-12 | 2013-04-02 | 3144.43
0927000081 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SBYA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | customer no need Abdullah sultan | ali m. gobain |  | 2013-04-02 | 9123
0827000593 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-21 | 2013-04-22 | JIZA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | Cover by WO 1127000236 | lari carboz |  | 2013-04-02 | 5840.51
1127000017 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-03 | 2013-06-30 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 11384.98 | PCC In Progress |  |  | agobain | 2013-07-14 | 2012-07-09 | 19483.9
0927000163 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-16 | SBYA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | SUBSCRIER DECLINED THE SERVICE | ali m. gobain |  | 2013-04-02 | 5194.56
0927000180 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-17 | 2013-04-18 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 17564.34 | Yes |  |  | lari carboz | 2013-04-27 | 2013-04-02 | 9195.65
0927000183 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 12272.93 | PCC In Progress |  |  | agobain | 2013-07-21 | 2013-05-04 | 18720.72
0927000373 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | customer served | ali m. gobain |  | 2013-05-04 | 7372.42
0927000246 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-03 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5590.22 | Yes |  |  | alfies benjamin | 2013-05-04 | 2013-04-02 | 5142.72
1027000120 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-03 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4677.2 | Yes |  |  | alfies benjamin | 2013-04-21 | 2013-04-02 | 5804.04
1027000061 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | JIZA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | Cable passes the land of another Customer &serves By Postep | lari carboz |  | 2013-04-02 | 19381.1
0927000352 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5758.02 | Yes |  |  | ernesto e. lai | 2013-05-06 | 2013-04-02 | 6081.93
0927000397 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-05 | 2013-05-07 | DAMD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 11362.75 | Yes |  |  | alfies benjamin | 2013-05-05 | 2013-05-05 | 10879.2
1027000442 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 8000.87 | PCC In Progress |  |  | jomeel g. antonio | 2013-06-17 | 2013-05-04 | 8600.98
1027000463 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-15 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 146.88 | Yes |  |  | lari carboz | 2013-04-14 | 2011-03-19 | 146.88
1027000451 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 7667.2 | Yes |  |  | ali gobain | 2013-05-25 | 2013-05-04 | 7297.8
1027000493 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-15 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 424.32 | Yes |  |  | lari carboz | 2013-04-21 | 2013-04-02 | 627.84
1027000510 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-03 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 10731.6 | Yes |  |  | alfies benjamin | 2013-05-04 | 2013-04-02 | 9618.04
1027000511 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | SUBSCRIBER CHANGED HIS BUILDING PLACE NEED REDESIGN | ali m. gobain |  | 2013-05-04 | 123.82
1027000500 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | DAMD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 13962.966 | Yes |  |  | alfies benjamin | 2013-05-08 | 2013-04-02 | 11861.61
1027000435 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 10305.28 | PCC In Progress |  |  | jomeel g. antonio | 2013-06-26 | 2013-05-04 | 10117.19
1027000389 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-09-12 | 2013-10-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 9129.34 | PCC In Progress |  | 30/10/2013 | lari carboz | 2013-10-21 | 2013-08-21 | 8445.88
1027000394 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 8689.56 | Yes |  |  | ali gobain | 2013-06-12 | 2013-05-04 | 10164.02
1027000364 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-03 | ARDH | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | CANCELLED WRONG CONTACT NUMBER | alfies benjamin |  | 2013-04-02 | 6064.28
1027000283 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SHUQ | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4953.71 | PCC In Progress |  |  | jomeel g. antonio | 2013-06-12 | 2013-04-02 | 6592.04
1027000277 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 3240 | Yes |  |  | agobain | 2013-06-01 | 2013-05-04 | 3268.8
1027000540 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-13 | 2013-04-14 | BAYS | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6438.196 | Yes |  |  | jomeel g. antonio | 2013-05-19 | 2013-04-02 | 4875.74
1027000544 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-09 | 2013-04-10 | BAYS | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 10814.49 | Yes |  |  | jomeel g. antonio | 2013-05-14 | 2013-04-02 | 10013.37
1027000514 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-23 | 2013-04-30 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2750.4 | Yes |  |  | lari carboz | 2013-04-27 | 2013-04-02 | 1828.8
1127000010 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5496.96 | PCC In Progress |  |  | agobain | 2013-07-10 | 2013-05-04 | 11203.2
1027000036 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-11 | 2013-04-12 | BAYS | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6736.24 | Yes |  | 15/06/2014 16/06/2014 | jomeel g. antonio | 2013-05-19 | 2013-04-02 | 6702.72
1127000285 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 7534.78 | PCC In Progress |  |  | ernesto e. lai | 2013-06-15 | 2013-05-04 | 7755.22
1127000628 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2013-12-19 | 2013-04-02 | 150.72
1227000084 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-17 | 2013-04-18 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 17764.3952 | PCC In Progress |  |  | lari carboz | 2013-10-24 | 2013-04-02 | 12809.97
1227000073 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-03 | 2013-06-30 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin | 2013-06-15 | 2013-05-29 | 4522.52
1227000078 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 19274.96 | PCC In Progress |  |  | agobain | 2013-05-08 | 2013-04-02 | 17617.72
1227000090 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-15 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2197 | Yes |  |  | lari carboz | 2013-04-13 | 2013-04-02 | 1871.086
1127000542 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 3537.9 | Yes |  |  | ernesto e. lai | 2013-05-25 | 2013-05-04 | 4545.01
1227000016 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-02 | 2013-04-15 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6178.77 | Yes |  |  | lari carboz | 2013-04-27 | 2013-04-02 | 4884.48
1227000156 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-08-01 | 2013-08-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2096.64 | PCC In Progress |  | 05/08/2013 | lari carboz | 2013-10-09 | 2013-07-29 | 2025.6
1227000155 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-06 | 2013-05-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6637.44 | Yes |  |  | lari carboz | 2013-05-11 | 2013-05-06 | 8267.52
1227000157 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SHUQ | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 16626.88 | PCC In Progress |  |  | jomeel g. antonio | 2013-06-12 | 2013-04-02 | 12040.73
1227000186 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-30 | 2013-04-30 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2088 | Yes |  |  | alfies benjamin | 2013-04-30 | 2012-10-20 | 1800
1227000191 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-03 | 2013-04-15 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 26732.2 | Yes |  |  | lari carboz | 2013-04-07 | 2013-04-03 | 16046.86
1227000193 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 775.68 | Yes |  |  | lari carboz | 2013-05-19 | 2013-05-04 | 44.16
1227000195 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 9691.71 | Yes |  |  | ali gobain | 2013-06-01 | 2013-04-02 | 9272.97
1227000214 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-15 | 2013-04-30 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4106.58 | Yes |  |  | ernesto e. lai | 2013-05-06 | 2013-04-03 | 4523.78
1227000134 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-03 | 2013-04-15 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5608.64 | Yes |  |  | lari carboz | 2013-04-27 | 2013-04-03 | 4050.76
1227000251 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-04 | 2013-05-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 775.68 | Yes |  |  | lari carboz | 2013-05-19 | 2013-05-04 | 191.04
1227W00004 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-01 | 2013-06-30 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4625.26 | PCC In Progress |  |  | lari carboz | 2013-06-02 | 2013-06-01 | 4055.02
1227W00005 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-07-14 | 2013-07-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 194.8 | PCC In Progress |  |  | lari carboz | 2013-07-14 | 2013-07-14 | 194.8
1227W00016 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-10-01 | 2013-10-20 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2013-11-05 | 2013-09-02 | 12416.81
1327000049 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-10-01 | 2013-10-26 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4276.96 | PCC In Progress |  |  | lari carboz | 2013-10-21 | 2013-08-26 | 4259.14
1327000093 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-03 | 2013-04-15 | SBYA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | customer service | ali gobain |  | 2013-04-03 | 112.32
1327000216 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-18 | 2013-06-18 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 9188.13 | Yes |  | 06/12/2013 07/12/2013 | laary | 2013-05-19 | 2013-05-18 | 8955.006
1327000217 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-18 | 2013-06-18 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 18939 | Yes |  |  | alfies benjamin | 2013-05-19 | 2013-05-18 | 18143.2
1227W00006 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-01 | 2013-06-30 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 12353.544 | PCC In Progress |  |  | lari carboz | 2013-06-02 | 2013-06-01 | 12771.12
1227W00023 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-12 | 2013-06-30 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 402.22 | Yes |  | 10/11/2013 11/11/2013 | lari carboz | 2013-06-15 | 2013-06-12 | 2375.02
1227W00037 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-11-01 | 2013-11-21 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2013-12-04 | 2013-08-26 | 16738.1
1327000009 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-23 | 2013-07-23 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 15460.638 | Yes |  | 17/07/2013 18/07/2013 | lari carboz | 2013-06-24 | 2013-06-23 | 25294.652
1227W00011 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-12 | 2013-06-30 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5640.218 | PCC In Progress |  | 16/12/2013 17/12/2013 | lari carboz | 2013-06-15 | 2013-06-12 | 4797.86
1227W00018 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-23 | 2013-07-23 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 603.648 | Yes |  | 21/09/2013 22/09/2013 | lari carboz | 2013-06-24 | 2013-06-23 | 1810.59
1327000120 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-01 | 2013-06-30 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 11079.92 | PCC In Progress |  |  | lari carboz | 2013-06-02 | 2013-06-01 | 8574.32
1327000032 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-04-27 | 2013-04-30 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 23783.516 | PCC In Progress |  |  | lari carboz | 2013-06-15 | 2013-04-27 | 18411.7
1327000113 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-23 | 2013-07-23 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 3331.2 | Yes |  | 23/10/2013 24/10/2013 | lari carboz | 2013-06-24 | 2013-06-23 | 3268.8
1327000473 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-23 | 2014-02-28 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-23 | 8970.72
1327000469 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-10-01 | 2013-10-31 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | lari carboz |  | 2013-09-17 | 4286.75
1327000333 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-09-12 | 2013-10-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 7286.18 | PCC In Progress |  |  | lari carboz | 2013-10-22 | 2013-08-26 | 6688.1
1327000337 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-09-12 | 2013-10-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 313.9 | PCC In Progress |  |  | lari carboz | 2013-11-07 | 2013-08-26 | 226.63
1327000347 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-10-08 | 2013-11-13 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | lari carboz | 2014-01-13 | 2013-08-26 | 6441.2
1327000356 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-09-12 | 2013-10-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 11481.6 | PCC In Progress |  | Majd AlJanoub 1-Aug-13 | lari carboz | 2013-10-21 | 2013-08-26 | 10732.8
1327000501 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-12-05 | 2013-12-20 | KHAW | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2013-12-09 | 2013-10-03 | 1080
1327000497 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-11-11 | 2013-12-25 | KHAW | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-08 | 2013-10-03 | 349.44
1327000502 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-12-05 | 2013-12-25 | KHAW | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2013-12-09 | 2013-10-03 | 3556.66
1327000503 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-10-03 | 2013-10-31 | KHAW | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2013-12-19 | 2013-10-03 | 867.86
1327000285 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-11-11 | 2013-12-20 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | laary | 2013-11-17 | 2013-10-03 | 388.8
1327000513 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-12-05 | 2013-12-25 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2013-12-09 | 2013-10-23 | 7091.53
1327000512 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-12-05 | 2013-12-25 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2013-12-09 | 2013-10-23 | 5476.62
1327000681 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-01 | 2014-01-30 | KHAW | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-06 | 2013-11-18 | 3126.28
1327000688 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-11-28 | 2013-12-13 | SAMI | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-28 | 2013-11-28 | 12295.94
1327000672 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-02-01 | 2014-02-28 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-02-03 | 2013-11-18 | 13177.05
1327000673 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-01 | 2014-01-30 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-06 | 2013-11-18 | 7842.93
1327000677 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-11-20 | 2013-12-31 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | laary |  | 2013-11-18 | 3662.3
1327000679 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-04-01 | 2014-04-30 | SLHD | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | ernesto e. lai |  | 2013-11-18 | 3802.91
1327000328 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-03-05 | 2014-04-15 | SLHD | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | 15/04/2014 | ernesto e. lai |  | 2013-08-26 | 32196.41
1327000361 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-05 | 2014-02-12 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-28 | 2013-08-26 | 8427.97
1327000365 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-10-01 | 2013-10-31 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2013-11-05 | 2013-07-29 | 648.96
1327000266 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-07-29 | 2013-08-15 | SLHD | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  | 28-May-13 | ernesto e. lai | 2014-01-28 | 2013-07-29 | 6076.2
1327000267 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-07-29 | 2013-08-29 | ABAR | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  | 31-May-13 | alfies benjamin |  | 2013-07-29 | 5577.416
1327000265 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-12-19 | 2013-12-31 | SAMI | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai |  | 2013-10-23 | 5421.98
1327000273 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-03-19 | 2014-04-19 | SLHD | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | ernesto e. lai |  | 2013-08-26 | 1195.18
1327000231 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-05-20 | 2013-06-30 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 14360.57 | Yes |  | 03/07/2013 04/07/2013 | alfies benjamin | 2013-06-17 | 2013-05-20 | 13177.62
1327000261 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-02-25 | 2014-04-01 | SLHD | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | ernesto e. lai |  | 2013-08-26 | 5530.3
1327000223 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-12 | 2013-06-30 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6148.8 | PCC In Progress |  | 17/09/2013 18/09/2013 | lari carboz | 2013-06-15 | 2013-06-12 | 6148.8
1327000320 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-08 | 2014-02-14 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-28 | 2013-08-26 | 12514.82
1327000293 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-12-06 | 2014-01-06 | SLHD | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  | 06/01/2014 | ernesto e. lai |  | 2013-08-26 | 3442.22
1327000292 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-02-01 | 2014-02-20 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | lari carboz | 2014-02-03 | 2013-08-26 | 504
1327000304 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-08-01 | 2013-08-31 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 7399.48 | PCC In Progress |  |  | lari carboz | 2013-10-05 | 2013-07-29 | 6120
1327000271 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-07-17 | 2013-08-17 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 1512 | PCC In Progress |  |  | lari carboz | 2013-09-30 | 2013-07-17 | 1512
1327000277 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-11-05 | 2013-12-05 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2548.8 | PCC In Progress |  |  | lari carboz | 2013-11-07 | 2013-08-26 | 2950.96
1327000290 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-09 | 2013-06-30 | BRDR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 1944 | PCC In Progress |  |  | ernesto e. lai | 2013-08-25 | 2013-06-09 | 2160
1327000299 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-06-22 | 2013-07-31 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2013-10-29 | 2013-06-09 | 11678.33
1427000040 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-23 | 2014-02-28 | SAMI | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | ernesto e. lai |  | 2014-01-23 | 16496.96
1427000045 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-23 | 2014-02-28 | SLHD | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | ernesto e. lai |  | 2014-01-23 | 8823.2
1427000007 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-12 | 2014-01-31 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-12 | 7687.95
1427000038 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-23 | 2014-02-28 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-23 | 6372.22
1427000024 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-15 | 2014-02-28 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho |  |  | need scope of work |  | ernesto e. lai | 2014-01-28 | 2014-01-15 | 6082.81
1427000016 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-16 | 2014-02-28 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-16 | 748.8
1427000020 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-15 | 2014-02-28 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-15 | 748.8
1427000013 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-15 | 2014-02-28 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-15 | 28135.36
1427000010 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-14 | 2014-01-31 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-14 | 3628.8
1427000011 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-14 | 2014-01-31 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-14 | 8981.48
1427000008 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-14 | 2014-01-31 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-14 | 5479.05
1327000211 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-06 | 2014-01-31 | YSMN | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho |  |  | need scope of work |  | lari carboz | 2014-01-13 | 2014-01-06 | 7218.4
1327000718 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-12-18 | 2014-01-24 | 703-00-000 | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | lari carboz | 2014-02-02 | 2013-12-18 | 7502.48
1327000691 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2013-12-28 | 2014-01-26 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-28 | 2013-12-26 | 2706.15
1327000685 | 79811 | Majd AlJanoub for general Contracting Ltd. | 2014-01-01 | 2014-01-31 | BRDR | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai |  | 2014-01-01 | 2577.7
1327000025 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-11-01 | 2013-12-01 | SBYA | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | Cancelled By customer | ali gobain |  | 2013-08-26 | 4204.8
1327000028 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-03-01 | 2014-03-22 | SBYA | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | 22/03/2014 | ali gobain |  | 2013-08-26 | 2188.8
1327000019 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-03-01 | 2014-03-26 | SBYA | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | ali gobain |  | 2013-08-26 | 6059.46
1327000017 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-14 | 2013-08-25 | BAYS | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | Cancelled By Customer | jomeel g. antonio |  | 2013-07-14 | 1547.52
1327000016 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-09-12 | 2013-10-12 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2013-12-19 | 2013-08-20 | 9174.72
1327000001 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-11-01 | 2013-11-25 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2013-11-03 | 2013-08-26 | 6110.4
1327000353 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-14 | 2013-08-25 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2013-12-03 | 2013-07-14 | 7279.91
1327000357 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-14 | 2013-08-25 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2013-12-15 | 2013-07-14 | 2025.6
1327000375 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-23 | 2013-08-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  | 13/12/2013 | ali gobain | 2013-10-10 | 2013-07-23 | 30860.16
1327000404 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-12-01 | 2013-12-31 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  | 17-Dec-13 | ali gobain |  | 2013-07-29 | 1909.83
1327000405 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-05-01 | 2014-05-31 | SBYA | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | 10-Mar-14 | ali gobain |  | 2013-07-29 | 3523.2
1327000406 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-12-01 | 2013-12-31 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2013-12-04 | 2013-07-29 | 1828.8
1327000351 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-12-01 | 2013-12-31 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2013-12-04 | 2013-07-29 | 720
1327000427 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-04-02 | 2014-05-02 | SBYA | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | ali gobain |  | 2013-08-26 | 3628.8
1327000425 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-05-06 | 2014-06-08 | SBYA | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Majed Garboo 8-Jun-14 | ali gobain |  | 2013-08-26 | 2774.4
1327000435 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-05-06 | 2014-06-06 | SBYA | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Majed Garboo 6-Jun-14 | ali gobain |  | 2013-08-26 | 748.8
1327000436 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-04-04 | 2014-05-04 | SBYA | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Majed Garboo 4-Mar-14 | ali gobain |  | 2013-08-26 | 3268.8
1327000325 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-29 | 2013-08-31 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2013-12-04 | 2013-07-29 | 10895.76
1327000370 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-29 | 2013-08-31 | BAYS | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2013-12-15 | 2013-07-29 | 14476.8
1327000407 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-11-15 | 2013-12-23 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  | Majed Garboo 23-Dec-13 | ali gobain |  | 2013-08-26 | 41128.93
1327000426 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-11-15 | 2013-12-15 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2014-01-19 | 2013-08-26 | 770.86
1327000429 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-20 | 2014-02-24 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | ali gobain |  | 2013-08-26 | 7853.15
1327000431 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-11-09 | 2013-12-09 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2014-01-27 | 2013-08-26 | 2025.6
1327000372 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-09-12 | 2013-10-25 | BAYS | held order | Held Order-HBU-Additional | cancelled | 2013 objective design issued - ho | 0 |  |  | Cancelled By customer 0563322017 | jomeel g. antonio |  | 2013-08-20 | 9360
1327000350 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-24 | 2013-08-31 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 7704 |  |  |  | jomeel g. antonio | 2013-09-30 | 2013-07-24 | 9360
1327000352 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-09-12 | 2013-10-25 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2013-12-12 | 2013-08-20 | 5568.2
1327000368 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-24 | 2013-08-31 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 9541.7 |  |  | 20-Jun-13 | jomeel g. antonio | 2013-09-24 | 2013-07-24 | 12240
1327000389 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-09-12 | 2013-10-25 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 9433.7 |  |  | 23-Aug-13 | jomeel g. antonio | 2013-09-30 | 2013-08-20 | 9496.53
1327000390 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-24 | 2013-08-31 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 15233.038 |  |  | 10-Jun-13 | jomeel g. antonio | 2013-09-30 | 2013-07-24 | 12335.4
1327000396 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-09-12 | 2013-10-25 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 9400.32 |  |  |  | jomeel g. antonio | 2013-09-16 | 2013-08-20 | 12240
1327000428 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-25 | 2014-02-14 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2014-01-27 | 2013-08-26 | 638.4
1327000400 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-12-15 | 2013-12-31 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio |  | 2013-12-15 | 9524.4
1327000403 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-09-12 | 2013-10-25 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2013-12-04 | 2013-08-26 | 8002.4
1327000302 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-06-24 | 2013-07-30 | BAYS | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2744.71 |  |  |  | jomeel g. antonio | 2013-12-03 | 2013-06-09 | 2880
1327000307 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-06-24 | 2013-07-30 | BAYS | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 720 |  |  |  | jomeel g. antonio | 2013-09-24 | 2013-06-09 | 720
1327000287 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-06-24 | 2013-07-30 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 748.8 |  |  |  | jomeel g. antonio | 2013-12-03 | 2013-06-22 | 1080
1327000297 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-09-12 | 2013-10-25 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 1080 |  |  |  | jomeel g. antonio | 2013-09-16 | 2013-08-20 | 1080
1327000300 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-14 | 2013-08-25 | BAYS | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2013-12-10 | 2013-07-14 | 1080
1327000315 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-14 | 2013-08-25 | BAYS | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  | 21/07/2013 22/07/2013 | jomeel g. antonio |  | 2013-07-14 | 6839.04
1327000323 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-07-14 | 2013-08-25 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 4895.472 |  |  | 29/07/2013 30/07/2013 | jomeel g. antonio | 2013-09-22 | 2013-07-14 | 4243.2
1327000544 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-06-01 | 2014-06-30 | BAYS | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | 30-Jun-14 | jomeel g. antonio |  | 2013-11-03 | 1996.8
1327000286 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-06-03 | 2014-06-30 | BAYS | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio |  | 2013-11-03 | 5760
1327000516 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-01 | 2014-02-12 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio |  | 2013-12-01 | 15047.02
1327000698 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-02-01 | 2014-02-28 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2014-02-03 | 2013-12-01 | 3960
1327000465 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-01 | 2014-01-14 | SQYQ | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2014-01-05 | 2013-09-09 | 15089.784
1327000496 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-10-23 | 2013-11-30 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2013-11-28 | 2013-10-23 | 6199.6
1327000492 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-10-03 | 2013-10-31 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 2880 |  |  |  | jomeel g. antonio | 2013-10-28 | 2013-10-03 | 2304
1327000411 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-09-12 | 2013-10-25 | BAYS | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 3478.11 |  |  |  | jomeel g. antonio | 2013-10-28 | 2013-08-26 | 5124.4
1327000460 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-05-01 | 2014-05-28 | SBYA | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | ali gobain |  | 2013-09-09 | 4088.05
1427000006 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-20 | 2014-02-28 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  | need scope of work |  | jomeel g. antonio | 2014-02-04 | 2014-01-20 | 3871.4
1427000039 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-23 | 2014-02-28 | SHUQ | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | jomeel g. antonio |  | 2014-01-23 | 6166.9
1427000021 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-15 | 2014-02-28 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | agobain |  | 2014-01-15 | 7920
1427000017 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-15 | 2014-01-31 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | jomeel g. antonio |  | 2014-01-15 | 5800.32
1427000029 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-19 | 2014-02-28 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho |  |  | need scope of work |  | agobain |  | 2014-01-19 | 18447.2
1427000004 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-12 | 2014-01-31 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | jomeel g. antonio |  | 2014-01-12 | 7966.37
1427000005 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-14 | 2014-01-31 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | ali gobain |  | 2014-01-14 | 4108.8
1427000014 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-15 | 2014-02-28 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | agobain |  | 2014-01-15 | 5850.72
1427000015 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-15 | 2014-02-28 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | agobain |  | 2014-01-15 | 11744.14
1427000012 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-15 | 2014-02-28 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | jomeel g. antonio |  | 2014-01-15 | 5837.7
1427000001 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-05 | 2014-01-31 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio |  | 2014-01-05 | 7346.6
1327000723 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-01 | 2014-01-31 | BAYS | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio |  | 2014-01-01 | 9551.92
1327000721 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-12-28 | 2014-01-26 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio |  | 2013-12-26 | 12600
1327000706 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-12-04 | 2014-01-18 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio |  | 2013-12-04 | 8925.7
1327000709 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2013-12-15 | 2013-12-31 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio |  | 2013-12-15 | 3096
1427000043 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-23 | 2014-02-28 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | ali m. gobain |  | 2014-01-23 | 7893.12
1427000046 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-23 | 2014-02-28 | SBYA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | agobain |  | 2014-01-23 | 8455.2
1427000048 | 80383 | MAGED RASHED AL GARBOA EST FOR CONTRACTING | 2014-01-23 | 2014-02-28 | DARB | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | jomeel g. antonio |  | 2014-01-23 | 7766.78
1327000034 | 80388 | Mohemmed Bin Gerboo EST. | 2013-05-19 | 2013-06-19 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 1651.18 |  |  |  | lari carboz | 2013-06-24 | 2013-05-19 | 5020.8
1327000529 | 80388 | Mohemmed Bin Gerboo EST. | 2014-01-01 | 2014-01-31 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-08 | 2013-11-03 | 8097.94
1327000542 | 80388 | Mohemmed Bin Gerboo EST. | 2014-02-01 | 2014-02-28 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | lari carboz |  | 2013-11-03 | 853.44
1327000545 | 80388 | Mohemmed Bin Gerboo EST. | 2013-11-11 | 2013-12-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | laary | 2014-01-29 | 2013-11-07 | 4811.3
1327000538 | 80388 | Mohemmed Bin Gerboo EST. | 2013-11-11 | 2013-12-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | laary | 2014-01-29 | 2013-11-03 | 5842.4
1327000485 | 80388 | Mohemmed Bin Gerboo EST. | 2013-11-11 | 2013-12-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5716.99 |  |  |  | laary | 2013-12-11 | 2013-11-03 | 4963.27
1327000659 | 80388 | Mohemmed Bin Gerboo EST. | 2014-02-02 | 2014-02-28 | SAMI | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai |  | 2013-11-07 | 3409.416
1327000666 | 80388 | Mohemmed Bin Gerboo EST. | 2013-11-12 | 2013-12-20 | SAMI | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai |  | 2013-11-12 | 14326.33
1327000654 | 80388 | Mohemmed Bin Gerboo EST. | 2013-12-01 | 2013-12-30 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | laary |  | 2013-11-12 | 10631.27
1327000661 | 80388 | Mohemmed Bin Gerboo EST. | 2014-01-01 | 2014-01-30 | SLHD | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai | 2014-01-08 | 2013-11-12 | 1533.06
1327000668 | 80388 | Mohemmed Bin Gerboo EST. | 2013-12-01 | 2013-12-30 | SLHD | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai |  | 2013-11-12 | 8661.1
1327000667 | 80388 | Mohemmed Bin Gerboo EST. | 2013-11-12 | 2013-12-20 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | laary | 2014-01-29 | 2013-11-12 | 4781.15
1327000509 | 80388 | Mohemmed Bin Gerboo EST. | 2014-01-01 | 2014-01-30 | SLHD | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | ernesto e. lai |  | 2013-10-23 | 323.5
1327000510 | 80388 | Mohemmed Bin Gerboo EST. | 2014-01-08 | 2014-01-31 | SAMI | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho |  |  | need scope of work |  | ernesto e. lai | 2014-01-12 | 2013-10-23 | 3945.6
1327000524 | 80388 | Mohemmed Bin Gerboo EST. | 2014-04-02 | 2014-04-30 | SLHD | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | ernesto e. lai |  | 2013-11-03 | 4567.27
1327000526 | 80388 | Mohemmed Bin Gerboo EST. | 2014-05-01 | 2014-05-31 | BRDR | held order | Held Order-HBU-Additional | not started | 2013 objective design issued - ho | 0 |  |  | Completed | ernesto e. lai |  | 2013-11-03 | 2568.18
1327000461 | 80388 | Mohemmed Bin Gerboo EST. | 2013-11-11 | 2013-12-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | laary | 2014-01-29 | 2013-09-17 | 7200
1327000464 | 80388 | Mohemmed Bin Gerboo EST. | 2013-11-11 | 2013-12-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | laary | 2014-01-29 | 2013-09-17 | 3240
1427000023 | 80388 | Mohemmed Bin Gerboo EST. | 2014-01-23 | 2014-02-28 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  | need scope of work |  | lari carboz |  | 2014-01-23 | 7325.95
1427000030 | 80388 | Mohemmed Bin Gerboo EST. | 2014-01-23 | 2014-02-28 | JIZA | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho |  |  | need scope of work | 053719669 | lari carboz |  | 2014-01-23 | 7948.8
1027000201 | 80388 | Mohemmed Bin Gerboo EST. | 2013-04-15 | 2013-04-30 | SHUQ | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 8388.78 |  |  |  | jomeel g. antonio | 2013-08-01 | 2013-04-02 | 7857.98
1127000398 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-06-22 | 2013-07-31 | FRSN | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin |  | 2013-04-02 | 30896.18
1127000013 | 80230 | DETCON Saudia Co. (Data_SAD) | 2012-07-09 | 2012-08-20 | SBYA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | ali gobain | 2013-12-01 | 2012-07-09 | 15047.04
1327000311 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-07-14 | 2013-08-25 | FRSN | held order | Held Order-HBU-Additional | in progress | 2013 objective design issued - ho | 0 |  |  |  | alfies benjamin |  | 2013-07-14 | 3426.88
1227000184 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-06-03 | 2013-06-30 | DARB | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio | 2013-11-24 | 2012-10-08 | 6880.32
1327000295 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-07-14 | 2013-08-25 | JIZA | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 5699.6 | PCC In Progress |  |  | laary | 2013-08-21 | 2013-07-14 | 5092.8
1027000354 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-07-15 | 2013-08-15 | ABAR | held order | Held Order-HBU-Additional | completed | 2013 objective design issued - ho | 6046.2 | PCC In Progress |  |  | alfies benjamin | 2013-08-15 | 2013-07-15 | 5495.16
0927000405 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-10 | 2012-08-16 | SBYA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 4952.55 | DM In Progress |  |  | agobain | 2013-01-01 | 2012-07-10 | 5090.5
1127000242 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-08 | 2012-08-20 | DARB | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 4082.04 | CM In Progress |  |  | jgantonio | 2012-12-01 | 2012-07-08 | 4851.27
1127000239 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-08 | 2012-08-20 | ABAR | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 3092.53 | DM In Progress |  |  | abenjamin | 2013-02-19 | 2012-07-08 | 2818.37
1127000400 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-08 | 2012-08-20 | DARB | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 7078.262 | CM In Progress |  |  | jgantonio | 2012-11-03 | 2012-07-08 | 14014.81
1127000617 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-08 | 2012-08-20 | ABAR | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 3594.24 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | abenjamin | 2013-02-10 | 2012-07-08 | 3993.6
1127000597 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 4974.72 | PM In Progress |  |  | lscarboz | 2013-10-07 | 2012-07-10 | 5760
1127000611 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 4690.4 | PM In Progress |  |  | lscarboz | 2013-04-14 | 2012-07-10 | 4107.7
1127000493 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 2524.8 | PM In Progress |  |  | lscarboz | 2012-11-28 | 2012-07-10 | 3928.2
1127000476 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 2867.54 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2012-07-10 | 1993.86
1127000466 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | SLHD | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 3044.94 | PM In Progress |  |  | elai | 2013-03-13 | 2012-07-10 | 8991.73
1127000468 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 67.39 | PM In Progress |  |  | lscarboz | 2013-01-16 | 2012-07-10 | 95.02
1127000469 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | SAMI | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 3600 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-03-13 | 2012-07-10 | 3600
1127000477 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | SAMI | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 6863.04 | PM In Progress |  |  | elai | 2013-03-13 | 2012-07-10 | 7093.44
1127000467 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 889.03 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2012-07-10 | 1343.96
1127000456 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 1676.16 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2012-07-10 | 394.56
1127000533 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 2764.8 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-04-07 | 2012-07-10 | 394.56
1127000507 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | SAMI | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 12418.2 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-11-21 | 2012-07-10 | 3542.24
1127000517 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | SLHD | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 3742.733 | PM In Progress |  |  | elai | 2013-03-13 | 2012-07-10 | 3476.63
1127000474 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 156.48 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2012-07-10 | 156.48
1127000291 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 10639.05 | PM In Progress |  |  | lscarboz | 2013-01-16 | 2012-07-10 | 11276.42
1227000071 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 6119.6 | Yes |  |  | laary | 2012-11-07 | 2012-07-10 | 6925.94
1227000070 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-09-16 | 2012-10-24 | JIZA | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 31277.73 | Yes |  | Jeel AlFursan Est. FOR TRADING &CO | laary | 2013-01-02 | 2012-07-10 | 15822.86
1127000598 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | SAMI | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 4176.96 | Yes |  |  | ernesto e. lai | 2012-10-22 | 2012-07-10 | 6555.66
1127000525 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-10 | 2012-08-24 | SAMI | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 3594.24 | Yes |  |  | ernesto e. lai | 2012-10-23 | 2012-07-10 | 10895.76
1127000488 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-08 | 2012-08-20 | BAYS | held order | Held Order-HBU-P1 | cancelled | 2013 objective design issued | 0 |  |  | Cancelled By Customer | jomeel g. antonio |  | 2012-07-08 | 331.2
1127000451 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-08 | 2012-08-20 | BAYS | held order | Held Order-HBU-P1 | completed | 2013 objective design issued | 135.34 | Yes |  |  | jomeel g. antonio | 2012-10-23 | 2012-07-08 | 135.34
1127000309 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-07-08 | 2012-08-20 | ABAR | held order | Held Order-HBU-P1 | cancelled | 2013 objective design issued | 0 |  |  | Cancelled By Customer refused | alfies benjamin |  | 2012-07-08 | 10783.64
1127000207 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-19 | 2011-07-09 | DAMD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 892.8 | PM In Progress |  |  | abenjamin | 2013-01-12 | 2011-06-19 | 864
1127000230 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-19 | 2011-07-19 | SAMI | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2496 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-02-11 | 2011-06-19 | 2275.2
1127000272 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SAMI | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3972.47 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-03-03 | 2011-09-19 | 4587.21
1127000271 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1180.8 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-02-02 | 2011-09-19 | 1108.8
1127000274 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1226.88 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-08-20 | 658.56
1127000228 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-19 | 2011-07-12 | TWAL | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1704.96 | PM In Progress |  |  | elai | 2013-03-13 | 2011-06-19 | 1578.56
1127000245 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2486.14 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | jgantonio | 2013-02-02 | 2011-09-19 | 2224.26
1127000020 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 720 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-09-19 | 748.8
1127000030 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-18 | 2011-07-18 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 7085.74 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-06-18 | 7085.74
1127000148 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 5020.8 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-02-02 | 2011-09-19 | 4771.2
1127000150 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 8739.84 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-02-06 | 2011-09-19 | 8016
1127000166 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2679.77 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-09-19 | 2587.61
1127000134 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | DARB | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3240 | PM In Progress |  |  | jgantonio | 2013-03-19 | 2011-09-19 | 3240
1127000090 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4521.52 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | abenjamin | 2013-02-10 | 2011-09-19 | 3003.2
1127000122 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4908.448 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-09-19 | 4738.95
1127000120 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-18 | 2011-07-08 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3971.44 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-04-07 | 2011-06-18 | 4218.22
1127000162 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1268.762 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-09-19 | 916.2
1127000473 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-03 | 2011-11-15 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3100.37 | DM In Progress |  |  | lscarboz | 2011-12-26 | 2011-10-03 | 2844
1127000338 | 76677 | Mohemmed Bin Gerboo EST. | 2011-09-18 | 2011-10-20 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 24310.05 | DM In Progress |  |  | agobain | 2011-11-26 | 2011-09-18 | 18960
1127000087 | 76677 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | DAMD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2904 | DM In Progress |  |  | abenjamin | 2011-06-21 | 2011-04-13 | 3072
1127000092 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-12-03 | 2011-12-24 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 6988.044 | DM In Progress |  |  | lscarboz | 2012-02-08 | 2011-11-26 | 8290.56
1127000138 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-12-10 | 2012-01-18 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4567.24 | DM In Progress |  |  | elai | 2013-03-16 | 2011-12-10 | 6007.24
1127000355 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-09 | 2012-05-23 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 12469.14 | DM In Progress |  |  | abenjamin | 2012-06-02 | 2012-04-09 | 14906.22
1127000465 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-01-25 | 2012-02-29 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4417.92 |  |  |  | lscarboz | 2012-11-26 | 2012-01-25 | 6376.32
1127000418 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-09-19 | 2011-10-31 | DAMD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 10410.42 | DM In Progress |  |  | abenjamin | 2011-09-20 | 2011-09-10 | 10432.5
1127000379 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2601.6 | DM In Progress |  |  | lscarboz | 2013-02-25 | 2011-09-19 | 2601.6
1127000489 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-10-30 | 2011-12-14 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2953.35 | DM In Progress |  |  | lscarboz | 2012-11-26 | 2011-10-30 | 2953.35
1127000001 | 81002 | Mohemmed Bin Gerboo EST. | 2011-06-18 | 2011-06-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1966.07 | CM In Progress |  |  | lscarboz | 2011-06-18 | 2011-06-15 | 1860.48
1127000225 | 81002 | Mohemmed Bin Gerboo EST. | 2011-06-18 | 2011-06-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 366.18 | CM In Progress |  |  | lscarboz | 2011-06-18 | 2011-06-18 | 154.26
1127000234 | 81002 | Mohemmed Bin Gerboo EST. | 2011-06-18 | 2011-06-21 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 112.32 | CM In Progress |  |  | lscarboz | 2011-06-18 | 2011-06-18 | 112.32
1127000388 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1328.6 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-09-19 | 678.7
1127000362 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | DAMD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2631.48 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | abenjamin | 2013-02-10 | 2011-08-20 | 2558.81
1127000377 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3394.56 | PM In Progress |  |  | abenjamin | 2012-02-06 | 2011-08-20 | 3744
1127000375 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 8854.05 | PM In Progress |  |  | elai | 2013-03-13 | 2011-08-20 | 5849.85
1127000392 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1699.008 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-09-19 | 1368
1127000435 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2169.96 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-02-02 | 2011-09-19 | 2054.4
1127000448 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1952.4 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | jgantonio | 2013-02-02 | 2011-09-19 | 1952.4
1127000458 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2175.36 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-09-19 | 1848
1127000382 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 123.82 | PM In Progress |  |  | abenjamin | 2011-10-12 | 2011-09-19 | 114.22
1127000331 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-21 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1838.976 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2013-03-03 | 2011-08-20 | 653.76
1127000319 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3052.032 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | jgantonio | 2013-02-02 | 2011-09-19 | 2624.05
1127000351 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2103.04 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-02-06 | 2011-09-19 | 2863.52
1127000369 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | DARB | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 964.38 | PM In Progress |  |  | jgantonio | 2013-03-19 | 2011-08-20 | 1022.29
1127000281 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2809.92 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-03-13 | 2011-09-19 | 4320
1127000282 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-13 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 156.08 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | elai | 2013-03-13 | 2011-08-20 | 152.73
1127000277 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3006.27 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | agobain | 2013-02-06 | 2011-09-20 | 3148.32
1127000267 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2003.76 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | lscarboz | 2012-12-24 | 2011-08-20 | 2126.56
1127000292 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2268 | PM In Progress |  | Email From Adel BaAbdullah Sub.Not assigned Work | jgantonio | 2013-02-02 | 2011-09-19 | 1328.6
1127000619 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-04-23 | 2012-05-31 | DARB | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 95.02 | Yes |  |  | jomeel g. antonio | 2012-04-28 | 2012-04-23 | 114.22
1127000389 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1776.07 | Yes |  |  | laary | 2012-02-08 | 2011-09-19 | 1471.5
1127000385 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 44.16 | Yes |  |  | laary | 2011-10-01 | 2011-09-19 | 44.16
1127000365 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-11 | 2011-10-26 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3794.88 | Yes |  |  | laary | 2011-11-26 | 2011-09-11 | 2628.4
1127000360 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 95.02 | Yes |  |  | jomeel g. antonio | 2011-10-01 | 2011-08-20 | 95.02
1127000394 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3317.15 | Yes |  |  | laary | 2011-12-07 | 2011-09-19 | 3317.15
1127000384 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SAMI | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 149.76 | Yes |  |  | ernesto e. lai | 2011-10-18 | 2011-09-19 | 149.76
1127000431 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 178.56 | Yes |  |  | laary | 2011-10-01 | 2011-09-19 | 76.89
1127000404 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 895.08 | Yes |  |  | laary | 2012-01-10 | 2011-09-19 | 808.68
1127000414 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 529.92 | Yes |  |  | laary | 2011-10-03 | 2011-09-19 | 532.8
1127000383 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | DARB | held order | ICMS-HO-HBU-2012 | in progress | 2012 objective design issued | 0 |  |  | Email From Adel BaAbdullah Sub.Not assigned Work | jomeel g. antonio |  | 2011-09-19 | 246.7
1127000405 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 638.4 | Yes |  |  | laary | 2011-10-12 | 2011-09-19 | 638.4
1127000401 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 191.8 | Yes |  |  | laary | 2011-10-16 | 2011-09-19 | 191.8
1127000406 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-26 | 2011-10-31 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1718.54 | Yes |  |  | ali gobain | 2012-01-08 | 2011-09-19 | 1653.55
1127000391 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1022.66 | Yes |  |  | laary | 2012-01-11 | 2011-09-19 | 1231.05
1127000325 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3523.2 | Yes |  |  | jomeel g. antonio | 2012-10-23 | 2011-09-19 | 1472.58
1127000324 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-26 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2624.78 | Yes |  |  | lari carboz | 2012-01-10 | 2011-08-20 | 2631.48
1127000316 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 682.05 | Yes |  |  | laary | 2011-10-09 | 2011-09-19 | 1003.65
1127000329 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-11 | 2011-10-26 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3538.26 | Yes |  |  | laary | 2011-11-27 | 2011-09-11 | 3603.25
1127000516 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-01-10 | 2012-02-16 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 6566.208 | Yes |  |  | lari carboz | 2012-02-27 | 2012-01-10 | 6202.85
1127000429 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 377.2 | Yes |  |  | laary | 2011-10-01 | 2011-09-19 | 123.82
1127000427 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1968.68 | Yes |  |  | laary | 2012-01-08 | 2011-09-19 | 2978.72
1127000439 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4060.03 | Yes |  |  | laary | 2012-01-21 | 2011-09-19 | 3201.48
1127000443 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 696 | Yes |  |  | laary | 2011-10-03 | 2011-09-19 | 696
1127000444 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 272.64 | Yes |  |  | laary | 2011-10-03 | 2011-09-19 | 272.64
1127000447 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1440 | Yes |  |  | jomeel g. antonio | 2013-01-01 | 2011-09-19 | 1328.6
1127000197 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-18 | 2011-06-25 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 114.22 | Yes |  |  | lari carboz | 2011-10-09 | 2011-06-18 | 114.22
1127000296 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-13 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 131.61 | Yes |  |  | lari carboz | 2011-09-17 | 2011-08-20 | 131.61
1127000278 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 7194.24 | Yes |  |  | ernesto e. lai | 2011-12-31 | 2011-09-19 | 8094.81
1127000264 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-28 | DARB | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3871.31 | Yes |  |  | alfies benjamin | 2013-01-01 | 2011-08-20 | 4374.43
1127000314 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 394.56 | Yes |  |  | lari carboz | 2011-09-07 | 2011-08-20 | 394.56
1127000308 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 505.92 | Yes |  |  | lari carboz | 2011-10-09 | 2011-08-20 | 141.12
1127000294 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-20 | DARB | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 79.67 | Yes |  |  | jomeel g. antonio | 2011-09-20 | 2011-08-20 | 98.87
1127000306 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 409.92 | Yes |  |  | lari carboz | 2011-09-07 | 2011-08-20 | 409.92
1127000339 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 443.52 | Yes |  |  | lari carboz | 2011-09-07 | 2011-08-20 | 443.52
1127000300 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 278.4 | Yes |  |  | lari carboz | 2011-09-07 | 2011-08-20 | 278.4
1127000327 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 837.1 | Yes |  |  | lari carboz | 2011-09-07 | 2011-08-20 | 837.1
1127000298 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 152.73 | Yes |  |  | ernesto e. lai | 2012-01-25 | 2011-09-19 | 152.73
1127000336 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2524.8 | Yes |  |  | laary | 2012-09-15 | 2011-09-19 | 2524.8
1127000371 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-20 | DARB | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 199.68 | Yes |  |  | jomeel g. antonio | 2011-09-20 | 2011-08-20 | 199.68
1127000366 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 112.32 | Yes |  |  | laary | 2011-10-09 | 2011-09-19 | 112.32
1127000364 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-29 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 95.02 | Yes |  |  | lari carboz | 2011-09-07 | 2011-08-20 | 95.02
1127000373 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1008 | Yes |  |  | alfies benjamin | 2011-09-18 | 2011-08-20 | 1008
1127000046 |  | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-03-31 | DARB | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued |  |  | need cr | Zero Design | jomeel g. antonio | 2011-10-18 | 2011-03-19 | 277.96
1127000098 |  | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-04-20 | TWAL | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued |  |  | need cr | Zero Design | ernesto e. lai | 2012-01-03 | 2011-03-20 | 1248
1127000580 |  | Mohemmed Bin Gerboo EST. | 2011-11-19 | 2011-11-28 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued |  |  | need cr | Zero Design | laary | 2011-12-05 | 2011-11-13 | 288
1127000106 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-18 | 2011-06-28 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 394.56 | Yes |  | This job is not yet implemented Email From Lari S. Carboz | lari carboz | 2011-06-27 | 2011-06-18 | 394.56
1127000330 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-07-24 | 2011-08-24 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 516.48 | Yes |  |  | lari carboz | 2011-07-27 | 2011-07-24 | 516.48
1127000537 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-01-21 | 2012-02-29 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4161.32 | Yes |  | Completed | laary | 2012-06-02 | 2012-01-21 | 4161.32
1127000172 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-18 | 2011-07-18 | SAMI | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 6018.78 | Yes |  |  | ernesto e. lai | 2011-10-31 | 2011-06-18 | 6327.82
1127000593 |  | DETCON Saudia Co. (Data_SAD) | 2011-12-04 | 2012-01-18 | JIZA | held order | ICMS-HO-HBU-2012 | cancelled | 2012 objective design issued |  |  | job wo cancelled | Canceled will be cover by FTTH Email from Khalil Al-ali Wednesday, August 17, 2011 11:19 AM | laary |  | 2011-12-04 | 5006.88
1127000118 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-03 | 2011-08-17 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 10723.9 | Yes |  |  | alfies benjamin | 2011-09-27 | 2011-07-03 | 9909.4
1127000034 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-03 | 2011-08-12 | ARDH | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 5896 | Yes |  |  | alfies benjamin | 2011-10-03 | 2011-07-03 | 6541
1127000425 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2012-01-02 | 2012-02-14 | FRSN | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 9222.5 | Yes |  |  | alfies benjamin | 2012-02-08 | 2012-01-02 | 7232.1
1127000530 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2012-01-10 | 2012-02-16 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 10014.4 | Yes |  |  | alfies benjamin | 2012-02-19 | 2012-01-10 | 17296.4
1127000266 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-03 | 2011-08-11 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 13966 | Yes |  |  | lari carboz | 2011-08-10 | 2011-07-03 | 16141
1127000244 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-19 | 2011-06-29 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 30 | Yes |  |  | ali gobain | 2011-07-18 | 2011-06-19 | 30
1127000252 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-19 | 2011-07-19 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1528.8 | Yes |  |  | lari carboz | 2011-09-27 | 2011-06-19 | 1560
1127000263 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-19 | 2011-07-09 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 417 | Yes |  |  | lari carboz | 2011-09-07 | 2011-06-19 | 409
1127000220 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-19 | 2011-06-26 | ARDH | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 68.7 | Yes |  |  | alfies benjamin | 2011-09-06 | 2011-06-19 | 68.7
1127000212 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-03 | 2011-08-11 | DARB | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 5370.6 | Yes |  |  | jomeel g. antonio | 2011-09-16 | 2011-07-03 | 6487
1127000287 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4982.5 | Yes |  |  | laary | 2011-11-28 | 2011-09-19 | 3937
1127000332 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-07-10 | 2011-08-19 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 158 | Yes |  |  | lari carboz | 2011-07-24 | 2011-07-10 | 388
1127000202 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-19 | 2011-07-09 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2610 | Yes |  |  | jomeel g. antonio | 2011-09-03 | 2011-06-19 | 2610
1127000209 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-19 | 2011-07-09 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2343 | Yes |  |  | lari carboz | 2011-10-29 | 2011-06-19 | 4454
1127000214 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-19 | 2011-07-19 | DAMD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3679.9 | Yes |  | is not completed yet Email From Alfies J. Benjamin | alfies benjamin | 2011-08-24 | 2011-06-19 | 4590.6
1127000222 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-19 | 2011-07-19 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 651 | Yes |  |  | lari carboz | 2011-06-27 | 2011-06-19 | 665
1127000229 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-19 | 2011-07-19 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 966 | Yes |  |  | ernesto e. lai | 2011-07-11 | 2011-06-19 | 1323.1
1127000232 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-19 | 2011-07-19 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1455 | Yes |  |  | lari carboz | 2011-06-27 | 2011-06-19 | 1455
1127000255 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-19 | 2011-07-19 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3831 | Yes |  |  | lari carboz | 2011-06-27 | 2011-06-19 | 3831
1127000250 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-06-19 | 2011-07-19 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3728 | Yes |  |  | jomeel g. antonio | 2011-07-30 | 2011-06-19 | 3728
1127000348 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-08-14 | 2011-08-21 | SHUQ | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3939.8 | Yes |  |  | jomeel g. antonio | 2011-08-17 | 2011-08-14 | 3975
1127000019 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 25004.8 | Yes |  |  | ernesto e. lai | 2011-10-23 | 2011-04-13 | 25502.5
1127000018 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-04-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 6874 | Yes |  |  | lari carboz | 2011-04-11 | 2011-03-19 | 6074
1127000023 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | BAYS | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 6692 | Yes |  |  | jomeel g. antonio | 2011-10-10 | 2011-03-19 | 6692
1127000016 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-04-20 | SAMI | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 134 | Yes |  |  | ernesto e. lai | 2011-05-21 | 2011-04-13 | 156
1127000174 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-18 | 2011-05-08 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 173 | Yes |  |  | ernesto e. lai | 2011-08-20 | 2011-04-18 | 193
1127000117 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 195 | Yes |  |  | lari carboz | 2011-06-04 | 2011-04-13 | 129
1127000112 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 342 | Yes |  |  | lari carboz | 2011-08-06 | 2011-04-13 | 342
1127000141 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4343.3 | Yes |  |  | agobain | 2011-11-19 | 2011-04-13 | 3747.5
1127000152 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 411 | Yes |  |  | agobain | 2011-04-20 | 2011-04-13 | 411
1127000147 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 676 | Yes |  |  | agobain | 2011-05-30 | 2011-04-13 | 550
1127000103 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-03-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 411 | Yes |  |  | lari carboz | 2011-04-23 | 2011-03-19 | 411
1127000111 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 665 | Yes |  |  | lari carboz | 2011-09-10 | 2011-04-13 | 411
1127000093 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-04-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1798 | Yes |  |  | lari carboz | 2011-04-20 | 2011-03-20 | 1590
1127000095 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-03-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 255 | Yes |  |  | lari carboz | 2011-06-13 | 2011-03-19 | 255
1127000109 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 538 | Yes |  |  | lari carboz | 2011-09-11 | 2011-04-13 | 411
1127000116 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-13 | 2011-05-27 | SAMI | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 119 | Yes |  |  | ernesto e. lai | 2011-05-08 | 2011-04-13 | 119
1127000065 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 5783.7 | Yes |  |  | alfies benjamin | 2011-10-02 | 2011-03-19 | 7677.1
1127000066 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 836 | Yes |  |  | alfies benjamin | 2011-04-18 | 2011-03-19 | 1168
1127000067 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1230 | Yes |  |  | agobain | 2011-11-19 | 2011-03-19 | 1230
1127000063 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 99 | Yes |  |  | alfies benjamin | 2011-04-11 | 2011-03-19 | 77
1127000076 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-03-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 665 | Yes |  |  | lari carboz | 2011-04-30 | 2011-03-19 | 665
1127000074 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-03-31 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 109 | Yes |  |  | alfies benjamin | 2011-05-08 | 2011-03-20 | 129
1127000077 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-04-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3883.6 | Yes |  |  | lari carboz | 2011-04-30 | 2011-03-20 | 3044
1127000088 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-04-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2730 | Yes |  |  | laary | 2011-07-02 | 2011-03-20 | 3030
1127000086 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-04-20 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4634 | Yes |  |  | lari carboz | 2011-11-19 | 2011-03-20 | 1994
1127000082 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-04-20 | DAMD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 5331.1 | Yes |  |  | ernesto e. lai | 2011-10-10 | 2011-03-20 | 6288.9
1127000085 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-20 | 2011-04-20 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 7171.6 | Yes |  |  | alfies benjamin | 2011-06-04 | 2011-03-20 | 7029.5
1127000051 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | SLHD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 260 | Yes |  |  | ernesto e. lai | 2011-06-13 | 2011-03-19 | 364
1127000035 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1196 | Yes |  |  | alfies benjamin | 2011-04-19 | 2011-03-19 | 1560
1127000038 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3784 | Yes |  |  | alfies benjamin | 2011-05-07 | 2011-03-19 | 4160
1127000057 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4750.2 | Yes |  |  | lari carboz | 2011-03-20 | 2011-03-19 | 7922
1127000053 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | DAMD | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 52 | Yes |  |  | alfies benjamin | 2011-04-20 | 2011-03-19 | 52
1127000061 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 975 | Yes |  |  | alfies benjamin | 2011-10-02 | 2011-03-19 | 1125
1127000058 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 1647 | Yes |  |  | alfies benjamin | 2011-10-02 | 2011-03-19 | 1647
1127000014 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2406 | Yes |  |  | lari carboz | 2011-06-08 | 2011-03-19 | 897
1127000055 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 411 | Yes |  |  | lari carboz | 2011-08-06 | 2011-03-19 | 411
1127000027 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 180 | Yes |  |  | lari carboz | 2011-09-11 | 2011-03-19 | 180
1127000052 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-30 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 630 | Yes |  |  | alfies benjamin | 2011-04-19 | 2011-03-19 | 315
1127000333 | 75745 | Mohemmed Bin Gerboo EST. | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3514 | Yes |  |  | laary | 2011-10-09 | 2011-09-19 | 3548
1127000004 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-16 | 2011-05-30 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 466 | Yes |  |  | ali m. gobain | 2011-09-03 | 2011-04-16 | 510
1127000005 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 99 | Yes |  |  | lari carboz | 2011-06-04 | 2011-04-17 | 99
1127000006 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-17 | 2011-05-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 300 | Yes |  |  | lari carboz | 2011-11-19 | 2011-04-17 | 300
1027000506 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-12-14 | 2012-01-26 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2448 | Yes |  |  | alfies benjamin | 2012-02-19 | 2011-12-14 | 2592
1127000127 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-18 | 2011-07-18 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4131.69 | Yes |  |  | alfies benjamin | 2011-07-09 | 2011-06-18 | 4491.69
1127000161 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-06-18 | 2011-07-08 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3314.98 | Yes |  |  | lari carboz | 2011-06-27 | 2011-06-18 | 3327.75
1127000168 | 90711 | STC CREW | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued |  |  |  |  | laary | 2011-10-03 | 2011-09-19 | 429
1127000156 | 90711 | STC CREW | 2011-06-18 | 2011-06-28 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued |  |  |  |  | alfies benjamin | 2011-09-20 | 2011-06-18 | 900
1027000496 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | cancelled | 2012 objective design issued | 0 |  |  | Canceled will be cover by FTTH Email from Khalil Al-ali Wednesday, August 17, 2011 11:19 AM | lari carboz |  | 2011-09-19 | 4177.9
1027000441 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | cancelled | 2012 objective design issued | 0 |  |  | Canceled will be cover by FTTH Email from Khalil Al-ali Wednesday, August 17, 2011 11:19 AM | lari carboz |  | 2011-09-19 | 3677.66
1127000171 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-18 | 2011-07-18 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 8065.92 | Yes |  |  | lari carboz | 2011-10-12 | 2011-06-18 | 7777.92
1127000154 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-13 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 6886.38 | Yes |  |  | ali gobain | 2011-07-26 | 2011-04-13 | 7612.14
1127000158 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-17 | 2011-04-30 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 2764.8 | Yes |  |  | lari carboz | 2011-07-31 | 2011-04-17 | 1334.4
1127000180 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 292.02 | Yes |  |  | laary | 2011-10-12 | 2011-09-19 | 292.02
1127000184 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 131.61 | Yes |  |  | laary | 2012-01-23 | 2011-09-19 | 131.61
1127000137 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-18 | 2011-07-18 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4093.44 | Yes |  |  | ali gobain | 2012-01-11 | 2011-06-18 | 3993.6
1127000160 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-18 | 2011-06-28 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 394.56 | Yes |  |  | lari carboz | 2011-09-17 | 2011-06-18 | 394.56
1127000164 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 5857.76 | Yes |  |  | laary | 2011-12-06 | 2011-09-19 | 5857.76
1127000040 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 394.56 | Yes |  |  | lari carboz | 2011-10-03 | 2011-09-19 | 394.56
1127000043 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | cancelled | 2012 objective design issued | 0 |  |  | Canceled will be cover by FTTH Email from Khalil Al-ali Wednesday, August 17, 2011 11:19 AM | laary |  | 2011-09-19 | 3268.8
1127000049 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 404.16 | Yes |  |  | laary | 2011-10-03 | 2011-09-19 | 404.16
1127000208 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-20 | 2011-09-23 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 428.16 | Yes |  |  | lari carboz | 2011-09-17 | 2011-08-20 | 428.16
1127000273 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3509.75 | Yes |  |  | ali gobain | 2013-01-01 | 2011-09-19 | 3303.83
1127000275 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-13 | 2011-08-26 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4253.15 | Yes |  |  | ali gobain | 2011-11-22 | 2011-07-13 | 4253.15
1127000235 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-19 | 2011-10-31 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 28.8 | Yes |  |  | laary | 2011-10-01 | 2011-09-19 | 28.8
1027000159 |  |  |  |  | JIZA | held order | ICMS-HO-HBU-2012 | cancelled | 2012 objective design issued |  |  | job wo cancelled | Cancelled By Al-Suwaidi company |  |  |  | 2779.62
1127000021 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-03-02 | 2011-04-02 | SAMI | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 4285.9 | Yes |  |  | ernesto e. lai | 2011-04-19 | 2011-03-01 | 4041.5
1127000009 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-04-27 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3533 | Yes |  |  | ali gobain | 2011-05-10 | 2011-04-13 | 3533
1127000036 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-04-27 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 5151.6 | Yes |  |  | alfies benjamin | 2011-05-10 | 2011-04-13 | 4860
1127000081 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-13 | JIZA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 18705.26 | Yes |  |  | lari carboz | 2011-06-07 | 2011-04-13 | 12903.5
1127000153 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-04-20 | SBYA | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 597.7 | Yes |  |  | ali gobain | 2011-04-16 | 2011-04-13 | 443.8
1127000146 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-13 | 2011-05-03 | ABAR | held order | ICMS-HO-HBU-2012 | completed | 2012 objective design issued | 3314.8 | Yes |  |  | alfies benjamin | 2011-05-10 | 2011-04-13 | 3314.8
1127000003 | 75745 | Mohemmed Bin Gerboo EST. | 2011-01-08 | 2011-02-22 | JIZA | junction | Junction | completed | 2010 objective design issued | 1020 | Yes |  | ALJARBOO | ali m. gobain | 2011-01-25 | 2011-01-08 | 1020
1127000007 | 75745 | Mohemmed Bin Gerboo EST. | 2011-01-08 | 2011-02-22 | DARB | junction | Junction | completed | 2010 objective design issued | 1020 | Yes |  | ALJARBOO | jomeel g. antonio | 2011-01-31 | 2011-01-08 | 1180
1027000386 | 75745 | Mohemmed Bin Gerboo EST. | 2010-12-13 | 2011-02-15 | JIZA | junction | Junction | completed | 2010 objective design issued | 4970 | Yes |  | Hold Sales confirmation | lari carboz | 2011-03-07 | 2010-12-17 | 7155
1127000259 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-02 | 2011-07-02 | JIZA | junction | Junction | completed | 2011 objective design issued | 20326.6 | Yes |  |  | lari carboz | 2011-07-02 | 2011-06-29 | 19111.6
1027000443 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-11-27 | 2010-12-15 | KWBH | junction | Junction | completed | 2010 objective design issued | 8000.1 | Yes |  |  | ernesto e. lai | 2010-12-27 | 2010-11-27 | 8048.8
1227000079 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-31 | 2012-04-30 | ABAR | junction | Junction Ddependencies | completed | 2012 objective design issued | 4444.8 | CM In Progress |  |  | abenjamin | 2012-04-21 | 2012-03-31 | 4444.8
1127000610 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-12-19 | 2012-01-31 | JIZA | junction | Junction Ddependencies | completed | 2012 objective design issued | 2960 | Yes |  |  | laary | 2011-12-20 | 2011-12-19 | 2380
1227000118 | 78382 | Majd AlJanoub for general Contracting Ltd. | 2012-05-26 | 2012-06-30 | SLHD | junction | Junction Ddependencies | completed | 2012 objective design issued | 678799.228 | Yes |  |  | ernesto e. lai | 2012-10-14 | 2012-05-26 | 626743.36
1227000129 | 78382 | Majd AlJanoub for general Contracting Ltd. | 2012-05-26 | 2012-06-30 | TWAL | junction | Junction Ddependencies | completed | 2012 objective design issued | 661351.426 | Yes |  |  | ernesto e. lai | 2012-09-19 | 2012-05-26 | 646836.16
1227000121 | 78382 | Majd AlJanoub for general Contracting Ltd. | 2012-05-26 | 2012-06-30 | SAMI | junction | Junction Ddependencies | completed | 2012 objective design issued | 880881.956 | Yes |  |  | ernesto e. lai | 2012-10-14 | 2012-05-26 | 442448.76
1227000119 | 78382 | Majd AlJanoub for general Contracting Ltd. | 2012-05-26 | 2012-06-30 | SLHD | junction | Junction Ddependencies | completed | 2012 objective design issued | 330042.876 | Yes |  |  | ernesto e. lai | 2012-09-19 | 2012-05-26 | 391276.8
1327000031 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-03-18 | 2013-04-30 | ABAR | junction | Junction Ddependencies | completed | 2013 objective design issued | 0 |  |  | Done | alfies benjamin | 2013-12-24 | 2013-03-18 | 1235859
1227000021 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-26 | 2012-04-10 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 2002.72 | CM In Progress |  | FTTM issued to detasad as per hamoud bakri instruction" | lscarboz | 2012-05-28 | 2012-02-26 | 12266.72
1127000651 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-26 | 2012-04-10 | SBYA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 19739.552 | CM In Progress |  | FTTM issued to detasad as per hamoud bakri instruction" | agobain | 2012-06-30 | 2012-02-26 | 55757.12
1427000041 |  | Mohemmed Bin Gerboo EST. | 2014-01-28 | 2014-03-11 | SLHD | fttm | Junction GSM | not started | 2012 objective design issued - lead |  |  | contractor over budget |  | ernesto e. lai |  | 2014-01-26 | 27887.77
1227000139 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | SAMI | fttm | Junction GSM | completed | 2012 objective design issued - lead | 26611.2 | Director In Progress |  | LTE | elai | 2012-08-15 | 2012-05-14 | 45084.32
1227000018 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | ABAR | fttm | Junction GSM | completed | 2012 objective design issued - lead | 869646.24 | Director In Progress |  | LTE | abenjamin | 2013-08-22 | 2012-05-14 | 1061673.45
1227000024 | 79738 | ISSA AL ISSA FOR contracting EST. | 2012-11-03 | 2012-12-13 | DAMD | fttm | Junction GSM | completed | 2012 objective design issued - lead | 142723.248 | CM In Progress |  | Jeel AlFursan Est. FOR TRADING &CO by Adel baadullah Completed | abenjamin | 2013-04-15 | 2012-11-03 | 217306.52
1227000116 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 24412.8 | Director In Progress |  | LTE | lscarboz | 2012-08-02 | 2012-05-14 | 52054.4
1127000514 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-26 | 2011-12-10 | ABAR | fttm | Junction GSM | completed | 2012 objective design issued - lead | 5693.61 | DM In Progress |  | FTTM | abenjamin | 2012-02-19 | 2011-10-09 | 4856
1127000484 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-26 | 2011-12-10 | ABAR | fttm | Junction GSM | completed | 2012 objective design issued - lead | 44960.4 | DM In Progress |  | FTTM | abenjamin | 2012-09-15 | 2011-10-09 | 73787.2
1127000495 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-26 | 2011-12-10 | ABAR | fttm | Junction GSM | completed | 2012 objective design issued - lead | 212854.81 | DM In Progress |  | FTTM | abenjamin | 2012-09-15 | 2011-10-09 | 71304
1127000515 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-26 | 2011-12-10 | ABAR | fttm | Junction GSM | completed | 2012 objective design issued - lead | 18393.63 | DM In Progress |  | FTTM | abenjamin | 2012-02-12 | 2011-10-09 | 10676.16
1127000480 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-18 | 2011-10-20 | SBYA | junction | Junction GSM | completed | 2011 objective design issued | 48936.64 | Yes |  |  | ali gobain | 2012-05-27 | 2011-09-18 | 82865.7
1227000117 |  | Mohemmed Bin Gerboo EST. | 2013-01-16 | 2013-02-28 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead |  |  | district contractor over budget | No PO, completed-Job implemented by Mohemmed Bin Garboo | lari carboz | 2013-07-18 | 2012-11-03 | 3251.85
1227000109 |  | Mohemmed Bin Gerboo EST. | 2013-01-16 | 2013-02-28 | SAMI | fttm | Junction GSM | completed | 2012 objective design issued - lead |  |  | job wo cancelled | Only site - ZJZ897 not done, it is cancelled. | ernesto e. lai | 2014-01-28 | 2012-08-01 | 0
1127000647 |  |  | 2012-05-14 | 2012-06-26 | SAMI | fttm | Junction GSM | cancelled | 2012 objective design issued - lead |  |  | job wo cancelled | Cancelled | ernesto e. lai |  | 2012-02-26 | 521329.586
1227000147 | 81127 | Majd AlJanoub for general Contracting Ltd. | 2013-11-21 | 2014-01-02 | SLHD | fttm | Junction GSM | in progress | 2012 objective design issued - lead | 0 |  |  |  | ernesto e. lai |  | 2013-10-08 | 297637.33
1227000142 | 80013 | Mohemmed Bin Gerboo EST. | 2012-05-15 | 2012-06-28 | SLHD | fttm | Junction GSM | completed | 2012 objective design issued - lead | 368493.544 |  |  | LTE | ernesto e. lai | 2013-01-02 | 2012-05-15 | 314944
1127000485 | 80012 | DETCON Saudia Co. (Data_SAD) | 2011-09-19 | 2011-10-31 | SBYA | junction | Junction GSM | completed | 2011 objective design issued | 260114.792 | Con/Insp In Progress |  | FTTM | ali gobain | 2012-06-16 | 2011-09-19 | 300314.8
1127000503 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-26 | 2011-12-10 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 72545.78 | Yes |  | FTTM | lari carboz | 2012-05-27 | 2011-10-09 | 75307
1127000528 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-26 | 2011-12-10 | ABAR | fttm | Junction GSM | completed | 2012 objective design issued - lead | 499 |  |  |  | alfies benjamin | 2012-06-03 | 2011-10-10 | 696
1127000520 | 76677 | Mohemmed Bin Gerboo EST. | 2011-10-26 | 2011-12-10 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 179225.25 | Yes |  | FTTM | laary | 2012-06-16 | 2011-10-09 | 71564.7
1127000415 | 76677 | Mohemmed Bin Gerboo EST. | 2011-09-10 | 2011-10-25 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 1506 |  |  | 2012 Objective Design Issued – LEAD | laary | 2012-02-05 | 2011-09-10 | 1092
1127000481 | 76677 | Mohemmed Bin Gerboo EST. | 2011-09-18 | 2011-10-20 | SBYA | junction | Junction GSM | completed | 2011 objective design issued | 0 |  | pu price adjustment with bat/pcc |  | ali gobain | 2012-09-15 | 2011-09-18 | 8164.8
1127000535 | 76677 | Mohemmed Bin Gerboo EST. | 2011-11-01 | 2011-12-13 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 14757.86 | Yes |  | FTTM | lari carboz | 2012-09-15 | 2011-10-16 | 26004.2
1227000120 | 76677 | Mohemmed Bin Gerboo EST. | 2012-05-13 | 2012-06-25 | SBYA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 97489.9 |  |  | LTE | ali gobain | 2013-02-02 | 2012-05-13 | 126539.2
1327000012 | 76677 | Mohemmed Bin Gerboo EST. | 2013-02-19 | 2013-03-31 | BAYS | fttm | Junction GSM | completed | 2012 objective design issued - lead | 1165.5 |  |  |  | jomeel g. antonio | 2013-03-18 | 2013-02-19 | 48
1227000025 | 81128 | DETCON Saudia Co. (Data_SAD) | 2012-03-05 | 2012-04-18 | ABAR | fttm | Junction GSM | completed | 2012 objective design issued - lead | 0 |  |  | No PO, completed FTTM site-ZJZ718 | alfies benjamin | 2012-06-30 | 2012-01-30 | 81853.6153
1227000114 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 55487.65 |  |  | LTE | ali gobain | 2013-03-02 | 2012-05-14 | 21951.37
1227000099 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 21438.48 | Yes |  | LTE | ali gobain | 2012-06-16 | 2012-05-14 | 11903.85
1227000115 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | SBYA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 0 |  | pu price adjustment with bat/pcc | LTE | ali gobain | 2013-03-02 | 2012-05-14 | 623666.76
1227000017 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | SBYA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 0 |  |  | LTE | ali gobain | 2013-03-02 | 2012-05-14 | 424075
1227000011 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 892676.71 | Yes |  | LTE | lari carboz | 2013-02-12 | 2012-05-14 | 1063107.4432
1127000652 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | JIZA | fttm | Junction GSM | completed | 2012 objective design issued - lead | 214782.4 | Yes |  | LTE | laary | 2012-09-15 | 2012-02-26 | 323069.0584
1227000140 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-15 | 2012-06-28 | SAMI | fttm | Junction GSM | completed | 2012 objective design issued - lead | 343928.3948 |  |  | LTE | ernesto e. lai | 2012-10-15 | 2012-05-15 | 390017.7
1227000138 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-15 | 2012-06-28 | SLHD | fttm | Junction GSM | completed | 2012 objective design issued - lead | 51142.09 |  |  | LTE | ernesto e. lai | 2012-11-17 | 2012-05-15 | 47654.85
1227000102 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-14 | 2012-06-26 | ABAR | fttm | Junction GSM | completed | 2012 objective design issued - lead | 0 |  |  | Done | alfies benjamin | 2014-01-14 | 2012-05-14 | 1287061.5
1227000141 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-15 | 2012-06-28 | TWAL | fttm | Junction GSM | completed | 2012 objective design issued - lead | 473412.55 |  |  | LTE | ernesto e. lai | 2013-02-02 | 2012-05-15 | 362369.96
1227000146 | 79722 | Mohemmed Bin Gerboo EST. | 2012-05-27 | 2012-06-30 | SLHD | fttm | Junction GSM | completed | 2012 objective design issued - lead | 72254.19 |  |  |  | ernesto e. lai | 2012-09-15 | 2012-05-27 | 72312.4
1227000160 | 79722 | Mohemmed Bin Gerboo EST. | 2012-09-16 | 2012-10-24 | DAMD | fttm | Junction GSM | completed | 2012 objective design issued - lead | 480 |  |  | LTE | alfies benjamin | 2012-10-15 | 2012-09-16 | 963.32
1227000161 | 79722 | Mohemmed Bin Gerboo EST. | 2012-09-10 | 2012-10-25 | SAMI | fttm | Junction GSM | completed | 2012 objective design issued - lead | 0 |  |  | LTE | ernesto e. lai | 2012-12-03 | 2012-09-10 | 2024.58
1027000011 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-01-18 | 2010-02-18 | ARDH | junction | Junction GSM | completed | 2010 objective not in the design master sheet | 71649.44 | Yes |  | Email From: Abdulmoti A. Dahlawi | alfies benjamin | 2010-07-19 | 2010-01-18 | 54889.343
0827000497 | 73847 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2008-10-25 | 2008-12-25 | KWBH | key account | Key Account EBU 2009 | completed | 2009 objective design issued | 6558.364 | Yes |  |  | ernesto e. lai | 2009-10-26 | 2008-10-25 | 8243.4
1027000221 | 75745 | Mohemmed Bin Gerboo EST. | 2010-05-01 | 2010-06-15 | DARB | msan | MSAN | completed | 2011 objective not in the design master sheet | 0 |  |  | as per appved by Ali on 30-10-2010 with MOT project | jomeel g. antonio | 2010-11-02 | 2010-11-01 | 0
1027000339 | 75745 | Mohemmed Bin Gerboo EST. | 2010-05-01 | 2010-06-15 | SBYA | msan | MSAN | completed | 2011 objective not in the design master sheet | -314489.02 |  |  | as per appved by Ali on 30-10-2010 with MOT project | ali m. gobain | 2010-11-02 | 2010-11-01 | 0
1027000153 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | KWBH | msan | MSAN | completed | 2010 objective not in the design master sheet | 17290 | Yes |  | Email From: Abdulmoti A. Dahlawi | ernesto e. lai | 2011-03-20 | 2010-06-07 | 16015
1327000319 | 80013 | Mohemmed Bin Gerboo EST. | 2013-06-11 | 2013-07-20 | SBYA | key account | MSAN | completed | 2013 objective design issued | 106367.91 |  |  | DONE GENERAL ORGANIZATION FOR TECH. & VOCATIONAL TRAINI | ali gobain | 2013-10-21 | 2013-06-11 | 121276.16
1327000480 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-25 | 2013-11-07 | SBYA | key account | MSAN | completed | 2013 objective design issued | 0 |  |  | Done | ali gobain | 2013-12-29 | 2013-09-22 | 101894.4
1327000037 | 80013 | Mohemmed Bin Gerboo EST. | 2013-04-15 | 2013-05-30 | JIZA | key account | MSAN | completed | 2013 objective design issued | 15926.904 |  |  | DONE abdu khaleg saeed | laary | 2013-10-21 | 2013-04-15 | 19634.024
1327000222 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-08-01 | 2013-08-31 | JIZA | key account | MSAN | completed | 2013 objective design issued | 76701.984 | PCC In Progress |  | Done - Al Atheer Gallary | lari carboz | 2013-09-30 | 2013-06-08 | 86746.6
1327000680 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-12-26 | 2014-02-09 | SLHD | msan | MSAN BAD CABLE-2013 | in progress | 2013 objective design issued - lead | 0 |  |  | JUHAJZAA | ernesto e. lai |  | 2013-11-26 | 673796.55
1327000682 | 79738 | ISSA AL ISSA FOR contracting EST. | 2013-12-26 | 2014-02-09 | SLHD | msan | MSAN BAD CABLE-2013 | in progress | 2013 objective design issued - lead | 0 |  |  | JUHAJZAA - | ernesto e. lai |  | 2013-11-26 | 5201.47
1327000683 | 79738 | ISSA AL ISSA FOR contracting EST. | 2014-01-05 | 2014-02-19 | SLHD | msan | MSAN BAD CABLE-2013 | in progress | 2013 objective design issued - lead | 0 |  |  | JUHAJZAA | ernesto e. lai |  | 2013-11-26 | 24512.41
1327000484 | 81002 | Mohemmed Bin Gerboo EST. | 2013-10-02 | 2013-11-14 | SLHD | other | MSAN HBU - 2012 | completed | 2012 objective not in the design master sheet | 13785.6 | CM In Progress |  |  | elai | 2013-10-28 | 2013-10-02 | 13785.6
0827000484 | 73803 | Mohemmed Bin Gerboo EST. | 2008-09-16 | 2008-10-16 | SHUQ | msan | MSAN HBU 2009 | completed | 2009 objective design issued | 127933 | Yes |  | Email From: Abdulmoti A. Dahlawi Sent to Aljarboo | jomeel g. antonio | 2010-02-08 | 2008-09-16 | 131394.2
1227000131 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-07-11 | 2012-08-24 | SBYA | msan | MSAN-HBU | completed | 2013 objective design issued | 13823.84 | PM In Progress |  | AL ATHALAH | agobain | 2013-07-21 | 2012-07-11 | 13823.84
1227000112 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-22 | 2012-06-06 | ABAR | msan | MSAN-HBU | completed | 2012 objective design issued | 15150.6 | CM In Progress |  | ASAMILAH | abenjamin | 2013-08-25 | 2012-04-22 | 14715.28
1227000111 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-22 | 2012-06-06 | ABAR | msan | MSAN-HBU | completed | 2012 objective design issued | 18362.04 | CM In Progress |  | ASAMILAH | abenjamin | 2013-08-25 | 2012-04-22 | 24893.32
1227000103 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-22 | 2012-06-06 | DAMD | msan | MSAN-HBU | completed | 2012 objective design issued | 17793.86 | CM In Progress |  | AL QAYIM | abenjamin | 2013-06-24 | 2012-04-22 | 14962.89
1227000105 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-22 | 2012-06-06 | DAMD | msan | MSAN-HBU | completed | 2012 objective design issued | 23738.68 | CM In Progress |  | BAYADH | abenjamin | 2013-06-24 | 2012-04-22 | 17046.69
1227000106 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-22 | 2012-06-06 | DAMD | msan | MSAN-HBU | completed | 2012 objective design issued | 14070.33 | CM In Progress |  | BAYADH | abenjamin | 2013-06-24 | 2012-04-22 | 12212.08
1227000110 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-22 | 2012-06-06 | DAMD | msan | MSAN-HBU | completed | 2012 objective design issued | 24536.18 | CM In Progress |  | FALAS | abenjamin | 2013-08-05 | 2012-04-22 | 20268.48
1227000107 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-22 | 2012-06-06 | DAMD | msan | MSAN-HBU | completed | 2012 objective design issued | 19388.48 | CM In Progress |  | FALAS | abenjamin | 2013-08-05 | 2012-04-22 | 14173.4
1227000096 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-22 | 2012-06-06 | DAMD | msan | MSAN-HBU | completed | 2012 objective design issued | 15521.43 | CM In Progress |  | AL QAYIM | abenjamin | 2013-06-24 | 2012-04-22 | 14662.05
1127000601 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-11-30 | 2012-01-13 | DAMD | msan | MSAN-HBU | completed | 2012 objective design issued | 22074.878 | CM In Progress |  | AL KHADRAH AL JANUBIYAH | abenjamin | 2013-01-07 | 2011-11-30 | 30568.74
1127000600 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-11-30 | 2012-01-13 | DAMD | msan | MSAN-HBU | completed | 2012 objective design issued | 21458.56 | CM In Progress |  | AL KHADRAH AL JANUBIYAH | abenjamin | 2013-01-07 | 2011-11-30 | 26515.84
1127000100 | 76677 | Mohemmed Bin Gerboo EST. | 2011-06-04 | 2011-07-15 | JIZA | msan | MSAN-HBU | completed | 2011 objective design issued | 322950.03 | DM In Progress |  |  | lscarboz | 2011-08-25 | 2011-06-04 | 250836.8
1127000206 | 76677 | Mohemmed Bin Gerboo EST. | 2011-06-04 | 2011-07-15 | BAYS | msan | MSAN-HBU | completed | 2011 objective design issued | 16145.08 | DM In Progress |  |  | jgantonio | 2011-08-17 | 2011-06-04 | 716.8
1127000205 | 76677 | Mohemmed Bin Gerboo EST. | 2011-06-04 | 2011-07-15 | BAYS | msan | MSAN-HBU | completed | 2011 objective design issued | 34128.26 | DM In Progress |  |  | jgantonio | 2011-08-04 | 2011-05-08 | 2475.44
1127000301 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-15 | 2011-07-15 | SLHD | msan | MSAN-HBU | completed | 2011 objective design issued | 26075.52 | Yes |  |  | ernesto e. lai | 2012-01-04 | 2011-06-15 | 35553.23
1127000302 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-15 | 2011-07-15 | SLHD | msan | MSAN-HBU | completed | 2011 objective design issued | 16310.61 | Yes |  |  | ernesto e. lai | 2012-02-19 | 2011-06-15 | 15259.38
1227000092 |  | Mohemmed Bin Gerboo EST. | 2012-04-22 | 2012-06-06 | JIZA | msan | MSAN-HBU | completed | 2012 objective design issued |  |  | district contractor over budget | No PO, completed MSAN site - AL FUQAHA | laary | 2013-06-24 | 2012-04-22 | 17066.56
1127000110 |  | Mohemmed Bin Gerboo EST. | 2011-03-12 | 2011-04-12 | JIZA | msan | MSAN-HBU | completed | 2011 objective design issued |  |  | under hq finalization | No PO - completed project | lari carboz | 2012-01-25 | 2011-03-09 | 5278.74
1127000196 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-07-27 | 2011-09-09 | JIZA | msan | MSAN-HBU | completed | 2011 objective design issued | 43464.52 | Yes |  |  | lari carboz | 2012-02-05 | 2011-07-27 | 35995.08
1227000098 |  | Mohemmed Bin Gerboo EST. | 2012-04-22 | 2012-06-06 | BAYS | msan | MSAN-HBU | completed | 2012 objective design issued |  |  |  | No PO, completed MSAN, site - GDSHJZAC, ready for cut-over | jomeel g. antonio | 2013-10-27 | 2012-04-22 | 20471.5
1227000104 |  | Mohemmed Bin Gerboo EST. | 2012-09-17 | 2012-10-24 | BAYS | msan | MSAN-HBU | completed | 2012 objective design issued |  |  |  | No PO, completed MSAN, site - GDSHJZAC | jomeel g. antonio | 2013-10-27 | 2012-09-17 | 14236.27
1227000101 |  | Mohemmed Bin Gerboo EST. | 2012-04-22 | 2012-06-06 | BAYS | msan | MSAN-HBU | completed | 2012 objective design issued |  |  |  | No PO, completed MSAN, site - GDSHJZAC | jomeel g. antonio | 2013-10-27 | 2012-04-22 | 2234.04
1227000095 |  | Mohemmed Bin Gerboo EST. | 2012-04-22 | 2012-06-06 | SAMI | msan | MSAN-HBU | completed | 2012 objective design issued |  |  |  | No PO, completed MSAN, site - HDRRJZAC | ernesto e. lai | 2013-10-27 | 2012-04-22 | 27960.8
1227000091 |  | Mohemmed Bin Gerboo EST. | 2012-04-22 | 2012-06-06 | JIZA | msan | MSAN-HBU | completed | 2012 objective design issued |  |  | district contractor over budget | No PO, completed MSAN, site - AL FUQAHA | laary | 2013-06-24 | 2012-04-22 | 19946.38
1227000108 | 81002 | Mohemmed Bin Gerboo EST. | 2012-04-22 | 2012-06-06 | BAYS | msan | MSAN-HBU | completed | 2012 objective design issued | 0 |  |  | MASLIYAH | jomeel g. antonio | 2013-12-16 | 2012-04-22 | 69108.18
1227000113 | 81002 | Mohemmed Bin Gerboo EST. | 2012-04-22 | 2012-06-06 | BAYS | msan | MSAN-HBU | completed | 2012 objective design issued | 0 |  |  | MASLIYAH | jomeel g. antonio | 2013-12-16 | 2012-04-22 | 26701.02
1127000194 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-05-03 | 2011-06-17 | JIZA | msan | MSAN-HBU | completed | 2011 objective design issued | 24054 | Yes |  |  | lari carboz | 2012-01-02 | 2011-05-03 | 21347.5
1127000187 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-05-02 | 2011-06-15 | SAMI | msan | MSAN-HBU | completed | 2011 objective design issued | 13587.2 | Yes |  |  | ernesto e. lai | 2012-01-11 | 2011-05-02 | 13119
1127000199 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-05-03 | 2011-06-17 | ABAR | msan | MSAN-HBU | completed | 2011 objective design issued | 18962.8 | Yes |  |  | alfies benjamin | 2012-01-11 | 2011-05-03 | 17564
1127000198 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-05-03 | 2011-06-17 | ABAR | msan | MSAN-HBU | completed | 2011 objective design issued | 30286.6 | Yes |  |  | alfies benjamin | 2012-01-04 | 2011-05-03 | 30042.4
1127000190 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-05-02 | 2011-06-15 | SAMI | msan | MSAN-HBU | completed | 2011 objective design issued | 11418 | Yes |  |  | ernesto e. lai | 2012-01-11 | 2011-05-02 | 10481
1127000191 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-05-02 | 2011-06-16 | DAMD | msan | MSAN-HBU | completed | 2011 objective design issued | 34676.6 | Yes |  |  | alfies benjamin | 2012-01-04 | 2011-05-02 | 33264
1127000114 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-03-09 | 2011-04-09 | DAMD | msan | MSAN-HBU | completed | 2011 objective design issued | 37418.1 | Yes |  |  | alfies benjamin | 2012-01-04 | 2011-03-09 | 38145.202
1127000129 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-13 | 2011-05-27 | JIZA | msan | MSAN-HBU | completed | 2011 objective design issued | 130668.2 | Yes |  |  | lari carboz | 2012-01-04 | 2011-04-13 | 125614.8
1127000186 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-27 | 2011-06-10 | SAMI | msan | MSAN-HBU | completed | 2011 objective design issued | 16834 | Yes |  |  | ernesto e. lai | 2012-01-04 | 2011-04-27 | 16924
1127000193 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-27 | 2011-06-10 | DAMD | msan | MSAN-HBU | completed | 2011 objective design issued | 16612.4 | Yes |  |  | alfies benjamin | 2012-01-11 | 2011-04-27 | 15185.5
1127000189 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-27 | 2011-06-10 | SAMI | msan | MSAN-HBU | completed | 2011 objective design issued | 17085.8 | Yes |  |  | ernesto e. lai | 2012-01-04 | 2011-04-27 | 16689
1127000165 | 75745 | Mohemmed Bin Gerboo EST. | 2011-04-04 | 2011-05-19 | ARDH | msan | MSAN-HBU | completed | 2011 objective design issued | 28567 | Yes |  |  | alfies benjamin | 2012-01-04 | 2011-04-04 | 27082.8
1027000076 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 33568.938 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2011-02-26 | 2010-06-07 | 27987.938
1027000214 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | BAYS | msan | MSAN-HBU | completed | 2010 objective design issued | 50272.2 | Yes |  | MSAN 004 | jomeel g. antonio | 2011-01-25 | 2010-06-07 | 50583.6
1027000215 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | BAYS | msan | MSAN-HBU | completed | 2010 objective design issued | 36065.6 | Yes |  | 031,032,033,034,035 | jomeel g. antonio | 2011-01-25 | 2010-06-07 | 35915.6
1027000219 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | BAYS | msan | MSAN-HBU | completed | 2010 objective design issued | 162341 | Yes |  | MSAN 005 | jomeel g. antonio | 2011-01-10 | 2010-06-07 | 150297
1027000220 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | BAYS | msan | MSAN-HBU | completed | 2010 objective design issued | 7102.2 | Yes |  | BAYS 037 | jomeel g. antonio | 2011-01-10 | 2010-06-07 | 6772
1327000713 | 80011 | Al Gihaz for Contracting & Trading Company Ltd | 2013-12-17 | 2013-12-31 | JIZA | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  |  | laary | 2014-02-03 | 2013-12-15 | 66400
1327000253 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-22 | 2013-11-30 | ABAR | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  | Done | alfies benjamin | 2013-12-03 | 2013-10-22 | 340492.4
1327000269 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-22 | 2013-11-30 | ABAR | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  | Done | alfies benjamin | 2013-12-03 | 2013-10-22 | 31444.06
1327000283 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-23 | 2013-10-31 | BAYS | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  | Done | jomeel g. antonio | 2014-02-04 | 2013-09-05 | 15279.65
1327000308 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-05 | 2013-10-17 | BAYS | msan | MSAN-HBU | in progress | 2013 objective design issued | 0 |  |  | HAQU | jomeel g. antonio |  | 2013-09-05 | 27984.9
1327000511 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-22 | 2013-10-31 | SLHD | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2013-10-23 | 2013-10-22 | 23456.4
1327000517 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-22 | 2013-10-31 | SLHD | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2013-10-23 | 2013-10-22 | 9111.86
1327000504 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-08 | 2013-11-21 | SBYA | msan | MSAN-HBU | completed | 2013 objective design issued | 15772.812 |  |  |  | jomeel g. antonio | 2013-10-23 | 2013-10-07 | 15559.56
1327000506 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-08 | 2013-11-21 | SBYA | msan | MSAN-HBU | completed | 2013 objective design issued | 20267.2 |  |  |  | jomeel g. antonio | 2013-10-23 | 2013-10-07 | 26846.08
1327000507 | 80013 | Mohemmed Bin Gerboo EST. | 2013-10-08 | 2013-11-21 | SBYA | msan | MSAN-HBU | completed | 2013 objective design issued | 39743.66 |  |  |  | jomeel g. antonio | 2013-10-23 | 2013-10-07 | 3595
1227000127 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-23 | 2013-09-05 | BAYS | msan | MSAN-HBU | in progress | 2013 objective design issued | 0 |  |  |  | jomeel g. antonio |  | 2013-06-09 | 12745.13
1227000123 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-23 | 2013-09-04 | BAYS | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  | Done | alfies benjamin | 2014-01-27 | 2013-06-09 | 21815
1227000122 | 80206 | ISSA AL ISSA FOR contracting EST. | 2013-06-09 | 2013-06-30 | ABAR | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  | ARIDHAH | alfies benjamin | 2013-07-21 | 2013-06-09 | 17284.144
1227000125 | 80206 | ISSA AL ISSA FOR contracting EST. | 2013-06-09 | 2013-06-30 | ABAR | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  | ARIDHAH | alfies benjamin | 2013-07-21 | 2013-06-09 | 10748.1
1227000260 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-07-23 | 2013-09-05 | DMAD | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  | Done | alfies benjamin | 2013-12-08 | 2013-07-23 | 456327.8
1327000392 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-11-17 | 2013-12-31 | SBYA | msan | MSAN-HBU | completed | 2013 objective design issued | 0 |  |  | Done | agobain | 2014-01-27 | 2013-11-06 | 72395.8
1327000395 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-11-17 | 2013-12-31 | SBYA | msan | MSAN-HBU | in progress | 2013 objective design issued | 0 |  |  |  | agobain |  | 2013-11-06 | 26331.6
1027000142 | OSP12006 | Jeel AlFursan Est. FOR TRADING &CO | 2010-04-11 | 2010-07-11 | SBYA | msan | MSAN-HBU | completed | 2010 objective design issued | 0 |  |  |  | ali m. gobain | 2011-01-25 | 2010-04-11 | 53115
1027000054 | 73822 | Middle Sea for Telecommunication Establishment | 2010-02-28 | 2010-04-14 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 65400.55 | Yes |  | MSAN 032 (JIZAN) | lari carboz | 2011-03-01 | 2010-02-23 | 55551.985
1027000071 | 73822 | Middle Sea for Telecommunication Establishment | 2010-02-28 | 2010-04-14 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 42679.1 | Yes |  | MSAN 032 (JIZAN) | lari carboz | 2011-03-01 | 2010-02-23 | 38231.2
1027000081 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-13 | 2010-04-27 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 39319.64 | Yes |  | MSAN 026(JIZA) | lari carboz | 2011-02-16 | 2010-03-09 | 42695.68
1027000099 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-13 | 2010-04-27 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 22806.4 | Yes |  | MSAN 026(JIZA) | lari carboz | 2011-02-16 | 2010-03-09 | 20369.7
1027000125 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-04-06 | 2010-06-06 | SBYA | msan | MSAN-HBU | completed | 2010 objective design issued | 36863.1 | Yes |  | Email From: Abdulmoti A. Dahlawi | ali m. gobain | 2011-01-25 | 2010-04-06 | 30620.562
1027000141 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-04-06 | 2010-06-06 | SBYA | msan | MSAN-HBU | completed | 2010 objective design issued | 46220.2 | Yes |  |  | ali m. gobain | 2011-01-25 | 2010-04-06 | 45615.815
1027000134 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-04-06 | 2010-06-06 | SBYA | msan | MSAN-HBU | completed | 2010 objective design issued | 28877.25 | Yes |  | Email From: Abdulmoti A. Dahlawi | ali m. gobain | 2011-01-25 | 2010-04-06 | 26301.156
1027000041 | 73803 | Mohemmed Bin Gerboo EST. | 2010-02-27 | 2010-03-27 | ARDH | msan | MSAN-HBU | completed | 2010 objective design issued | 28859.1215 | Yes |  | MSAN 000 (ARDH) | alfies benjamin | 2011-03-09 | 2010-02-27 | 29126.293
1027000042 | 73803 | Mohemmed Bin Gerboo EST. | 2010-02-27 | 2010-03-27 | ARDH | msan | MSAN-HBU | completed | 2010 objective design issued | 15258.4 | Yes |  | MSAN 032 (ARDH) | alfies benjamin | 2011-03-09 | 2010-02-27 | 14232.32
1027000048 | 73803 | Mohemmed Bin Gerboo EST. | 2010-02-28 | 2010-04-14 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 9555.18 | Yes |  | MSAN 022 (ST BETROMEN) | lari carboz | 2011-01-25 | 2010-02-23 | 8898.84
1027000043 | 73803 | Mohemmed Bin Gerboo EST. | 2010-02-28 | 2010-04-14 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 66238.46 | Yes |  | MSAN 022 (ST BETROMEN) | lari carboz | 2011-01-25 | 2010-02-23 | 61710.7
1027000072 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-02 | 2010-05-02 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 60053.52 | Yes |  | MSAN01 (AL MERJAN) | lari carboz | 2011-01-25 | 2010-03-02 | 64673.8
1027000085 | 73803 | Mohemmed Bin Gerboo EST. | 2010-05-12 | 2010-06-30 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 58903.7 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2011-03-01 | 2010-03-26 | 70809.69
1027000080 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-02 | 2010-03-02 | JIZA | msan | MSAN-HBU | completed | 2010 objective design issued | 10844.55 | Yes |  | MSAN01 (AL MERJAN) | lari carboz | 2011-01-25 | 2010-03-02 | 8666.9
1027000055 | 73822 | Middle Sea for Telecommunication Establishment | 2010-02-28 | 2010-04-14 | ABAR | msan | MSAN-HBU | completed | 2010 objective design issued | 18347.35 | Yes |  | MSAN 011 (AL WASELI) | alfies benjamin | 2011-01-25 | 2010-02-23 | 21396.804
1027000056 | 73822 | Middle Sea for Telecommunication Establishment | 2010-02-28 | 2010-04-14 | ABAR | msan | MSAN-HBU | completed | 2010 objective design issued | 20522.6 | Yes |  | MSAN 011 (AL WASELI) | alfies benjamin | 2011-01-25 | 2010-02-23 | 15922.3
1027000321 | 75745 | Mohemmed Bin Gerboo EST. | 2010-08-01 | 2010-09-30 | JIZA | msan | MSAN-HBU Ad | completed | 2010 objective design issued | 19997 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2011-03-01 | 2010-08-09 | 19823
1027000322 | 75745 | Mohemmed Bin Gerboo EST. | 2010-08-01 | 2010-09-30 | JIZA | msan | MSAN-HBU Ad | completed | 2010 objective design issued | 3111.4 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2011-03-01 | 2010-08-09 | 3082
1027000323 | 75745 | Mohemmed Bin Gerboo EST. | 2010-08-01 | 2010-09-30 | JIZA | msan | MSAN-HBU Ad | completed | 2010 objective design issued | 14129.7 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2011-03-01 | 2010-08-09 | 14351
1027000294 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-11 | 2010-12-31 | SBYA | msan | MSAN-HBU-Reloc | completed | 2010 objective design issued | 46654 | Yes |  | Secondery MSAN ADAYA | ali m. gobain | 2011-01-10 | 2010-07-11 | 47314
1027000292 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-11 | 2010-12-31 | SBYA | msan | MSAN-HBU-Reloc | completed | 2010 objective design issued | 49138.3 | Yes |  |  | ali m. gobain | 2011-01-10 | 2010-07-11 | 44952.1
1027000293 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-11 | 2010-12-31 | SBYA | msan | MSAN-HBU-Reloc | completed | 2010 objective design issued | 40122.4 | Yes |  |  | ali m. gobain | 2011-01-10 | 2010-07-11 | 39789.1
0927000241 | 73803 | Mohemmed Bin Gerboo EST. | 2010-12-08 | 2011-01-22 | SBYA | msan | MSAN-HBU-Reloc | completed | 2010 objective design issued | 0 |  |  | (MOT) Relocation For Road Widen Projector | ali m. gobain | 2010-12-18 | 2010-12-08 | 0
0927000713 | 71475 | Mohemmed Bin Gerboo EST. | 2010-03-26 | 2010-05-10 | SBYA | msan | MSAN-HBU-Reloc | completed | 2010 objective design issued | 0 |  |  | (MOT) Relocation For Road Widen Projector | ali m. gobain | 2010-12-18 | 2010-03-26 | 0
0927000704 | 71475 | Mohemmed Bin Gerboo EST. | 2010-03-26 | 2010-05-10 | SBYA | msan | MSAN-HBU-Reloc | completed | 2010 objective design issued | 0 |  |  | (MOT) Relocation For Road Widen Projector | ali m. gobain | 2010-12-18 | 2010-03-26 | 0
1027000536 | 81002 | Mohemmed Bin Gerboo EST. | 2011-08-23 | 2011-08-31 | JIZA | key account | MSAN-K.A | completed | 2010 objective design issued | 2043.28 | CM In Progress |  |  | agobain | 2011-09-03 | 2011-08-23 | 2043.28
1227000164 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-06-11 | 2012-07-22 | SAMI | key account | MSAN-K.A | completed | 2012 objective design issued | 13881.696 | CM In Progress |  | Alsalam Market | elai | 2012-06-10 | 2012-06-11 | 7876.2
1127000440 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-09-04 | 2011-10-15 | JIZA | key account | MSAN-K.A | completed | 2011 objective design issued | 50993.016 | DM In Progress |  |  | lscarboz | 2011-10-16 | 2011-09-04 | 52956.06
1127000378 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-08-08 | 2011-09-16 | JIZA | key account | MSAN-K.A | completed | 2011 objective design issued | 36872.356 | DM In Progress |  |  | lscarboz | 2012-01-04 | 2011-08-08 | 37159.14
1227000166 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-06-17 | 2012-07-31 | JIZA | key account | MSAN-K.A | completed | 2012 objective design issued | 8360.428 | Yes |  | Completed | laary | 2012-10-23 | 2012-06-17 | 16260.2
1127000395 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-08 | 2011-09-22 | SHUQ | key account | MSAN-K.A | completed | 2011 objective design issued | 243256 | Yes |  |  | jomeel g. antonio | 2012-02-13 | 2011-08-08 | 238805
1127000299 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-15 | 2011-07-25 | DARB | key account | MSAN-K.A | completed | 2011 objective design issued | 22668 | Yes |  |  | jomeel g. antonio | 2011-12-28 | 2011-06-15 | 58593
1027000196 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | key account | MSAN-K.A | completed | 2010 objective design issued | 103196.34 | Yes |  |  | lari carboz | 2011-03-20 | 2010-06-07 | 110873.5
1127000424 | 80012 | DETCON Saudia Co. (Data_SAD) | 2011-10-31 | 2011-12-15 | JIZA | key account | MSAN-K.A | completed | 2011 objective design issued | 150344.092 | Con/Insp In Progress |  |  | laary | 2012-03-03 | 2011-10-31 | 135601.44
1027000151 | 73803 | Mohemmed Bin Gerboo EST. | 2010-04-11 | 2010-07-17 | KWBH | key account | MSAN-K.A | completed | 2010 objective design issued | 19061.2 | Yes |  | Email From: Abdulmoti A. Dahlawi | ernesto e. lai | 2011-03-20 | 2010-04-11 | 16579.4
1027000152 | 73803 | Mohemmed Bin Gerboo EST. | 2010-04-11 | 2010-07-17 | KWBH | key account | MSAN-K.A | completed | 2010 objective design issued | 5165.7 | Yes |  | Email From: Abdulmoti A. Dahlawi | ernesto e. lai | 2011-03-20 | 2010-04-11 | 2616.3
0927000545 | 73803 | Mohemmed Bin Gerboo EST. | 2009-11-20 | 2010-01-04 | JIZA | key account | MSAN-K.A | completed | 2010 objective design issued | 19983.8 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2010-10-05 | 2009-10-18 | 10178.4
0927000563 | 73803 | Mohemmed Bin Gerboo EST. | 2009-11-20 | 2010-01-04 | JIZA | key account | MSAN-K.A | completed | 2010 objective design issued | 22521.5 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2010-10-10 | 2009-11-02 | 21960.429
0927000615 | 73803 | Mohemmed Bin Gerboo EST. | 2010-02-01 | 2010-04-01 | JIZA | key account | MSAN-K.A | completed | 2010 objective design issued | 77978.4 | Yes |  | Email From: Abdulmoti A. Dahlawi | ali gobain | 2011-03-12 | 2010-02-01 | 59080.34
0927000629 | 73803 | Mohemmed Bin Gerboo EST. | 2010-02-01 | 2010-04-01 | JIZA | key account | MSAN-K.A | completed | 2010 objective design issued | 3059.2 | Yes |  | Email From: Abdulmoti A. Dahlawi | lari carboz | 2011-01-30 | 2010-02-01 | 3882.2
1027000197 | 73803 | Mohemmed Bin Gerboo EST. | 2010-05-18 | 2010-06-16 | JIZA | key account | MSAN-K.A | completed | 2010 objective design issued | 780854.043 | Yes |  | EBU10-BBC-KA | lari carboz | 2011-03-20 | 2010-05-18 | 772105.3
0927000524 | 73803 | Mohemmed Bin Gerboo EST. | 2009-09-27 | 2009-11-18 | JIZA | key account | MSAN-K.A | completed | 2010 objective design issued | 30898.8 | Yes |  | From: Abdulmoti A. Dahlawi Sent to Aljarboo | lari carboz | 2010-01-19 | 2009-09-27 | 26658.6
1227000211 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-09-17 | 2012-10-24 | JIZA | msan | MSAN-NGN | completed | 2012 objective design issued | 2602.06 | PM In Progress |  |  | lscarboz | 2013-04-28 | 2012-09-17 | 12602.48
1227000233 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-11-20 | 2012-12-31 | JIZA | msan | MSAN-NGN | completed | 2012 objective design issued | 2314.56 | CM In Progress |  | KARBUS M01 | lscarboz | 2013-06-24 | 2012-11-20 | 2402.56
1227000100 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-24 | 2012-06-07 | JIZA | msan | MSAN-NGN | completed | 2012 objective design issued | 5205.28 | CM In Progress |  | MABUJ | lscarboz | 2013-04-14 | 2012-04-24 | 9107.59
1227000097 |  | Mohemmed Bin Gerboo EST. | 2012-04-22 | 2012-06-06 | JIZA | msan | MSAN-NGN | completed | 2012 objective design issued |  |  | district contractor over budget | No PO, completed MSAN, site - Al Galaah | laary | 2013-02-09 | 2012-04-22 | 13847.04
1127000445 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-11-28 | 2012-01-12 | JIZA | msan | MSAN-OPTIMIZ | cancelled | 2012 objective not in the design master sheet | 0 |  |  | Insufficient cards | laary |  | 2011-11-28 | 44391.24
1327000387 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-23 | 2014-02-06 | JIZA | msan | MSAN-OPTIMIZ | in progress | 2013 objective design issued | 0 |  |  |  | lari carboz |  | 2013-09-03 | 89898.24
1127000237 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-05-21 | 2011-06-30 | JIZA | msan | MSAN-OPTIMIZ | completed | 2011 objective design issued | 11018.88 | Yes |  | Site in upgrade Email from Ibrahim R. Balhareth Completed | lari carboz | 2012-10-22 | 2011-05-18 | 13098.24
1127000570 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-19 | 2012-04-01 | SLHD | key account | MS-SDH | completed | 2012 objective not in the design master sheet | 12174.32 | CM In Progress |  |  | elai | 2013-03-15 | 2012-02-19 | 23197.698
1227000047 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-19 | 2012-04-01 | TWAL | key account | MS-SDH | completed | 2012 objective design issued | 36476.128 | CM In Progress |  |  | elai | 2012-08-04 | 2012-02-19 | 39163.836
1127000572 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-07 | 2012-03-21 | TWAL | key account | MS-SDH | completed | 2012 objective not in the design master sheet | 22439.752 | CM In Progress |  |  | elai | 2012-11-13 | 2012-02-07 | 20587.128
1127000571 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-02-19 | 2012-04-01 | SLHD | key account | MS-SDH | completed | 2012 objective not in the design master sheet | 47687.48 | CM In Progress |  |  | elai | 2013-01-07 | 2012-02-19 | 52901.5392
1127000295 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-11-12 | 2011-11-30 | BAYS | key account | MS-SDH | completed | 2011 objective design issued | 76681 | DM In Progress |  |  | jgantonio | 2011-11-30 | 2011-06-15 | 78808.66
1127000257 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-01 | 2011-07-14 | DARB | junction | MS-SDH | completed | 2012 objective design issued | 48812.7 | Yes |  |  | jomeel g. antonio | 2011-09-12 | 2011-06-01 | 43975.4
1027000385 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-16 | 2010-12-31 | DARB | key account | MS-SDH | completed | 2010 objective design issued | 120909.1 | Yes |  |  | jomeel g. antonio | 2011-03-20 | 2010-10-20 | 98726
1027000368 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-02 | 2010-12-31 | SBYA | key account | MS-SDH | completed | 2010 objective design issued | 26870.6 | Yes |  |  | ali m. gobain | 2010-12-22 | 2010-10-02 | 47675
1327000369 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-15 | 2013-08-28 | ABAR | key account | MS-SDH | completed | 2013 objective design issued | 29423.16 |  |  | Done | alfies benjamin | 2013-09-07 | 2013-07-15 | 27697.4
1327000247 | 80013 | Mohemmed Bin Gerboo EST. | 2013-05-07 | 2013-06-16 | SAMI | key account | MS-SDH | completed | 2013 objective design issued | 12089.592 |  |  | SAUDI CUSTOMS | ernesto e. lai | 2013-07-14 | 2013-05-07 | 19500.2
1227000222 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | SBYA | key account | MS-SDH | completed | 2013 objective design issued | 0 |  |  | Done | ali gobain | 2013-12-30 | 2013-06-09 | 123022.69
1227000230 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-09-01 | 2013-09-30 | DARB | key account | MS-SDH | completed | 2013 objective design issued | 56687.6 |  |  | MINISTRY OF JUSTICE (DARB) | jomeel g. antonio | 2013-09-01 | 2013-06-08 | 90423.22
1127000568 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-11-24 | 2014-01-07 | SAMI | key account | MS-SDH | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-11-21 | 21192.5964
1327000402 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-10-01 | 2013-10-31 | DARB | key account | MS-SDH | completed | 2013 objective design issued | 0 |  |  | No PO, completed-Job implemented by Detcon same route of MoJ & MoH, all works Completed 100% | jomeel g. antonio | 2013-11-04 | 2013-07-23 | 16618.8
1227000229 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-06-26 | 2013-08-06 | SBYA | key account | MS-SDH | completed | 2013 objective design issued | 0 |  |  | Done | ali gobain | 2013-12-30 | 2013-06-09 | 8306.34
1027000168 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-04-19 | 2010-06-20 | DARB | key account | MS-SDH | completed | 2010 objective design issued | 38794.7 | Yes |  |  | jomeel g. antonio | 2010-05-31 | 2010-04-19 | 37810
1027000121 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-04-11 | 2010-07-11 | SHUQ | key account | MS-SDH | completed | 2010 objective design issued | 153586.9 | Yes |  |  | jomeel g. antonio | 2010-07-19 | 2010-04-11 | 153503.2
1027000111 | 73803 | Mohemmed Bin Gerboo EST. | 2010-03-27 | 2010-05-11 | JIZA | key account | MS-SDH | completed | 2010 objective design issued | 18164.82 | Yes |  | MOT FOC | lari carboz | 2010-05-08 | 2010-03-27 | 14225.075
1027000107 | 73822 | Middle Sea for Telecommunication Establishment | 2010-03-13 | 2010-04-27 | FRSN | key account | MS-SDH-Zain | completed | 2010 objective design issued | 28768.15 | Yes |  |  | lari carboz | 2010-03-27 | 2010-03-09 | 26233.6
1027000231 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-06-10 | 2010-09-30 | ARDH | key account | MS-SDH-Zain | completed | 2010 objective design issued | 2472.1 | Yes |  |  | alfies benjamin | 2010-11-02 | 2010-06-14 | 2391.1
1027000113 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-07 | 2010-09-10 | JIZA | copper cabinet | New | completed | 2010 objective not in the design master sheet | 40431.4 | Yes |  | Email From :Abdulmoti A. Dahlawi | lari carboz | 2010-06-16 | 2010-06-07 | 11324
1227000088 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2013-05-19 | 2013-05-31 | SAMI | key account | ONT | completed | 2013 objective design issued - ho | 38011.6 | PM In Progress |  | SAMIS-CIVIL AFFAIRS | elai | 2012-12-17 | 2012-04-11 | 35473.29
1227000086 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2013-05-05 | 2013-05-31 | JIZA | key account | ONT | completed | 2013 objective design issued - ho | 8000.14 | PM In Progress |  | SAMIS-Civil Affairs | lscarboz | 2012-12-08 | 2012-04-11 | 5785.12
1227000232 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2013-05-19 | 2013-05-31 | JIZA | key account | ONT | completed | 2013 objective design issued - ho | 18898.156 | PM In Progress |  | Saudi Electricity Company | lscarboz | 2012-12-17 | 2012-11-03 | 30152.78
1227000087 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-04-11 | 2012-05-17 | JIZA | key account | ONT | completed | 2013 objective design issued - ho | 16779.626 | Yes |  |  | laary | 2012-09-18 | 2012-04-11 | 28237.05
1227000081 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-04-01 | 2012-05-10 | SBYA | key account | ONT | completed | 2013 objective design issued - ho | 74960.922 | Yes |  |  | ali gobain | 2012-04-23 | 2012-04-01 | 78542.82
1227000190 | 80388 | Mohemmed Bin Gerboo EST. | 2013-06-22 | 2013-07-31 | JIZA | key account | ONT | completed | 2013 objective design issued - ho | 13522.782 |  |  | Ministry of Interior-Civil Defence | laary | 2013-07-14 | 2013-06-08 | 11538
1227000208 | 80388 | Mohemmed Bin Gerboo EST. | 2013-07-21 | 2013-09-04 | JIZA | key account | ONT | completed | 2013 objective design issued - ho | 139296.576 |  |  | Completed | lari carboz | 2013-08-27 | 2013-06-08 | 1126198.9
1227000248 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-05-06 | 2013-06-14 | ABAR | key account | ONT | completed | 2013 objective design issued - ho | 0 |  |  | MODA-STRATEGIC MISSILE ELECTRONICALLY COMMUNICATION DEPT | alfies benjamin | 2013-07-30 | 2013-05-06 | 2563.68
1227000213 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-05-06 | 2013-06-14 | BAYS | key account | ONT | completed | 2013 objective design issued - ho | 40949.992 |  |  | DONE | jomeel g. antonio | 2013-07-25 | 2013-05-06 | 87800
1127000624 | 80230 | DETCON Saudia Co. (Data_SAD) | 2013-05-06 | 2013-06-14 | ABAR | key account | ONT | in progress | 2013 objective design issued - ho | 0 |  |  | JIZAN UNIVERSITY ABU ARISH | alfies benjamin |  | 2013-05-06 | 19635.54
1427000032 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2014-01-27 | 2014-03-11 | JIZA | key account | OSP/ONT | in progress | 2013 objective design issued |  |  |  |  | lari carboz |  | 2014-01-26 | 16648.64
1327000374 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-24 | 2013-09-05 | JIZA | key account | OSP/ONT | completed | 2013 objective design issued | 25123.04 |  |  | Done | lari carboz | 2013-10-03 | 2013-07-23 | 26516
1327000349 | 80013 | Mohemmed Bin Gerboo EST. | 2013-07-15 | 2013-08-28 | ABAR | key account | OSP/ONT | in progress | 2013 objective design issued | 0 |  |  | Customer issue, no internal duct | alfies benjamin |  | 2013-07-15 | 86430.7
1327000272 | 80013 | Mohemmed Bin Gerboo EST. | 2013-06-08 | 2013-07-18 | JIZA | key account | OSP/ONT | completed | 2013 objective design issued | 10036.8 |  |  | MINISTRY OF FINANCE | lari carboz | 2013-08-01 | 2013-06-08 | 14445.8
1327000214 | 80013 | Mohemmed Bin Gerboo EST. | 2013-04-15 | 2013-05-30 | JIZA | key account | OSP/ONT | completed | 2013 objective design issued | 25713.5 |  |  | MINISTRY OF WATER & ELECTRICITY | lari carboz | 2013-06-24 | 2013-04-15 | 22533.4
1327000229 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-05-07 | 2013-06-15 | ABAR | key account | OSP/ONT | completed | 2013 objective design issued | 0 |  |  | Done (Technical College for Girls) | alfies benjamin | 2013-11-05 | 2013-05-07 | 208792
1327000220 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-05-06 | 2013-06-15 | SBYA | key account | OSP/ONT | completed | 2013 objective design issued | 7606.04 | PCC In Progress |  | SAMIS-CIP | ali gobain | 2013-07-31 | 2013-05-06 | 23309.8
1327000259 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-06-22 | 2013-08-05 | SBYA | key account | OSP/ONT | completed | 2013 objective design issued | 52805.08 | PCC In Progress |  | MINISTRY OF EDUCATION | ali gobain | 2013-07-31 | 2013-06-09 | 63753.64
1327000696 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-12-22 | 2014-02-05 | JIZA | key account | OSP/ONT | completed | 2013 objective design issued | 0 |  |  | Done | lari carboz | 2013-12-30 | 2013-12-01 | 25922.95
0927000683 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-10 | 2010-09-10 | SLHD | posttep | POSTTEP 2010 | completed | 2010 objective design issued | 104095.8 | Yes |  | Email From: Abdulmoti A. Dahlawi Sent to Aljarboo | ernesto e. lai | 2009-12-09 | 2009-12-02 | 102849.4
1027000210 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-03 | 2010-08-18 | JIZA | posttep | POSTTEP 2010 | completed | 2010 objective design issued | 851421.33 | Yes |  |  | lari carboz | 2011-02-07 | 2010-08-18 | 817212.237
1127000376 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-26 | 2011-09-06 | JIZA | posttep | POSTTEP 2011 | completed | 2011 objective design issued | 1097.08 | PM In Progress |  |  | lscarboz | 2011-08-22 | 2011-07-26 | 1097.08
1127000367 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-09-04 | 2011-10-15 | JIZA | posttep | POSTTEP 2011 | completed | 2011 objective design issued | 52259.272 |  |  | Rehab 075 | lscarboz | 2012-10-15 | 2011-09-04 | 59296.84
1127000592 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-12-04 | 2012-01-18 | JIZA | posttep | POSTTEP 2011 | completed | 2012 objective not in the design master sheet | 846.52 | DM In Progress |  |  | lscarboz | 2012-04-28 | 2011-12-04 | 793.72
1127000363 | 76677 | Mohemmed Bin Gerboo EST. | 2011-08-10 | 2011-09-10 | JIZA | posttep | POSTTEP 2011 | completed | 2011 objective design issued | 6778.6 | DM In Progress |  | Ready only stincel & redline. | lscarboz | 2011-10-21 | 2011-08-10 | 487.04
1127000434 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-09-04 | 2011-10-17 | BAYS | posttep | POSTTEP 2011 | completed | 2011 objective design issued | 2335.68 | Yes |  |  | jomeel g. antonio | 2011-10-29 | 2011-09-04 | 472.12
1127000284 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-06-19 | 2011-07-30 | JIZA | posttep | POSTTEP 2011 | completed | 2011 objective design issued | 25681.848 | Yes |  |  | lari carboz | 2011-12-24 | 2011-06-19 | 21394.23
1127000342 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-04-03 | 2012-04-30 | JIZA | posttep | POSTTEP 2011 | completed | 2012 objective not in the design master sheet | 2501.88 | Yes |  |  | laary | 2012-06-18 | 2012-04-03 | 2574.84
1127000322 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-07-10 | 2011-08-10 | JIZA | posttep | POSTTEP 2011 | completed | 2011 objective design issued | 659 | Yes |  |  | lari carboz | 2011-07-12 | 2011-07-10 | 590
1127000185 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-05-01 | 2011-06-11 | JIZA | posttep | POSTTEP 2011 | completed | 2011 objective design issued | 301410.76 | Yes |  |  | lari carboz | 2011-08-17 | 2011-04-27 | 330226
1027000213 | 75745 | Mohemmed Bin Gerboo EST. | 2010-10-02 | 2010-12-31 | JIZA | posttep | POSTTEP 2011 | completed | 2011 objective design issued | 278018.02 | Yes |  |  | lari carboz | 2012-03-05 | 2010-10-02 | 435229.6
1027000212 | 75745 | Mohemmed Bin Gerboo EST. | 2010-03-07 | 2010-12-31 | JIZA | posttep | POSTTEP 2011 | completed | 2011 objective design issued | 436638.6 | Yes |  |  | lari carboz | 2012-03-05 | 2010-10-02 | 439352
1227000262 | 78262 | Al Gihaz for Contracting & Trading Company Ltd | 2012-10-21 | 2012-11-21 | JIZA | other | Power Connection | completed | 2012 objective not in the design master sheet | 371239.2 | Yes |  | Al- Gihaz | laary | 2012-10-21 | 2012-10-21 | 371334.24
1327000281 | 78262 | Al Gihaz for Contracting & Trading Company Ltd | 2013-05-21 | 2013-05-31 | JIZA | other | Quality Assurance | completed | 2012 objective not in the design master sheet | 333283.968 | Yes |  |  | laary | 2013-05-31 | 2013-05-21 | 333283.968
1327000282 | 78262 | Al Gihaz for Contracting & Trading Company Ltd | 2013-05-21 | 2013-05-31 | SBYA | other | Quality Assurance | completed | 2012 objective not in the design master sheet | 390532.848 | Yes |  |  | ali gobain | 2013-06-04 | 2013-05-21 | 390532.848
1327000322 |  | Majd AlJanoub for general Contracting Ltd. | 2013-12-23 | 2014-01-23 | SBYA | msan | RAN Replacement | cancelled | 2013 objective design issued |  |  |  | No PO / MSAN and ISOW status - cancelled | ali gobain |  | 2013-12-23 | 19764.42
1327000326 |  | Majd AlJanoub for general Contracting Ltd. | 2013-12-23 | 2014-01-23 | SBYA | msan | RAN Replacement | cancelled | 2013 objective design issued |  |  |  | No PO / MSAN and ISOW status - cancelled | ali gobain |  | 2013-12-23 | 16725.5
1327000327 |  | Majd AlJanoub for general Contracting Ltd. | 2013-12-23 | 2014-01-23 | SBYA | msan | RAN Replacement | cancelled | 2013 objective design issued |  |  |  | No PO / MSAN and ISOW status - cancelled | ali gobain |  | 2013-12-23 | 15564.9
1327000329 |  | Majd AlJanoub for general Contracting Ltd. | 2013-12-23 | 2014-01-23 | SBYA | msan | RAN Replacement | cancelled | 2013 objective design issued |  |  |  | No PO / MSAN and ISOW status - cancelled | ali gobain |  | 2013-12-23 | 22581.58
1327000336 |  | Majd AlJanoub for general Contracting Ltd. | 2013-12-23 | 2014-01-23 | SBYA | msan | RAN Replacement | cancelled | 2013 objective design issued |  |  |  | No PO / MSAN and ISOW status - cancelled | ali gobain |  | 2013-12-23 | 16518.64
1327000344 |  | Majd AlJanoub for general Contracting Ltd. | 2013-12-23 | 2014-01-23 | SBYA | msan | RAN Replacement | cancelled | 2013 objective design issued |  |  |  | No PO / MSAN and ISOW status - cancelled | ali gobain |  | 2013-12-23 | 6350.7
1327000348 |  | Majd AlJanoub for general Contracting Ltd. | 2013-12-23 | 2014-01-23 | SBYA | msan | RAN Replacement | cancelled | 2013 objective design issued |  |  |  | No PO / MSAN and ISOW status - cancelled | ali gobain |  | 2013-12-23 | 20829.72
1027000229 | 75745 | Mohemmed Bin Gerboo EST. | 2010-05-01 | 2010-06-15 | SBYA | relocation | Relocation | completed | 2011 objective not in the design master sheet | 0 |  |  | as per appved by Ali on 30-10-2010 with MOT project | ali m. gobain | 2010-11-02 | 2010-11-01 | 0
1027000230 | 75745 | Mohemmed Bin Gerboo EST. | 2010-06-16 | 2010-09-16 | SBYA | relocation | Relocation | completed | 2010 objective not in the design master sheet | 20056.2 | Yes |  |  | ali m. gobain | 2010-08-04 | 2010-06-16 | 18032.2
1327000380 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-05 | 2013-10-16 | ARDA2 | relocation | Relocation | in progress | 2013 objective design issued | 0 |  |  |  | alfies benjamin |  | 2013-09-05 | 33718.8
1327000393 | 80013 | Mohemmed Bin Gerboo EST. | 2013-09-05 | 2013-10-16 | JIZA | relocation | Relocation | in progress | 2013 objective design issued | 0 |  |  |  | lari carboz |  | 2013-09-05 | 63337.86
1327000655 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-13 | 2013-12-22 | SLHD | relocation | Relocation | completed | 2013 objective design issued | 0 |  |  |  | ernesto e. lai | 2013-12-22 | 2013-11-13 | 11728.77
1227000057 | 80013 | Mohemmed Bin Gerboo EST. | 2013-11-18 | 2013-12-31 | KHAW | relocation | Relocation | in progress | 2013 objective design issued |  |  | need scope of work | Customer Jub | ernesto e. lai |  | 2012-09-08 | 0
1327000719 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-22 | 2014-01-22 | SLHD | relocation | Relocation | in progress | 2013 objective design issued |  |  | need scope of work |  | ernesto e. lai |  | 2013-12-22 | 44375.42
1327000689 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-04 | 2014-01-18 | SAMI | relocation | Relocation | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-12-04 | 34977.15
1327000692 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-04 | 2014-01-18 | SAMI | relocation | Relocation | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-12-04 | 16687.5
1327000693 | 80013 | Mohemmed Bin Gerboo EST. | 2013-12-04 | 2014-01-18 | SAMI | relocation | Relocation | in progress | 2013 objective design issued | 0 |  |  |  | ernesto e. lai |  | 2013-12-04 | 17530.2
1327000715 | 80012 | DETCON Saudia Co. (Data_SAD) | 2013-12-18 | 2014-01-23 | ABAR | relocation | Relocation | in progress | 2013 objective design issued |  |  | need scope of work |  | alfies benjamin |  | 2013-12-18 | 37765.9
0927000309 | 73822 | Middle Sea for Telecommunication Establishment | 2009-09-05 | 2009-11-05 | TWAL | relocation | Relocation | completed | 2011 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | ernesto e. lai | 2010-12-18 | 2009-09-05 | 0
0927000671 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-07-13 | 2010-12-18 | SLHD | relocation | Relocation | completed | 2011 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | ernesto e. lai | 2010-12-18 | 2010-07-13 | 0
1027000049 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2010-11-29 | 2010-12-31 | SLHD | relocation | Relocation | completed | 2011 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | ernesto e. lai | 2010-12-18 | 2010-11-29 | 0
1027000267 | 73803 | Mohemmed Bin Gerboo EST. | 2010-07-12 | 2010-08-31 | ABAR | relocation | Relocation | completed | 2010 objective not in the design master sheet | 6997.6 | Yes |  | Email From: Ali Alasiri | alfies benjamin | 2010-07-17 | 2010-07-12 | 5970
0927000184 | 73803 | Mohemmed Bin Gerboo EST. | 2010-02-01 | 2011-09-14 | SBYA | relocation | Relocation | completed | 2011 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | ali m. gobain | 2010-12-18 | 2010-02-01 | 0
0927000360 | 71475 | Mohemmed Bin Gerboo EST. | 2010-03-26 | 2010-05-10 | ABAR | relocation | Relocation | completed | 2010 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | alfies benjamin | 2010-12-18 | 2010-03-26 | 0
0927000361 | 71475 | Mohemmed Bin Gerboo EST. | 2010-03-26 | 2010-05-10 | ABAR | relocation | Relocation | completed | 2010 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | alfies benjamin | 2010-12-18 | 2010-03-26 | 0
0927000362 | 71475 | Mohemmed Bin Gerboo EST. | 2010-03-26 | 2010-05-10 | ABAR | relocation | Relocation | completed | 2010 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | alfies benjamin | 2010-12-18 | 2010-03-26 | 0
0927000240 | 71475 | Mohemmed Bin Gerboo EST. | 2010-03-26 | 2010-05-10 | SBYA | relocation | Relocation | completed | 2010 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | ali m. gobain | 2010-12-18 | 2010-03-26 | 0
0727000724 | 71479 | Middle Sea for Telecommunication Establishment | 2008-08-03 | 2008-09-03 | DARB | relocation | Relocation | completed | 2008 objective design issued | 0 |  |  |  | jomeel g. antonio | 2009-01-20 | 2008-08-03 | 0
0727000729 | 71479 | Middle Sea for Telecommunication Establishment | 2008-07-06 | 2008-08-06 | DARB | relocation | Relocation | completed | 2008 objective design issued | 0 |  |  | THE RIGHT CONTRACTOR : MDLE SEA | jomeel g. antonio | 2008-09-06 | 2008-07-06 | 0
0727000711 | 71479 | Middle Sea for Telecommunication Establishment | 2008-07-06 | 2008-08-06 | DARB | relocation | Relocation | completed | 2008 objective design issued | 0 |  |  |  | jomeel g. antonio | 2009-01-30 | 2008-07-06 | 0
0727000712 | 71479 | Middle Sea for Telecommunication Establishment | 2008-07-06 | 2008-08-06 | DARB | relocation | Relocation | completed | 2008 objective design issued | 0 |  |  |  | jomeel g. antonio | 2009-01-30 | 2008-07-06 | 0
0727000721 | 71479 | Middle Sea for Telecommunication Establishment | 2008-07-06 | 2008-08-06 | DARB | relocation | Relocation | completed | 2008 objective design issued | 0 |  |  |  | jomeel g. antonio | 2008-12-24 | 2008-07-06 | 0
0727000714 | 71479 | Middle Sea for Telecommunication Establishment | 2008-07-06 | 2008-08-06 | DARB | relocation | Relocation | completed | 2008 objective design issued | 0 |  |  |  | jomeel g. antonio | 2008-08-05 | 2008-07-06 | 0
0727000713 | 71479 | Middle Sea for Telecommunication Establishment | 2008-07-06 | 2008-08-06 | DARB | relocation | Relocation | completed | 2008 objective design issued | 0 |  |  |  | jomeel g. antonio | 2008-08-04 | 2008-07-06 | 0
0727000716 | 71479 | Middle Sea for Telecommunication Establishment | 2008-07-06 | 2008-08-06 | DARB | relocation | Relocation | completed | 2008 objective design issued | 0 |  |  |  | jomeel g. antonio | 2008-12-24 | 2008-07-06 | 0
0727000719 | 71479 | Middle Sea for Telecommunication Establishment | 2008-07-06 | 2008-08-06 | DARB | relocation | Relocation | completed | 2008 objective design issued | 0 |  |  |  | ernesto e. lai | 2008-12-24 | 2008-07-06 | 0
0927000287 | 73822 | Middle Sea for Telecommunication Establishment | 2010-01-02 | 2010-06-02 | TWAL | relocation | Relocation | completed | 2011 objective not in the design master sheet | 0 |  |  | (MOT) Relocation For Road Widen Projector | ernesto e. lai | 2010-12-18 | 2010-01-02 | 0
1327000710 | 80388 | Mohemmed Bin Gerboo EST. | 2013-12-18 | 2014-01-24 | DARB | held order | STC SALES OFFICE | in progress | 2013 objective design issued - ho | 0 |  |  |  | jomeel g. antonio |  | 2013-12-18 | 29242.62
1327000701 | 80388 | Mohemmed Bin Gerboo EST. | 2013-12-18 | 2014-01-24 | SBYA | held order | STC SALES OFFICE | completed | 2013 objective design issued - ho |  |  | need scope of work | Done | ali gobain | 2013-12-30 | 2013-12-18 | 31873.8
1227000261 | 78262 | Al Gihaz for Contracting & Trading Company Ltd | 2012-10-21 | 2012-11-21 | ABAR | other | Temporary Generator | completed | 2012 objective not in the design master sheet | 961280 | Yes |  | Al- Gihaz | alfies benjamin | 2012-11-14 | 2012-10-21 | 961280
1327000535 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-11-05 | 2013-12-19 | DARB | cable replacement | TIE CABLE- 2013 | completed | 2013 objective design issued | 0 |  |  | Done | jomeel g. antonio | 2013-12-05 | 2013-11-04 | 1977.6
1327000536 | 80201 | Majd AlJanoub for general Contracting Ltd. | 2013-11-05 | 2013-12-19 | AYBN | cable replacement | TIE CABLE- 2013 | completed | 2013 objective design issued | 0 |  |  | Done | ali gobain | 2013-12-08 | 2013-11-04 | 13420.8
1127000603 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-03-05 | 2012-04-18 | DARB | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 54408.51 | PM In Progress |  | Proceed from Email Eyad M. Alkussayer Mon 2012-03-05 7:50 AM | jgantonio | 2012-09-16 | 2012-03-05 | 59821.41
1227000040 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-05 | 2012-04-18 | ABAR | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 26898.68 | CM In Progress |  | Proceed from Email Eyad M. Alkussayer Mon 2012-03-05 7:50 AM | abenjamin | 2012-07-07 | 2012-03-05 | 26840.48
1227000026 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-05 | 2012-04-18 | ABAR | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 5974.8 | CM In Progress |  | Proceed from Email Eyad M. Alkussayer Mon 2012-03-05 7:50 AM | abenjamin | 2012-07-07 | 2012-03-05 | 4196.08
1227000031 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-05 | 2012-04-18 | DAMD | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 212821.088 | CM In Progress |  | Proceed from Email Eyad M. Alkussayer Mon 2012-03-05 7:50 AM | abenjamin | 2012-09-24 | 2012-03-05 | 315019.97
1227000028 | 79722 | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | JIZA | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 18047.12 | Director In Progress |  |  | lscarboz | 2012-08-05 | 2012-02-07 | 33492
1227000050 | 79722 | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | TWAL | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 8068.56 | Director In Progress |  |  | elai | 2012-06-30 | 2012-02-19 | 7965.6
1127000585 | 79722 | Mohemmed Bin Gerboo EST. | 2012-02-06 | 2012-03-22 | SAMI | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 95344.32 | Director In Progress |  |  | elai | 2012-08-15 | 2011-12-20 | 41928
1127000615 | 79738 | ISSA AL ISSA FOR contracting EST. | 2012-03-05 | 2012-04-18 | BAYS | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 73388.87 | CM In Progress |  | Jeel AlFursan Est. FOR TRADING &CO by Adel baadullah Completed | jgantonio | 2012-07-03 | 2012-03-05 | 64262.21
1127000578 | 79738 | ISSA AL ISSA FOR contracting EST. | 2012-06-04 | 2012-07-18 | SBYA | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 39751.4 | CM In Progress |  | Jeel AlFursan Est. FOR TRADING &CO | agobain | 2012-07-03 | 2011-12-11 | 37744.24
1227000012 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2012-03-05 | 2012-04-18 | SBYA | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 44342.84 | Yes |  |  | ali gobain | 2012-07-01 | 2012-03-05 | 92709.04
1127000031 |  | Mohemmed Bin Gerboo EST. | 2012-02-06 | 2012-03-22 | SBYA | vdsl | VDSL2 – 2012 | cancelled | 2012 objective design issued - lead |  |  | job wo cancelled | Coverd By 1227000031 Email From Hasan Ghashim | ali gobain |  | 2012-01-22 | 5040
1127000584 |  | Mohemmed Bin Gerboo EST. | 2012-02-06 | 2012-03-22 | JIZA | vdsl | VDSL2 – 2012 | cancelled | 2012 objective design issued - lead |  |  | job wo cancelled | Cancelled OUT Of Scope | lari carboz |  | 2011-12-11 | 7252
1227000034 |  | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | JIZA | vdsl | VDSL2 – 2012 | cancelled | 2012 objective design issued - lead |  |  | job wo cancelled | Cancelled OUT Of Scope | laary |  | 2012-02-06 | 9989.76
1227000041 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-05 | 2012-04-18 | ABAR | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 232201.0304 | Yes |  | Proceed from Email Eyad M. Alkussayer Mon 2012-03-05 7:50 AM | alfies benjamin | 2012-06-30 | 2012-03-05 | 146638.08
1127000145 | 76677 | Mohemmed Bin Gerboo EST. | 2011-11-01 | 2011-12-13 | SLHD | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 229558 |  |  | 2012 Objective Design Issued – LEAD | ernesto e. lai | 2011-12-20 | 2011-08-14 | 210924
1127000596 | 79722 | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | JIZA | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 37417.68 | Yes |  |  | laary | 2013-02-12 | 2012-02-19 | 8208.8
1127000582 | 79722 | Mohemmed Bin Gerboo EST. | 2012-02-06 | 2012-03-22 | JIZA | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 69488.06 | Yes |  |  | lari carboz | 2012-09-16 | 2011-12-11 | 19332
1127000591 | 79722 | Mohemmed Bin Gerboo EST. | 2012-02-06 | 2012-03-22 | SAMI | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 4807.42 |  |  |  | ernesto e. lai | 2013-02-12 | 2011-12-20 | 6663.68
1127000583 | 79722 | Mohemmed Bin Gerboo EST. | 2012-02-06 | 2012-03-22 | SAMI | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 102467.2 | Yes |  |  | ernesto e. lai | 2012-06-30 | 2011-12-11 | 107059.2
1127000586 | 79722 | Mohemmed Bin Gerboo EST. | 2012-02-06 | 2012-03-22 | SAMI | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 18642.16 |  |  |  | ernesto e. lai | 2012-07-29 | 2011-12-11 | 13187.84
1227000030 | 79722 | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | JIZA | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 7445 | Yes |  |  | lari carboz | 2012-09-16 | 2012-02-06 | 11614.48
1227000014 | 79722 | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | SLHD | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 90674.95 |  |  |  | ernesto e. lai | 2012-09-16 | 2012-02-06 | 219401.6
1227000033 | 79722 | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | JIZA | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 25755.04 | Yes |  |  | laary | 2012-09-16 | 2012-02-06 | 42248
1227000015 | 79722 | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | SLHD | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 32023.34 |  |  |  | ernesto e. lai | 2012-10-15 | 2012-02-06 | 29906.85
1227000037 | 79722 | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | JIZA | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 44705.12 | Yes |  |  | lari carboz | 2012-10-15 | 2012-02-07 | 95652.16
1227000039 | 79722 | Mohemmed Bin Gerboo EST. | 2012-04-30 | 2012-06-10 | TWAL | vdsl | VDSL2 – 2012 | completed | 2012 objective design issued - lead | 40067.7 |  |  |  | ernesto e. lai | 2012-09-16 | 2012-02-07 | 61390.05
1227000038 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-12 | 2012-04-05 | DAMD | vdsl | VDSL2 – Ran 2012 | completed | 2012 objective design issued - lead | 306012.3392 | DM In Progress |  |  | abenjamin | 2012-09-16 | 2012-03-12 | 277412.324
1227000023 | 78364 | DETCON Saudia Co. (Data_SAD) | 2012-03-05 | 2012-04-18 | ARDH | vdsl | VDSL2 – Ran 2012 | completed | 2012 objective design issued - lead | 29507.712 | CM In Progress |  | Proceed from Email Eyad M. Alkussayer Mon 2012-03-05 7:50 AM | abenjamin | 2012-06-30 | 2012-03-05 | 28567.904
1227000032 | 79738 | ISSA AL ISSA FOR contracting EST. | 2012-11-03 | 2012-12-13 | BAYS | vdsl | VDSL2 – Ran 2012 | completed | 2012 objective design issued - lead | 290154.52 | CM In Progress |  | Jeel AlFursan Est. FOR TRADING &CO by Adel baadullah Completed | jgantonio | 2013-01-26 | 2012-11-03 | 293510.386
1227000053 | 79738 | ISSA AL ISSA FOR contracting EST. | 2012-11-03 | 2012-12-13 | BAYS | vdsl | VDSL2 – Ran 2012 | completed | 2012 objective design issued - lead | 31893.595 | CM In Progress |  | Jeel AlFursan Est. FOR TRADING &CO by Adel baadullah Completed | jgantonio | 2013-07-21 | 2012-11-03 | 32780.32
1127000105 | 81343 | Jeel AlFursan Est. FOR TRADING &CO | 2011-03-20 | 2011-04-30 | SBYA | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 90279.55 | PM In Progress |  |  | agobain | 2011-05-28 | 2011-03-20 | 85472
1127000128 | 76677 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-19 | SAMI | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 430091.05 | DM In Progress |  |  | elai | 2011-10-08 | 2011-03-16 | 283466.25
1127000070 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2011-03-01 | 2011-03-31 | JIZA | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 14798.35 | Yes |  |  | lari carboz | 2011-04-16 | 2011-02-26 | 19945
1127000069 | 76021 | BIG NET NETWORKS EST. FOR TRADING CONTRACTING & ASPHALTING WORKS | 2011-03-01 | 2011-03-31 | JIZA | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 61739.2 | Yes |  |  | lari carboz | 2011-05-14 | 2011-02-26 | 77969.5
1127000149 | 76020 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-14 | 2011-09-28 | ARDH | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 362375.4 | Yes |  |  | alfies benjamin | 2011-12-20 | 2011-08-14 | 458804.4
1127000015 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-03-01 | 2011-03-31 | DAMD | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 169836.55 | Yes |  |  | alfies benjamin | 2011-04-16 | 2011-02-26 | 205589.3
1127000113 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-03-09 | 2011-04-09 | DAMD | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 8992.28 | Yes |  |  | alfies benjamin | 2011-04-16 | 2011-03-09 | 49511.5
1127000130 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-05-18 | 2011-06-30 | JIZA | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 289775.6 | Yes |  |  | lari carboz | 2011-08-15 | 2011-05-18 | 215547.8
1127000089 | 75783 | DETCON Saudia Co. (Data_SAD) | 2011-04-11 | 2011-05-25 | DAMD | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 109185.4 | Yes |  |  | alfies benjamin | 2011-05-21 | 2011-04-11 | 93592.4
1127000139 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-19 | 2011-04-19 | SAMI | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 49555 | Yes |  |  | ernesto e. lai | 2011-05-14 | 2011-03-16 | 52260
1127000159 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-21 | 2011-05-05 | ABAR | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 80724 | Yes |  |  | alfies benjamin | 2011-06-20 | 2011-03-21 | 77620
1127000157 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-21 | 2011-05-05 | ABAR | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 28380 | Yes |  |  | alfies benjamin | 2011-04-16 | 2011-03-21 | 26603
1127000101 | 75745 | Mohemmed Bin Gerboo EST. | 2011-03-01 | 2011-04-01 | JIZA | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 68500.4 | Yes |  |  | lari carboz | 2011-11-01 | 2011-03-01 | 65982
1127000181 | 78364 | DETCON Saudia Co. (Data_SAD) | 2011-11-01 | 2011-12-13 | DAMD | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 265841.8336 | Yes |  |  | alfies benjamin | 2012-01-10 | 2011-11-01 | 231831.1
1127000155 | 78383 | Jeel AlFursan Est. FOR TRADING &CO | 2011-08-14 | 2011-09-28 | SAMI | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 211716.0096 | Yes |  |  | ernesto e. lai | 2011-12-27 | 2011-08-14 | 212647.78
1127000142 | 76677 | Mohemmed Bin Gerboo EST. | 2011-08-14 | 2011-09-28 | ARDH | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 591760 |  | pu price adjustment with bat/pcc |  | alfies benjamin | 2011-12-20 | 2011-08-14 | 249222.53
1127000107 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-03-01 | 2011-04-01 | BAYS | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 27033.34 | Yes |  |  | jomeel g. antonio | 2011-04-16 | 2011-03-01 | 21487.6
1127000175 | 73828 | Jeel AlFursan Est. FOR TRADING &CO | 2011-04-19 | 2011-05-19 | SBYA | vdsl | VDSL2-2011 | completed | 2011 objective design issued | 73606.1 | Yes |  |  | agobain | 2011-05-28 | 2011-04-18 | 56436.6
1898

## dاl
OSP Number | Project | Project Year | Service Order Number | HBU Priority | Reason Code | SO Status | SO Type | Surveyor Status | Reason | OSP Status | SO Remarks | HO Type | CAB | DP | BSW | FDT | FAT | TB | Design Job Type | Design WO ID | Prime WO | Design WO | Job Status | Approved Status | Approved Status Date | RFW Number | Request Origin | RFW Status | Job WorkOrder | Contractor Name | NFTS WO Status | Design Completed Date | Design Forecast Date | NI Forecast Date | Held Order Date | TAG | Design Contractor | RFW Stage | Surveyor | Senior Designer | Designer | Imp HQ Reject Status | Imp HQ Reject Reason | Imp HQ Reject Remarks | Imp Dist. Reject Status | Imp Dist. Reject Reason | Imp Dist. Reject Remarks | WO Assigned Date | Region | District Code | District | ICMS Eng. Work Order | Exchange Code | Account Number | Cabinet Number or Building Name | Switch Code | Analysis Code | First Name | Last Name | Contact # 1 | Contact # 2 | Service Order Type | Customet Address | Customer Address 2 | Owner
220588 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 00422472 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال لا يخص المشترك | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/16/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 08/07/2013 | South | 27 | JIZAN |  | KJRH | 0000000000 | NJRU1206 20121017 |  |  | سم ال اداره - التعليم بمنط قه جازان |  | 0507767438 |  | ET41 | مركز الطوال - جيزان
220596 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 00457117 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 7/17/2012 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | ABAR | 0128440062 | ABAR 022:0004 |  |  | والمه المؤسسة العامة للتدر يب التقني |  | 0507764481 |  | ET15 | ابو عريش - جيزان
251413 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 00511566 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 9/29/2013 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | ARSHJZ00 | 0615917397 | ABAR 005:0004 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIAN DIA New lnstall
220626 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 00632676 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | العميل لا يرد رقم الاتصال خاطئ | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 4/17/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JIZ7A | 0620103802 | JIZA 046:0013 |  |  | شعبه - الدله الجنائي |  | 503101191 |  | ET15 | JZN
163424 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 00654991 | High | 7 | Issue RFW | New | Completed | Covered by Existing Work Order | Completed | ICMS Archive Migration | [7 empty] | Fiber | 1127W000637_45916 | Checked | 1127000637 | Completed | Approved |  | 1000050358 | ICMS | Completed | 1127000637 | Mohemmed Bin Gerboo EST. | Completed | 03/01/2012 | 15/06/2013 |  |  |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Khalid Muaafa | [6 empty] | 24/01/2013 | South | 27 | JIZAN | [9 empty] | 1000050358
251675 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 00734397 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/6/2013 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | NSIMJZAB | 0615917397 | JIZA 030:0149 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIA New Install
251547 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 00946546 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/7/2013 |  |  |  | Khalid Muaafa | [9 empty] | South | 27 | JIZAN |  | SHTIJZAB | 0615917397 | JIZA 062:0076 |  |  | وزارة التربية والتعليم |  | 561933477 |  | DIA New Install
242799 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 00947098 | HIGH | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 103 | 078 | 0 |  |  |  | Secondary | 1327000703 | Checked | 1327000703 | Completed | Approved | 28/11/2013 | 1311273195 | ICMS | Completed |  |  | In Progress | 28/11/2013 |  |  | 7/23/2013 12:00:00 AM |  |  | Design Completed | Jaber Abdaly | Hasan Ghashim | Jaber Abdaly | [6 empty] | 27/11/2013 | South | 27 | JIZAN |  | SBYA | 697121129 | SBYA 103:0078 |  |  | مكتب الإشراف على حلقات | تحفيظ القرآن الكريم | 0505769649 | 0505769649 | ET36 | صبياء
251671 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 00980951 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/12/2013 |  |  |  | Emad Mahdi | [9 empty] | South | 27 | JIZAN |  | BYSHJZAC | 2004080435 | BAYS 032:0009 |  |  | امانة بلدية منطقة جيزات |  | 560022998 |  | توصيل جديد خ. اكيد
220710 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01022046 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | GRIB 011 | 052B | 1 |  |  |  | Secondary | 1327000459 | Checked | 1327000459 | Completed | Approved | 20/08/2013 | 1304168167 | ICMS | Completed |  |  | Completed | 20/08/2013 | 30/05/2013 |  | 12/9/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 16/04/2013 | South | 27 | JIZAN |  | GRIB | 0000000000 | JZNU1159 20121209 |  |  | بى وزارة الصحة - ادارة التموين ال |  | 0558326788 |  | ET35 | ابو عريش - جيزان
220715 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01035514 | High | 7 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 051 | 484A | 000 |  |  |  | Secondary | 1327000699 | Checked | 1327000699 | Completed | Approved | 27/11/2013 | 1311263149 | ICMS | Completed |  |  | In Progress | 27/11/2013 | 30/12/2013 |  | 1/8/2013 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 26/11/2013 | South | 27 | JIZAN |  | ABAR | 0000000000 | 0 |  |  | ام مكتب - هيئة التحقيق والدعاء ال |  | 0557743781 |  | ET15 | ابو عريش - جيزان
251456 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01039894 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/6/2013 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | SHMTJZ00 | 0615917397 | SAMI 001:0017 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIAN DIA New Install
220735 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01059574 | High | 2 | Rejected | Rejected | Rejected | Facility available but needs maintenance | Rejected | الإمكانية متوفرة و الشبكة واصلة على جدار العميل وتحتاج إلى صيانة وقائية على الكبينة 134 للبكسيات 156& 157& 158 | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 1/16/2013 |  |  |  | Ali Zogmah | [8 empty] | 24/11/2013 | South | 27 | JIZAN |  | JIND | 0000000000 | JIND 134:0159 |  |  | رات شركة التقوى لبيع قطع غيار السي |  | 0566667700 |  | ET15 | جيزان
220742 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01067490 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 1/16/2013 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | SBYA | 0000000000 | 0 |  |  | عاوني شركة اياك السعودية ل لتامين ال |  | 0565816661 |  | ET15 | صبياء- جيزان
155075 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01079884 | Medium | 7 | Issue RFW | New | Completed | BSW Work | Completed | [8 empty] | Secondary | 1227W00042 | Checked | 1227W00042 | Completed | Approved | 14/01/2013 | 1212230903 | ICMS | Completed |  |  | Completed | 29/12/2012 | 15/06/2013 |  | 22/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 23/12/2012 | South | 27 | JIZAN |  | SBYA | 2017778148 | 019 |  |  | مدارس رياض صبيا العالمية |  | 0591308175 |  | ED02 | NA
134232 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01094456 |  | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 002 | 0090 | 1 |  |  |  | Secondary | 1327000011 | Checked | 1327000011 | Completed | Approved | 19/03/2013 | 1301151800 | ICMS | Completed |  |  | In Progress | 17/04/2013 | 30/05/2013 |  | 18/07/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/01/2013 | South | 27 | JIZAN |  | ARDA1 | 2015192693 | ARDA1 002:0008 |  | E02 | مؤسسة معدات الجنوب ل لتجارة وا | مقاول | 0502848568 | 0502848568 | ET14 | 2701 | ابو عريش - جيزان
252420 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01157034 |  | 10 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 4/18/2012 | [13 empty] | South | 27 | JIZAN |  | HQU1A | 2001377666 | HQU1A 041:0006 |  |  | بلديه جيزان - المكتب |  | 569996921 |  |  | Jizan
220782 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01158192 | High | 6 | Issue RFW | New | Completed | Secondary Work (DP) | In-Progress | [8 empty] | Secondary |  | Indeterminate |  | In-Progress | In-Progress |  | 1312183850 | ICMS | In-Progress |  |  | Design |  | 30/12/2013 |  | 12/17/2012 |  |  | Design Team | Jaber Abdaly | Hasan Ghashim | Jaber Abdaly | [6 empty] | 18/12/2013 | South | 27 | JIZAN |  | SBY7A | 0000000000 | 0 |  |  | شركة الجميح للمعدات فرع جازان |  | 0558555353 |  | ED02 | صبياء- جيزان
251600 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01176177 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/21/2013 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | SBYAJZ00 | 0615917397 | SBYA 117:0108 |  |  | وزارة التربية والتعليم |  | 549313688 |  | DIA New Install
251446 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01177760 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/3/2013 |  |  |  | Emad Mahdi | [9 empty] | South | 27 | JIZAN |  | BAYS07 | 0615917397 | BAYS 014:0079 |  |  | وزارة التربية والتعليم |  | 505766455 |  | DIAN DIA New Install
251741 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01181000 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/21/2013 |  |  |  | Emad Mahdi | [9 empty] | South | 27 | JIZAN |  | BAYS07 | 0615917397 | BAYS 001:0082 |  |  | وزارة التربية والتعليم |  | 505766455 |  | DIA New Install
251674 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01188439 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/8/2013 |  |  |  | Emad Mahdi | [9 empty] | South | 27 | JIZAN |  | DARBJZ00 | 0615917397 | DARB 010:0068 |  |  | وزارة التربية والتعليم |  | 505766455 |  | DIA New Install
209618 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01188566 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 059 | 013-014 | 0 |  |  |  | Secondary | 1327000331 | Checked | 1327000331 | Completed | Approved | 16/06/2013 | 1306164356 | ICMS | Completed |  |  | Completed | 16/06/2013 | 30/05/2013 |  | 3/3/2013 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 16/06/2013 | South | 27 | JIZAN |  | JIZA | 0628512728 | E59 | 5MBPS_E2E |  | MODA-PRESIDENCY OF CIVIL AVIATION | NA | 0503013493 |  | ET14 | JIZA03_41-JIZA03_41 IP70 | JIZA E59
155078 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01235367 | Medium | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed | [8 empty] | Secondary | 1227W00040 | Unchecked | 1127000637 | Completed | Approved | 26/12/2012 | 1212230901 | ICMS | Completed |  |  | Completed | 26/12/2012 | 15/06/2013 |  | 23/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 23/12/2012 | South | 27 | JIZAN |  | JIZA | 0696688877 | 042 |  |  | القوات البرية | احمد الحربي | 0555550382 |  | ET35 | NA
220819 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01258867 | High | 2 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 1/21/2013 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZA | 0000000000 | JIZA 065:1274 |  |  | شركه مستودع الصفا للادويه |  | 0555755321 |  | ET14 | جيزان
220871 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01339549 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 10/20/2012 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | لعطور الشركه العربيه لتجار ه العود و |  | 0505101134 |  | ET14 | جيزان
252544 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01412830 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 9/17/2012 | [13 empty] | South | 27 | JIZAN |  | UQDA | 0303474269 | MZHR 096:0082 |  |  | الداره العامه للتربي |  | 505797645 |  |  | Jizan
220916 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01425505 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد شبكة على المبنىء العميل .. يحول للتركيب | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/19/2012 |  |  |  | Ali Zogmah | [8 empty] | 01/10/2013 | South | 27 | JIZAN |  | JIZ9A | 0000000000 | 0 |  |  | لعام مؤسسة عبد الخاق سعيد للمقاولت |  | 0566027427 |  | ET14 | جيزان
240365 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01429268 | High | 1 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 034 | 0008 | 000 |  |  |  | Secondary | 1427000026 | Checked | 1427000026 | Completed | Approved | 15/01/2014 | 1401134536 | ICMS | Completed |  |  | Under Assign | 15/01/2014 | 30/12/2013 |  | 13/04/2013 12:00:00 AM |  |  | Design Completed | Emad Mahdi | Hasan Ghashim | Emad Mahdi | [6 empty] | 13/01/2014 | South | 27 | JIZAN |  | JEZAN | 2001288701 | BAYS 032:0009 |  |  | امانه جازان - بلدية العالية |  | 543629402 |  | تأسيس خط هاتف | BAYS 032:0009
240366 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01429268 | High | 2 | Assign | Covered by DWO | Completed | BSW Work | Completed |  | Copper | 034 | 0008 | 000 |  |  |  | Secondary | 1427000026 | Checked | 1427000026 | Completed | Approved | 15/01/2014 | 1401134536 | ICMS | Completed |  |  | Under Assign | 15/01/2014 | 30/12/2013 |  | 14/04/2013 12:00:00 AM |  |  | Design Completed | Emad Mahdi | Hasan Ghashim | Emad Mahdi | [6 empty] | 14/01/2014 | South | 27 | JIZAN |  | JEZAN | 2001288701 | BAYS 032:0009 |  |  | امانه جازان - بلدية العالية |  | 543629402 |  | تأسيس خط هاتف | BAYS 032:0010
240417 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01429268 | High | 7 | Assign | Covered by DWO | Completed | BSW Work | Completed |  | Copper | 034 | 0008 | 000 |  |  |  | Secondary | 1427000026 | Checked | 1427000026 | Completed | Approved | 15/01/2014 | 1401134536 | ICMS | Completed |  |  | Under Assign | 15/01/2014 | 30/12/2013 |  | 13/04/2013 12:00:00 AM |  |  | Design Completed | Emad Mahdi | Hasan Ghashim | Emad Mahdi | [6 empty] | 14/01/2014 | South | 27 | JIZAN |  | JEZAN | 2001288701 | BAYS 032:0009 |  |  | امانه جازان - بلدية العالية |  | 543629402 |  | تأسيس خط هاتف | BAYS 032:0009
220941 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01456244 | High | 7 | Rejected | Rejected | Rejected | Service order belongs to other stage / Wrong reason code/ Wrong region/ District/ City code | Rejected | منطقة غير مخدومة رمز السبب 05 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/17/2012 |  |  |  | Ali Zogmah | [8 empty] | 19/09/2013 | South | 27 | JIZAN |  | JIND | 0000000000 | 0 |  |  | منتاج مؤسسة عبدالله ابراهي م لوتاه ل |  | 0506467943 |  | ED02 | جيزان
252697 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01496698 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 4/29/2013 | [13 empty] | South | 27 | JIZAN |  | JIZA | 2019675850 | JIZA 205 |  |  | مؤسسة علياء التجارية |  | 533348880 |  |  | Jizan
220975 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01500849 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | اتصلت برقم الاتصال وردالمشترك بانه لا يعلم بالموقع وسوف يعطيني رقم شخص اخر عنده الموضوع لم اتلقى اي فاد | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 10/20/2011 |  |  |  | Jaber Abdaly | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | SBYA | 0303809163 | SBYA 020:0130 |  |  | ار ه وزارة التربية والتعل يم بنين ا |  | 0555781788 |  | ET15 | صبياء- جيزان
209602 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01565776 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على البكسية 0124 كبينة 001 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 22/06/2013 | South | 27 | JIZAN |  | TUWA | 0652779859 | 001:0124 | 2MBPS_E2E |  | JIZAN MUNICIPALITY | NA | 0547842341 |  | ET14 | JIZAN-JIZAN IP209 | TUWAL M 01
221004 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01571297 | High | 7 | Rejected | Rejected | Rejected | Facility available but needs maintenance | Rejected | يوجد امكانية في البكسية .. وحسب افادة العميل يوجد عندة خدمة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/22/2011 |  |  |  | Ali Zogmah | [8 empty] | 29/09/2013 | South | 27 | JIZAN |  | JIZ9A | 0657329835 | JIZA 092:0019 |  |  | جامعة جازان |  | 0545999458 |  | ET14 | جيزان
252426 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01591091 |  | 13 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 4/22/2012 | [13 empty] | South | 27 | JIZAN |  | SBYA | 0303809163 | SBYA 022:0110 |  |  | وزارة التربية والتعل |  | 505771816 |  |  | Jizan
221060 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01667365 | High | 6 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد سلك خدمة وامكانية في البكسية 067+070B في الكبينة 069 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 1/22/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 15/08/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | مستشفى صبيا العام |  | 0555782175 |  | ET14 | جيزان
221062 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01668854 | High | 2 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 058 | 012 | 0 |  |  |  | Secondary | 1327000454 | Unchecked | 1327000438 | Completed | Approved | 18/08/2013 | 1308148020 | ICMS | Completed |  |  | Completed | 18/08/2013 | 30/05/2013 |  | 1/22/2013 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 14/08/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | JIZA 058:0022 |  |  | وزاره الصحه - مستشفى جيزان |  | 0555782175 |  | ET14 | جيزان
252212 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01743439 |  | 12 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 7/25/2011 | [13 empty] | South | 27 | JIZAN |  | JIZ4C | 0282119870 | JIZA 035:0111 |  |  | شركه - تاجير اللت وت |  | 509311171 |  |  | Jizan
221113 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01746241 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | العميل لا يرد العميل جواله مغلق العميل جواله مغلق | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/25/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JIZDA | 0000000000 | 0 |  |  | ادارة الانظمة |  | 0595240045 |  | ED02 | جيزان
209619 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01762149 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية لدي العميل ويوجد امكانية في البكسية رقم 009 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | Ali Zogmah | [8 empty] | 15/09/2013 | South | 27 | JIZAN |  | JIZA | 0196663738 | 059:0009 | 3MBPS_E2E |  | SAMIS | - GID | 0505453424 |  | ET14 | JIZAN-JIZAN IP167 | JIZA E59
221134 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01777377 | High | 7 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | العميل لا يرغب بالخدمة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/23/2012 |  |  |  | Ali Zogmah | [8 empty] | 06/10/2013 | South | 27 | JIZAN |  | JIZ9A | 0000000000 | 0 |  |  | العا شركة الفوزان للتجارة والمقاولت |  | 0507647977 |  | ED02 | جيزان
152086 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01813639 |  | 7 | Rejected | Rejected | Rejected | Transfer to Planning to issue planning memo | Rejected | موقع العميل خارج نطاق الشبكة يحول للتخطيط لعمل الدراسة اللازمة لتوصيل الخدمة للعميل | [9 empty] | Indeterminate | [13 empty] | 9/25/2012 07:27:10 |  |  |  | ICMS027 (Jizan) | [8 empty] | 17/10/2012 | South | 27 | JIZAN |  | JIZA | 0608738835 | JIZA 044:0123 | 044:0123 | E01 | رطه | وزاره الداخليه - الش | 0505296070 | 0505771005 | ET15 | جيزان | 0 00 0
252548 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01813639 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 9/25/2012 | [13 empty] | South | 27 | JIZAN |  | JIZA | 0608738835 | JIZA 044:0123 |  |  | وزاره الداخليه - الش |  | 505296070 |  |  | Jizan
209611 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01819068 | High | 6 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 007 | 014 | 3 |  |  |  | Secondary | 1327000651 | Checked | 1327000651 | Completed | Approved | 05/11/2013 | 1310312241 | ICMS | Completed |  |  | In Progress | 05/11/2013 | 30/12/2013 | 28/02/2014 | 3/3/2013 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 31/10/2013 | South | 27 | JIZAN |  | DEHM | 0649440751 | 007:0145 | 2MBPS_E2E |  | JIZAN MUNICIPALITY | NA | 0557799129 |  | ET14 | JIZAN-JIZAN IP214 | DEHEMAH
251517 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01819068 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/6/2013 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | DYHMJZAA | 2004080435 | DEHM 007:0145 |  |  | امانة بلدية منطقة جيزات |  | 557799129 |  | توصيل جديد خ. اكيد
221172 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01824829 | High | 2 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | جوال العميل مغلق جوال العميل مغلق جوال العميل مغلق | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 4/24/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JIZA | 0175363335 | JIZA 004:0012 |  |  | عام و مدير عام الشئون الما لية/ديوان |  | 0506767807 |  | ET15 | جيزان
221201 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01857343 | High | 6 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على البكسية 017B وسلك الخدمة 1-2 ويمكن التركيب للمشترك | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/26/2011 |  |  |  | ICMS027 (Jizan) | [8 empty] | 02/09/2013 | South | 27 | JIZAN | 1227000064 | SBYA | 0303804552 | SBYA 019:0017 |  |  | بصبي مدرسه - صلهبه البتدا ئيه للبني |  | 0504577556 |  | ET35 | صبياء- جيزان
221205 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01863423 | High | 2 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 082 | 021-022+026 | 0 |  |  |  | Secondary | 1327000386 | Checked | 1327000386 | Completed | Approved | 14/07/2013 | 1307076092 | ICMS | Completed |  |  | Completed | 14/07/2013 | 30/05/2013 |  | 11/25/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 07/07/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | JIZA 082:0022 |  |  | طالشركه - المتحده للب يع بالتقس |  | 0501234413 |  | ET14 | جيزان
221236 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01908271 | VIP | 7 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | تم التواصل مع المنسق وأفاد بأنه لا يوجد طلب للموقع | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 7/29/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 08/07/2013 | South | 27 | JIZAN |  | BRDR | 0303469443 | BRDR 006:0007 |  |  | مباحث - منطقة جازان |  | 0505272801 |  | ET15 | مركز الطوال - جيزان
240326 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01911521 | high | 1 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | رقم الاتصال لا يخص المشترك | [9 empty] | Indeterminate | [13 empty] | 9/12/2013 12:00:00 AM |  |  |  | Mahdy Salami | [8 empty] | 22/10/2013 | South | 27 | JIZAN |  | MWSM | 0601053578 | MWSM 001:0110 |  |  | وزارة الصحة |  | 554408015 |  | EBU | MWSM 001:0110
251884 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01911521 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 5/28/2013 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | BADRDN153 | 0601053578 | MWSM 001:0110 |  |  | مساعد مدير عام الدفاع المدني للشئوون الفنية |  | 966554408015 |  | توصيل جديد خ. اكيد
209614 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01915060 | High | 6 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | الجوال مفصول عن الخدمة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | Mahdy Salami | [8 empty] | 01/10/2013 | South | 27 | JIZAN |  | SLHD | 0626404480 | 010:0017 | 4MBPS_E2E |  | MINISTRY OF HEALTH | NA | 0590010468 |  | ET14 | JIZAN-RIYADH DIA42 | SUQ AI AHAD
209616 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01937936 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 020 | 003+002 | 000 |  |  |  | Secondary | 1327000330 | Checked | 1327000330 | Completed | Approved | 16/06/2013 | 1306154315 | ICMS | Completed |  |  | Completed | 16/06/2013 | 30/05/2013 |  | 3/3/2013 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Mahdy Salami | [6 empty] | 15/06/2013 | South | 27 | JIZAN |  | DMAD | 0100685563 | 020:0003 | 6MBPS_E2E |  | MINISTRY OF HEALTH | NA | 0590010468 |  | ET14 | JIZAN-JIZAN IP187 | DAMAD
221256 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01938687 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية تركيب للمشترك على البكسية 001-012+015 كبينة 059 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/17/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 09/07/2013 | South | 27 | JIZAN |  | JIZFA | 0000000000 | 0 |  |  | مباحث - منطقة جازان |  | 0505272801 |  | ET15 | جيزان
252706 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01959033 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 5/4/2013 | [13 empty] | South | 27 | JIZAN |  | ABAR | 2019729268 | ABAR 007:0089 |  |  | شركه - العزيزيه بنده |  | 503787100 |  |  | Jizan
221269 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01959402 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد سلك خدمة وامكانية في البكسية 067+070B في الكبينة 069 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 7/28/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 14/08/2013 | South | 27 | JIZAN |  | JIZBB | 0303200762 | JIZA 200 |  |  | بى وزارة الصحة - ادارة التموين ال |  | 0555782175 |  | ET14 | جيزان
252508 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 01959402 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 7/28/2012 | [13 empty] | South | 27 | JIZAN |  | JIZA | 0303200762 | JIZA 069:0070 |  |  | وزارة الصحة - ادارة |  | 555782175 |  |  | Jizan
252792 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02029355 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/3/2013 | [13 empty] | South | 27 | JIZAN |  | JZN | 2022647299 | SBYA 060:0068 |  |  | شركة دانيا للاغذية ا |  | 555585538 |  |  | Jizan
221338 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02085820 | High | 2 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال غير صحيح | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 2/2/2013 |  |  |  | Ali Zogmah | [8 empty] | 28/01/2014 | South | 27 | JIZAN |  | SWIS | 0000000000 | SWIS 105 |  |  | وزاره الداخليه - الش |  | 503101191 |  | ET15 | JZN
221342 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02088327 | High | 7 | Rejected | Rejected | Rejected | Covered by FTTH CAPEX Project | Rejected | توجد كبينة داخلية تخدمة موقع العميل بالإضافة إلى أنه تم خدمتهم بفايبر ONT | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/6/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 07/07/2013 | South | 27 | JIZAN |  | JIZA | 0303541497 | JIZA 022:0081 |  |  | هوزاره الداخليه - الح وال المدن |  | 0507769245 |  | ET15 | جيزان
209617 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02092117 | High | 6 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على الكبينة 005 بكسية 0047 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 30/06/2013 | South | 27 | JIZAN |  | EDBE | 0101797683 | 005:0047 | 2MBPS_E2E |  | JIZAN MUNICIPALITY | NA | 0501259928 |  | ET14 | JIZAN-JIZAN IP217 | AYDABI MSAN 32
251466 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02092117 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 2/19/2013 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | EDABJZAE | 2004080435 | EDBE2 005:0047 |  |  | امانة بلدية منطقة جيزات |  | 501259928 |  | توصيل جديد خ. اكيد
221363 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02114119 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | KSHB 069 | 003 | 1-2 & 3-4 |  |  |  | Secondary | 1327000458 | Checked | 1327000458 | Completed | Approved | 20/08/2013 | 1304168164 | ICMS | Completed |  |  | Completed | 20/08/2013 | 30/05/2013 |  | 12/29/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 16/04/2013 | South | 27 | JIZAN |  | KSHB | 0000000000 | JZNU1159 20121231 |  |  | همركز - الرعايه الولي ه بالخشاب |  | 0558326788 |  | ET35 | ابو عريش - جيزان
209608 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02155268 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | امكانية التركيب متوفرة على البكسية 079 كبينة 024 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 22/06/2013 | South | 27 | JIZAN |  | SBYA | 0101837123 | 024:0086 | 1MBPS_E2E |  | AL EMEIS HOSPITAL | NA | 0556555972 |  | ET14 | JEDDAH-JIZAN DIA34 | SABYA
221405 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02165727 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | جوال العميل مغلق جوال العميل مغلق جوال العميل مغلق | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/7/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JIZ7E | 2012174899 | NJRU1206 20121216 |  |  | نات مدرسه - المقاريه الب تدائيه لل |  | 0541453468 |  | ET36 | جيزان
221411 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02170663 | High | 2 | Rejected | Rejected | Rejected | Transfer to Planning to issue planning memo | Rejected | لا يوجد امكانية بالشبكه الحالية الموقع يحتاج امسان جديد | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 12/31/2011 |  |  |  | Jaber Abdaly | [8 empty] | 29/10/2013 | South | 27 | JIZAN |  | ABA4 | 0303200762 | ABA4 076:0034 |  |  | مستشفى - ابوعريش ال جديد |  | 0555783175 |  | ET15 | ابو عريش - جيزان
221424 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02188303 | High | 8 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | تمت خدمة العميل | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/1/2011 |  |  |  | ICMS027 (Jizan) | [8 empty] | 18/05/2013 | South | 27 | JIZAN |  | FRSN | 0303469443 | FRSN 006:0015 |  |  | مباحث - منطقة جازان |  | 0564082201 |  | ET35 | JZN
221433 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02197460 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 1/29/2013 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | ABAR | 0000000000 | 0 |  |  | بجاز الداره العامه للتربي ه والتعلي |  | 0507597824 |  | ET14 | ابو عريش - جيزان
221474 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02241590 | High | 7 | Rejected | Rejected | Rejected | Transfer to Planning to issue planning memo | Rejected | لا يوجد امكانية بالكيبل | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 2/3/2013 |  |  |  | Jaber Abdaly | [8 empty] | 22/12/2013 | South | 27 | JIZAN |  | SBY7C | 0000000000 | 0 |  |  | ودة شركة فال العربية الق ابضة المح |  | 0566542064 |  | ED02 | صبياء- جيزان
221480 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02247993 | High | 2 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 075 | 022-023+024 | 0 |  |  |  | Secondary | 1327000378 | Checked | 1327000378 | Completed | Approved | 08/07/2013 | 1307076146 | ICMS | Completed |  |  | Completed | 08/07/2013 | 30/05/2013 |  | 2/3/2013 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 07/07/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | JIZA 075:0021 |  |  | اداره - الحوال المدن يه بجازان |  | 0507769245 |  | ET15 | جيزان
221481 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02249678 | High | 2 | Rejected | Rejected | Rejected | Covered by FTTH CAPEX Project | Rejected | تم خدمة الموقع بفايبر ONT | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 2/3/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 07/07/2013 | South | 27 | JIZAN |  | SBYA | 0000000000 | SBYA 019:0013 |  |  | هوزاره الداخليه - الح وال المدي |  | 0507769245 |  | ET15 | صبياء- جيزان
209615 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02290920 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | العميل مخدوم بفايبر رقم امر العمل 1127000078 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 16/06/2013 | South | 27 | JIZAN |  | DMAD | 0649168830 | 020:0013 | 5MBPS_E2E |  | MINISTRY OF INTERIOR-JIZAN EMIRATES | NA | 0505614100 |  | ET14 | DMAD19-DMAD19 IP27 | DAMAD
221551 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02344510 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 012 | 030 | 000 |  |  |  | Secondary | 1427000022 | Checked | 1427000022 | Completed | Approved | 14/01/2014 | 1401134547 | ICMS | Completed |  |  | Under Assign | 14/01/2014 | 30/12/2013 |  | 11/4/2012 |  |  | Design Completed | Emad Mahdi | Hasan Ghashim | Emad Mahdi | [6 empty] | 13/01/2014 | South | 27 | JIZAN |  | ALY1M | 0000000000 | 0 |  |  | اداره - تعليم صبياء |  | 0561703434 |  | ET14 | بيش - جيزان
252567 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02353068 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/13/2012 | [13 empty] | South | 27 | JIZAN |  | JIZA | 2016666907 | JIZA 204:0023 |  |  | الحكير |  | 506789994 |  |  | Jizan
221564 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02353260 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 002 | 092 | 1 |  |  |  | Secondary | 1327000486 | Checked | 1327000486 | Completed | Approved | 29/09/2013 | 1309240555 | ICMS | Completed |  |  | Completed | 29/09/2013 | 30/05/2013 |  | 11/4/2012 |  |  | Design Completed | Emad Mahdi | Hasan Ghashim | Emad Mahdi | [6 empty] | 24/09/2013 | South | 27 | JIZAN |  | BAYS | 0000000000 | 0 |  |  | بجاز الداره العامه للتربي ه والتعلي |  | 0508336799 |  | ET14 | بيش - جيزان
221588 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02370353 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 151 | 006 | 1 |  |  |  | Secondary | 1327000697 | Checked | 1327000697 | Completed | Approved | 28/11/2013 | 1311253069 | ICMS | Completed |  |  | In Progress | 28/11/2013 | 30/12/2013 |  | 12/10/2012 |  |  | Design Completed | Ali Zogmah | Hasan Ghashim | Ali Zogmah | [6 empty] | 25/11/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | دوده الشركه الساسيه للكتر ونيات الم |  | 0504654464 |  | ET14 | جيزان
221621 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02395364 | High | 1 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية تركيب للمشترك في البكسية رقم 033 في الكبينة 005 ويوجد سلك خدمة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 2/9/2013 |  |  |  | Mahdy Salami | [8 empty] | 12/09/2013 | South | 27 | JIZAN |  | SLHD | 0000000000 | SLHD 005:0031 |  |  | مؤسسة الوليف التجاري |  | 553031981 |  | ED02 | JZN
221639 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02414647 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 062 | 156+167B | 6 |  |  |  | Secondary | 1327000528 | Unchecked | 1327000498 | Completed | Approved | 22/10/2013 | 1310221760 | ICMS | Completed |  |  | Completed | 22/10/2013 | 30/05/2013 |  | 11/18/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 22/10/2013 | South | 27 | JIZAN |  | SAMI | 0000000000 | 0 |  |  | مكتب - شركه بن زقر |  | 0500647008 |  | ET14 | صامطه- جيزان
221658 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02443087 | High | 2 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 058 | 011 | 0 |  |  |  | Secondary | 1327000438 | Checked | 1327000438 | Completed | Approved | 01/08/2013 | 1307317737 | ICMS | Completed |  |  | Completed | 01/08/2013 | 30/05/2013 |  | 7/14/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 31/07/2013 | South | 27 | JIZAN |  | JIZA | 0303200762 | JIZA 058:0022 |  |  | الول وزاره الصحه - مكتب م ديرالرعاي |  | 0509544424 |  | ET15 | جيزان
209606 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02443191 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 019 | 016B | 0 |  |  |  | Secondary | 1327000362 | Checked | 1327000362 | Completed | Approved | 01/07/2013 | 1306265467 | ICMS | Completed |  |  | Completed | 01/07/2013 | 30/05/2013 |  | 3/3/2013 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 26/06/2013 | South | 27 | JIZAN |  | SBYA | 0628371393 | 019:0014 | 6MBPS_E2E |  | MINISTRY OF AGRICULTURE | NA | 0552283888 |  | ET14 | JIZAN-RIYADH DIA26 | SABYA
221694 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02472454 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية تركيب للمشترك على الكبينة 001 البكسية 0166 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/14/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 19/08/2013 | South | 27 | JIZAN |  | FRSN | 0000000000 | JZNU1159 20121117 |  |  | طقة الدارة العامة لتعليم البنين بم |  | 0562470033 |  | ET35 | فرسان - جيزان
155085 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02483203 | Medium | 7 | Issue RFW | New | Completed | BSW Work | Completed | [8 empty] | Secondary | 1227W00036 | Checked | 1227W00036 | Completed | Approved | 14/01/2013 | 1212250971 | ICMS | Completed |  |  | Completed | 25/12/2012 | 15/06/2013 |  | 24/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 25/12/2012 | South | 27 | JIZAN |  | SBYA | 0303200762 | 101 |  |  | وزارة الصحة- ادارة التموين الطبي |  | 0556655360 | 0557600578 | ET36 | na
221717 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02490499 | High | 6 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | جوال العميل مغلق جوال العميل مغلق جوال العميل مغلق | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/15/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | UQDA | 0000000000 | 0 |  |  | نات مدرسه - الدغارير الب تدائيه لل |  | 0565787680 |  | ED02 | جيزان
221726 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02494904 | High | 2 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على البكسية 0138+0139 كبينة 008 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/14/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 08/07/2013 | South | 27 | JIZAN |  | ARDA4 | 0000000000 | ARDA4 008:0138 |  |  | وزارة الداخلية - سلح الحدود |  | 0506767807 |  | ET15 | ابو عريش - جيزان
252346 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02540050 |  | 5 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 2/15/2012 | [13 empty] | South | 27 | JIZAN |  | JZN | 0305198994 | GKHR 112:0006 |  |  | وزارة التربية والتعل |  | 555761667 |  |  | Jizan
221798 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02568255 | High | 7 | Rejected | Rejected | Rejected | Transfer to Planning to issue planning memo | Rejected | موقع العميل يحتاج الى كبينة امسان جديدة وعليه يتم تحويل الطلب للتخطيط لعمل الخطة اللازمة لذلك | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 6/17/2012 |  |  |  | Emad Mahdi | [8 empty] | 19/09/2013 | South | 27 | JIZAN |  | BAYS | 0303506217 | BAYS 009:0231 |  |  | قة جا الشركة السعودية للكه رباء - من |  | 0506851866 |  | ET15 | بيش - جيزان
221821 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02599560 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 102 | 060 | 5-6 |  |  |  | Secondary | 1327000707 | Checked | 1327000707 | Completed | Approved | 10/12/2013 | 1312013247 | ICMS | Completed |  |  | Completed | 10/12/2013 | 30/12/2013 |  | 5/16/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 01/12/2013 | South | 27 | JIZAN |  | JIZEA | 0303548742 | WSLY 102:0060 |  |  | ين مدرسه - الواصلى البت دائيه للب |  | 0505768009 |  | ET41 | ابو عريش - جيزان
221857 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02634794 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 034 | 022 | 1 |  |  |  | Secondary | 1327000419 | Checked | 1327000419 | Completed | Approved | 18/08/2013 | 1307257410 | ICMS | Completed |  |  | In Progress | 18/08/2013 | 30/05/2013 |  | 11/16/2011 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Emad Mahdi | [6 empty] | 25/07/2013 | South | 27 | JIZAN |  | BAYS | 0303200762 | BAYS 007 |  |  | بى وزارة الصحة - ادارة التموين ال |  | 0555310693 |  | ET35 | بيش - جيزان
155030 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02637428 | Medium | 7 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | يتم ايقاف الطلب حسب رغبة العميل | [9 empty] | Indeterminate | [11 empty] | 15/06/2013 |  | 08/12/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 13/01/2013 | South | 27 | JIZAN |  | JIZA | 2017091029 | 061 |  |  | ALINMA BANK |  | 0559898994 |  | ET14 | NA
221862 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02641183 | High | 6 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على جدار العميل ويوجد لدية بكسية جدارية وبها امكانية التركيب رقم 041 مم كبينة رقم 044 .. يحول للتركيبات | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 2/3/2013 |  |  |  | Ali Zogmah | [8 empty] | 14/01/2014 | South | 27 | JIZAN |  | JIZA | 0000000000 | RYDU5340 20130210 |  |  | داري وزاره الداخليه - فرع المباحث ا |  | 0503124485 |  | ET34 | جيزان
221866 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02644865 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | الرقم مفصول | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 3/5/2012 |  |  |  | Jaber Abdaly | [8 empty] | 16/12/2013 | South | 27 | JIZAN |  | ABABA | 0645359127 | ARDA2 003:0015 |  |  | والد وزارة - الشئون السلم ية والوقا |  | 0599114451 |  | ET14 | ابو عريش - جيزان
240295 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02665941 | high | 6 | Rejected | Rejected | Rejected | Transfer to Planning to issue planning memo | Rejected | الطلب لا يخص المنطقة الطلب يخص منطقة نجران | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 9/12/2013 12:00:00 AM |  |  |  | ICMS027 (Jizan) | [8 empty] | 12/01/2014 | South | 27 | JIZAN |  | QBMF | 0615917397 | QBMF 001:0012 |  |  | وزارة التربية والتعليم |  | 505820657 |  | EBU | QBMF 001:0012
251792 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02686774 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 9/17/2013 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | BADRDN52 | 0615917397 | MWSM 001:0019 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIA New Install
231019 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02694266 | High | 7 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | لا يرغب بالخدمة | [9 empty] | Indeterminate | [11 empty] | 21/06/2013 |  | 3/2/2013 12:00:00 AM |  |  |  | Ali Zogmah | [8 empty] | 29/09/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | JIZA 082:0024 |  |  | EID-OMER - |  | 507930699 |  | NA | JIZAN
251780 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02694266 |  | 2 | Under Reject | Rejecting | In Progress | In Progress | In-Progress | تم الاتصال على العميل اكثر من مرة جوال العميل مغلق تم الاتصال على العميل اكثر من مرة جوال العميل مغلق | Copper | [8 empty] | Indeterminate | [13 empty] | 3/2/2013 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | BADRDN39 | 0649556032 | JIZA 082:0024 |  |  | الشركة المتحدة |  | 507930699 |  | توصيل جديد خ. اكيد
221929 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02756827 | High | 6 | Rejected | Rejected | Rejected | Covered by FTTH network, needs TB installation | Rejected | يوجد على موقع العميل علبة الياف بصرية FTTH بياناتها كالتالي : SHTIJZU 0516 FTTH/FDT 042 ODF5/PORT 5-19 SP5/PORT 5-19 TB 036 يرجى تعديل بطاقة خط العميل من شبكة نحاسية لشبكة الـ FTTH | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 8/25/2012 |  |  |  | Khalid Muaafa | [8 empty] | 29/09/2013 | South | 27 | JIZAN |  | JIZA | 2015579660 | JIZA 042:0017 |  |  | مؤسسة سناس للتجارة والمقاولت |  | 0504805611 |  | ET14 | جيزان
221935 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02769182 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 9/5/2012 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | SWIS | 0303506217 | SWIS 105 |  |  | قة جا الشركة السعودية للكه رباء - من |  | 0509574550 |  | ET15 | جيزان
221993 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02831473 | High | 2 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | العميل لا يرغب | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/25/2012 |  |  |  | Ali Zogmah | [8 empty] | 06/10/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | JIZA 065:1274 |  |  | شركة الشايع الدوليه للتجاره |  | 0596666963 |  | ET15 | جيزان
222001 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02846116 | High | 6 | Issue RFW | New | Completed | Secondary Work (DP) | Completed | المشترك لا يرد | Copper | 021 | 022 | 9-10 |  |  |  | Secondary | 1427000027 | Indeterminate | 1327000534 | Completed | Approved | 15/01/2014 | 1310221730 | ICMS | Completed |  |  | In Progress | 15/01/2014 | 30/05/2013 |  | 2/4/2013 |  |  | Design Completed | Jaber Abdaly | Hasan Ghashim | Mahdy Salami | [6 empty] | 22/10/2013 | South | 27 | JIZAN |  | ABAR | 0000000000 | 0 |  |  | لده شركة عبدالله بن محمد باجبير وا |  | 0505699759 |  | ET14 | ابو عريش - جيزان
222071 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02919438 | High | 6 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | العميل لايرغب بالخدمة | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 11/26/2012 |  |  |  | Ali Zogmah | [8 empty] | 14/01/2014 | South | 27 | JIZAN |  | JIZFC | 0000000000 | 0 |  |  | شركه الشقيق للمياه و الكهرباء |  | 0555328875 |  | ED02 | جيزان
222080 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02924822 | High | 6 | Rejected | Rejected | Rejected | Covered by FTTH CAPEX Project | Rejected | العميل مخدوم بفايبر FTTH FDT 043, ODF 10, P 21-24,SP 10 P 21-24 ,TB 037 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/28/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 09/07/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | مباحث - منطقة جازان |  | 0503124485 |  | ET15 | جيزان
209620 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02930836 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | In-Progress | [8 empty] | Secondary |  | Indeterminate |  | In-Progress | In-Progress |  | 1311142791 | ICMS | In-Progress |  |  | Design |  | 30/12/2013 |  | 3/3/2013 |  |  | Design Team | Jaber Abdaly | Hasan Ghashim | Jaber Abdaly | [6 empty] | 14/11/2013 | South | 27 | JIZAN |  | RYAN | 0100806478 | 074:0009 | 256KBPS_E2E |  | MINISTRY OF PTT- POST | NA | 0500668339 |  | ET14 | JIZAN-JIZAN IP147 | RYAN
251608 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02930836 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/19/2012 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | RYANJZAE | 0642366351 | RYAN 074:0009 |  |  | مؤسسة البريد السعودي |  | 500668339 |  | توصيل جديد خ. اكيد
209605 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02950314 | High | 6 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | افاد المشترك بعدم وجود طلب للشركة بهذا الموقع | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | Jaber Abdaly | [8 empty] | 01/10/2013 | South | 27 | JIZAN |  | ABAR | 0100685563 | 062:0075 | 4MBPS_E2E |  | AL RAJHI ISP | NA | 0507087202 |  | ET14 | JIZAN-RIYADH DIA55 | ABU ARISH
252461 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02955809 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 5/23/2012 | [13 empty] | South | 27 | JIZAN |  | ASLH | 2014244797 | ASLH 012:0024 |  |  | مؤسسة عيد يحي مفرح ا |  | 503332906 |  |  | Jizan
231027 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02959619 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال خاطئ | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 3/13/2013 12:00:00 AM |  |  |  | Emad Mahdi | [8 empty] | 18/11/2013 | South | 27 | JIZAN |  | BAYS | 0000000000 | BAYS 029:0088 |  |  | ALHSEN-MOHAMMD - |  | 507087202 |  | NA | JIZAN
222138 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02975715 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed | [8 empty] | Secondary | 1327000385 | Checked | 1327000385 | Completed | Approved | 28/07/2013 | 1307086249 | ICMS | Completed |  |  | Completed | 28/07/2013 | 30/05/2013 |  | 5/23/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Mahdy Salami | [6 empty] | 08/07/2013 | South | 27 | JIZAN |  | WLAN | 0303200762 | WLAN 016:0149 |  |  | بى وزارة الصحة - ادارة التموين ال |  | 0509544424 |  | ET35 | مركز الطوال - جيزان
222139 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 02976569 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 005 | 1-2 |  |  |  | Secondary | 1327000221 | Checked | 1327000221 | Completed | Approved | 17/04/2013 | 1304137761 | ICMS | Completed |  |  | Completed | 17/04/2013 | 30/05/2013 |  | 5/23/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Mahdy Salami | [6 empty] | 13/04/2013 | South | 27 | JIZAN |  | KJRH | 0303200762 | KJRH 004:0007 |  |  | مركز - الرعايه الولي ه بالطوال |  | 0509544424 |  | ET36 | مركز الطوال - جيزان
222182 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03006218 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الإمكانية متوفرة على البكسية 072 سلك خدمة 1-2 على الكبينة 109 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 2/22/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 29/08/2013 | South | 27 | JIZAN |  | SBYA | 0303882871 | 0 |  |  | اداره - تعليم محافظه صبيا |  | 0555770861 |  | ED02 | صبياء- جيزان
62011 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03031164 |  | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 002 | 011-012 | 1 |  |  |  | Secondary | 1327000013 | Checked | 1327000013 | Completed | Approved | 19/03/2013 | 1301161847 | ICMS | Completed |  |  | Completed | 19/01/2013 | 30/05/2013 |  | 2/29/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 16/01/2013 | South | 27 | JIZAN |  | SBYA | 0303474269 | SBYA 007:0228 |  | E02 | وزارة التربيه والتعل يم بنات ا | اره ا | 0553018361 | 0553018361 | ET14 | 2706 | صبياء- جيزان
251752 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03044307 |  | 2 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 6/30/2013 |  |  |  | Khalid Muaafa | [9 empty] | South | 27 | JIZAN |  | BADRDN09 | 0185722309 | JIZA 062:0076 |  |  | وكالة الوزارة للشئؤون الاجتماعية |  | 966569939123 |  | توصيل جديد خ. اكيد
222245 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03081012 | High | 6 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على JIZA 080:0026 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/27/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 05/06/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | ولت مؤسسة محمد عبدالرحمن الملاللمق |  | 0561144167 |  | ET14 | جيزان
222247 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03084873 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed | العميل لا يرد | Copper | RAN015 | 006+003-002 | 2 |  |  |  | Secondary | 1327000708 | Checked | 1327000708 | Completed | Approved | 09/12/2013 | 1312013271 | ICMS | Completed |  |  | Completed | 09/12/2013 | 30/05/2013 |  | 3/3/2012 |  |  | Design Completed | Ali Zogmah | Hasan Ghashim | Ali Zogmah | [6 empty] | 01/12/2013 | South | 27 | JIZAN |  | JIZ7A | 0128440062 | JIZA 046:0050 |  |  | والمه المؤسسة العامة للتدر يب التقني |  | 0598863136 |  | ET14 | جيزان
222287 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03124661 | VIP | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 062 | 156+167 | 11-12 |  |  |  | Secondary | 1327000498 | Checked | 1327000498 | Completed | Approved | 01/10/2013 | 1309300850 | ICMS | Completed |  |  | Completed | 01/10/2013 | 30/05/2013 |  | 8/29/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 30/09/2013 | South | 27 | JIZAN |  | SAMI | 2015652643 | SAMI 062:0176 |  |  | شركه - بن زقر |  | 0544414401 |  | ET15 | صامطه- جيزان
222305 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03137702 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 11/28/2012 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | SBYA | 0000000000 | 0 |  |  | لت موسسه - المبطى للتجا ره والمقا |  | 0500650587 |  | ET14 | صبياء- جيزان
222317 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03143404 | High | 7 | Rejected | Rejected | Rejected | Transfer to Planning to issue planning memo | Rejected | موقع العميل يقع خارج نطاق الشبكة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 8/29/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 08/07/2013 | South | 27 | JIZAN |  | KHSL | 0303551301 | KHSL 001:0011 |  |  | امارة منطقة جازان |  | 0552334447 |  | ET35 | سوق الحد- جيزان
222370 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03192588 | High | 2 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | لايوجد اشكالية في شبكة البرايمري ويمكن التركيب للمشترك على البكسية 0139 كبينة 004 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 1/30/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 09/07/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | JIZA 004:0139 |  |  | وزارة الداخلية - سلح الحدود |  | 0506767807 |  | ET15 | جيزان
209612 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03195770 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية تركيب للمشترك على الكبينة 002 بكسية 0093 سلك خدمة رقم 1&2 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 15/06/2013 | South | 27 | JIZAN |  | BAYS | 0649168830 | 014:0089 | 2MBPS_E2E |  | MINISTRY OF EDUCATION | NA | 0505766455 |  | ET14 | BAYS07-BAYS07 IP39 | BAYSH
222377 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03203912 | High | 7 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 015 | 031B | 1-2 |  |  |  | Secondary | 1327000657 | Checked | 1327000657 | Completed | Approved | 05/11/2013 | 1311042310 | ICMS | Completed |  |  | In Progress | 05/11/2013 | 30/12/2013 |  | 2/26/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 04/11/2013 | South | 27 | JIZAN |  | MKTR | 0303443657 | MKTR 015:0032 |  |  | طقة الدارة العامة لتعليم البنين بم |  | 0544410888 |  | ET41 | سوق الحد- جيزان
252359 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03203912 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 2/26/2012 | [13 empty] | South | 27 | JIZAN |  | MKTR | 0303443657 | MKTR 015:0011 |  |  | الدارة العامة لتعليم |  | 544410888 |  |  | Jizan
222378 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03205639 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | In-Progress | [8 empty] | Secondary |  | Indeterminate |  | In-Progress | In-Progress |  | 1312183851 | ICMS | In-Progress |  |  | Design |  | 30/12/2013 |  | 2/26/2012 |  |  | Design Team | Jaber Abdaly | Hasan Ghashim | Jaber Abdaly | [6 empty] | 18/12/2013 | South | 27 | JIZAN |  | SBYA | 0303807411 | SBYA 022:0108 |  |  | مدرسه - صبياء المتوس طه |  | 0504892300 |  | ET14 | صبياء- جيزان
222398 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03238430 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | العميل لا يرد على الاتصال بالإضافة إلى أن بيانات الشبكة خاطئة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 2/27/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 11/07/2013 | South | 27 | JIZAN |  | JIZA | 0620258571 | JIZA 208 |  |  | لمدنى وزاره الداخليه - مرك ز الدفاع |  | 0551764648 |  | ET15 | جيزان
252363 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03238430 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 2/27/2012 | [13 empty] | South | 27 | JIZAN |  | JIZA | 0620258571 | JIZA 208 |  |  | وزاره الداخليه - مرك |  | 551764648 |  |  | Jizan
222400 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03240195 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | الرقم مفصول | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 5/28/2012 |  |  |  | Jaber Abdaly | [8 empty] | 23/12/2013 | South | 27 | JIZAN |  | SBYA | 0303477012 | SBYA 032:0013 |  |  | الل اداره - تعليم البنات قسم الحاس |  | 504572548 |  | ET35 | صبياء- جيزان
222410 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03251493 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 030 | 005 | 1 |  |  |  | Secondary | 1327000243 | Checked | 1327000243 | Completed | Approved | 05/05/2013 | 1304279217 | ICMS | Completed |  |  | Completed | 05/05/2013 | 30/05/2013 |  | 5/28/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 27/04/2013 | South | 27 | JIZAN |  | JIZ8A | 0303200762 | JIZA 030:0005 |  |  | مركز - صحى المعبوج |  | 0531113880 |  | ET36 | جيزان
222414 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03258222 | VIP | 7 | Issue RFW | New | Completed | BSW Work | Completed | العميل لا يرد على الاتصال | Copper | 136 | 0002 | 2 |  |  |  | Secondary | 1327000499 | Checked | 1327000499 | Completed | Approved | 09/10/2013 | 1309300855 | ICMS | Completed |  |  | Completed | 09/10/2013 | 30/05/2013 |  | 11/27/2011 |  |  | Design Completed | Ali Zogmah | Hasan Ghashim | Ali Zogmah | [6 empty] | 30/09/2013 | South | 27 | JIZAN |  | JIND | 2011096940 | JIND 136:0030 |  |  | شركة المهيدب للغذية |  | 0565203251 |  | ET14 | جيزان
222424 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03267762 | High | 7 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | العميل لا يرغب بالخدمة وغير متعاون | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/6/2012 |  |  |  | Ali Zogmah | [8 empty] | 18/09/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | هيئة الطيران المدني |  | 0554927126 |  | ET15 | جيزان
222432 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03272312 | High | 6 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 006 | 054 | 2 |  |  |  | Secondary | 1327000463 | Checked | 1327000463 | Completed | Approved | 29/08/2013 | 1308298642 | ICMS | Completed |  |  | Completed | 29/08/2013 | 30/05/2013 |  | 11/27/2011 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 29/08/2013 | South | 27 | JIZAN |  | DARB | 0303916873 | DARB 004:0003 |  |  | اداره - تعليم محافظه صبيا |  | 0555797961 |  | ED02 | صبياء- جيزان
222452 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03297290 | High | 2 | Rejected | Rejected | Rejected | Transfer to Planning to issue planning memo | Rejected | الموقع خارج نطاق الشبكه مستشفى العيدابي | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 2/27/2012 |  |  |  | Jaber Abdaly | [8 empty] | 06/10/2013 | South | 27 | JIZAN |  | EDBE2 | 0303200762 | EDBE2 006:0036 |  |  | همكتب - مكتب قطاع الر عايه الصح |  | 0509544424 |  | ET15 | صبياء- جيزان
252362 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03298533 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 2/27/2012 | [13 empty] | South | 27 | JIZAN |  | EDBE2 | 0303200762 | EDBE2 006:0036 |  |  | مكتب - مكتب قطاع الر |  | 509544424 |  |  | Jizan
222460 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03304400 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال خاطئ رقم الاتصال خاطئ رقم الاتصال خاطئ | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/5/2012 |  |  |  | Ali Zogmah | [8 empty] | 19/09/2013 | South | 27 | JIZAN |  | JIZ8B | 0128440062 | JIZA 030:0027 |  |  | والمه المؤسسة العامة للتدر يب التقني |  | 0554765159 |  | ET36 | جيزان
222489 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03362503 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed | يوجد على موقع العميل علبة FTTH وبياناتها كالتالي SHTI JZU 0859 FTTH/FDT 062-1 ODF8 PORT 26-29 SP8 PORT 26-29 TB 039 | Copper | 060 | 026 | 2 |  |  |  | Secondary | 1327000684 | Checked | 1327000684 | Completed | Approved | 21/11/2013 | 1311182865 | ICMS | Completed |  |  | In Progress | 21/11/2013 | 30/05/2013 |  | 12/3/2012 |  |  | Design Completed | Ali Zogmah | Hasan Ghashim | Ali Zogmah | [6 empty] | 18/11/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | NJRU1206 20121203 |  |  | ه جيز وزارة التربيه والتعل يم - بمنط |  | 0505793141 |  | ET41 | جيزان
252267 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03369273 |  | 13 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/28/2011 | [13 empty] | South | 27 | JIZAN |  | GKHR | 0303916873 | GKHR 112:0006 |  |  | اداره - تعليم محافظه |  | 505769166 |  |  | Jizan
222520 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03393676 | High | 6 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 022 | 064 | 1-2 |  |  |  | Secondary | 1327000488 | Checked | 1327000488 | Completed | Approved | 29/09/2013 | 1309240552 | ICMS | Completed |  |  | Completed | 29/09/2013 | 30/05/2013 |  | 12/3/2011 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 24/09/2013 | South | 27 | JIZAN |  | SHD1A | 0303395776 | SLHD 022:0066 |  |  | مدرسه - سوق الليل الابتدائيه |  | 0564988552 |  | ET35 | سوق الحد- جيزان
252270 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03394349 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 12/3/2011 | [13 empty] | South | 27 | JIZAN |  | HRJH | 0303474269 | HRJH 036:0029 |  |  | وزارة التربيه والتعل |  | 598187210 |  |  | Jizan
222523 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03396832 | High | 8 | Rejected | Rejected | Rejected | Facility available but needs maintenance | Rejected | الامكانية متوفرة والشبكة واصلة على جدار العميل لكن هناك اعمال تحت الصيانة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/3/2012 |  |  |  | Ali Zogmah | [8 empty] | 06/10/2013 | South | 27 | JIZAN |  | JIZ9A | 0000000000 | 0 |  |  | شركة عبدالخالق محمد سعيد |  | 0566027427 |  | ET14 | جيزان
222529 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03400743 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | تمت خدمة العميل | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/3/2011 |  |  |  | ICMS027 (Jizan) | [8 empty] | 18/05/2013 | South | 27 | JIZAN |  | FRSN | 0303506217 | FRSN 001:0045 |  |  | قة جا الشركة السعودية للكه رباء - من |  | 0506066015 |  | ET15 | فرسان - جيزان
222531 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03401461 | High | 7 | Rejected | Rejected | Rejected | Service order belongs to other stage / Wrong reason code/ Wrong region/ District/ City code | Rejected | الموقع على شارع سوف تقوم المواصلات بهدمه لتوسعة الطريق | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 12/3/2011 |  |  |  | Jaber Abdaly | [8 empty] | 03/11/2013 | South | 27 | JIZAN |  | EDBE2 | 0303506217 | EDBE2 006:0037 |  |  | قة جا الشركة السعودية للكه رباء - من |  | 0506066015 |  | ET15 | صبياء- جيزان
252472 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03435828 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 6/4/2012 | [13 empty] | South | 27 | JIZAN |  | BAYS | 2014486065 | BAYS 009:0231 |  |  | موسسة ابو عامرية للد |  | 507773319 |  |  | Jizan
222570 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03445127 | High | 2 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على البكسية الجدراية011 -012 في موقع العميل | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/3/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 02/09/2013 | South | 27 | JIZAN |  | SBYA | 0000000000 | NJRU1206 20121203 |  |  | ف ال اداره - تعليم البنات مكتب الشر |  | 0508336799 |  | ET35 | صبياء- جيزان
222573 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03447769 | High | 2 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 002 | 011-012 | 0 |  |  |  | Secondary | 1327000254 | Unchecked | 1327000013 | Completed | Approved | 06/05/2013 | 1305050205 | ICMS | Completed |  |  | Completed | 06/05/2013 | 30/05/2013 |  | 12/3/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 05/05/2013 | South | 27 | JIZAN |  | SBYA | 0000000000 | NJRU1206 20121203 |  |  | مدرسه - الول البتدائ يه للبنات |  | 0508336799 |  | ET35 | صبياء- جيزان
222584 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03459147 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 3/6/2012 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | ABAR | 0657329835 | ABAR 031:0029 |  |  | جامعة جازان |  | 0566997551 |  | ET14 | ابو عريش - جيزان
222587 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03463267 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 9/3/2012 |  |  |  | Emad Mahdi | [9 empty] | South | 27 | JIZAN |  | GRIF | 2015744564 | GRIF 111:0048 |  |  | شركه - سعيد محمد الب سامى |  | 0553301221 |  | ET15 | الدرب
251410 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03474107 |  | 6 | Issue RFW | New | Completed | Distribution Point | In-Progress |  | Copper | 006 | 025B | 1-2 |  |  |  | Secondary | 1427000055 | Checked | 1427000055 | Completed | Under Review |  | 1401295010 | ICMS | In-Progress |  |  | Design |  |  |  | 9/29/2013 |  |  | Design Team | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 29/01/2014 | South | 27 | JIZAN |  | FRSNJZAA | 0254875635 | FRSN 006:0028 |  |  | الرئاسة العامة للامر بالمعروف والنهي عن المنكر |  | 555255323 |  | توصيل جديد خ. اكيد
252722 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03520707 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 5/21/2013 | [13 empty] | South | 27 | JIZAN |  | BAYS | 2019949861 | BAYS 029:0068 |  |  | مؤسسة حسين لحق موسى |  | 506762816 |  |  | Jizan
222633 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03526653 | High | 2 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 048 | 015+013 | 9-10 |  |  |  | Secondary | 1327000495 | Checked | 1327000495 | Completed | Approved | 01/10/2013 | 1309290777 | ICMS | Completed |  |  | In Progress | 23/10/2013 | 30/05/2013 |  | 12/5/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 29/09/2013 | South | 27 | JIZAN |  | SAMI | 0000000000 | SAMI 48 |  |  | لده شركة عبدالله بن محمد باجبير وا |  | 0505699759 |  | ET14 | صامطه- جيزان
222634 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03527317 | High | 6 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | جوال العميل مغلق جوال العميل مغلق جوال العميل مغلق | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 9/5/2012 |  |  |  | Ali Zogmah | [8 empty] | 25/09/2013 | South | 27 | JIZAN |  | JIZA | 2015784507 | JIZA 081:0119 |  |  | الدو شركة-محمد علي الحمرا ني للتجار |  | 0564220747 |  | ET14 | جيزان
222642 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03528990 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 12/3/2012 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | UQDA | 0000000000 | 0 |  |  | بجاز الداره العامه للتربي ه والتعلي |  | 0505768795 |  | ET14 | جيزان
231021 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03531230 | High | 7 | Issue RFW | New | Completed | Distribution Point | Completed | حسب افادة - اسامة العمري 0534555329 تم تركيب الهواتف للبنك العربي في ابو عريش ولا يحتاج الي خدمة جديدة | Copper | 051 | 484A | 000 |  |  |  | Secondary | 1327000702 | Unchecked | 1327000699 | Completed | Approved | 27/11/2013 | 1311273176 | ICMS | Completed |  |  | In Progress | 27/11/2013 | 25/06/2013 | 30/01/2014 | 9/17/2012 12:00:00 AM |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 27/11/2013 | South | 27 | JIZAN |  | ABAR | 0000000000 | ABAR 030:0108 |  |  | FAHAD-ALSANAD - |  | 505453424 |  | NA | JIZAN
251511 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03531230 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 9/17/2012 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | ARSHJZ00 | 0797014397 | ABAR 030:0108 |  |  | هيئة التحقيق والادعاء العام |  | 966505453424 |  | توصيل جديد خ. اكيد
155055 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03534607 | Medium | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed | [8 empty] | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابوحمامة |  | 0555745535 |  | ET14 | NA
231083 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03546494 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 006 | 170+163 | 5-6 |  |  |  | Secondary | 1327000360 | Checked | 1227000259 | Completed | Approved | 01/07/2013 | 1306265457 | ICMS | Completed |  |  | Completed | 01/07/2013 | 07/07/2013 |  | 9/17/2012 12:00:00 AM |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 26/06/2013 | South | 27 | JIZAN |  | EDBE2 | 0000000000 | EDBE2 006:0170 |  |  | FAHAD-ALSANAD - |  | 505453424 |  | NA | JIZAN
222678 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03572503 | High | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 12/8/2012 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | ARSH | 0000000000 | 0 |  |  | قران مكتب الشراف على حلقا ت تحفيظ ا |  | 0542886675 |  | ED02 | صبياء- جيزان
251393 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03581270 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/9/2013 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | SHMTJZ00 | 0615917397 | SAMI 003:0097 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIAN DIA New Install
222692 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03583846 | High | 7 | Under Reject | Rejecting | In Progress | In Progress | In-Progress | رقم الجوال مقفل | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 2/21/2011 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | MWSM | 0303530959 | MWSM 001:0104 |  |  | لديه بلديه جيزان - المكتب الفنى بال |  | 0508859950 |  | ET15 | صامطه- جيزان
222702 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03592018 | VIP | 6 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | GRIF 111 | 038+035 | 4 |  |  |  | Secondary | 1327000377 | Checked | 1327000377 | Completed | Approved | 08/07/2013 | 1307076147 | ICMS | Completed |  |  | In Progress | 08/07/2013 | 30/05/2013 |  | 5/23/2011 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 07/07/2013 | South | 27 | JIZAN |  | GRIF | 0303562680 | GRIF 111:0133 |  |  | وزاره الداخليه - الم رور |  | 0555771392 |  | ET15 | الدرب
155077 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03624381 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | EDBE 004 | 058 | 1 |  |  |  | Secondary | 1327000002 | Checked | 1327000002 | Completed | Approved | 06/01/2013 | 1212230898 | ICMS | Completed |  |  | Completed | 06/01/2013 | 15/06/2013 |  | 23/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 23/12/2012 | South | 27 | JIZAN |  | EDBE2 | 0649184623 | E004 |  |  | وزارة العمل | احمد-الحكي | 0541999986 |  | LCAK | na
155091 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03627144 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | العميل مخدوم ببكسية جدارية رقم 0129 -0130 وبها امكانية تركيب | [9 empty] | Indeterminate | [11 empty] | 15/06/2013 |  | 06/01/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 14/01/2013 | South | 27 | JIZAN |  | frsn | 0616352709 | 04 |  |  | وزارة العمل |  | 0505590955 |  | LCAK | JIZAN-JIZAN IP160
155056 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03628014 | Medium | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 0000 | 0 |  |  |  | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابوحمامة |  | 0555745535 |  | ET14 | NA
155090 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03630424 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 060 | 071 | 3 & 4 |  |  |  | Secondary | 1327000003 | Checked | 1327000003 | Completed | Approved | 07/01/2013 | 1301071427 | ICMS | Completed |  |  | Completed | 07/01/2013 | 15/06/2013 |  | 06/01/2013 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 07/01/2013 | South | 27 | JIZAN |  | sbya | 0616352709 | 060 |  |  | وزارة العمل |  | 0505590955 |  | LCAK | JIZAN-JIZAN IP161
209621 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03630424 | High | 6 | Issue RFW | New | Completed | Secondary Work (DP) | In-Progress | [8 empty] | Secondary |  | Indeterminate |  | In-Progress | In-Progress |  | 1311042321 | ICMS | In-Progress |  |  | Design |  | 30/12/2013 |  | 3/3/2013 |  |  | Design Team | Jaber Abdaly | Hasan Ghashim | Jaber Abdaly | [6 empty] | 04/11/2013 | South | 27 | JIZAN |  | SBYA | 0196672796 | 060:0071 | 3MBPS_E2E |  | MINISTRY OF LABOR | NA | 0541999986 |  | ET14 | JIZAN-JIZAN IP161 | SBYA E24
251384 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03650598 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 7/21/2013 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | HMTRJZAK | 0196663223 | JIZA 059:0007 |  |  | وزارة الداخلية |  | 559798999 |  | توصيل جديد خ. اكيد
155057 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03661033 | Medium | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 0000 | 0 |  |  |  | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابو حمامة |  | 0555745535 |  | ET14 | NA
252095 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03661767 |  | 5 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 5/23/2011 | [13 empty] | South | 27 | JIZAN |  | JZN | 2007839947 | DMAD 021:0021 |  |  | شركة العزيزية بندة ا |  | 555991473 |  |  | Jizan
222766 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03683238 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 12/24/2012 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZDA | 0000000000 | 0 |  |  | اره ا وزارة التربيه والتعل يم بنات ا |  | 0505769497 |  | ET14 | جيزان
155058 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03683545 | Medium | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 0000 | 0 |  |  |  | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابو حمامة |  | 0555745535 |  | ET14 | NA
155092 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03686938 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 013 | 009 | 2 & 3 |  |  |  | Secondary | 1327000004 | Checked | 1327000004 | Completed | Approved | 07/01/2013 | 1301071432 | ICMS | Completed |  |  | Completed | 07/01/2013 | 15/06/2013 |  | 06/01/2013 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 07/01/2013 | South | 27 | JIZAN |  | darb | 0616352709 | 013 |  |  | وزارة العمل |  | 0505590955 |  | LCAK | JIZAN-JIZAN IP163
155059 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03712689 | Medium | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 0000 | 0 |  |  |  | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابو حمامة |  | 0555745535 |  | ET14 | NA
252376 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03728338 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 3/11/2012 | [13 empty] | South | 27 | JIZAN |  | SBYA | 2012888301 | SBYA 019:0215 |  |  | مؤسسة عبدالله يحى طي |  | 504571433 |  |  | Jizan
222816 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03729489 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 081 | 063 | 3 |  |  |  | Secondary | 1327000466 | Checked | 1327000466 | Completed | Approved | 09/09/2013 | 1309028825 | ICMS | Completed |  |  | In Progress | 09/09/2013 | 30/05/2013 |  | 3/11/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 02/09/2013 | South | 27 | JIZAN |  | SBYA | 0303839437 | SBYA 081:0064 |  |  | رسة ا وزارة التربية والتعل يم بنين م |  | 0505793505 |  | ET41 | صبياء- جيزان
222821 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03736847 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | جوال العميل مغلق جوال العميل مغلق جوال العميل مغلق | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/13/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JIZBA | 0000000000 | 0 |  |  | زان مؤسسة عمر علي عبيد ب االشرف بج |  | 0501069891 |  | ET14 | جيزان
155060 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03740720 | Medium | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 0000 | 0 |  |  |  | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابو حمامة |  | 0555745535 |  | ET14 | NA
209613 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03769593 | High | 6 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة عند العميل ولكن يحتاج الى خدمة DSL | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 15/06/2013 | South | 27 | JIZAN |  | SQYQ | 0649433763 | 001:0179 | 2MBPS_E2E |  | MINISTRY OF EDUCATION | NA | 0505766455 |  | ET14 | SQYQ07_41_208-SQYQ07_41_208 IP8 | SHUQAIQ MSAN01
155061 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03775024 | Medium | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 0000 | 0 |  |  |  | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابو حمامة |  | 0555745535 |  | ET14 | NA
155062 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03793334 | Medium | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 0000 | 0 |  |  |  | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 16/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابو حمامة |  | 0555745535 |  | ET14 | NA
222859 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03811595 | High | 7 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 010 | 031 | 1 |  |  |  | Secondary | 1327000491 | Checked | 1227000244 | Completed | Approved | 12/01/2014 | 1309250639 | ICMS | Completed |  |  | In Progress | 12/01/2014 | 30/05/2013 |  | 10/2/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 25/09/2013 | South | 27 | JIZAN |  | SLHD | 0000000000 | 0 |  |  | رع ا الشركة المتحدة للبيع بالتقسيط |  | 0508513940 |  | ET14 | سوق الحد- جيزان
252555 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03811595 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/2/2012 | [13 empty] | South | 27 | JIZAN |  | SLHD | 2016417125 | SLHD 010:0035 |  |  | الشركة المتحدة للبيع |  | 508513940 |  |  | Jizan
155063 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03812558 | Medium | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 0000 | 0 |  |  |  | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابو حمامة |  | 0555745535 |  | ET14 | NA
222864 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03821250 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 133 | 000 |  |  |  | Secondary | 1327000279 | Unchecked | 1227000165 | Completed | Approved | 19/05/2013 | 1305019910 | ICMS | Completed |  |  | Completed | 19/05/2013 | 30/05/2013 |  | 8/14/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Mahdy Salami | [6 empty] | 01/05/2013 | South | 27 | JIZAN |  | FRSN | 2015526745 | FRSN 004:0144 |  |  | البنك العربى الوطنى |  | 0556454643 |  | ET14 | فرسان - جيزان
155064 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03826052 | Medium | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 0004 | 0000 | 0 |  |  |  | Secondary | 1227W00021 | Checked | 1227W00021 | Completed | Approved | 14/01/2013 | 1212150541 | ICMS | Completed |  |  | Completed | 16/12/2012 | 15/06/2013 |  | 12/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Jaber Abdaly | [6 empty] | 15/12/2012 | South | 27 | JIZAN |  | JIZA | 2016230300 | 004 |  |  | مؤسسة احمد سعيد ابو حمامة |  | 0555745535 |  | ET14 | NA
240363 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03845749 | High | 1 | Rejected | Rejected | Rejected | Transfer to Planning to issue planning memo | Rejected | الطلب لا يخص المنطقة الطلب يخص منطقة عسير | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 09/01/2013 12:00:00 AM |  |  |  | ICMS027 (Jizan) | [8 empty] | 12/01/2014 | South | 27 | JIZAN |  | KBH1 | 0691347656 | KBH1 201:0002 |  |  | مجمع قروي بحر ابو سكينه |  | 508031065 |  | تأسيس هاتف ثابت | KBH1 201:0002
251464 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03864271 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/6/2013 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | SENAJZAF | 0615917397 | SWIS 105:0017 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIAN DIA New Install
222893 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03872745 | High | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 12/14/2011 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | SBYA | 0303443657 | SBYA 081:0027 |  |  | مدرسة - فرسان العداد ية للبنين |  | 0506766555 |  | ET35 | صبياء- جيزان
222907 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03895506 | High | 7 | Rejected | Rejected | Rejected | Service order Inactive or closed/ Suspended by subscription office | Rejected | المسافة اكثر من 1000 متر يقع العميل في منطقة غير مخدومة رمز السبب 5 | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 3/14/2012 |  |  |  | Ali Zogmah | [8 empty] | 14/01/2014 | South | 27 | JIZAN |  | JIZ7H | 0303530959 | JIZA 006:0123 |  |  | لديه بلديه جيزان - المكتب الفنى بال |  | 0502306664 |  | ET36 | جيزان
222908 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03897308 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية لدي العميل في البكسية رقم 0123 من كبينة رقم 006 .. يحول للتركيب | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 3/14/2012 |  |  |  | Ali Zogmah | [8 empty] | 14/01/2014 | South | 27 | JIZAN |  | JIZ7H | 0303530959 | JIZA 006:0123 |  |  | الع بلديه منطقه جيزان - خزانات مصل |  | 0502306664 |  | ET42 | جيزان
222917 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03902552 | High | 2 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | تم الاتصال على العميل اكثر من 3 مرات متفرقات ولايجيب | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 9/15/2012 |  |  |  | Ali Zogmah | [8 empty] | 20/01/2014 | South | 27 | JIZAN |  | JIZA | 2015988994 | JIZA 033:0005 |  |  | العا مؤسسة ناصر محمد زيلع ي للمقاول |  | 0553455047 |  | ET14 | جيزان
222948 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03935705 | VIP | 7 | Under Reject | Rejecting | In Progress | In Progress | In-Progress | هاتف العميل مغلق | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/3/2012 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZFC | 0000000000 | 0 |  |  | شركه - العزيزيه بنده |  | 0555092587 |  | ET15 | جيزان
155084 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03947858 | Medium | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed | [8 empty] | Secondary | 1227W00038 | Checked | 1227W00038 | Completed | Approved | 14/01/2013 | 1212250965 | ICMS | Completed |  |  | Completed | 25/12/2012 | 15/06/2013 |  | 24/12/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 25/12/2012 | South | 27 | JIZAN |  | FQRA | 0303200762 | 025 |  |  | وزارة الصحة-ادراة التموين الطبي |  | 0556655360 |  | ET35 | na
240294 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03960139 | high | 6 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | تم اتصال على المشترك وسالته عن الموقع فقال ليس لدي فكرة عندنا اكثر من 100 مدرسة تحتاج خط والموقع المحدد ببطاقة الخط لا يعرفه | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 9/12/2013 12:00:00 AM |  |  |  | Jaber Abdaly | [8 empty] | 03/11/2013 | South | 27 | JIZAN |  | SBYA | 0615917397 | SBYA 018:0080 |  |  | وزارة التربية والتعليم |  | 505766455 |  | EBU | SBYA 018:0080
222988 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 03993831 | High | 6 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 003 | 031 | 1-2 |  |  |  | Secondary | 1427000028 | Checked | 1427000028 | Completed | Approved | 16/01/2014 | 1401144584 | ICMS | Completed |  |  | Under Assign | 16/01/2014 | 30/12/2013 |  | 9/16/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 14/01/2014 | South | 27 | JIZAN |  | ABABA | 0000000000 | 0 |  |  | بالعا لجنة التنمية الجتماع ية الهلية |  | 0503768946 |  | ED02 | ابو عريش - جيزان
252119 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04059179 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 6/18/2012 | [13 empty] | South | 27 | JIZAN |  | JIZA | 0792955959 | JIZA 062:0077 |  |  | الهيئة العامة للسكان |  | 555771258 |  |  | Jizan
223069 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04106023 | High | 7 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 020 | 019+018 | 7-8 |  |  |  | Secondary | 1327000514 | Checked | 1327000514 | Completed | Approved | 08/10/2013 | 1310031076 | ICMS | Completed |  |  | In Progress | 08/10/2013 | 30/05/2013 |  | 5/30/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 03/10/2013 | South | 27 | JIZAN |  | DMAD | 0607446768 | DMAD 020:0019 |  |  | جازان وزارة العدل رئاسة مح اكم منطقة |  | 0556789011 |  | ET41 | ضمد - جيزان
223096 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04126899 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | تمت خدمة العميل | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/20/2011 |  |  |  | ICMS027 (Jizan) | [8 empty] | 18/05/2013 | South | 27 | JIZAN |  | FRSN | 0620258571 | FRSN 001:0006 |  |  | المدن وزاره الداخليه - ادا رة الدفاع |  | 0544778005 |  | ET14 | فرسان - جيزان
223110 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04148312 | High | 7 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 005 | 145 | 1-2 |  |  |  | Secondary | 1327000500 | Checked | 1227000179 | Completed | Approved | 27/11/2013 | 1309300870 | ICMS | Completed |  |  | In Progress | 27/11/2013 | 30/05/2013 |  | 3/21/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 30/09/2013 | South | 27 | JIZAN | 1227000179 | FRSN | 0128440062 | FRSN 005:0145 |  |  | والمه المؤسسة العامة للتدر يب التقني |  | 0533497473 |  | ET14 | فرسان - جيزان
223133 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04172077 | High | 8 | Rejected | Rejected | Rejected | HBU to Activate Fiber Optic | Rejected | يوجد على موقع العميل FTTH وبياناتها كالتالي: SHTI JZU 0859 FTTH/FDT 062-1 ODF8 PORT 26-29 SP8 PORT 26-29 TB039 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 1/1/2013 |  |  |  | Ali Zogmah | [8 empty] | 11/09/2013 | South | 27 | JIZAN |  | JIZ7A | 0000000000 | NJRU1206 20130101 |  |  | بجاز الداره العامه للتربي ه والتعلي |  | 0503766281 |  | ET35 | JZN
223143 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04179863 | VIP | 6 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 002 | 004 | 000 |  |  |  | Secondary | 1327000288 | Checked | 1327000288 | Completed | Approved | 25/05/2013 | 1305191529 | ICMS | Completed |  |  | Completed | 25/05/2013 | 30/05/2013 |  | 12/26/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Mahdy Salami | [6 empty] | 19/05/2013 | South | 27 | JIZAN |  | ABAR | 0000000000 | 0 |  |  | البنك العربى الوطنى |  | 0534555329 |  | ET15 | ابو عريش - جيزان
223148 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04191315 | High | 6 | Issue RFW | New | Completed | Secondary Work (DP) | In-Progress | [8 empty] | Secondary |  | Indeterminate |  | In-Progress | In-Progress |  | 1310221731 | ICMS | In-Progress |  |  | Design |  | 30/12/2013 |  | 1/21/2013 |  |  | Design Team | Jaber Abdaly | Hasan Ghashim | Jaber Abdaly | [6 empty] | 22/10/2013 | South | 27 | JIZAN |  | SBYA | 0000000000 | 0 |  |  | لده شركة عبدالله بن محمد باجبير وا |  | 0505699759 |  | ET14 | صبياء- جيزان
223198 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04260259 | High | 4 | Issue RFW | New | Completed | BSW Work | Completed | خارج نطاق الشبكة منطقة غير مخدومة (مسح شامل | Copper | 205 | 027 | 000 |  |  |  | Secondary | 1327000717 | Checked | 1327000717 | Completed | Approved | 16/12/2013 | 1312123637 | ICMS | Completed |  |  | In Progress | 16/12/2013 | 30/05/2013 |  | 12/26/2012 |  |  | Design Completed | Ali Zogmah | Hasan Ghashim | Ali Zogmah | [6 empty] | 12/12/2013 | South | 27 | JIZAN |  | JIZDA | 0000000000 | NJRU1206 20121229 |  |  | الثا مدرسه - تحفيظ القران المتوسطه |  | 0590936006 |  | ET35 | جيزان
223207 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04268490 | High | 7 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 053 | 003 | 2-3 |  |  |  | Secondary | 1327000652 | Checked | 1327000652 | Completed | Approved | 05/11/2013 | 1310312267 | ICMS | Completed |  |  | In Progress | 05/11/2013 | 30/12/2013 |  | 10/7/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 31/10/2013 | South | 27 | JIZAN |  | ABA1C | 0000000000 | NJRU1206 20121013 |  |  | ه وال مدرسه - البديع والقر فى الثانو |  | 0555799114 |  | ET41 | ابو عريش - جيزان
209604 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04295781 | High | 6 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | افاد المشترك بعدم وجود طلب للشركة بهذا الموقع | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | Jaber Abdaly | [8 empty] | 01/10/2013 | South | 27 | JIZAN |  | ABAR | 0100509159 | 062:0075 | 4MBPS_E2E |  | AL RAJHI ISP | NA | 0507087202 |  | ET14 | JIZAN-RIYADH DIA49 | ABU ARISH
252283 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04327520 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 12/25/2011 | [13 empty] | South | 27 | JIZAN |  | JZN | 2011579100 | JIZA 028:0007 |  |  | مؤسسة الوسيط المبتكر |  | 503093552 |  |  | Jizan
231091 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04356066 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال لايخص المشترك | [9 empty] | Indeterminate | [11 empty] | 10/07/2013 |  | 4/29/2013 12:00:00 AM |  |  |  | Mahdy Salami | [8 empty] | 20/09/2013 | South | 27 | JIZAN |  | SCCT | 0000000000 | SCCT 1111111100 |  |  | AHMED-ALZAHRINE - |  | 506049779 |  | NA | JIZAN
251857 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04356066 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 4/29/2013 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | BADRDN124 | 0691717682 | JIZA 075:0087 |  |  | مصرف الانماء |  | 966506049779 |  | توصيل جديد خ. اكيد
223269 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04356139 | High | 6 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 087 | 065 | 3 |  |  |  | Secondary | 1327000467 | Checked | 1327000467 | Completed | Approved | 09/09/2013 | 1309028824 | ICMS | Completed |  |  | In Progress | 09/09/2013 | 30/05/2013 |  | 9/29/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 02/09/2013 | South | 27 | JIZAN |  | SBY2B | 0000000000 | 0 |  |  | اداره - تعليم محافظه صبيا |  | 0564278805 |  | ET14 | صبياء- جيزان
231020 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04356305 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال لا يخص المشترك | [9 empty] | Indeterminate | [11 empty] | 23/06/2013 |  | 3/12/2013 12:00:00 AM |  |  |  | Mahdy Salami | [8 empty] | 20/09/2013 | South | 27 | JIZAN |  | SCCT | 0000000000 | SCCT 1111111100 |  |  | AHMED-ALZAHRINE - |  | 506049779 |  | NA | JIZAN
251855 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04356305 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 3/12/2013 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | BADRDN122 | 0691717682 | JIZA 075:0087 |  |  | مصرف الانماء |  | 966506049779 |  | توصيل جديد خ. اكيد
223273 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04359666 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال خاطئ | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/29/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | مؤسسة الستشاريون الت |  | 553031981 |  | ET14 | JZN
223284 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04365597 | VIP | 2 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 037 | 043B | 0 |  |  |  | Secondary | 1327000383 | Checked | 1327000383 | Completed | Approved | 09/07/2013 | 1307086291 | ICMS | Completed |  |  | Completed | 09/07/2013 | 30/05/2013 |  | 3/31/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 08/07/2013 | South | 27 | JIZAN |  | JIZA | 0175140190 | JIZA 037:0121 |  |  | ةوزارة الداخلية القيا دة والسيط |  | 0542412211 |  | ET15 | جيزان
209603 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04418941 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم اتصال العميل مفصول عن الخدمة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | Khalid Muaafa | [8 empty] | 25/10/2013 | South | 27 | JIZAN |  | JIZA | 0649372985 | 062:0083 | 2MBPS_E2E |  | SCFHS | NA | 0566969665 |  | ET14 | JIZAN-JIZAN IP102 | JIZAN II
251648 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04418941 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 2/18/2013 |  |  |  | Khalid Muaafa | [9 empty] | South | 27 | JIZAN |  | SHTIJZAB | 0692188527 | WDYH E000 |  |  | الهيئه السعودية للتخصصات الصحية |  | 566969665 |  | توصيل جديد خ. اكيد
223330 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04427776 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على البكسية 025 كبينة 030 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 7/14/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 08/07/2013 | South | 27 | JIZAN |  | SHQR1 | 0303444505 | SHQR1 030:0025 |  |  | وزاره الداخليه - سجو ن جيزان |  | 0557364973 |  | ET15 | ضمد - جيزان
252496 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04427776 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 7/14/2012 | [13 empty] | South | 27 | JIZAN |  | SHQR1 | 0303444505 | SHQR1 030:0025 |  |  | وزاره الداخليه - سجو |  | 557364973 |  |  | Jizan
223349 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04453713 | High | 7 | Rejected | Rejected | Rejected | Service order belongs to other stage / Wrong reason code/ Wrong region/ District/ City code | Rejected | يقع في منطقة غير مخدومة .. يحتاج مسح شامل | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/8/2012 |  |  |  | Ali Zogmah | [8 empty] | 17/09/2013 | South | 27 | JIZAN |  | JIND | 0000000000 | 0 |  |  | ابنا شركة سالم احمد يماني بن محفوظ |  | 0531523145 |  | ET14 | جيزان
223351 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04456860 | High | 6 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 009 | 048-049 | 7 |  |  |  | Secondary | 1327000376 | Checked | 1327000376 | Completed | Approved | 08/07/2013 | 1307076143 | ICMS | Completed |  |  | Completed | 08/07/2013 | 30/05/2013 |  | 7/14/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 07/07/2013 | South | 27 | JIZAN |  | BAYS | 0304062215 | BAYS 009:0048 |  |  | لسجون وزاره الخليه - الدار ه العامه |  | 0557364973 |  | ET15 | بيش - جيزان
223417 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04548668 | High | 6 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 001 | 081 | 1-2 |  |  |  | Secondary | 1327000472 | Checked | 1327000472 | Completed | Approved | 11/09/2013 | 1309018745 | ICMS | Completed |  |  | In Progress | 11/09/2013 | 30/05/2013 |  | 1/8/2013 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Mahdy Salami | [6 empty] | 01/09/2013 | South | 27 | JIZAN |  | SAMI | 0000000000 | JZNU1159 20130115 |  |  | اره ا وزارة التربيه والتعل يم بنات ا |  | 0555771006 |  | ET41 | صامطه- جيزان
252556 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04583787 |  | 5 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/2/2012 | [13 empty] | South | 27 | JIZAN |  | JZN | 2016417257 | DMAD 021:0021 |  |  | مستشفى المواساة الري |  | 554207995 |  |  | Jizan
223458 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04599374 | High | 2 | Under Reject | Rejecting | In Progress | In Progress | In-Progress | العميل لا يرد | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 1/1/2013 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZA | 0000000000 | JZNU1022 20130101 |  |  | اعبدا مؤسسةالستراتيجي للتج ارة لصاحب |  | 0507774400 |  | ET35 | جيزان
223497 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04642831 | High | 6 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 032 | 064+063 | 0 |  |  |  | Secondary | 1327000422 | Checked | 1327000422 | Completed | Approved | 28/07/2013 | 1307257436 | ICMS | Completed |  |  | Completed | 28/07/2013 | 30/05/2013 |  | 7/4/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 25/07/2013 | South | 27 | JIZAN |  | SBYA | 0303200762 | SBYA 033:0004 |  |  | وزاره الصحه - المستش فى العام |  | 0542221359 |  | ET35 | صبياء- جيزان
223514 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04663261 | High | 2 | Under Reject | Rejecting | In Progress | In Progress | In-Progress | المشترك لا يرد | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 1/7/2013 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | SBYA | 0000000000 | JZNU1022 20130107 |  |  | زربطان - ابراهيم حسن زين |  | 0557676247 |  | ET35 | صبياء- جيزان
223522 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04673671 | High | 6 | Rejected | Rejected | Rejected | Facility available but needs maintenance | Rejected | جوال العميل مغلق العميل لا يرد في الاتصال الثاني يوجد شبكة على جدار العميل وبها امكانية .. والكبينة 060 فل شغال في التوسعة الزميل جابر الفيفي يحول الطلب لجابر الفيفي كتوسة كبينة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 9/27/2011 |  |  |  | Ali Zogmah | [8 empty] | 24/09/2013 | South | 27 | JIZAN |  | JIZA | 0303248803 | JIZA 060:0116 |  |  | امة قسم المحاسبة - بفرع الرئاسة ال |  | 0590577051 |  | ET35 | جيزان
223531 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04688890 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية تركيب على الكبينة 200 بكسية 060 و يوجد سلك خدمة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 1/4/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 01/09/2013 | South | 27 | JIZAN |  | MDYA | 0303474269 | MDYA 200:0060 |  |  | اره ا وزارة التربيه والتعل يم بنات ا |  | 0569463868 |  | ED02 | جيزان
223532 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04688915 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | العميل مخدوم موقع العميل في مبنيء الراشد مول .. ويوجد شبكة داخلية .. يحول للتركيب | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 10/2/2012 |  |  |  | Ali Zogmah | [8 empty] | 21/11/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | فندق هوليدي جاازان |  | 0505767707 |  | ET14 | جيزان
209607 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04695170 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | الموقع غير معروف ورقم الاتصال لا يرد | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | Jaber Abdaly | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | SBYA | 0649168830 | 0014 | 6MBPS_E2E |  | MINISTRY OF AGRICULTURE | NA | 0569161162 |  | ET14 | JIZAN-RIYADH DIA4 | SABYA
251678 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04695170 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/27/2012 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | SBYAJZ00 | 0649511381 | SBYA 019:0014 |  |  | وزارة الزراعة |  | 569161162 |  | DIA Install Change
223542 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04704818 | High | 8 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | العميل لا يرد العميل لا يرد العميل لا يرد | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 1/4/2012 |  |  |  | Ali Zogmah | [8 empty] | 25/09/2013 | South | 27 | JIZAN |  | JIZA | 0303474269 | JIZA 058:0090 |  |  | روضه - الطفال الثاني ه بجيزان |  | 0598922692 |  | ET36 | JZN
223548 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04713498 | High | 7 | Rejected | Rejected | Rejected | Facility available but needs maintenance | Rejected | الامكانية متوفرة عند العميل بكسية 016 الكبينة 009 والخطوط العاملة تحتاج الى صيانة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 1/6/2013 |  |  |  | ICMS027 (Jizan) | [8 empty] | 08/07/2013 | South | 27 | JIZAN |  | ANTU | 0000000000 | 0 |  |  | المدن وزاره الداخليه - ادا رة الدفاع |  | 0551764648 |  | ET15 | مركز الطوال - جيزان
223579 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04751776 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | العميل مخدوم | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 1/11/2011 |  |  |  | Emad Mahdi | [8 empty] | 15/09/2013 | South | 27 | JIZAN |  | KDRA | 0657329835 | KDRA 119 |  |  | جامعة جازان |  | 0545999458 |  | ET14 | الدرب - جيزان
252146 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04751776 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 1/11/2011 | [13 empty] | South | 27 | JIZAN |  | KDRA | 0657329835 | KDRA 119 |  |  | جامعة جازان |  | 545999458 |  |  | Jizan
223588 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04767528 | High | 6 | Under Reject | Rejecting | Completed | Secondary Work (DP) | Completed | جوال العميل مغلق | [7 empty] | Secondary | 1327000481 | Checked | 1327000481 | Completed | Approved | 28/10/2013 | 1309159917 | ICMS | Completed |  |  | In Progress | 28/10/2013 | 30/05/2013 |  | 1/13/2013 |  |  | Design Completed | Ali Zogmah | Hasan Ghashim | Ali Zogmah | [7 empty] | South | 27 | JIZAN |  | JIND | 0000000000 | 0 |  |  | شركه - الكابلى التجا ريه |  | 0564053868 |  | ET15 | جيزان
223589 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04768421 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | العميل مخدوم ويوجد شبكة على الجدار | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 6/18/2012 |  |  |  | Ali Zogmah | [8 empty] | 03/10/2013 | South | 27 | JIZAN |  | JIZA | 0657329835 | JIZA 027:0008 |  |  | جامعة جازان |  | 0545999458 |  | ET14 | جيزان
187233 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04776677 |  | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 075 | 003 -004 | 0 |  |  |  | Secondary | 1327000030 | Checked | 1327000030 | Completed | Approved | 26/02/2013 | 1302253428 | ICMS | Completed |  |  | Completed | 25/02/2013 | 15/06/2013 |  | 20/02/2013 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 25/02/2013 | South | 27 | JIZAN |  | JIZA | 0175930760 | 213 |  |  | البنك السعودي البريطاني |  | 0500696663 |  | ET15 | NA
251874 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04821524 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/7/2013 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | BADRDN143 | 0615917397 | ABAR 057:0089 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIA New Install
223650 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04822758 | High | 6 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | العميل لا يرغب بالخدمة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/30/2012 |  |  |  | Ali Zogmah | [8 empty] | 22/10/2013 | South | 27 | JIZAN |  | JIZFC | 0000000000 | 0 |  |  | مكتب - شركه بن زقر |  | 0500647008 |  | ET14 | جيزان
223651 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04822789 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على جدار العميل البكسية 003 كبينة 004 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/1/2011 |  |  |  | ICMS027 (Jizan) | [8 empty] | 08/07/2013 | South | 27 | JIZAN |  | KHAW | 0303582940 | KHAW 001:0003 |  |  | ادارة - المجاهدين بم نطقة جيزا |  | 0543774532 |  | ET34 | سوق الحد- جيزان
223654 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04823852 | High | 7 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | العميل لا يرغب بالخدمة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/1/2012 |  |  |  | Ali Zogmah | [8 empty] | 21/10/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | شركة ابعاد المدار لل تجاره |  | 0592438223 |  | ET15 | جيزان
251567 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04860437 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/9/2013 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | FRSNJZAA | 0615917397 | FRSN 001:0166 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIA New Install
223686 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04867628 | High | 2 | Rejected | Rejected | Rejected | Covered by FTTH CAPEX Project | Rejected | العميل مخدوم بالفايبر FDT057-1 , SP 4 P5-8, ODF 4 P5-8, TB 7 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/2/2011 |  |  |  | ICMS027 (Jizan) | [8 empty] | 28/07/2013 | South | 27 | JIZAN |  | ABA4 | 0303200762 | ABA4 076:0034 |  |  | بى وزارة الصحة - ادارة التموين ال |  | 0542489967 |  | ET15 | ابو عريش - جيزان
223688 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04868914 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية تركيب للمشترك على البكسيات الداخلية رقم 017+023-022-021-020 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/2/2011 |  |  |  | Ali Zogmah | [8 empty] | 24/09/2013 | South | 27 | JIZAN |  | JIZA | 0303200762 | JIZA 058:0023 |  |  | بى وزارة الصحة - ادارة التموين ال |  | 0542488967 |  | ET15 | جيزان
223692 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04872097 | High | 2 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة عند العميل على البكسية الداخلية 001 كبينة 022 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/2/2011 |  |  |  | ICMS027 (Jizan) | [8 empty] | 25/07/2013 | South | 27 | JIZAN |  | ABAR | 0303200762 | ABAR 022:0002 |  |  | بى وزارة الصحة - ادارة التموين ال |  | 0556559279 |  | ET15 | ابو عريش - جيزان
223695 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04875312 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 2/2/2011 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN | 1127000170 | AMRH | 0657329835 | AMRH 002:002 |  |  | جامعة جازان |  | 0566997551 |  | ET14 | جيزان
223703 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04913646 | High | 6 | Rejected | Rejected | Rejected | Covered by FTTH network, needs TB installation | Rejected | يوجد بغرفة إتصالات المبنى علبتين الياف بصرية FTTH بياناتها كالتالي : SHTIJZU 0629 FTTH/FDT 062 ODF17 PORT 1-32 SP17PORT 1-32 TB 012 ------------------- SHTIJZU 0634 FTTH/FDT 062 ODF18 PORT 1-32 SP18PORT 1-32 TB 013 يرجى تعديل بطاقة الخط للعميل من الشبكة النحاسية لشبكة الFTTH | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 5/25/2011 |  |  |  | Khalid Muaafa | [8 empty] | 29/09/2013 | South | 27 | JIZAN | 1127000555 | JIZA | 0182803936 | JIZA 062:0083 |  |  | اييس الهيئة السعودية للمو صفات والم |  | 0506494345 |  | ET14 | جيزان
223704 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04914462 | High | 8 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 006 | 002 | 1-2 |  |  |  | Secondary | 1327000705 | Checked | 1327000705 | Completed | Approved | 01/12/2013 | 1311283227 | ICMS | Completed |  |  | In Progress | 01/12/2013 | 30/12/2013 |  | 5/7/2012 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 28/11/2013 | South | 27 | JIZAN |  | ARDA3 | 0303200762 | ARDA3 005:0101 |  |  | مستوصف - العارضه |  | 0532475981 |  | ET35 | JZN
251514 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04964090 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 10/2/2013 |  |  |  | Emad Mahdi | [9 empty] | South | 27 | JIZAN |  | DARBJZ00 | 0615917397 | DARB 0073462528 |  |  | وزارة التربية والتعليم |  | 505766455 |  | DIA New Install
209609 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04992879 | High | 7 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | تم الاتصال على الرقم المرفق وابلغنا بعدم معلرفته بالموقع | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/3/2013 |  |  |  | Jaber Abdaly | [8 empty] | 28/10/2013 | South | 27 | JIZAN |  | SBYA | 0643800713 | 021:0003 | 2MBPS_E2E |  | MINISTRY OF EDUCATION | NA | 0501702118 |  | ET14 | SBYA05-SBYA05 IP81 | SABYA
223741 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04994318 | High | 8 | Under Reject | Rejecting | In Progress | In Progress | In-Progress | العميل لا يرد | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 11/17/2012 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZFC | 0000000000 | 0 |  |  | محمد يوسف ناغي للسيا رات |  | 0500021256 |  | ET15 | جيزان
252589 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 04994318 |  | 8 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/17/2012 | [13 empty] | South | 27 | JIZAN |  | JIZFC | 2017323833 | JIZA 038:0075 |  |  | محمد يوسف ناغي للسيا |  | 500021256 |  |  | Jizan
223755 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05014400 | High | 6 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 014 | 004 | 4 |  |  |  | Secondary | 1327000690 | Checked | 1327000690 | Completed | Approved | 25/11/2013 | 1311212992 | ICMS | Completed |  |  | In Progress | 25/11/2013 | 30/12/2013 |  | 4/18/2011 |  |  | Design Completed | Emad Mahdi | Hasan Ghashim | Emad Mahdi | [6 empty] | 21/11/2013 | South | 27 | JIZAN |  | BAYS | 0303200762 | BAYS 014:0015 |  |  | يش م اداره - الرعايه الول يه بقطاع |  | 0506783937 |  | ET35 | JZN
223767 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05034065 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | جوال العميل مغلق الامكانية واصلة على جدار العميل في الموقع الجديد يتم نقل الخطوط من كبينة 076 الى الموقع الادارة الجديد في مخطط 6 063 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 7/16/2012 |  |  |  | Ali Zogmah | [8 empty] | 08/10/2013 | South | 27 | JIZAN |  | JIZA | 0303623507 | JIZA 076:0070 |  |  | اصلحيه - سجن جيزان ا لجديد |  | 0569996618 |  | ET14 | جيزان
223770 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05038760 | High | 7 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 030 | 110+101B+106B | 4 |  |  |  | Secondary | 1327000382 | Checked | 1327000382 | Completed | Approved | 11/07/2013 | 1307086294 | ICMS | Completed |  |  | Completed | 11/07/2013 | 30/05/2013 |  | 7/16/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 08/07/2013 | South | 27 | JIZAN |  | ABAR | 0303704728 | ABAR 030:0109 |  |  | مكتب - مدير سجن ابوع ريش |  | 0557364973 |  | ET14 | ابو عريش - جيزان
223772 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05039979 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال لا يخص المشترك | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 7/16/2012 |  |  |  | Mahdy Salami | [8 empty] | 19/09/2013 | South | 27 | JIZAN |  | TUWA | 0303178287 | TUWA 002:0219 |  |  | مركز - سجون الطوال |  | 0557364973 |  | ET14 | مركز الطوال - جيزان
231193 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05063005 | High | 6 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | المشترك يرغب في الخدمة ولكن هو متواجد في جدة ومقر الطلب الخاص فية جدة وليس جازان | [9 empty] | Indeterminate | [11 empty] | 13/07/2013 |  | 11/14/2012 12:00:00 AM |  |  |  | Mahdy Salami | [8 empty] | 15/09/2013 | South | 27 | JIZAN |  | XXXX | 0000000000 | XXXX |  |  | Baabbad-Salah - |  | 504382743 |  | NA | JIZAN
251366 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05063005 |  | 2 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 11/14/2012 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | SHTIJZAB | 0196673067 | JIZA 151:0069 |  |  | شركة الكمبيوتر |  | 966504382743 |  | DIAN DIA New Install
223803 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05093004 | High | 6 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | العميل لا يرد العميل لا يرد جوال العميل مغلق | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 12/22/2012 |  |  |  | Ali Zogmah | [8 empty] | 20/11/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | بجاز الداره العامه للتربي ه والتعلي |  | 0500759848 |  | ED02 | جيزان
223805 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05096041 | High | 2 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية تركيب للمشترك في البكسية رقم 033 في الكبينة 005 ويوجد سلك خدمة | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/15/2012 |  |  |  | Mahdy Salami | [8 empty] | 12/09/2013 | South | 27 | JIZAN |  | SLHD | 0000000000 | SLHD 005:0031 |  |  | الشركه - العربيه لتج اره العود |  | 0505101134 |  | ET14 | سوق الحد- جيزان
223817 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05115071 | High | 1 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | العميل لا يرد العميل لا يرد العميل لا يرد | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 12/22/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | JIZA 082:0109 |  |  | الجمعية السعودية لهو |  | 553031981 |  | ET14 | JZN
240368 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05225386 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 09/04/2013 12:00:00 AM |  |  |  | Emad Mahdi | [9 empty] | South | 27 | JIZAN |  | BAYS | 2001288701 | BAYS 035:0003 |  |  | بلديه العالية |  | 560022998 |  | نقل هاتف | BAYS 035:0003
223923 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05272095 | High | 6 | Issue RFW | New | Completed | BSW Work | Completed |  | Copper | 021 | 022 | 9 |  |  |  | Secondary | 1327000534 | Checked | 1327000534 | Completed | Approved | 28/10/2013 | 1310231888 | ICMS | Completed |  |  | In Progress | 28/10/2013 | 30/05/2013 |  | 1/8/2013 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 23/10/2013 | South | 27 | JIZAN |  | ABAR | 0000000000 | 0 |  |  | رة مؤسسة مركز النسيم ال بارد للتج |  | 0502787369 |  | ET14 | ابو عريش - جيزان
223924 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05274981 | High | 6 | Rejected | Rejected | Rejected | Service order belongs to other stage / Wrong reason code/ Wrong region/ District/ City code | Rejected | العميل يقع في منطقه غير مخدومه رمز السبب 5 | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 1/8/2013 |  |  |  | Emad Mahdi | [8 empty] | 30/10/2013 | South | 27 | JIZAN |  | BAYS | 0000000000 | 0 |  |  | لده شركة عبدالله بن محمد باجبير وا |  | 0555699759 |  | ET14 | بيش - جيزان
223980 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05365901 | High | 7 | Under Reject | Rejecting | In Progress | In Progress | In-Progress | المشتر لا يرد | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 11/18/2012 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | SBY7A | 0000000000 | 0 |  |  | مصنع - اتحاد الخليج للغذيه |  | 0509608561 |  | ET15 | صبياء- جيزان
223992 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05378387 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال خاطئ | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/21/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | صندوق تنميه الموارد |  | 553031981 |  | ET14 | JZN
223998 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05385720 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | رقم الاتصال لايخص المشترك | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/3/2012 |  |  |  | Mahdy Salami | [8 empty] | 20/09/2013 | South | 27 | JIZAN |  | SLHD | 0000000000 | RHQU4089 20121006 |  |  | حده شركه - الكهراباء الس عوديه الم |  | 0505711530 |  | ET34 | سوق الحد- جيزان
223999 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05389790 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 004 | 004 | 1-2 |  |  |  | Secondary | 1327000468 | Checked | 1327000468 | Completed | Approved | 11/09/2013 | 1309018746 | ICMS | Completed |  |  | Completed | 11/09/2013 | 30/05/2013 |  | 10/3/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Mahdy Salami | [6 empty] | 01/09/2013 | South | 27 | JIZAN |  | KJRH | 0000000000 | NJRU1206 20121013 |  |  | ىالمدرسه - البتدائيه بالحى الشر |  | 0503094678 |  | ET42 | مركز الطوال - جيزان
224004 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05395205 | High | 1 | Issue RFW | New | Completed | Secondary Work (DP) | In-Progress | [8 empty] | Secondary |  | Indeterminate |  | In-Progress | In-Progress |  | 1312183853 | ICMS | In-Progress |  |  | Design |  | 30/12/2013 |  | 10/3/2012 |  |  | Design Team | Jaber Abdaly | Hasan Ghashim | Jaber Abdaly | [6 empty] | 18/12/2013 | South | 27 | JIZAN |  | SBYA | 0000000000 | SBYA 019:0213 |  |  | شركة بلشرف التجارية |  | 553031981 |  | ET14 | JZN
224017 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05423458 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 11/19/2012 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZFA | 0000000000 | 0 |  |  | شركه - ذيب التاجير ا لسيارات |  | 0540660099 |  | ET14 | جيزان
251434 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05424890 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 6/5/2013 |  |  |  | Emad Mahdi | [9 empty] | South | 27 | JIZAN |  | BYSHJZAB | 2004080435 | BAYS 035:0067 |  |  | امانة بلدية منطقة جيزات |  | 560022998 |  | توصيل جديد خ. اكيد
224028 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05448191 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 10/3/2012 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZDA | 0000000000 | 0 |  |  | الهاد فرع مؤسسة محمد عبد ا للطيف عبد |  | 0504600600 |  | ET14 | جيزان
224034 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05455640 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية تركيب للمشترك على البكسية 096 كبينة 046 . وايضا على البكسية 063 كبينة 092 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 3/31/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 07/07/2013 | South | 27 | JIZAN |  | JIZ7A | 0303508538 | JIZA 046:0015 |  |  | مة لل وزارة الداخليه / الم ديرية الع |  | 0569552123 |  | ET15 | جيزان
224037 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05457843 | High | 8 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة على جدار العميل ويوجد بكسيتين جدارية 046:083 046:84 بها امكانية التركيب يحول للتركيب | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 8/6/2012 |  |  |  | Ali Zogmah | [8 empty] | 12/11/2013 | South | 27 | JIZAN |  | JIZ7A | 0657037044 | JIZA 072:0029 |  |  | قيادة قوات امن المنش ات |  | 0500130947 |  | ET14 | جيزان
251618 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05460129 |  | 6 | Under Reject | Rejecting | In Progress | In Progress | In-Progress | رقم الاتصال خاطئ | Copper | [8 empty] | Indeterminate | [13 empty] | 6/4/2013 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | SWYSJZAB | 2004080435 | JIZA 092 |  |  | امانة بلدية منطقة جيزات |  | 504250526 |  | توصيل جديد خ. اكيد
240359 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05466305 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 28/05/2013 12:00:00 AM |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZA | 0303530959 | JIZA 060:0088 |  |  | بلدية منطقة جيزان- مبناء الصيانه |  | 504250526 |  | تأسيس افاق واير لس | JIZA 060:0088
242753 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05473745 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 020 | 051 | 0 |  |  |  | Secondary | 1327000687 | Checked | 1327000687 | Completed | Approved | 20/11/2013 | 1311142790 | ICMS | Completed |  |  | In Progress | 20/11/2013 |  |  | 9/10/2013 12:00:00 AM |  |  | Design Completed | Jaber Abdaly | Hasan Ghashim | Jaber Abdaly | [6 empty] | 14/11/2013 | South | 27 | JIZAN |  | SBYA | 303816445 | SBYA 020:0053 |  |  | مكتب وزارة العمل | والشؤون الإجتماعية | 0555772582 | 0555772582 | ET35 | صبياء | صبياء
224058 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05505501 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 1/28/2013 |  |  |  | Emad Mahdi | [9 empty] | South | 27 | JIZAN |  | GRIF | 0000000000 | 0 |  |  | مؤسسة عبود احمد المج رذي |  | 0506398531 |  | ET14 | الدرب
224059 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05507044 | High | 8 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد امكانية تركيب للمشترك على البكسية 094 كبينة 016 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/20/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 07/07/2013 | South | 27 | JIZAN |  | JIZ7A | 0000000000 | 0 |  |  | وزارة الداخلية - سلح الحدود |  | 0504509454 |  | ET15 | جيزان
224106 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05583548 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | جوال العميل مغلق جوال العميل مغلق | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 11/21/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | شركه سمسا للنقل السر يع |  | 0559022433 |  | ET14 | جيزان
224141 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05704733 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | يوجد سلك خدمة وامكانية في البكسية 067-+070B في الكبينة 069 | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 4/15/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 28/07/2013 | South | 27 | JIZAN |  | JIZA | 0303200762 | JIZA 069:0067 |  |  | وزاره الصحه - مستشفى جيزان |  | 0509544424 |  | ET35 | جيزان
240314 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05709641 | high | 1 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | تم الاتصال على العميل رقم الجوال 0590010468 اكثر من اربع مرات متفرقة وتم ارسال رسالة | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 9/12/2013 12:00:00 AM |  |  |  | Mahdy Salami | [8 empty] | 06/11/2013 | South | 27 | JIZAN |  | ABAR | 0308198383 | ABAR 030:0071 |  |  | وزارة الصحة |  | 590010468 |  | EBU | ABAR 030:0071
251585 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05709641 |  | 1 | Under Reject | Rejecting | In Progress | In Progress | In-Progress | هاتف المشترك مفصول عن الخدمة نهائيا | Copper | [8 empty] | Indeterminate | [13 empty] | 5/7/2013 |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | ARSHJZ00 | 0308198383 | ABAR 030:0071 |  |  | وزارة الصحة |  | 590010468 |  | DIA New Install
233112 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05739969 | High | 7 | Issue RFW | New | Completed | Distribution Point | Completed |  | Copper | 011 | 101-102 | 0 |  |  |  | Secondary | 1327000384 | Checked | 1327000384 | Completed | Approved | 10/07/2013 | 1307106449 | ICMS | Completed |  |  | Completed | 10/07/2013 |  |  | 05/05/2013 12:00:00 AM |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 10/07/2013 | South | 27 | JIZAN |  | DARB | 0620258571 | DARB 011:0008 |  |  | الدفاع المدني |  | 551764648 |  | ET35 | الدرب-جيزان
233113 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05742757 | High | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 011 | 0008 | 000 |  |  |  | Secondary | 1327000384 | Checked | 1327000384 | Completed | Approved | 10/07/2013 | 1307106449 | ICMS | Completed |  |  | Completed | 10/07/2013 |  |  | 05/05/2013 12:00:00 AM |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 10/07/2013 | South | 27 | JIZAN |  | DARB | 0620258342 | DARB 011:0008 |  |  | الدفاع المدني |  | 551764648 |  | ET35 | الدرب-جيزان
224184 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05869812 | High | 7 | Rejected | Rejected | Rejected | Covered by FTTH CAPEX Project | Rejected | العميل مخدوم بفايبر FDT062-1, ODF 2 PORT 3-6,SP 2 PORT 3-6, FB 005. | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 10/16/2012 |  |  |  | ICMS027 (Jizan) | [8 empty] | 08/07/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | 0 |  |  | ادارة - المجاهدين بم نطقة جيزا |  | 0569437643 |  | ET15 | جيزان
231017 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05876283 | High | 7 | Rejected | Rejected | Rejected | Covered by FTTH network, needs TB installation | Rejected | يوجد على موقع العميل علبة الياف بصرية FTTH بياناتها كالتالي : SHTI JZU 0516 FTTH/FDT 042 ODF5/PORT 5-19 SP5/PORT 5-19 TB 036 يرجى تعديل بطاقة الخط للعميل من الشبكة النحاسية لشبكة الـ FTTH | [9 empty] | Indeterminate | [11 empty] | 17/06/2013 |  | 3/27/2013 12:00:00 AM |  |  |  | Khalid Muaafa | [8 empty] | 29/09/2013 | South | 27 | JIZAN |  | JIZA | 0000000000 | JIZA 042:0017 |  |  | FADI-- - |  | 505353395 |  | NA | JIZAN
251816 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05876283 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 3/27/2013 |  |  |  | Khalid Muaafa | [9 empty] | South | 27 | JIZAN |  | BADRDN80 | 0628378304 | JIZA 042:0017 |  |  | مؤسسة سناس للتجارة |  | 966555737085 |  | توصيل جديد خ. اكيد
224193 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05913749 | High | 7 | Rejected | Rejected | Rejected | Customer Unavailable | Rejected | جوال العميل مغلق جوال العميل مغلق جوال العميل مغلق | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 5/5/2012 |  |  |  | Ali Zogmah | [8 empty] | 04/11/2013 | South | 27 | JIZAN |  | JZNU1159 | 0128440062 | FQHA 015:0008 |  |  | المؤسسة العامة للتدر |  | 503106929 |  | ET42 | JZN
231192 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05922298 | High | 6 | Rejected | Rejected | Rejected | Customer rejected the service | Rejected | حسب افادة - اسامة العمري 0534555329 تم تركيب الهواتف للبنك العربي في فرسان ولا يحتاج الي خدمة جديدة | [9 empty] | Indeterminate | [11 empty] | 12/07/2013 |  | 5/8/2012 12:00:00 AM |  |  |  | Mahdy Salami | [8 empty] | 09/09/2013 | South | 27 | JIZAN |  | SCCT | 0000000000 | SCCT 1111111100 |  |  | MOHAMMED-AL SUNADI - |  | 506406248 |  | NA | JIZAN
227041 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05968244 |  | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 049 | 0008 | 0 |  |  |  | Secondary | 1227W00026 | Checked | 1227W00026 | Completed | Approved | 06/01/2013 | 1212190776 | ICMS | Completed |  |  | Completed | 19/12/2012 | 15/06/2013 |  | 5/6/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 19/12/2012 | South | 27 | JIZAN |  | SBY7A | 2013964176 | SBYA 049:0008 |  | E02 | شركة الجميح للمعدات فرع جازان |  | 0559969663 | 0559969663 | ET14 | 2706 | صبياء- جيزان
111087 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05968667 |  | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed | [8 empty] | Secondary | 1227W00026 | Checked | 1227W00026 | Completed | Approved | 06/01/2013 | 1212190776 | ICMS | Completed |  |  | Completed | 19/12/2012 | 15/06/2013 |  | 5/6/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 19/12/2012 | South | 27 | JIZAN |  | SBY7A | 2013964389 | SBYA 049:0007 |  | E02 | شركة الجميح للمعدات فرع جازان |  | 0559969663 | 0559969663 | ET14 | 2706 | صبياء- جيزان
227039 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05969118 |  | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 049 | 0007 | 0 |  |  |  | Secondary | 1227W00026 | Checked | 1227W00026 | Completed | Approved | 06/01/2013 | 1212190776 | ICMS | Completed |  |  | Completed | 19/12/2012 | 15/06/2013 |  | 5/6/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 19/12/2012 | South | 27 | JIZAN |  | SBY7A | 2013964508 | SBYA 049:0007 |  | E02 | شركة الجميح للمعدات فرع جازان |  | 0559969663 | 0559969663 | ET14 | 2706 | صبياء- جيزان
227040 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05969598 |  | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 049 | 0007 | 0 |  |  |  | Secondary | 1227W00026 | Checked | 1227W00026 | Completed | Approved | 06/01/2013 | 1212190776 | ICMS | Completed |  |  | Completed | 19/12/2012 | 15/06/2013 |  | 5/6/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 19/12/2012 | South | 27 | JIZAN |  | SBY7A | 2013964664 | SBYA 049:0007 |  | E02 | شركة الجميح للمعدات فرع جازان |  | 0559969663 | 0559969663 | ET14 | 2706 | صبياء- جيزان
227038 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05970108 |  | 7 | Assign | Covered by DWO | Completed | Secondary Work (DP) | Completed |  | Copper | 049 | 0007 | 0 |  |  |  | Secondary | 1227W00026 | Checked | 1227W00026 | Completed | Approved | 06/01/2013 | 1212190776 | ICMS | Completed |  |  | Completed | 19/12/2012 | 15/06/2013 |  | 5/6/2012 |  |  | Design Completed | ICMS027 (Jizan) | Hasan Ghashim | Cecilio Bactol | [6 empty] | 19/12/2012 | South | 27 | JIZAN |  | SBY7A | 2013964176 | SBYA 049:0007 |  | E02 | شركة الجميح للمعدات فرع جازان |  | 0559969663 | 0559969663 | ET14 | 2706 | صبياء- جيزان
224203 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05975279 | High | 2 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الطلب يخص القوات المسلحة في ابو عريش وهم يرغبون في وجود كبينة داخلية لديهم بدلا عن الكبينة 023 MOJR 023 رقم المنسق /0555550382 | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 5/6/2012 |  |  |  | Mahdy Salami | [8 empty] | 05/11/2013 | South | 27 | JIZAN |  | MOJR | 0175363335 | MOJR 023:0011 |  |  | عام و مدير عام الشئون الما لية/ديوان |  | 0501575854 |  | ET15 | ابو عريش - جيزان
240465 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05984566 | High | 7 | Issue RFW | New | Completed | Secondary Work (DP) | Completed |  | Copper | 115 | 081 | 00 |  |  |  | Secondary | 1327000519 | Checked | 1327000519 | Completed | Approved | 21/10/2013 | 1310101543 | ICMS | Completed |  |  | In Progress | 21/10/2013 |  |  | 4/22/2013 12:00:00 AM |  |  | Design Completed | Ali Zogmah | Hasan Ghashim | Emad Mahdi | [6 empty] | 10/10/2013 | South | 27 | JIZAN |  | SBYA | 2019591983 | SBYA 115:0120 |  |  | البنك الاهلي التجاري |  | 569069695 |  | تاسيس خط ثابت اضافي | SBYA 115:0120
252682 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 05984566 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 4/22/2013 | [13 empty] | South | 27 | JIZAN |  | SBYA | 2019591983 | SBYA 115:0120 |  |  | البنك الاهلي التجاري |  | 569069695 |  |  | Jizan
209610 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 06060916 | High | 7 | Assign | Covered by DWO | Completed | BSW Work | Completed |  | Copper | 062 | 156+167 | 11-12 |  |  |  | Secondary | 1327000498 | Checked | 1327000498 | Completed | Approved | 01/10/2013 | 1309300850 | ICMS | Completed |  |  | Completed | 01/10/2013 | 30/05/2013 | 30/01/2014 | 3/3/2013 |  |  | Design Completed | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 30/09/2013 | South | 27 | JIZAN |  | SAMI | 0100685563 | 062:156+167B | 512KBPS_E2E |  | BIN ZAGR COMPANY | NA | 0556794873 |  | ET14 | JIZAN-JIZAN IP158 | SAMITAH
251686 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 06060916 |  | 1 | Issue RFW | New | Completed | BSW Work | In-Progress |  | Copper | 062 | 156+167 | 5 |  |  |  | Secondary | 1427000057 | Indeterminate | 1327000498 | In-Progress | In-Progress |  | 1402025149 | ICMS | In-Progress |  |  | Completed |  |  |  | 12/3/2012 |  |  | Design Team | Mahdy Salami | Hasan Ghashim | Mahdy Salami | [6 empty] | 02/02/2014 | South | 27 | JIZAN |  | SHMTJZ00 | 0628393869 | SAMI 014:0054 |  |  | شركة سعيد محمد عبي وشركاه |  | 966556794873 |  | توصيل جديد خ. اكيد
251708 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 06543746 |  | 1 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 12/5/2013 |  |  |  | Jaber Abdaly | [9 empty] | South | 27 | JIZAN |  | SBYAJZ00 | 0615917397 | SBYA 020:0093 |  |  | وزارة التربية والتعليم |  | 500500018 |  | توصيل جديد خ. اكيد
243246 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 06638166 | High | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 19/11/2013 12:00:00 AM |  |  |  | Mahdy Salami | [9 empty] | South | 27 | JIZAN |  | ABAR | 2022869879 | ABAR 062 |  |  | احمد | حجازي | 550578866 |  | EBU | ABAR 062
224238 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 06834002 | High | 7 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | تمت خدمة العميل بأمر عمل سابق قيد التنفيذ بتوصيل طرفية ONT وتم التنسيق مع مدير الحساب وممثل الهيئة بإلغاء طلب توصيل الشبكة النحاسية في ظل وجود شبكة فايبر . | [9 empty] | Indeterminate | [11 empty] | 30/05/2013 |  | 5/14/2011 |  |  |  | Khalid Muaafa | [8 empty] | 30/09/2013 | South | 27 | JIZAN |  | JIZA | 0303453229 | JIZA 042:0108 |  |  | ام مكتب - هيئه التحقيق والدعاء ال |  | 0552580007 |  | ET35 | جيزان
224239 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 06852294 | High | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 5/15/2011 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZA | 0632855222 | JIZA 075:0090 |  |  | جازان المديريه العامه للمي اه بمنطقة |  | 0555877745 |  | ET15 | جيزان
224256 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 08641347 | High | 6 | Rejected | Rejected | Rejected | Facility available / Customer already served | Rejected | الامكانية متوفرة لدي العميل في البكسية رقم 081-089 من كبينة رقم 151 .. والبكسية داخل حرم المبني المحكمة العامة وبها الامكانية التركيب .. يحول للتركيبات . | [9 empty] | Indeterminate | [11 empty] | 30/12/2013 |  | 5/15/2011 |  |  |  | Ali Zogmah | [8 empty] | 14/01/2014 | South | 27 | JIZAN | 1127000592 | JIZA | 0303311580 | JIZA 151:0081 |  |  | جازان وزارة العدل رئاسة مح اكم منطقة |  | 0531698077 |  | ET15 | جيزان
252164 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 08641347 |  | 6 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 5/15/2011 | [13 empty] | South | 27 | JIZAN |  | JIZA | 0303311580 | JIZA 151:0081 |  |  | وزارة العدل رئاسة مح |  | 531698077 |  |  | Jizan
252181 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 09076273 |  | 7 |  |  | In Progress | In Progress | In-Progress |  | Copper | [8 empty] | Indeterminate | [13 empty] | 6/8/2011 | [13 empty] | South | 27 | JIZAN |  | JIZDA | 2008167632 | JIZA 082:0062 |  |  | شركة صالح سالم بابقي |  | 542278990 |  |  | Jizan
243708 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 1039894 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 11/6/2013 2:32:37 PM | [13 empty] | South | 27 | JIZAN |  | SHMTJZ00 | 615917397 | JEDDAH-JIZAN MDIA33 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIAN DIA New Install | JEDDAH-JIZAN MDIA33 (1MBPS_E2E:MDIA)
243845 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 1176177 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 10/21/2013 9:51:00 AM | [13 empty] | South | 27 | JIZAN |  | SBYAJZ00 | 615917397 | JEDDAH-JIZAN MDIA71 |  |  | وزارة التربية والتعليم |  | 549313688 |  | DIA New Install | JEDDAH-JIZAN MDIA71 (1MBPS_E2E:MDIA)
243700 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 1177760 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 10/3/2013 9:19:29 AM | [13 empty] | South | 27 | JIZAN |  | BAYS07 | 615917397 | JEDDAH-JIZAN MDIA72 |  |  | وزارة التربية والتعليم |  | 505766455 |  | DIAN DIA New Install | JEDDAH-JIZAN MDIA72 (1MBPS_E2E:MDIA)
243976 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 1181000 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 10/21/2013 10:40:34 AM | [13 empty] | South | 27 | JIZAN |  | BAYS07 | 615917397 | JEDDAH-JIZAN MDIA74 |  |  | وزارة التربية والتعليم |  | 505766455 |  | DIA New Install | JEDDAH-JIZAN MDIA74 (1MBPS_E2E:MDIA)
243913 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 1188439 | HIGH | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 10/8/2013 12:29:42 PM | [13 empty] | South | 27 | JIZAN |  | DARBJZ00 | 615917397 | JEDDAH-JIZAN MDIA81 |  |  | وزارة التربية والتعليم |  | 505766455 |  | DIA New Install | JEDDAH-JIZAN MDIA81 (1MBPS_E2E:MDIA)
243767 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 1819068 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 10/6/2013 10:46:06 AM | [13 empty] | South | 27 | JIZAN |  | DYHMJZAA | 2004080435 | JIZAN-JIZAN IP214 |  |  | امانة بلدية منطقة جيزات |  | 557799129 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP214 (2MBPS_E2E:IP)
243718 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 2092117 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 2/19/2013 3:18:50 PM | [13 empty] | South | 27 | JIZAN |  | EDABJZAE | 2004080435 | JIZAN-JIZAN IP217 |  |  | امانة بلدية منطقة جيزات |  | 501259928 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP217 (2MBPS_E2E:IP)
243494 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 2108718 |  | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 20131107 |  |  |  | Ali Zogmah | [9 empty] | South | 27 | JIZAN |  | JIZA | 303469443 | JIZA 173:0012 |  |  | GID |  | 554701114 | 555220565 | ET41 | JEZAN
243581 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 2176654 |  | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 20121112 | [13 empty] | South | 27 | JIZAN |  | JIZA | 303469443 | JIZA 093:0120 |  |  | GID |  | 554701114 | 555220565 | ET15 | JEZAN
243580 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 2191880 |  | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 20121112 | [13 empty] | South | 27 | JIZAN |  | JIZA | 303469443 | JIZA 093:0120 |  |  | GID |  | 554701114 | 555220565 | ET15 | JEZAN
244026 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 2686774 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 9/17/2013 9:53:53 AM | [13 empty] | South | 27 | JIZAN |  | BADRDN52 | 615917397 | JEDDAH-JIZAN MDIA48 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIA New Install | JEDDAH-JIZAN MDIA48 (1MBPS_E2E:MDIA)
244014 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 2694266 | HIGH | 2 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 3/2/2013 9:41:15 AM | [13 empty] | South | 27 | JIZAN |  | BADRDN39 | 649556032 | JIZAN-JIZAN IP230 |  |  | الشركة المتحدة |  | 507930699 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP230 (2MBPS_E2E:IP)
243852 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 2930836 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 11/19/2012 9:32:16 AM | [13 empty] | South | 27 | JIZAN |  | RYANJZAE | 642366351 | JIZAN-JIZAN IP147 |  |  | مؤسسة البريد السعودي |  | 500668339 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP147 (256KBPS_E2E:IP)
243986 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 3044307 | HIGH | 2 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 6/30/2013 7:16:18 AM | [13 empty] | South | 27 | JIZAN |  | BADRDN09 | 185722309 | JIZAN-JIZAN IP331 |  |  | وكالة الوزارة للشئؤون الاجتماعية |  | 966569939123 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP331 (2MBPS_E2E:IP)
243666 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 3474107 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 9/29/2013 9:23:11 AM | [13 empty] | South | 27 | JIZAN |  | FRSNJZAA | 254875635 | JIZAN-JIZAN IP348 |  |  | الرئاسة العامة للامر بالمعروف والنهي عن المنكر |  | 555255323 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP348 (1MBPS_E2E:IP)
243761 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 3531230 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 9/17/2012 9:18:44 AM | [13 empty] | South | 27 | JIZAN |  | ARSHJZ00 | 797014397 | JIZAN-JIZAN IP124 |  |  | هيئة التحقيق والادعاء العام |  | 966505453424 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP124 (6MBPS_E2E:IP)
243649 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 3581270 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 10/9/2013 7:20:20 AM | [13 empty] | South | 27 | JIZAN |  | SHMTJZ00 | 615917397 | JEDDAH-JIZAN MDIA54 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIAN DIA New Install | JEDDAH-JIZAN MDIA54 (1MBPS_E2E:MDIA)
243640 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 3650598 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 7/21/2013 11:08:13 AM | [13 empty] | South | 27 | JIZAN |  | HMTRJZAK | 196663223 | JIZAN-JIZAN IP252 |  |  | وزارة الداخلية |  | 559798999 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP252 (2MBPS_E2E:IP)
243716 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 3864271 | HIGH | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 11/6/2013 10:04:25 AM | [13 empty] | South | 27 | JIZAN |  | SENAJZAF | 615917397 | JEDDAH-JIZAN MDIA57 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIAN DIA New Install | JEDDAH-JIZAN MDIA57 (1MBPS_E2E:MDIA)
243531 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 3967012 |  | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 20130917 | [13 empty] | South | 27 | JIZAN |  | JIZ7A | 303469443 | JIZA 046:0013 |  |  | GID |  | 554701114 | 555220565 | ET15 | JEZAN
244085 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 4356066 | HIGH | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 4/29/2013 4:37:01 PM | [13 empty] | South | 27 | JIZAN |  | BADRDN124 | 691717682 | JIZAN-JIZAN IP165 |  |  | مصرف الانماء |  | 966506049779 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP165 (64KBPS_E2E:IP)
244083 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 4356305 | HIGH | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 3/12/2013 1:18:20 PM | [13 empty] | South | 27 | JIZAN |  | BADRDN122 | 691717682 | JIZAN-JIZAN IP164 |  |  | مصرف الانماء |  | 966506049779 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP164 (64KBPS_E2E:IP)
243888 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 4418941 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 2/18/2013 11:35:34 AM | [13 empty] | South | 27 | JIZAN |  | SHTIJZAB | 692188527 | JIZAN-JIZAN IP102 |  |  | الهيئه السعودية للتخصصات الصحية |  | 566969665 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP102 (2MBPS_E2E:IP)
243917 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 4695170 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 11/27/2012 11:52:13 AM | [13 empty] | South | 27 | JIZAN |  | SBYAJZ00 | 649511381 | JIZAN-RIYADH DIA4 |  |  | وزارة الزراعة |  | 569161162 |  | DIA Install Change | JIZAN-RIYADH DIA4 (6MBPS_E2E:DIA)
244101 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 4821524 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 11/7/2013 7:45:55 AM | [13 empty] | South | 27 | JIZAN |  | BADRDN143 | 615917397 | JEDDAH-JIZAN MDIA35 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIA New Install | JEDDAH-JIZAN MDIA35 (1MBPS_E2E:MDIA)
243813 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 4860437 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 10/9/2013 7:23:06 AM | [13 empty] | South | 27 | JIZAN |  | FRSNJZAA | 615917397 | JEDDAH-JIZAN MDIA9 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIA New Install | JEDDAH-JIZAN MDIA9 (1MBPS_E2E:MDIA)
243764 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 4964090 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 10/2/2013 12:02:57 PM | [13 empty] | South | 27 | JIZAN |  | DARBJZ00 | 615917397 | JEDDAH-JIZAN MDIA86 |  |  | وزارة التربية والتعليم |  | 505766455 |  | DIA New Install | JEDDAH-JIZAN MDIA86 (1MBPS_E2E:MDIA)
243623 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 5063005 | HIGH | 2 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 11/14/2012 11:00:44 AM | [13 empty] | South | 27 | JIZAN |  | SHTIJZAB | 196673067 | JEDA02_00_203-JIZA03_41 DIA2 |  |  | شركة الكمبيوتر |  | 966504382743 |  | DIAN DIA New Install | JEDA02_00_203-JIZA03_41 DIA2 (1MBPS_E2E:DIA)
243669 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 511566 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 9/29/2013 2:20:21 PM | [13 empty] | South | 27 | JIZAN |  | ARSHJZ00 | 615917397 | JEDDAH-JIZAN MDIA37 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIAN DIA New lnstall | JEDDAH-JIZAN MDIA37 (1MBPS_E2E:MDIA)
243689 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 5424890 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 6/5/2013 10:10:27 AM | [13 empty] | South | 27 | JIZAN |  | BYSHJZAB | 2004080435 | JIZAN-JIZAN IP316 |  |  | امانة بلدية منطقة جيزات |  | 560022998 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP316 (2MBPS_E2E:IP)
243861 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 5460129 | HIGH | 6 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 6/4/2013 9:50:08 AM | [13 empty] | South | 27 | JIZAN |  | SWYSJZAB | 2004080435 | JIZAN-JIZAN IP319 |  |  | امانة بلدية منطقة جيزات |  | 504250526 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP319 (2MBPS_E2E:IP)
244049 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 5876283 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 3/27/2013 11:07:19 AM | [13 empty] | South | 27 | JIZAN |  | BADRDN80 | 628378304 | JIZAN-JIZAN IP139 |  |  | مؤسسة سناس للتجارة |  | 966555737085 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP139 (256KBPS_E2E:IP)
243924 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 6060916 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 12/3/2012 3:55:10 PM | [13 empty] | South | 27 | JIZAN |  | SHMTJZ00 | 628393869 | JIZAN-JIZAN IP158 |  |  | شركة سعيد محمد عبي وشركاه |  | 966556794873 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP158 (512KBPS_E2E:IP)
243945 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 6543746 | HIGH | 1 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 12/5/2013 9:18:37 AM | [13 empty] | South | 27 | JIZAN |  | SBYAJZ00 | 615917397 | JIZAN-JIZAN IP397 |  |  | وزارة التربية والتعليم |  | 500500018 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP397 (2MBPS_E2E:IP)
243914 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 734397 | HIGH | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 11/6/2013 2:34:20 PM | [13 empty] | South | 27 | JIZAN |  | NSIMJZAB | 615917397 | JEDDAH-JIZAN MDIA27 |  |  | وزارة التربية والتعليم |  | 966505769857 |  | DIA New Install | JEDDAH-JIZAN MDIA27 (1MBPS_E2E:MDIA)
243793 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 946546 | HIGH | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 10/7/2013 12:49:58 PM | [13 empty] | South | 27 | JIZAN |  | SHTIJZAB | 615917397 | JEDDAH-JIZAN MDIA62 |  |  | وزارة التربية والتعليم |  | 561933477 |  | DIA New Install | JEDDAH-JIZAN MDIA62 (1MBPS_E2E:MDIA)
243910 | OSP PROGRAM HELD ORDER ( HO ) FOR EBU -2013 | 2013 | 980951 | HIGH | 7 |  |  | In Progress | In Progress | In-Progress | [10 empty] | Indeterminate | [13 empty] | 11/12/2013 8:31:31 AM | [13 empty] | South | 27 | JIZAN |  | BYSHJZAC | 2004080435 | JIZAN-JIZAN IP379 |  |  | امانة بلدية منطقة جيزات |  | 560022998 |  | توصيل جديد خ. اكيد | JIZAN-JIZAN IP379 (2MBPS_E2E:IP)
340 | [19 empty] | 340
المطلوب :
VLOOKUPهو عند استخدام دالة
للاسف لاتظهر النتيجة صحيحة بالعمودين
JopWorkOreder
المفترض تظهر القيمة 1127000637 وليس 092700031
Conrtactor Name
المفترض تظهر القيمة
Mohemmed Bin Gerboo EST.
وليس
STC CREW
شريحة المصدر هي
JZN