## D 11
Section ( D-11 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
`
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 12
Section ( D-12 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
`
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 13
Section ( D-13 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
`
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 14
Section ( D-14 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 14 | 17_T1 | 67 | 69.22 |  | 69.22 |  | 6.2298 |  | 69.22 | 12 |  | 19 |  | HDPI 125 MM
| 14_T2 | 67 | 69.28 |  | 69.28 |  | 6.2352 |  | 69.28 | 12 |  |  |  | HDPI 125 MM
| 12_T3 | 67 | 69.73 |  | 69.73 |  | 6.2757 |  | 69.73 | 11 |  |  |  | HDPI 125 MM
| 10_34 | 193 | 188.78 |  | 188.78 |  | 16.9902 |  | 188.78 | 20 | 6 |  |  | HDPI 125 MM
| 7_37 | 190 | 187.84 |  | 187.84 |  | 16.9056 |  | 187.84 | 32 | 2 |  |  | HDPI 125 MM
| 5_39 | 191 | 188.55 |  | 188.55 |  | 16.9695 |  | 188.55 | 34 |  |  |  | HDPI 125 MM
| A-A6 | 40 | 41.7 |  | 41.7 |  | 3.753 |  | 41.7 | 7 |  |  |  | HDPI 125 MM
| 51_T5 | 79 | 82.58 |  | 82.58 |  | 7.4322 |  | 82.58 |  | 1 |  |  | HDPI 125 MM
| T6-41 | 125 | 111.71 |  | 111.71 |  | 10.0539 |  | 111.71 | 18 | 3 |  |  | HDPI 125 MM
| T4-22 | 160 | 161.47 |  | 161.47 |  | 14.5323 |  | 161.47 | 2 | 1 |  |  | HDPI 125 MM
TOTAL |  | 1179 | 1170.86 | 0 | 1170.86 | 0 | 105.3774 | 0 | 1170.86 | 148 | 13 | 19 | 0
D 14 | TR28-S2 | 183 | 175.84 |  | 175.84 |  | 18.4632 |  |  | 5 | 2 |  | 3 | HDPI 200 MM
| 41-TR14 | 194 | 183.01 |  | 183.01 |  | 19.216 |  |  | 16 | 1 |  |  | HDPI 200 MM
| 41-S2 | 321 | 322.16 |  | 322.16 |  | 2.5 |  | 321.39 | 1 | 2 |  |  | HDPI 200 MM
| TR28-TR14 | 317 | 321.41 |  | 321.41 |  | 4.3754 |  | 315.05 | 0 | 0 |  |  | HDPI 200 MM
TOTAL |  | 1015 | 1002.42 | 0 | 1002.42 | 0 | 44.5546 | 0 | 636.44 | 22 | 5 | 0 | 3

## D 15
Section ( D-15 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 15 | 15_30 | 180 | 171.53 |  | 171.53 |  | 15.4377 |  | 171.53 | 30 | 2 | 2 |  | HDPI 125 MM
| 13_32 | 181 | 171.77 |  | 171.77 |  | 15.4593 |  | 171.77 | 30 | 2 | 2 |  | HDPI 125 MM
| 11_34 | 182 | 175 |  | 175 |  | 15.75 |  | 175 | 30 | 2 | 2 |  | HDPI 125 MM
| 8_37 | 184 | 175.14 |  | 175.14 |  | 15.7626 |  | 175.14 | 31 | 2 | 2 |  | HDPI 125 MM
| 6_39 | 185 | 176.07 |  | 176.07 |  | 15.8463 |  | 176.07 | 32 | 2 | 2 |  | HDPI 125 MM
TOTAL |  | 912 | 869.51 | 0 | 869.51 | 0 | 78.2559 | 0 | 869.51 | 153 | 10 | 10 | 0
D 15 | TR28_39 | 186 | 176.66 |  | 176.66 |  | 18.5493 | 176.66 |  | 14 | 2 |  | 3 | HDPI 200 MM
| 39_30 | 240 | 244.57 |  | 244.57 |  | 3.1006 |  | 244.57 | 0 | 0 |  |  | HDPI 200 MM
| 30-TR27 | 179 | 171.8 |  | 171.8 |  | 18.039 | 171.8 |  | 16 | 1 |  |  | HDPI 200 MM
| TR27_TR28 | 240 | 239.45 |  | 239.45 |  | 3.1006 |  | 111.65 | 0 | 0 |  |  | HDPI 200 MM
TOTAL |  | 845 | 832.48 | 0 | 832.48 | 0 | 42.7896 | 348.46 | 356.22 | 30 | 3 | 0 | 3

## D 16
Section ( D-16 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D16 | 21-34 | 162 | 155.47 |  | 155.47 |  | 13.9923 | 0 | 155.47 | 25 | 2 | 2 |  | HDPE 125 MM
| 18-37 | 164 | 158.37 |  | 158.37 |  | 14.2533 |  | 158.37 | 27 | 1 | 2 |  | HDPE 125 MM
| 16-39 | 167 | 160.43 |  | 160.43 |  | 14.4387 |  | 160.43 | 29 | 2 | 2 |  | HDPE 125 MM
| 14-41 | 169 | 159.82 |  | 159.82 |  | 14.3838 |  | 159.82 | 23 | 4 | 2 |  | HDPE 125 MM
| D16 11-44 | 171 | 164.1 |  | 164.1 |  | 14.769 |  | 164.1 | 19 | 2 | 2 |  | HDPE 125 MM
| 9-T2 | 68 | 65.73 |  | 65.73 |  | 5.9157 |  | 65.73 | 10 |  | 2 |  | HDPE 125 MM
| 7-T3 | 68 | 65.54 |  | 65.54 |  | 5.8986 |  | 65.54 | 12 |  | 2 |  | HDPE 125 MM
| D16 4-49 | 176 | 171.55 |  | 171.55 |  | 15.4395 |  | 171.55 | 17 | 3 | 2 |  | HDPE 125 MM
| T4-T1 | 119 | 119.2 |  | 119.2 | 24.52 | 10.728 |  | 119.2 | 2 |  | 2 |  | HDPE 125 MM
TOTAL |  | 1264 | 1220.21 | 0 | 1220.21 | 24.52 | 109.8189 | 0 | 1220.21 | 164 | 14 | 18 | 0
D16 | D16 21-2 | 363 | 361.65 |  | 361.65 |  | 30.9697 |  | 294.95 | 0 | 0 |  | 2 | HDPE 200 MM
| D16 2-49 | 178 | 171.27 |  | 171.27 |  | 17.9833 | 171.27 |  | 15 | 1 |  |  | HDPE 200 MM
| D16 49-34 | 362 | 361.49 |  | 361.49 |  | 35.0164 |  | 333.49 | 6 | 0 |  | 1 | HDPE 200 MM
| D16 34-21 | 156 | 153.23 |  | 153.23 |  | 16.0891 | 153.23 |  | 16 | 5 |  | 2 | HDPE 200 MM
TOTAL |  | 1059 | 1047.64 | 0 | 1047.64 | 0 | 100.0587 | 324.5 | 628.44 | 37 | 6 | 0 | 5

## D 17
Section ( D-17 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
| 54-T3 | 114 | 116.13 |  | 113.09 |  | 10.4517 |  | 116.13 | 3 | 0 | 1
| T1-44 | 127 | 115.07 |  | 114.06 |  | 10.3563 |  | 115.07 | 19 | 2 | 1
| T2-T8 | 60 | 119.08 |  | 100.22 |  | 10.7172 |  | 119.08 | 18 | 2 | 1
| 13_T7 | 168 | 166.27 |  | 166.27 |  | 14.9643 |  | 166.27 | 32 | 2
| 15_37 | 196 | 171.52 |  | 171.52 |  | 15.4368 |  | 171.52 | 30 | 0
| T4-28 |  | 121.94 |  |  |  | 10.9746 |  | 121.94
| 18_T5 | 120 | 123.73 |  | 123.73 |  | 11.1357 |  | 123.73 | 21 | 0
| TR13-T2 |  | 37.44 |  |  |  | 3.3696 |  | 37.44 | 3
| 15-37 |  | 174.21 |  |  |  | 15.6789 |  | 174.21
| 20_T6 | 126 | 124.95 |  | 124.95 |  | 11.2455 |  | 124.95 | 26 | 0 | 2
TOTAL |  | 911 | 1270.34 | 0 | 913.84 | 0 | 114.3306 | 0 | 1270.34 | 152 | 6 | 5 | 0
0
`
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 18
Section ( D-18 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
| 8_43 | 202 | 199.96 |  | 199.96 |  | 17.9964 |  |  | 15 | 7 | 24 |  | HDPI 125 MM
| T1-21 | 90 | 86.16 |  | 86.16 |  | 7.7544 |  |  | 7 |  |  |  | HDPI 125 MM
| 40-11 | 208.6 | 206.01 |  | 206.01 |  | 18.5409 |  |  | 35 | 2 |  |  | HDPI 125 MM
| 13-T4 | 63.1 | 65.47 |  | 65.47 |  | 5.8923 |  |  | 7 |  |  |  | HDPI 125 MM
| T9-T5 | 72 | 73.45 |  | 73.45 |  | 6.6105 |  |  | 6 |  |  |  | HDPI 125 MM
| T6-T7 | 53 | 51.92 | 51.92 |  |  | 4.6728 |  |  | 2 |  |  |  | HDPI 125 MM
| 23-T2 | 89 | 86.22 |  | 86.22 |  | 7.7598 |  |  | 7 |  |  |  | HDPI 125 MM
| 24-T3 | 90 | 86.81 |  | 86.81 |  | 7.8129 |  |  | 15 | 1 |  |  | HDPI 125 MM
| 27-T8 | 89.9 | 87.5 |  | 87.5 |  | 7.875 |  |  | 12 | 1 |  |  | HDPI 125 MM
| 29T7 | 90 | 89.37 |  | 89.37 |  | 8.0433 |  |  | 17 |  |  |  | HDPI 125 MM
| 31-T10 | 90 | 89.26 |  | 89.26 |  | 8.0334 |  |  | 8 | 3 |  |  | HDPI 125 MM
| 15_38 | 204 | 201.31 |  | 201.31 |  | 18.1179 |  |  | 13 |  |  |  | HDPI 125 MM
TOTAL |  | 1341.6 | 1323.44 | 51.92 | 1271.52 | 0 | 119.1096 | 0 | 0 | 144 | 14 | 24 | 0
| 4_H2 | 195 | 191.59 |  | 191.59 |  | 20.1169 |  | 191.59 |  | 5 |  | 5 | HDPI 200 MM
| TR12-TR31 | 310 | 313.26 |  | 313.26 |  | 2.625 |  | 313.26 | 12 | 1 |  |  | HDPI 200 MM
| TR31-H1 | 206 | 200.31 |  | 200.31 |  | 21.0325 |  | 200.31 | 7 | 5 |  |  | HDPI 200 MM
| H1-H2 | 306 | 310.64 | 304.66 | 310.64 |  | 2.0023 |  | 274.64 | 8 | 4 |  |  | HDPI 200 MM
TOTAL |  | 1017 | 1015.8 | 304.66 | 1015.8 | 0 | 45.7768 | 0 | 979.8 | 27 | 15 | 0 | 5

## D 19
Section ( D-19 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
`
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 20
Section ( D-20 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 20 | 49-T1 |  | 66.02 |  | 66.02 |  | 5.9418 |  | 44.02 | 12 |  | 15 |  | PIPE 125 MM
| 5-T3 |  | 46.22 |  | 46.22 |  | 4.1598 |  | 46.22 |  | 1 |  |  | PIPE 125 MM
| 47-D2-VC |  | 111.59 |  | 111.59 |  | 10.0431 |  | 111.59 | 6 |  |  |  | PIPE 125 MM
| 44-18 |  | 136.87 |  | 136.87 |  | 12.3183 |  | 136.87 | 23 |  |  |  | PIPE 125 MM
| 42-20 |  | 136.7 |  | 136.7 |  | 12.303 |  | 136.7 | 23 | 1 |  |  | PIPE 125 MM
| 40-22 |  | 137.74 |  | 137.74 |  | 12.3966 |  | 137.74 | 25 |  |  |  | PIPE 125 MM
| 37-25 |  | 136.64 |  | 136.64 |  | 12.2976 |  | 136.64 | 23 |  |  |  | PIPE 125 MM
TOTAL |  | 0 | 771.78 | 0 | 771.78 | 0 | 69.4602 | 0 | 749.78 | 112 | 2 | 15 | 0
D 20 | M1-35-TR6 |  | 271.18 |  | 271.18 |  | 20.3385 |  | 0 | 3 | 5 |  | 3 | PIPE 200 MM
| TR6-TR14 |  | 118.59 |  | 118.59 |  | 8.8942 |  | 0 | 7 | 1 |  |  | PIPE 200 MM
| TR14-TR12 |  | 298.62 |  | 298.62 |  | 10.0923 |  | 298.62 | 1 |  |  |  | PIPE 200 MM
| TR12-M1-35 |  | 132.87 |  | 132.87 |  | 13.9513 | 132.87 |  | 12 |  |  |  | PIPE 200 MM
TOTAL |  | 0 | 821.26 | 0 | 821.26 | 0 | 53.2764 | 132.87 | 298.62 | 23 | 6 | 0 | 3