## D 1
Section ( D- 1) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
| 41-12 |  | 56.75 | 56.75 | 56.75 |  | 5.1075 |  |  | 10
| 16_11 |  | 59.09 | 59.09 | 59.09 |  | 5.3181 |  |  | 11
| 10_9 |  | 56.84 | 56.84 | 56.84 |  | 5.1156 |  |  | 9
| 8_7 |  | 59.17 | 59.17 | 59.17 |  | 5.3253 |  |  | 7 | 2
| 5_6 |  | 67.32 | 67.32 | 67.32 |  | 6.0588 |  |  | 9
| 12_4 |  | 106.23 | 106.23 | 106.23 |  | 9.5607 |  |  | 19
| 2_1 |  | 143.41 | 143.41 | 143.41 |  | 12.9069 |  |  | 26 | 2
| M1-4-3 |  | 225.98 | 225.98 | 225.98 |  | 20.3382 |  |  | 9
| 5-T5 |  | 38.17 | 38.17 | 38.17 |  | 3.4353 |  |  | 6
| 8-BAR.RES |  | 164.74 | 164.74 | 164.74 |  | 14.8266 |  |  | 15
| 17_9 |  | 29.35 | 29.35 | 29.35 |  | 2.6415 |  |  | 3
| M1-11 |  | 253.81 | 253.81 | 253.81 |  | 22.8429 |  |  | 20
| T2-T4 |  | 31.74 | 31.74 | 31.74 |  | 2.8566 |  |  | 5
| A-B |  | 37.54 | 37.54 | 37.54 |  | 3.3786 |  |  | 6
TOTAL |  | 0 | 1330.14 | 1330.14 | 1330.14 | 0 | 119.7126 | 0 | 0 | 155 | 4 | 0 | 0
| M1-11-14 |  | 44.54 |  | 44.54 |  | 4.6767 |  |  | 7
| D2-18-M1-14 |  | 306.25 |  | 306.25 |  | 6.0742 |  |  | 4
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 350.79 | 0 | 350.79 | 0 | 10.7509 | 0 | 0 | 11 | 0 | 0 | 0

## D 2
Section ( D-2 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 3
Section ( D- 3 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
`
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 4
Section ( D- 4 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
`
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 5
Section ( D- 5) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
`
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 6 P1
Section ( D- 6 PART 1 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D6 | 28-71 | 173 | 161.6 |  | 161.6 |  | 14.544 |  |  | 32
| T53-T52 | 82 | 75.13 |  | 75.13 |  | 6.7617 |  |  | 7
| T50-T51 | 88 | 81.3 |  | 81.3 |  | 7.317 |  |  | 5
| 32-63 | 133 | 127.59 |  | 127.59 |  | 11.4831 |  |  | 13
| T54-61 | 115 | 112.04 |  | 112.04 |  | 10.0836 |  |  | 17
| T55-59 | 114 | 98.08 |  | 98.08 |  | 8.8272 |  |  | 18
| T56-56 | 110 | 106.44 |  | 106.44 |  | 9.5796 |  |  | 14
| T57-51 | 75 | 69.37 |  | 69.37 |  | 6.2433 |  |  | 10
| 66-T52 | 88 | 93.66 |  | 93.66 |  | 8.4294 |  |  | 15
| 74A-74B | 30 | 21.27 |  | 21.27 |  | 1.9143 |  |  | 3
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 1008 | 946.48 | 0 | 946.48 | 0 | 85.1832 | 0 | 0 | 134 | 0 | 0 | 0
D6 | 77-VC-W0-2 |  | 392.73 |  | 392.73 |  | 29.4548 |  |  | 20
| VC-W02-51 |  | 30.84 |  | 30.84 |  | 3.2382 |  |  | 6
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 423.57 | 0 | 423.57 | 0 | 32.693 | 0 | 0 | 26 | 0 | 0 | 0

## D 6 P2
Section ( D- 6 PART 2 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 7
Section ( D-7 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 8
Section ( D-8 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 125 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 125 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 125 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 125 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 125 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 125 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 125 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 125 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 125 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 200 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 200 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 200 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPI 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 9
Section ( D-9 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 9 | 9_45 | 253 | 244.78 |  | 244.78 |  | 22.0302 |  |  | 30
| T28-42 | 123 | 116.6 |  | 116.6 |  | 10.494 |  |  | 18
| T24-40 | 130 | 167.45 |  | 167.45 |  | 15.0705 |  |  | 18
| 12-T28 | 114 | 120.31 |  | 120.31 |  | 10.8279 |  |  | 19
| 14-37 | 217 | 219.19 |  | 219.19 |  | 19.7271 |  |  | 32 | 1
| T30-T31 | 40 | 50.7 |  | 50.7 |  | 4.563 |  |  | 3
| 16-35 | 190 | 171.33 |  | 171.33 |  | 15.4197 |  |  | 38 | 1
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 1067 | 1090.36 | 0 | 1090.36 | 0 | 98.1324 | 0 | 0 | 158 | 2 | 0 | 0
D 9 | VC\W02-102 |  | 377.55 |  | 377.55 |  | 39.6427 |  |  | 20 | 1
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 377.55 | 0 | 377.55 | 0 | 39.6427 | 0 | 0 | 20 | 1 | 0 | 0

## D 10
Section ( D-10 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0