## D 21
Section ( D- 21) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 21 | 6_46 | 133 | 136.67 |  | 136.67 |  | 12.3003 |  |  | 24 | 1 |  | 18 | HDPE125 MM
| 8_44 | 133 | 133.42 |  | 133.42 |  | 12.0078 |  |  | 23 |  |  |  | HDPE125 MM
| 10_42 | 133 | 130.18 |  | 130.18 |  | 11.7162 |  |  | 22 |  |  |  | HDPE125 MM
| 13_40 | 133 | 133.9 |  | 133.9 |  | 12.051 |  |  | 25 |  |  |  | HDPE125 MM
| 15_37 | 134 | 131.84 |  | 131.84 |  | 11.8656 |  |  | 24 |  |  |  | HDPE125 MM
| 17_35 | 133 | 133.73 |  | 133.73 |  | 12.0357 |  |  | 19 |  |  |  | HDPE125 MM
| TR3-24 | 87 | 84.77 |  | 84.77 |  | 7.6293 |  |  | 10 | 2 |  |  | HDPE125 MM
| T2-26 | 87 | 85.39 |  | 85.39 |  | 7.6851 |  |  | 13 |  |  |  | HDPE125 MM
| T1-28 | 87 | 85.04 |  | 85.04 |  | 7.6536 |  |  | 15 | 1
TOTAL |  | 1060 | 1054.94 | 0 | 1054.94 | 0 | 94.9446 | 0 | 0 | 175 | 4 | 0 | 18
D 21 | 4-M1-51 | 310 | 307.6 |  | 307.6 |  | 32.298 |  | 307.6 | 14 | 3 |  | 5 | HDPE 200 MM
| TR12-TR31 | 310 | 305.34 |  | 305.34 |  | 3.5049 |  | 305.34 | 10 | 1 |  |  | HDPE 200 MM
| 4-TR12 | 130 | 134.48 |  | 134.48 |  | 14.1204 |  | 134.48 | 13 |  |  |  | HDPE 200 MM
| M1-51-TR31 | 128 | 131.97 |  | 131.97 |  | 13.8568 |  | 131.97 | 4 |  |  |  | HDPE 200 MM
TOTAL |  | 878 | 879.39 | 0 | 879.39 | 0 | 63.7801 | 0 | 879.39 | 41 | 4 | 0 | 5

## D 22
Section ( D-22 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[7 empty] | 0 | [6 empty] | HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [6 empty] | HDPE 200 MM
HDPE 200 MM
[7 empty] | ` | [6 empty] | HDPE 200 MM
HDPE 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 23
Section ( D-23 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 23 | 49-36 | 133 | 130.41 |  | 130.41 |  | 11.7369 |  | 130.41 | 25 | 0 | 14 |  | HDPE 125 MM
| 51-33 | 132 | 133.17 |  | 133.17 |  | 11.9853 |  | 133.17 | 24 |  |  |  | HDPE 125 MM
| 53-31 | 131 | 133.12 |  | 133.12 |  | 11.9808 |  | 133.12 | 24 |  |  |  | HDPE 125 MM
| 2_29 | 131 | 133.02 |  | 133.02 |  | 11.9718 |  | 133.02 | 23 | 0 |  |  | HDPE 125 MM
| 4_27 | 131 | 132.98 |  | 132.98 |  | 11.9682 |  | 132.98 | 23 |  |  |  | HDPE 125 MM
| 6_24 | 131 | 132.54 |  | 132.54 |  | 11.9286 |  | 132.54 | 24 |  |  |  | HDPE 125 MM
| 9_22 | 130 | 132.23 |  | 132.23 |  | 11.9007 |  | 132.23 | 22 |  |  |  | HDPE 125 MM
TOTAL |  | 919 | 927.47 | 0 | 927.47 | 0 | 83.4723 | 0 | 927.47 | 165 | 0 | 14 | 0
D 23 | M312-TR28 | 130 | 131.19 |  | 131.19 |  | 13.7749 | 131.19 |  | 12 | 0 |  | 3 | HDPE 200 MM
| M220-M312 | 317 | 319.08 |  | 319.08 |  | 24.7254 |  | 235.48 | 4 | 1 |  |  | HDPE 200 MM
| TR14-M220 | 130 | 128.6 |  | 128.6 |  | 13.503 | 128.6 |  | 11 | 0 |  |  | HDPE 200 MM
| TR28-TR14 | 317 | 317.96 |  | 317.96 |  | 4.3365 |  | 317.96 | 0 | 0 |  |  | HDPE 200 MM
TOTAL |  | 894 | 896.83 | 0 | 896.83 | 0 | 56.3398 | 259.79 | 553.44 | 27 | 1 | 0 | 3

## D 24
Section ( D-24 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D24 | 15-28 | 131 | 137.32 |  | 137.32 |  | 12.3588 |  | 137.32 | 22 | 2 | 10 |  | HDPE 125 MM
| 13-31 | 132 | 137.77 |  | 137.77 |  | 12.3993 |  | 137.77 | 23 |  |  |  | HDPE 125 MM
| 11_33 | 132 | 138.31 |  | 138.31 |  | 12.4479 |  | 138.31 | 23 |  |  |  | HDPE 125 MM
| 8_35 | 132 | 137.5 |  | 137.5 |  | 12.375 |  | 137.5 | 20 | 1 |  |  | HDPE 125 MM
| 6_38 | 132 | 136.95 |  | 136.95 | 26.95 | 12.3255 |  | 136.95 | 24 |  |  |  | HDPE 125 MM
TOTAL |  | 659 | 687.85 | 0 | 687.85 | 26.95 | 61.9065 | 0 | 687.85 | 112 | 3 | 10 | 0
D24 | 4_TR28 | 131 | 132.73 |  | 132.73 |  | 13.9366 | 132.73 |  | 12 |  |  | 3 | HDPE 200 MM
| TR28-TR27 | 240 | 237.31 |  | 239.45 |  | 3.0996 |  | 109.51 | 0 | 0 |  |  | HDPE 200 MM
| TR27-TR25 | 131 | 137.01 |  | 137.01 |  | 14.386 | 137.01 |  | 14 | 0 |  |  | HDPE 200 MM
| TR25-4 | 240 | 240.16 |  | 240.16 |  | 25.2168 |  | 240.16 | 2 | 2 |  |  | HDPE 200 MM
TOTAL |  | 742 | 747.21 | 0 | 749.35 | 0 | 56.6391 | 269.74 | 349.67 | 28 | 2 | 0 | 3

## D 25
Section ( D-25 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
| 19 to 34 | 131 | 131.01 |  | 131.01 |  | 11.7909 |  | 131.01 | 24 |  | 2 |  | HDPE 125 MM
| 17to37 | 132 | 131.56 |  | 131.56 |  | 11.8404 |  | 131.56 | 24 |  | 2 |  | HDPE 125 MM
| 14 to 39 | 131.5 | 131.55 |  | 131.55 |  | 11.8395 |  | 131.55 | 24 |  | 2 |  | HDPE 125 MM
| 12 to41 | 132 | 134.19 |  | 134.19 |  | 12.0771 |  | 134.19 | 24 |  | 2 |  | HDPE 125 MM
D 25 | 10 to 44 | 132 | 134.46 |  | 134.46 |  | 12.1014 |  | 134.46 | 26 |  | 2 |  | HDPE 125 MM
| 7 to 46 | 132 | 132.9 |  | 132.9 |  | 11.961 |  | 132.9 | 23 |  | 2 |  | HDPE 125 MM
| 5 to 48 | 132 | 134.21 |  | 134.21 |  | 12.0789 |  | 134.21 | 22 |  | 2 |  | HDPE 125 MM
| 3 to 51 | 133 | 133.28 |  | 133.28 | 40.33 | 11.9952 |  | 133.28 | 24 |  | 2 |  | HDPE 125 MM
TOTAL |  | 1055.5 | 1063.16 | 0 | 1063.16 | 40.33 | 95.6844 | 0 | 1063.16 | 191 | 0 | 16 | 0
| 19 to 27 | 364 | 364.5 |  | 364.5 |  | 12.4152 |  | 225.5 | 4 | 3 |  | 1 | HDPE 200 MM
| 27 to 51 | 132 | 129.28 |  | 129.28 |  | 13.5744 | 129.28 |  | 11 |  |  | 2 | HDPE 200 MM
| 51 to 34 | 363 | 362.115 |  | 362.115 |  | 31.0186 |  | 295.42 | 1 |  |  | 2 | HDPE 200 MM
| 34 to 19 | 131 | 128.88 |  | 128.88 |  | 13.5324 | 128.88 |  | 8 | 4 |  |  | HDPE 200 MM
TOTAL |  | 990 | 984.775 | 0 | 984.775 | 0 | 70.5406 | 258.16 | 520.92 | 24 | 7 | 0 | 5
| D-25 19-27 concrete protaction slap=pipe in side road*0.7*0.15 =118.24*0.7*0.15 =12.42 M³ reinstatement by concrete=total asbuilt length -soil 364.5-139=225.5 m.l | [6 empty] | D25-51-34 CONCRETE PRO=(TOTAL LENGTH-SOIL)*0.15*0.7 =295.42*0.7*0.15 =31.02 M³ REINSTATEMENT=TOTAL LENGTH-SOIL =362.12-66.7 =295.42 M.L

## D 26
Section ( D- 26) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 26 | 40-T1 | 88.5 | 87.49 |  |  |  | 0 |  |  | 16 |  |  |  | HDPE 125 MM
| T2-47 | 67 | 64.08 | [6 empty] | 6 |  |  |  | HDPE 125 MM
| M2 17-T11 | 138 | 199.1 | [6 empty] | 26 |  |  |  | HDPE 125 MM
| 12_T3 |  | 200.68 | [6 empty] | 11 |  |  |  | HDPE 125 MM
| T10-T7 |  | 41.31 | [6 empty] | 2 |  |  |  | HDPE 125 MM
| 2-T6 |  | 90.08 | [6 empty] | 9 |  |  |  | HDPE 125 MM
| T12-M2-20 |  | 68.53 | [6 empty] | 6 |  |  |  | HDPE 125 MM
| T4-49 |  | 168.11 | [6 empty] | 13 |  |  |  | HDPE 125 MM
| T5-5 |  | 100.15 | [6 empty] | 3 |  |  |  | HDPE 125 MM
| 15-T6 |  | 86.38 | [6 empty] | 12 |  |  |  | HDPE 125 MM
| T9-8 |  | 65.45 | [6 empty] | 5 |  |  |  | HDPE 125 MM
| A8-B8 |  | 99.92 | [6 empty] | 4 | 1 |  |  | HDPE 125 MM
| A11-A12 |  | 33.36 | [6 empty] | 6 |  |  |  | HDPE 125 MM
| A9-A10 |  | 50.81 | [6 empty] | 8 |  |  |  | HDPE 125 MM
| T8-A0 |  | 31.18 | [6 empty] | 3 |  |  |  | HDPE 125 MM
TOTAL |  | 293.5 | 1386.63 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 1 | 0 | 0
| M3-12-A6 |  | 926.49 |  |  |  | 0 |  |  | 22 | 2 |  |  | HDPE 200 MM
| A6-A8 | [8 empty] | 17 | 1 |  |  | HDPE 200 MM
| A8-M2-25 | [5 empty] | ` |  |  | 18 |  |  |  | HDPE 200 MM
| M2-25-M2-12 | [8 empty] | 19 |  |  |  | HDPE 200 MM
TOTAL |  | 0 | 926.49 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 3 | 0 | 0

## D 27
Section ( D-27 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[7 empty] | 0 | [6 empty] | HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [6 empty] | HDPE 200 MM
HDPE 200 MM
[7 empty] | ` | [6 empty] | HDPE 200 MM
HDPE 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 28
Section ( D-28 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
| 4_38 | 98 | 116.13 |  | 116.13 |  | 10.4517 |  |  | 9 |  |  |  | HDPE 125 MM
| T7-T2 | 71 | 67.37 |  | 67.37 |  | 6.0633 |  |  | 8 |  |  |  | HDPE 125 MM
| T6-T4 | 71 | 61.27 |  | 61.27 |  | 5.5143 |  |  | 7 |  |  |  | HDPE 125 MM
| 11--14 | 41.8 | 32.53 |  | 32.53 |  | 2.9277 |  |  | 7 |  |  |  | HDPE 125 MM
| 9_23 | 49 | 33.99 |  | 33.99 |  | 3.0591 |  |  | 5 | 1 |  |  | HDPE 125 MM
| 6_33 | 81.4 | 76.2 |  | 76.2 |  | 6.858 |  |  | 10 | 1 |  |  | HDPE 125 MM
| 1_42 | 116 | 141.53 |  | 141.53 |  | 12.7377 |  |  | 10 |  |  |  | HDPE 125 MM
| 51-42 |  | 213.33 |  | 213.33 |  | 19.1997 |  |  | 17 | 1 |  |  | HDPE 125 MM
| 42-38 |  | 69.75 |  | 69.75 |  | 6.2775 |  |  | 9 |  |  |  | HDPE 125 MM
| T5-47 | 80 | 80.57 |  | 80.57 |  | 7.2513 |  |  | 7 |  |  |  | HDPE 125 MM
| T3-44 | 74 | 75.39 |  | 75.39 |  | 6.7851 |  |  | 10 |  |  |  | HDPE 125 MM
| 42A-42B |  | 32.86 |  | 32.86 |  | 2.9574 |  |  | 4 |  |  |  | HDPE 125 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPE 125 MM
TOTAL |  | 682.2 | 1000.92 | 0 | 1000.92 | 0 | 90.0828 | 0 | 0 | 103 | 3 | 0 | 0
[5 empty] | 0 |  | 0 | [6 empty] | HDPE 200 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPE 200 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPE 200 MM
[5 empty] | 0 |  | 0 | [6 empty] | HDPE 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 29
Section ( D-29 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[7 empty] | 0 | [6 empty] | HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [6 empty] | HDPE 200 MM
HDPE 200 MM
[7 empty] | ` | [6 empty] | HDPE 200 MM
HDPE 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## M2
Section ( M 2 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
M 2 | 28_T9 | 103 | 87.99 | 87.99 | [5 empty] | 10 |  |  |  | HDPE 125 MM
| T8-T6 | 88 | 87.55 | 87.55 | [5 empty] | 6 |  |  |  | HDPE 125 MM
| T10-T7 | 72 | 54.3 | 54.3 | [5 empty] | 7 |  |  |  | HDPE 125 MM
| T5-32 | 88 | 72.03 | 72.03 | [5 empty] | 9 | 1 |  |  | HDPE 125 MM
| T4-43 | 79 | 112.11 | 112.11 | [5 empty] | 16 |  |  |  | HDPE 125 MM
| T3-37 | 76 | 54.1 | 54.1 | [5 empty] | 9 |  |  |  | HDPE 125 MM
| 41-A4 | 73 | 72.09 | 72.09 | [5 empty] | 4 |  |  |  | HDPE 125 MM
| A2-A3 | 27 |  | 81.39 | [5 empty] | 8 |  |  |  | HDPE 125 MM
| 39-T2 | 81.6 | 90.14 | 90.14 |  |  | 8.1126 |  |  | 13 |  |  |  | HDPE 125 MM
TOTAL |  | 687.6 | 630.31 | 711.7 | 0 | 0 | 8.1126 | 0 | 0 | 82 | 1 | 0 | 0
M 2 | A1-M2-25 | 354 | 348.49 |  | 348.49 |  | 36.5914 |  | 348.49 | 25 |  |  |  | HDPE 200 MM
TOTAL |  | 354 | 348.49 | 0 | 348.49 | 0 | 36.5914 | 0 | 348.49 | 25 | 0 | 0 | 0

## M 3
Section ( M3 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
M3 | D26-4-D26-10 |  | 100.84 | 100.84 |  |  | 0 |  |  | 11 |  |  |  | HDPE 125 MM
| D-26-12-A |  | 85.54 | 85.54 | [5 empty] | 4 |  |  |  | HDPE 125 MM
| B-C |  | 59.73 | 59.73 | [5 empty] | 6 |  |  |  | HDPE 125 MM
| D-E |  | 209.21 | 209.21 | [5 empty] | 12 |  |  |  | HDPE 125 MM
| M2-8-T2 |  | 26.45 | 26.45 | [5 empty] | 9 |  |  |  | HDPE 125 MM
| M2-5-T5 |  | 33.54 | 33.54 | [5 empty] | 7 | 1 |  |  | HDPE 125 MM
| M2-3-F | [8 empty] | 14 |  |  |  | HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
TOTAL |  | 0 | 515.31 | 515.31 | 0 | 0 | 0 | 0 | 0 | 63 | 1 | 0 | 0
M3 | M3-12-M1-14 | 218 | 215.85 | 215.85 |  |  | 0 |  |  | 0 | 0 |  |  | HDPE 200 MM
TOTAL |  | 218 | 215.85 | 215.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0