## D 21
Section ( D- 21) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 21 | 6_46 | 133 | 136.67 |  | 136.67 |  | 12.3003 |  |  | 24 | 1 |  |  | HDPE125 MM
| 8_44 | 133 | 133.42 |  | 133.42 |  | 12.0078 |  |  | 23 |  |  |  | HDPE125 MM
| 10_42 | 133 | 130.18 |  | 130.18 |  | 11.7162 |  |  | 22 |  |  |  | HDPE125 MM
| 13_40 | 133 | 133.9 |  | 133.9 |  | 12.051 |  |  | 25 |  |  |  | HDPE125 MM
| 15_37 | 134 | 131.84 |  | 131.84 |  | 11.8656 |  |  | 24 |  |  |  | HDPE125 MM
| 17_35 | 133 | 133.73 |  | 133.73 |  | 12.0357 |  |  | 19 |  |  |  | HDPE125 MM
| TR3-24 | 87 | 84.77 |  | 84.77 |  | 7.6293 |  |  | 10 | 2 |  |  | HDPE125 MM
| T2-26 | 87 | 85.39 |  | 85.39 |  | 7.6851 |  |  | 13 |  |  |  | HDPE125 MM
| T1-28 | 87 | 85.04 |  | 85.04 |  | 7.6536 |  |  | 15 | 1
TOTAL |  | 1060 | 1054.94 | 0 | 1054.94 | 0 | 94.9446 | 0 | 0 | 175 | 4 | 0 | 0
D 21 | 4-M1-51 | 310 | 879.39 |  |  |  | 92.3359 |  | 879.39 | 14 | 3 |  |  | HDPE 200 MM
| TR12-TR31 | 310 | [7 empty] | 10 | 1 |  |  | HDPE 200 MM
| 4-TR12 | 130 | [7 empty] | 13 |  |  |  | HDPE 200 MM
| M1-51-TR31 | 128 | [7 empty] | 4 |  |  |  | HDPE 200 MM
TOTAL |  | 878 | 879.39 | 0 | 0 | 0 | 92.3359 | 0 | 879.39 | 41 | 4 | 0 | 0

## D 22
Section ( D-22 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[7 empty] | 0 | [6 empty] | HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [6 empty] | HDPE 200 MM
HDPE 200 MM
[7 empty] | ` | [6 empty] | HDPE 200 MM
HDPE 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 23
Section ( D-23 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 23 | 49-36 | 133 | 130.41 |  | 130.41 |  | 11.7369 |  | 130.41 | 25 | 0 |  |  | HDPE 125 MM
| 51-33 | 132 | 133.17 |  | 133.17 |  | 11.9853 |  | 133.17 | 24 |  |  |  | HDPE 125 MM
| 53-31 | 131 | 133.12 |  | 133.12 |  | 11.9808 |  | 133.12 | 24 |  |  |  | HDPE 125 MM
| 2_29 | 131 | 133.02 |  | 133.02 |  | 11.9718 |  | 133.02 | 23 | 0 |  |  | HDPE 125 MM
| 4_27 | 131 | 132.98 |  | 132.98 |  | 11.9682 |  | 132.98 | 23 |  |  |  | HDPE 125 MM
| 6_24 | 131 | 132.54 |  | 132.54 |  | 11.9286 |  | 132.54 | 24 |  |  |  | HDPE 125 MM
| 9_22 | 130 | 132.23 |  | 132.23 |  | 11.9007 |  | 132.23 | 22 |  |  |  | HDPE 125 MM
TOTAL |  | 919 | 927.47 | 0 | 927.47 | 0 | 83.4723 | 0 | 927.47 | 165 | 0 | 0 | 0
D 23 | M312-TR28 | 130 | 896.98 |  |  |  | 94.1829 |  | 896.98 | 12 | 0 |  |  | HDPE 200 MM
| TR28-TR14 | 317 | [7 empty] | 0 | 0 |  |  | HDPE 200 MM
| TR14-M220 | 130 | [7 empty] | 11 | 0 |  |  | HDPE 200 MM
| M220-M312 | 317 | [7 empty] | 4 | 1 |  |  | HDPE 200 MM
TOTAL |  | 894 | 896.98 | 0 | 0 | 0 | 94.1829 | 0 | 896.98 | 27 | 1 | 0 | 0

## D 24
Section ( D-24 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
| 15-28 | 131 | 137.32 |  | 137.32 |  | 12.3588 |  | 137.32 | 22 |  |  |  | HDPE 125 MM
| 13-31 | 132 | 137.77 |  | 137.77 |  | 12.3993 |  | 137.77 | 23 |  |  |  | HDPE 125 MM
| 11_33 | 132 | 138.31 |  | 138.31 |  | 12.4479 |  | 138.31 | 23 |  |  |  | HDPE 125 MM
| 8_35 | 132 | 137.5 |  | 137.5 |  | 12.375 |  | 137.5 | 20 | 1 |  |  | HDPE 125 MM
| 6_38 | 132 | 136.95 |  | 136.95 | 26.95 | 12.3255 |  | 136.95 | 24 |  |  |  | HDPE 125 MM
TOTAL |  | 659 | 687.85 | 0 | 687.85 | 26.95 | 61.9065 | 0 | 687.85 | 112 | 1 | 0 | 0
| 4_TR28 | 131 | 132.73 |  | 132.73 |  | 13.9366 | 132.73 |  | 0 |  |  |  | HDPE 200 MM
| TR28-TR27 | 240 | 239.45 |  | 239.45 |  | 25.1422 | 239.45 |  | 13 | 0 |  |  | HDPE 200 MM
| TR27-TR25 | 131 | 137.01 |  | 137.01 |  | 14.386 | 137.01 |  | 2 | 1 |  |  | HDPE 200 MM
| TR25-4 | 240 | 240.16 |  | 240.16 |  | 25.2168 | 240.16 | [5 empty] | HDPE 200 MM
TOTAL |  | 742 | 749.35 | 0 | 749.35 | 0 | 78.6817 | 749.35 | 0 | 15 | 1 | 0 | 0
[7 empty] | 140.5882 | 1437.2
[5 empty] | كيف تم حساب هذه القيم من الجدول أعلاه ؟ | [6 empty] | كيف تم حساب هذه القيم من الجدول أعلاه ؟
|  |  |  | 687 | 749 | 687 | 749 | 1437.2 | 140.59 | 112 | 1 | 0 | 0 |  | هذه القيم موجودة في ملفك all in one
السوال كيف تم حساب هذه القيم ؟
|  |  | ضع المعادلات هنا |  |  |  |  | 1437.2 | 140.5882 | [5 empty] | يعني اكتب هنا المعادلات في كل خلية
من خلال المعادلة التي وضعتها أنت فهمت أنا كيف تم حساب هذين الرقمين
أما بقية الأرقام فلم أفهم كيف تم حسابها أرجو التوضيح

## D 25
Section ( D-25 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
| 19 to 34 | 131 | 131.01 | 25.5 | 131.01 | 11 | 11.7909 | 12 | 131.01 | 24 | 10 | 2 | 4 | HDPE 125 MM
| 17to37 | 132 | 131.56 | 16.3 | 131.56 | 22 | 11.8404 | 13 | 131.56 | 24 | 20 | 2 | 5 | HDPE 125 MM
| 14 to 39 | 131.5 | 131.55 | 22 | 131.55 | 33 | 11.8395 | 14 | 131.55 | 24 | 30 | 2 | 6 | HDPE 125 MM
| 12 to41 | 132 | 134.19 | 55 | 134.19 | 44 | 12.0771 | 15 | 134.19 | 24 | 40 | 2 | 7 | HDPE 125 MM
D 25 | 10 to 44 | 132 | 134.46 | 19 | 134.46 | 55 | 12.1014 | 16 | 134.46 | 26 | 50 | 2 | 8 | HDPE 125 MM
| 7 to 46 | 132 | 132.9 | 15 | 132.9 | 66 | 11.961 | 17 | 132.9 | 23 | 60 | 2 | 9 | HDPE 125 MM
| 5 to 48 | 132 | 134.21 | 17 | 134.21 | 77 | 12.0789 | 18 | 134.21 | 22 | 70 | 2 | 11 | HDPE 125 MM
| 3 to 51 | 133 | 133.28 | 44 | 133.28 | 40.33 | 11.9952 | 19 | 133.28 | 24 | 80 | 2 | 14 | HDPE 125 MM
TOTAL |  | 1055.5 | 1063.16 | 213.8 | 1063.16 | 348.33 | 95.6844 | 124 | 1063.16 | 191 | 360 | 16 | 64
| 19 to 27 | 364 | 364.5 | 55 | 364.5 | 55 | 38.2725 | 50 | 364.5 | 4 | 3 | 4 | 1 | HDPE 200 MM
| 27 to 51 | 132 | 129.28 | 88 | 129.28 | 66 | 13.5744 | 129.28 | 10 | 11 | 8 | 8 | 2 | HDPE 200 MM
| 51 to 34 | 363 | 362.115 | 66 | 362.115 | 77 | 38.0221 | 120 | 362.12 | 1 | 3 | 9 | 2 | HDPE 200 MM
| 34 to 19 | 131 | 128.88 | 44 | 128.88 | 99 | 13.5324 | 128.88 | 20 | 9 | 4 | 3 | 9 | HDPE 200 MM
TOTAL |  | 990 | 984.775 | 253 | 984.775 | 297 | 103.4014 | 428.16 | 756.62 | 25 | 18 | 24 | 14
حتى أفهم الموضوع جيدا قمت بوضع أرقام عشوائية في المناطق الزرقاء بالجدول أعلاه
|  |  |  | ASBUILT length |  | pipe line |  | rienstatement | concrete pro | h.c |  | g.v
|  |  |  | 125 | 200 | 125 | 200 |  |  | 20 | 25 | 125 | 200
الرجاء وضع المعادلات في هذا السطر

## D 26
Section ( D- 26) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
D 26 | 40-T1 | 88.5 | 87.49 |  |  |  | 7.8741 |  |  | 15 |  |  |  | HDPE 125 MM
| 49-19 | 165.81 | 168.11 | [6 empty] | 13 |  |  |  | HDPE 125 MM
| T2-47 | 67 | 64.08 | [6 empty] | 6 |  |  |  | HDPE 125 MM
| M2 17-T11 | 138 | 139.1 | [10 empty] | HDPE 125 MM
| 12_T3 | [12 empty] | HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
TOTAL |  | 459.31 | 458.78 | 0 | 0 | 0 | 7.8741 | 0 | 0 | 34 | 0 | 0 | 0
[7 empty] | 0 | [6 empty] | HDPE 200 MM
HDPE 200 MM
[7 empty] | ` | [6 empty] | HDPE 200 MM
HDPE 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 27
Section ( D-27 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[7 empty] | 0 | [6 empty] | HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [6 empty] | HDPE 200 MM
HDPE 200 MM
[7 empty] | ` | [6 empty] | HDPE 200 MM
HDPE 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 28
Section ( D-28 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[7 empty] | 0 | [6 empty] | HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [6 empty] | HDPE 200 MM
HDPE 200 MM
[7 empty] | ` | [6 empty] | HDPE 200 MM
HDPE 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## D 29
Section ( D-29 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
[7 empty] | 0 | [6 empty] | HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
HDPE 125 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | [6 empty] | HDPE 200 MM
HDPE 200 MM
[7 empty] | ` | [6 empty] | HDPE 200 MM
HDPE 200 MM
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## M2
Section ( M 2 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
M 2 | 28_T9 | 103 | 87.99 | 87.99 | [5 empty] | 10 |  |  |  | HDPE 125 MM
| T8-T6 | 88 | 87.55 | 87.55 | [5 empty] | 6 |  |  |  | HDPE 125 MM
| T10-T7 | 72 | 54.3 | 54.3 | [5 empty] | 7 |  |  |  | HDPE 125 MM
| T5-32 | 88 | 72.03 | 72.03 | [5 empty] | 9 | 1 |  |  | HDPE 125 MM
| T4-43 | 79 | 112.11 | 112.11 | [5 empty] | 16 |  |  |  | HDPE 125 MM
| T3-37 | 76 | 54.1 | 54.1 | [5 empty] | 9 |  |  |  | HDPE 125 MM
| 41-A4 | 73 | 72.09 | 72.09 | [5 empty] | 4 |  |  |  | HDPE 125 MM
| A2-A3 | 27 | [11 empty] | HDPE 125 MM
| 39-T2 | 81.6 | 90.14 | 90.14 |  |  | 8.1126 |  |  | 13 |  |  |  | HDPE 125 MM
TOTAL |  | 687.6 | 630.31 | 630.31 | 0 | 0 | 8.1126 | 0 | 0 | 74 | 1 | 0 | 0
M 2 | A1-M2-25 | 354 | 348.49 |  | 348.49 |  | 36.5914 |  | 348.49 | 25 |  |  |  | HDPE 200 MM
TOTAL |  | 354 | 348.49 | 0 | 348.49 | 0 | 36.5914 | 0 | 348.49 | 25 | 0 | 0 | 0

## M 3
Section ( M3 ) Date:
Section Name | Line Name | Length Sh.dw(M) | Length Asbuild (M) | Backfilling (M.L.) |  | Extra Over Rock M³ | Reinf. Concrete M³ | Reinstatement (M.L.) |  | House Connection |  | Gate Valve |  | Pipe`s Type
|  |  |  | Soil | Crushed Stone |  |  | Asphalt | Concrete | 20 mm | 25mm | 125 | 200
M3 | 1_2 | 54 |  |  |  |  | 0 | [6 empty] | HDPE 125 MM
| 2_6 | 150 | [11 empty] | HDPE 125 MM
| 2_5 | 42 | [11 empty] | HDPE 125 MM
| 3_4 | 90 | [11 empty] | HDPE 125 MM
| D26-10-D26T3 | 70 | [11 empty] | HDPE 125 MM
| 13_4 | 35.5 | [11 empty] | HDPE 125 MM
| M2-8-M3-T2 | 47.8 | 26.45 | [6 empty] | 9 |  |  |  | HDPE 125 MM
| M2-5-M3-T5 | 87.7 | 35.23 | [6 empty] | 7 | 1 |  |  | HDPE 125 MM
| 3-N1 | 87 | [11 empty] | HDPE 125 MM
TOTAL |  | 664 | 61.68 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1 | 0 | 0
M3 | M3-12-M2-14 | 218 |  |  |  |  | 0 | [6 empty] | HDPE 200 MM
TOTAL |  | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0